## Coversheet
Rule 21 Timeline Reporting Coversheet
This coversheet aggregates quarterly PG&E, SCE and SDG&E (Utilities) interconnection timeline reports from January 2021. Utilities submit quarterly reports to the Rulemaking R.17-07-007 Service List. To sign up for the service list, click the link below in row 7 and navigate to the "Subscribe" button near the top of the page. Quarterly reports will also be archived and posted at the CPUC Rule 21 Webpage (link below in cell A6).
Links to relevant information:
D.20-09-035 (see Issue 12 and Issue 8c)
Electric Rule 21 Webpage
Subscription to Rulemaking 1707007 Service List
Notes for interpreting spreadsheet: Row 9 indicates the relevant Ordering Paragraph (OP) in Decision D.20-09-035 that mandated the timeline tracking, which is specified in Row 10. An asterisk next to the OP in Row 9 indicates that customer time (i.e., time that is outside of the direct control of the Utility) is included in the tracked time. Row 10 draws directly from text in Issues 12 and 8c in D.20-09-035. The text in red is intended to increase clarity beyond the Issue 12 language in the OP. References to the Rule 21 Tariff section appears in parenthesis for ease of reference.
Project Specifics | [8 empty] | OP 22 a) | OP 22 b)* | OP 22 c) (no upgrade) | OP 22 c) (if upgrade required) | OP 22 d) (no upgrade) | OP 22 d) (if upgrade required) | OP 22 e) (if Electrical Independence Test required) | OP 22 f) (if Detailed Study Required)* | OP 22 g) (if Detailed Study Required)* | OP 22 h) (if Detailed Study required) | OP 22 i) | OP 22 i) | OP 22 j)* | OP 22 k) | OP 22 l)* | OP 22 m) | OP 22 m) | OP 22 n) | OP 24 o) | OP 24 p) | OP 24 q) | OP 22 r) | OP 22 s)* | OP 4 | OP 4 | OP 4
Project ID | Utility | ZIP Code | NEM / Non-NEM | Project Type (Request Type) | Project Status (Current Phase) | Technology Type | Size (kW - Net Nameplate Rating) | Cost Envelope Requested? | Time from Submission of Interconnection Request to Utility's Acknowledgement of Receipt of Interconnection Request | Time from submission of Interconnection Request to time deemed complete | Time from Interconnection Request deemed complete to completion of initial review and provision of results (if no upgrades are required) | Time from Interconnection Request deemed complete to completion of initial review and provision of results (if upgrades are required) | Time from Supplemental Review start date to completion of Supplemental Review (if no upgrades are required) | Time from Supplemental Review start date to completion of Supplemental Review (if upgrades are required) | Time from receipt of Detailed Study Deposit (F.1.b) to perform Electrical Independence Test (Screens Q and R) and issue Electrical Independence Test (F.3.c.ii) results (if Electrical Independence Test required) | Time from Electrical Independence Test results issuance to scheduling of Detailed Study Scoping Meeting (F.3.b.i) (if Detailed Study required) | Time from Detailed Study Scoping Meeting held to issuance of draft Detailed Study Agreement (F.3.b.ii) (if Detailed Study required) | Time from Detailed Study Agreement execution to issuance of System Impact Study results/report (F.3.b.i.-ii) (if Detailed Study required) | Time from Applicable Milestone to Provision of Draft Generator Agreement (see applicable milestone in column U) | Applicable Milestone (referenced in column T) | Time from issuance of draft Generator Interconnection Agreement to date Generator Interconnection Agreement executed | Time from when the Producer completes "satisfactory compliance with the terms of all applicable agreements" to when the utility issues written Permission to Operate (F.5.b) | Total time from Utility receipt of Interconnection Request to issuance of Permission to Operate | Time from customer request to consider whether a proposed modification is material to issuance of material modification analysis/results by utility (F.3.b.v) (Note: customers are not limited in the number of material modification requests and the total number of customer material modification requests appears in column Z) | Total Number of Customer Material Modification Requests (referenced in column Y) | Time for responding to line-side taps variance requests (for Utilities that require a variance request) | Time from Utility confirmation that customer has taken all necessary steps to prepare for construction to Utility completion of design and invoice of net generation output meter | Time from date Utility issues a Service Request to date installation of net generation output meter is complete | Distribution Upgrades: Time from Utility confirmation that customer has taken all necessary steps to initiate Preliminary Design process to Utility submission of Preliminary Design to customer | Distribution Upgrades: Time from Customer Acceptance of Preliminary Design to Utility issuance of Final Design to Customer | Time from Utility scheduling commissioning test to completion of commissioning testing | (Y/N) Would Integration Capacity Analysis outdated values have lead to Interconnection Requests failing the Initial Review? | If Integration Capacity Analysis oudated values would have led to Interconnection Requests Failing the Initial Review, what cost was associated with the updates to the ICA necessitated by evaluating the outdated values? | Actual Costs Associated with processing of interconnection applications (as discussed in proposal 8s). | Notes
GFID100233 | SCE | 92407 | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 10 | No | 0 |  | 10 | [7 empty] | 0 | Fast Track Initial Review | 41 |  | 87
GFID100286 | SCE | 91390 | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 10 | No | 0 |  | 1 | [7 empty] | 0 | Fast Track Initial Review | 27 |  | 58
GFID100476 | SCE | 91761 | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Other (Combustion Turbine) | 240 | No | 0 | 5 |  | 28 | [6 empty] | 0 | Initial Review Cost Report
GFID100477 | SCE | 92352 | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 490 | No | 0 |  | 2 | [7 empty] | 0 | Fast Track Initial Review | 56 |  | 216
GFID100487 | SCE | 92399 | Non-NEM | Rule 21 Non-Export | Resolved-Withdrawn | Battery Storage | 10 | No | 0 | 1
GFID100496 | SCE | 91761 | Non-NEM | Rule 21 Non-Export | Pending-Withdrawn | Other (Combustion Turbine) | 240 | No | 0 | 8 |  | 28
GFID100497 | SCE | 92509 | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Other (Combustion Turbine) | 240 | No | 0 | 5 |  | 45
GFID100498 | SCE | 92509 | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Solar PV + Other (Combustion Turbine) | 4164.7 | No | 0 |  |  | 38
GFID100503 | SCE | 91390 | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 15 | No | 0 | 6 | 11 | [7 empty] | 0 | Fast Track Initial Review | 53 |  | 262
GFID100504 | SCE | 91320 | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 10 | No | 0 |  | 9 | [7 empty] | 0 | Fast Track Initial Review | 18 |  | 77
GFID100505 | SCE | 93105 | Non-NEM | Rule 21 Non-Export | Resolved-Withdrawn | Battery Storage | 10 | No | 0 |  | 15 | [7 empty] | 0 | Fast Track Initial Review
GFID100509 | SCE | 93105 | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 10 | No | 0 | 4 | 14 | [7 empty] | 0 | Fast Track Initial Review | 65 |  | 158
GFID100510 | SCE | 93060 | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 30 | No | 0 | 2 | 6 | [7 empty] | 0 | Fast Track Initial Review | 31 |  | 135
GFID100514 | SCE | 92886 | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 11.4 | No | 0 | 4 | 7 | [7 empty] | 0 | Fast Track Initial Review | 42
GFID100518 | SCE | 93065 | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 10 | No | 0 |  | 3 | [7 empty] | 0 | Fast Track Initial Review | 14 |  | 181
GFID100521 | SCE | 90650 | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Solar PV + Battery Storage | 1746.5 | No | 0 | 2 | 19
GFID100524 | SCE | 93065 | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 572 | No | 0 |  | 10 | [7 empty] | 0 | Fast Track Initial Review | 118
GFID100528 | SCE | 91776 | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 929.5 | No | 0 |  | 11 | [7 empty] | 0 | Fast Track Initial Review | 69
GFID100530 | SCE | 92867 | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 210 | No | 0 | 0 | 19 | [7 empty] | 3 | Fast Track Initial Review | 41 |  | 217
GFID100532 | SCE | 92571 | Non-NEM | Rule 21 Non-Export | Pending-MomentaryParallel Review | Internal Combustion Engine | 3125 | No | 0 | 5
GFID100535 | SCE | 91350 | Non-NEM | Rule 21 Non-Export | Pending-MomentaryParallel Review | Other (Combustion Turbine) | 1500 | No | 0 | 10
GFID100539 | SCE | 90274 | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 10 | No | 0 | 10 | 25 | [7 empty] | 0 | Fast Track Initial Review | 31
GFID100540 | SCE | 93108 | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 10 | No | 0 |  | 12 | [7 empty] | 0 | Fast Track Initial Review | 30 |  | 175
GFID100544 | SCE | 93108 | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 10 | No | 0 | 6 | 8 | [7 empty] | 0 | Fast Track Initial Review | 58 |  | 93
GFID100547 | SCE | 92262 | Non-NEM | Rule 21 Non-Export | Resolved-Withdrawn | Battery Storage | 210 | No | 0 | 5
GFID100548 | SCE | 92262 | Non-NEM | Rule 21 Non-Export | Resolved-Withdrawn | Battery Storage | 210 | No | 0
GFID100549 | SCE | 92373 | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 210 | No | 0 |  | 4 | [7 empty] | 0 | Fast Track Initial Review | 27 |  | 215
GFID100550 | SCE | 93023 | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 15 | No | 0 |  | 6 | [7 empty] | 0 | Fast Track Initial Review | 50 |  | 205
GFID100551 | SCE | 93023 | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 20 | No | 0 |  | 12 | [7 empty] | 0 | Fast Track Initial Review | 51 |  | 205
GFID100552 | SCE | 92530 | Non-NEM | Rule 21 Non-Export | Resolved-Withdrawn | Battery Storage | 30 | No | 0 | 4
GFID100556 | SCE | 93010 | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 210 | No | 0 | 3 | 2 | [7 empty] | 0 | Fast Track Initial Review | 22
GFID100559 | SCE | 92399 | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 350 | No | 0 |  | 12 | [7 empty] | 0 | Fast Track Initial Review | 73 |  | 293
GFID100560 | SCE | 91786 | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 210 | No | 0 | 9 | 13 | [7 empty] | 1 | Fast Track Initial Review | 45 |  | 280
GFID100561 | SCE | 93023 | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 20 | No | 0 |  | 10 | [7 empty] | 0 | Fast Track Initial Review | 27 |  | 110
GFID100565 | SCE | 91355 | Non-NEM | Rule 21 Non-Export | Resolved-Completed | Internal Combustion Engine | 6800 | No | 0 | [13 empty] | 260
GFID100568 | SCE | 92320 | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 350 | No | 0 | 1 | 15 | [7 empty] | 0 | Fast Track Initial Review | 281 |  | 400
GFID100569 | SCE | 90402 | Non-NEM | Rule 21 Non-Export | Resolved-Withdrawn | Battery Storage | 20 | No | 0
GFID100570 | SCE | 91302 | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 15 | No | 0 |  | 11 | [7 empty] | 0 | Fast Track Initial Review | 18 |  | 65
GFID100572 | SCE | 91362 | Non-NEM | Rule 21 Non-Export | Resolved-Withdrawn | Solar PV + Battery Storage + Internal Combustion Engine | 1968 | No | 0 | 8
GFID100573 | SCE | 93036 | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 572 | No | 0 | 5 | 8 | [7 empty] | 2 | Fast Track Initial Review | 28
GFID100574 | SCE | 91702 | Non-NEM | Rule 21 Non-Export | Pending Pre-Construction | Battery Storage | 1341 | No | 0 |  | 12 |  |  | 33 |  |  |  |  | 14 | Supplemental Review Cost Report | 25
GFID100576 | SCE | 90221 | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 5 | No | 0 | 4 | 6 | [7 empty] | 0 | Fast Track Initial Review | 67 |  | 150
GFID100589 | SCE | 93561 | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 951.3 | No | 0 |  | 13 |  | 24 | [5 empty] | 0 | Supplemental Review | 51
GFID100591 | SCE | 92309 | Non-NEM | Rule 21 Non-Export | Pending-Construction | Solar PV + Battery Storage | 1611 | No | 0 |  | 11 |  | 8 | [5 empty] | 6 | Supplemental Review | 107
GFID100593 | SCE | 92317 | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 630 | No | 0 |  | 12 | [7 empty] | 0 | Fast Track Initial Review | 63 |  | 387
GFID100596 | SCE | 91342 | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 10 | No | 0 | 9 | 12 | [7 empty] | 3 | Fast Track Initial Review | 19
GFID100601 | SCE | 92210 | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 50 | No | 0 |  | 11 | [7 empty] | 0 | Fast Track Initial Review | 59 |  | 152
GFID100606 | SCE | 91390 | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 10 | No | 0 |  | 5 | [7 empty] | 0 | Fast Track Initial Review | 14 |  | 43
GFID100607 | SCE | 93060 | Non-NEM | Rule 21 Non-Export | Resolved-Terminated | Battery Storage | 10 | No | 0 |  | 2 | [7 empty] | 0 | Fast Track Initial Review | 49 |  | 111
GFID100608 | SCE | 93065 | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Battery Storage | 420 | No | 0 | 4 | 11 |  | 20 | [5 empty] | 0 | Supplemental Review
GFID100612 | SCE | 92397 | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 174 | No | 0 | 26 | 4 | [7 empty] | 0 | Fast Track Initial Review | 43 |  | 201
GFID100615 | SCE | 90221 | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 490 | No | 0 |  | 7 | [7 empty] | 0 | Fast Track Initial Review | 35
GFID100616 | SCE | 91770 | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 210 | No | 0 | 10 | 5 | [7 empty] | 2 | Fast Track Initial Review | 16 |  | 161
GFID100617 | SCE | 90660 | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 210 | No | 0 |  | 10 | [7 empty] | 0 | Fast Track Initial Review | 75 |  | 239
GFID100630 | SCE | 93065 | Non-NEM | Rule 21 Non-Export | Resolved-Withdrawn | Battery Storage | 1859 | No | 0 | 4
GFID100632 | SCE | 92780 | Non-NEM | Rule 21 Non-Export | Resolved-Withdrawn | Other | 436 | No | 0 | 10
GFID100635 | SCE | 90275 | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 10 | No | 0 | #VALUE! | 12 | [7 empty] | 0 | Fast Track Initial Review | 50 |  | 243
GFID100637 | SCE | 93550 | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 572 | No | 0 |  | 10 |  | 15 | [5 empty] | 14 | Supplemental Review | 23
GFID100639 | SCE | 91765 | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Battery Storage | 210 | No | 0 | 2 | 16 | [7 empty] | 0 | Fast Track Initial Review
GFID100642 | SCE | 93101 | Non-NEM | Rule 21 Non-Export | Resolved-Withdrawn | Battery Storage | 10 | No | 0 | 30
GFID100647 | SCE | 93541 | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 10 | No | 0 | 4 | 14 | [7 empty] | 0 | Fast Track Initial Review | 26
GFID100648 | SCE | 91706 | Non-NEM | Rule 21 Non-Export | Resolved-Withdrawn | Internal Combustion Engine | 308 | No | 0
GFID100649 | SCE | 93023 | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 10 | No | 0 | 11 | 6 | [7 empty] | 5 | Fast Track Initial Review | 27 |  | 123
GFID100650 | SCE | 91307 | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 10 | No | 0 | 2 | 10 | [7 empty] | 1 | Fast Track Initial Review | 23 |  | 106
GFID100652 | SCE | 92382 | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 490 | No | 0 | 5 | 7 | [7 empty] | 0 | Fast Track Initial Review | 60 |  | 184
GFID100653 | SCE | 93063 | Non-NEM | Rule 21 Non-Export | Resolved-Withdrawn | Battery Storage | 350 | No | 0
GFID100657 | SCE | 90275 | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 10 | No | 0 | 4 | 13 | [7 empty] | 0 | Fast Track Initial Review | 15
GFID100667 | SCE | 93238 | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 174 | No | 0 | 5 | 15 | [7 empty] | 0 | Fast Track Initial Review | 86
GFID100668 | SCE | 90815 | Non-NEM | Rule 21 Non-Export | Pending-Construction | Solar PV + Battery Storage | 6405 | No | 0 | 15 | 11 | [7 empty] | 0 | Fast Track Initial Review | 28
GFID100669 | SCE | 93063 | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Battery Storage | 210 | No | 0 | 8 | 14 | [7 empty] | 15 | Fast Track Initial Review
GFID100670 | SCE | 91754 | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 210 | No | 0 | 4 | 13 | [7 empty] | 0 | Fast Track Initial Review | 47
GFID100671 | SCE | 93063 | Non-NEM | Rule 21 Non-Export | Pending Review | Battery Storage | 210 | No | 0 | 7
GFID100673 | SCE | 93063 | Non-NEM | Rule 21 Non-Export | Pending-Resubmission | Solar PV + Battery Storage | 280 | No | 0 | 9
GFID100675 | SCE | 91791 | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 280 | No | 0 | 9 | 17 |  | 12 | [5 empty] | 0 | Supplemental Review | 21 |  | 209
GFID100680 | SCE | 93001 | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 490 | No | 0 | 0 | 4 | [7 empty] | 0 | Fast Track Initial Review | 24 |  | 217
GFID100682 | SCE | 93065 | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 490 | No | 0 | 6 | 6 | [7 empty] | 0 | Fast Track Initial Review | 49
GFID100684 | SCE | 93003 | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 10 | No | 0 | 3 | 2 | [7 empty] | 0 | Fast Track Initial Review | 44
GFID100685 | SCE | 93021 | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 140 | No | 0 |  | 0 | [7 empty] | 0 | Fast Track Initial Review | 59 |  | 188
GFID100686 | SCE | 92320 | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 643.5 | No | 0 |  | 16 | [7 empty] | 0 | Fast Track Initial Review | 133
GFID100687 | SCE | 92708 | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 210 | No | 0 | 11 | 3 | [7 empty] | 0 | Fast Track Initial Review | 36
GFID100688 | SCE | 90303 | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 210 | No | 0 | 6 | 3 | [7 empty] | 0 | Fast Track Initial Review | 23 |  | 271
GFID100690 | SCE | 93063 | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 5 | No | 0 | 6 | 12 | [7 empty] | 0 | Fast Track Initial Review | 40 |  | 103
GFID100692 | SCE | 92604 | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 280 | No | 0 |  | 12 | [7 empty] | 0 | Fast Track Initial Review | 48 |  | 158
GFID100694 | SCE | 90660 | Non-NEM | Rule 21 Non-Export | Resolved-Withdrawn | Solar PV + Battery Storage + Fuel Cell | 1400 | No | 0
GFID100702 | SCE | 93238 | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 140 | No | 0 |  | 11 | [7 empty] | 0 | Fast Track Initial Review | 69
GFID100704 | SCE | 93541 | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 10 | No | 0 | 6 | 11 | [7 empty] | 0 | Fast Track Initial Review | 25
GFID100705 | SCE | 93225 | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 10 | No | 0 | 9 | 12 | [7 empty] | 0 | Fast Track Initial Review | 35 |  | 128
GFID100706 | SCE | 92583 | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 210 | No | 0 | 0 | 13 |  | 17 | [5 empty] | 0 | Supplemental Review | 62 |  | 193
GFID100707 | SCE | 91301 | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 10 | No | 0 | 10 | 13 | [7 empty] | 0 | Fast Track Initial Review | 26 |  | 62
GFID100708 | SCE | 92399 | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 280 | No | 0 |  | 16 | [7 empty] | 0 | Fast Track Initial Review | 38 |  | 203
GFID100711 | SCE | 92583 | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 140 | No | 0 | 3 | 12 |  | 24 | [5 empty] | 10 | Supplemental Review | 27 |  | 188
GFID100713 | SCE | 93063 | Non-NEM | Rule 21 Non-Export | Resolved-Withdrawn | Battery Storage | 10 | No | 0
GFID100714 | SCE | 92583 | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 210 | No | 0 |  | 12 |  | 24 | [5 empty] | 10 | Supplemental Review | 26 |  | 198
GFID100715 | SCE | 93108 | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 10 | No | 0 | 6 | 4 | [7 empty] | 0 | Fast Track Initial Review | 23 |  | 196
GFID100719 | SCE | 93015 | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 10 | No | 0 |  | 11 | [7 empty] | 0 | Fast Track Initial Review | 15 |  | 174
GFID100720 | SCE | 90242 | Non-NEM | Rule 21 Non-Export | Resolved-Withdrawn | Battery Storage | 250 | No | 0 | 8
GFID100722 | SCE | 92583 | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 210 | No | 0 | 5 | 10 |  | 30 | [5 empty] | 1 | Supplemental Review | 68 |  | 199
GFID100724 | SCE | 92530 | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 15 | No | 0 |  | 12 | [7 empty] | 0 | Fast Track Initial Review | 43
GFID100725 | SCE | 92691 | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 210 | No | 0 | 6 | 12 | [7 empty] | 2 | Fast Track Initial Review | 14 |  | 290
GFID100727 | SCE | 93021 | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 10 | No | 0 |  | 3 | [7 empty] | 0 | Fast Track Initial Review | 53
GFID100733 | SCE | 90274 | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 5 | No | 0 |  | 4 | [7 empty] | 0 | Fast Track Initial Review | 23
GFID100734 | SCE | 90815 | Non-NEM | Rule 21 Non-Export | Resolved-Withdrawn | Solar PV | 100 | No | 0 | 5
GFID100739 | SCE | 93063 | Non-NEM | Rule 21 Non-Export | Resolved-Withdrawn | Solar PV + Battery Storage | 1064.6 | No | 0 | 4
GFID100740 | SCE | 93063 | Non-NEM | Rule 21 Non-Export | Resolved-Withdrawn | Solar PV + Battery Storage | 1160 | No | 0 | 4
GFID100742 | SCE | 93063 | Non-NEM | Rule 21 Non-Export | Resolved-Withdrawn | Solar PV + Battery Storage | 382.16 | No | 0 |  |  | 41 | [6 empty] | 0 | Initial Review Cost Report
GFID100743 | SCE | 93063 | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 210 | No | 0 |  | 9 |  | 6 | [5 empty] | 0 | Supplemental Review | 35
GFID100746 | SCE | 92346 | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 210 | No | 0 | 9 | 10 | [7 empty] | 12 | Fast Track Initial Review | 13 |  | 181
GFID100747 | SCE | 92405 | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 10 | No | 0 | 1 | 13 | [7 empty] | 8 | Fast Track Initial Review | 14 |  | 76
GFID100750 | SCE | 93065 | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 210 | No | 0 | 3 | 11 | [7 empty] | 0 | Fast Track Initial Review | 48 |  | 163
GFID100755 | SCE | 92320 | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 174 | No | 0 |  | 13 |  | 18 | [5 empty] | 10 | Supplemental Review | 45 |  | 252
GFID100760 | SCE | 92548 | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 10 | No | 0 |  | 14 | [7 empty] | 0 | Fast Track Initial Review | 84 |  | 125
GFID100764 | SCE | 92882 | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 10 | No | 0 | 4 | 11 | [7 empty] | 0 | Fast Track Initial Review | 8 |  | 60
GFID100768 | SCE | 93510 | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 15 | No | 0 | 5 | 17 | [7 empty] | 0 | Fast Track Initial Review | 36 |  | 90
GFID100769 | SCE | 92399 | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 10 | No | 0 | 9 | 13 | [7 empty] | 0 | Fast Track Initial Review | 56 |  | 122
GFID100770 | SCE | 93063 | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Battery Storage | 210 | No | 0 | 1 | 39 |  | 18 | [5 empty] | 0 | Supplemental Review
GFID100772 | SCE | 93105 | Non-NEM | Rule 21 Non-Export | Resolved-Withdrawn | Battery Storage | 490 | No | 0 | 3
GFID100773 | SCE | 92346 | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 140 | No | 0 | 9 | 10 |  | 20 | [5 empty] | 0 | Supplemental Review | 104 |  | 191
GFID100774 | SCE | 92230 | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 210 | No | 0 |  | 14 |  | 12 | [5 empty] | 0 | Supplemental Review | 71 |  | 190
GFID100775 | SCE | 93105 | Non-NEM | Rule 21 Non-Export | Resolved-Withdrawn | Battery Storage | 588.9 | No | 0 | 1
GFID100776 | SCE | 90040 | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 491 | No | 0 |  | 6 | [7 empty] | 0 | Fast Track Initial Review | 164
GFID100777 | SCE | 93063 | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 10 | No | 0 | 0 | 9 | [7 empty] | 0 | Fast Track Initial Review | 16
GFID100779 | SCE | 93003 | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 10 | No | 0 |  | 7 | [7 empty] | 0 | Fast Track Initial Review | 15
GFID100780 | SCE | 91350 | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 10 | No | 0 | 10 | 8 | [7 empty] | 0 | Fast Track Initial Review | 16
GFID100781 | SCE | 90265 | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 10 | No | 0 |  | 25 | [7 empty] | 0 | Fast Track Initial Review | 28
GFID100782 | SCE | 93117 | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 10 | No | 0 | 4 | 11 | [7 empty] | 0 | Fast Track Initial Review | 38 |  | 251
GFID100786 | SCE | 92399 | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 572 | No | 0 |  | 13 |  | 20 | [5 empty] | 4 | Supplemental Review | 49
GFID100794 | SCE | 92867 | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 464 | No | 0 | 31 | 20 | [7 empty] | 0 | Fast Track Initial Review | 57
GFID100795 | SCE | 91320 | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Battery Storage | 100 | No | 0 | 1 | 7
GFID100798 | SCE | 91320 | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Battery Storage | 50 | No | 0 | 3 | 16
GFID100799 | SCE | 91006 | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Battery Storage | 1000 | No | 0 | 11 |  | 27
GFID100804 | SCE | 93040 | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 140 | No | 0 | 5 | 11 | [7 empty] | 0 | Fast Track Initial Review | 146
GFID100807 | SCE | 92324 | Non-NEM | Rule 21 Non-Export | Resolved-Withdrawn | Other | 60 | Yes | 0 | 25
GFID100809 | SCE | 92336 | Non-NEM | Rule 21 Non-Export | Resolved-Withdrawn | Battery Storage | 24 | No | 0
GFID100810 | SCE | 92411 | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 929.5 | No | 0 | 3 | 10 |  | 19 | [5 empty] | 0 | Supplemental Review | 26
GFID100813 | SCE | 91390 | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 10 | No | 0 |  | 13 | [7 empty] | 8 | Fast Track Initial Review | 1 |  | 84
GFID100814 | SCE | 93063 | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 10 | No | 0 | 9 | 9 | [7 empty] | 8 | Fast Track Initial Review | 5 |  | 60
GFID100815 | SCE | 92592 | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 10 | No | 0 |  | 13 | [7 empty] | 0 | Fast Track Initial Review | 97 |  | 166
GFID100819 | SCE | 92408 | Non-NEM | Rule 21 Non-Export | Resolved-Withdrawn | Battery Storage | 210 | No | 0 | 1
GFID100824 | SCE | 93510 | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 10 | No | 0 | 2 | 13 | [7 empty] | 0 | Fast Track Initial Review | 27 |  | 83
GFID100826 | SCE | 92869 | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 5 | No | 0 | 0 | 12 | [7 empty] | 1 | Fast Track Initial Review | 25 |  | 83
GFID100828 | SCE | 92410 | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 210 | No | 0 | 22 | 11 |  | 12 | [5 empty] | 0 | Supplemental Review | 15
GFID100849 | SCE | 91387 | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 10 | No | 0 | 3 | 13 | [7 empty] | 1 | Fast Track Initial Review | 20
GFID100850 | SCE | 91320 | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 10 | No | 0 | 4 | 17 | [7 empty] | 1 | Fast Track Initial Review | 13 |  | 145
GFID100851 | SCE | 92256 | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 10 | No | 0 | 9 | 17 | [7 empty] | 0 | Fast Track Initial Review | 51 |  | 118
GFID100853 | SCE | 92507 | Non-NEM | Rule 21 Non-Export | Pending-InitialReview | Battery Storage | 174 | No | 0 |  | 14
GFID100855 | SCE | 93012 | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 929.5 | No | 0 |  | 24 |  | 19 | [5 empty] | 11 | Supplemental Review | 10
GFID100856 | SCE | 92548 | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 10 | No | 0 | 1 | 14 | [7 empty] | 14 | Fast Track Initial Review | 29
GFID100857 | SCE | 91381 | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 10 | No | 0 |  | 15 | [7 empty] | 0 | Fast Track Initial Review | 91
GFID100858 | SCE | 93541 | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 10 | No | 0 | 7 | 12 | [7 empty] | 0 | Fast Track Initial Review | 29
GFID100861 | SCE | 93003 | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 10 | No | 0 | 30 | 4 | [7 empty] | 0 | Fast Track Initial Review | 44 |  | 182
GFID100863 | SCE | 93010 | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 10 | No | 0 |  | 5 | [7 empty] | 0 | Fast Track Initial Review | 19
GFID100866 | SCE | 93065 | Non-NEM | Rule 21 Non-Export | Resolved-Withdrawn | Battery Storage | 996.4 | No | 0 | 5
GFID100867 | SCE | 93012 | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 10 | No | 0 | 4 | 14 | [7 empty] | 0 | Fast Track Initial Review | 56
GFID100868 | SCE | 93527 | Non-NEM | Rule 21 Non-Export | On Hold | Battery Storage | 715 | No | 0 | 2
GFID100870 | SCE | 91706 | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 210 | No | 0 |  | 13 |  | 23 | [5 empty] | 0 | Supplemental Review | 45
GFID100873 | SCE | 92223 | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 140 | No | 0 |  | 13 |  | 18 | [5 empty] | 3 | Supplemental Review | 27
GFID100876 | SCE | 91360 | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 10 | No | 0 |  | 5 | [7 empty] | 0 | Fast Track Initial Review | 12
GFID100877 | SCE | 92870 | Non-NEM | Rule 21 Non-Export | Pending-InitialReview | Other (Microturbine) | 130 | No | 0 | 11
GFID100879 | SCE | 92311 | Non-NEM | Rule 21 Non-Export | Resolved-Withdrawn | Battery Storage | 1162.2 | No | 0 | 4
GFID100880 | SCE | 92345 | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Battery Storage | 625.8 | No | 0 | 1 | 20 | [7 empty] | 0 | Fast Track Initial Review
GFID100882 | SCE | 93065 | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 210 | No | 0 | 4 | 34 | [7 empty] | 0 | Fast Track Initial Review | 49
GFID100884 | SCE | 91733 | Non-NEM | Rule 21 Non-Export | Resolved-Withdrawn | Battery Storage | 250 | No | 0 | 3
GFID100885 | SCE | 91731 | Non-NEM | Rule 21 Non-Export | Resolved-Withdrawn | Battery Storage | 250 | No | 0 | 7
GFID100888 | SCE | 90275 | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 10 | No | 0 | 6 | 15 | [7 empty] | 0 | Fast Track Initial Review | 43
GFID100889 | SCE | 93535 | Non-NEM | Rule 21 Non-Export | Pending-InitialReview | Solar PV + Battery Storage + Internal Combustion Engine | 1956.5 | No | 0 | 0 | 15
GFID100891 | SCE | 92352 | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 7.6 | No | 0 |  | 14 | [7 empty] | 0 | Fast Track Initial Review | 35 |  | 107
GFID100892 | SCE | 92562 | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Battery Storage | 7.68 | No | 0 |  | 12 | [7 empty] | 2 | Fast Track Initial Review
GFID100895 | SCE | 92504 | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Battery Storage | 572 | No | 0 | 7 | 24 | [7 empty] | 0 | Fast Track Initial Review
GFID100908 | SCE | 91350 | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 10 | No | 0 | 4 | 7 | [7 empty] | 0 | Fast Track Initial Review | 8
GFID100909 | SCE | 92346 | Non-NEM | Rule 21 Non-Export | Resolved-Withdrawn | Battery Storage | 357.5 | No | 0 | 10
GFID100913 | SCE | 92325 | Non-NEM | Rule 21 Non-Export | Resolved-Withdrawn | Battery Storage | 10 | No | 0 | 3
GFID100917 | SCE | 91362 | Non-NEM | Rule 21 Non-Export | Resolved-Withdrawn | Solar PV + Battery Storage + Internal Combustion Engine | 1968 | No | 0 | 9
GFID100920 | SCE | 90670 | Non-NEM | Rule 21 Non-Export | Resolved-Withdrawn | Solar PV | 360 | No | 0 | 1
GFID100921 | SCE | 92301 | Non-NEM | Rule 21 Non-Export | Pending-Resubmission | Battery Storage | 804.6 | No | 0 | 4
GFID100922 | SCE | 91765 | Non-NEM | Rule 21 Non-Export | Pending-InitialReview | Battery Storage | 1287 | No | 0 | 4 |  | 34
GFID100923 | SCE | 93021 | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Battery Storage | 362.4 | No | 0 | 2 | 12
GFID100924 | SCE | 93227 | Non-NEM | Rule 21 Non-Export | Pending-Resubmission | Battery Storage | 983.4 | No | 0 | 4
GFID100927 | SCE | 91301 | Non-NEM | Rule 21 Non-Export | Resolved-Withdrawn | Battery Storage | 10 | No | 0 | 1 | 10 | [7 empty] | 0 | Fast Track Initial Review
GFID100928 | SCE | 92336 | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 7.6 | No | 0 |  | 15 | [7 empty] | 1 | Fast Track Initial Review | 27 |  | 147
GFID100934 | SCE | 93117 | Non-NEM | Rule 21 Non-Export | Resolved-Withdrawn | Internal Combustion Engine | 160 | No | 0 | 0
GFID100936 | SCE | 90660 | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Solar PV + Battery Storage + Fuel Cell | 1377.4 | No | 0 | 2 | 12 | [7 empty] | 0 | Fast Track Initial Review
GFID100940 | SCE | 93546 | Non-NEM | Rule 21 Non-Export | Resolved-Withdrawn | Solar PV + Battery Storage | 1285.5 | No | 0
GFID100942 | SCE | 92399 | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 10 | No | 0 |  | 6 | [7 empty] | 15 | Fast Track Initial Review | 28 |  | 84
GFID100943 | SCE | 91307 | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 20 | No | 0 | 42 | 14 | [7 empty] | 0 | Fast Track Initial Review | 25 |  | 67
GFID100944 | SCE | 93012 | Non-NEM | Rule 21 Non-Export | Pending-Construction | Other (Microturbine) | 130 | No | 0 |  | 9 | [7 empty] | 0 | Fast Track Initial Review | 39
GFID100945 | SCE | 92821 | Non-NEM | Rule 21 Non-Export | Pending-InitialReview | Other (Microturbine) | 1180 | No | 0 | 4 |  | 16
GFID100946 | SCE | 92562 | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Battery Storage | 7.68 | No | 0 | 1 | 12 | [7 empty] | 0 | Fast Track Initial Review
GFID100949 | SCE | 93021 | Non-NEM | Rule 21 Non-Export | Pending-InitialReview | Solar PV + Battery Storage + Internal Combustion Engine | 2322 | No | 0 | 5 |  | 27
GFID100950 | SCE | 90265 | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 10 | No | 0 | 11 | 18 | [7 empty] | 0 | Fast Track Initial Review | 7 |  | 82
GFID100951 | SCE | 93063 | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Battery Storage | 8.96 | No | 0 |  | 14 | [7 empty] | 3 | Fast Track Initial Review
GFID100952 | SCE | 93021 | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Battery Storage | 9 | No | 0 | 6 | 13
GFID100953 | SCE | 93063 | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Battery Storage | 6.4 | No | 0 | 6 | 13 | [7 empty] | 0 | Fast Track Initial Review
GFID100954 | SCE | 93063 | Non-NEM | Rule 21 Non-Export | Resolved-Withdrawn | Battery Storage | 8.96 | No | 0 |  | 10 | [7 empty] | 3 | Fast Track Initial Review
GFID100955 | SCE | 93021 | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Battery Storage | 6.4 | No | 0 |  | 12 | [7 empty] | 0 | Fast Track Initial Review
GFID100959 | SCE | 93021 | Non-NEM | Rule 21 Non-Export | Resolved-Withdrawn | Battery Storage | 6.4 | No | 0 | 6
GFID100960 | SCE | 92562 | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Battery Storage | 7.68 | No | 0 |  | 12 | [7 empty] | 0 | Fast Track Initial Review
GFID100961 | SCE | 93063 | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Battery Storage | 10.24 | No | 0 | 4 | 12 | [7 empty] | 0 | Fast Track Initial Review
GFID100962 | SCE | 93063 | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Battery Storage | 10.24 | No | 0 |  | 13 | [7 empty] | 0 | Fast Track Initial Review
GFID100963 | SCE | 90275 | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Battery Storage | 18 | No | 0 | #VALUE! | 12 | [7 empty] | 0 | Fast Track Initial Review
GFID100964 | SCE | 91360 | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Battery Storage | 18 | No | 0 | 2 | 11 | [7 empty] | 0 | Fast Track Initial Review
GFID100966 | SCE | 93063 | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Battery Storage | 18 | No | 0 | 2
GFID100972 | SCE | 92262 | Non-NEM | Rule 21 Non-Export | Pending Review | Solar PV + Battery Storage | 1796 | No | 0 | 8
GFID100973 | SCE | 90230 | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 210 | No | 0 |  | 13 | [7 empty] | 0 | Fast Track Initial Review | 30
GFID100974 | SCE | 92234 | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Solar PV + Battery Storage | 1250 | No | 0 | 12 |  | 28 | [6 empty] | 0 | Initial Review Cost Report
GFID100975 | SCE | 92270 | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Solar PV + Battery Storage | 1250 | No | 0 |  |  | 2 | [6 empty] | 0 | Initial Review Cost Report
GFID100976 | SCE | 92264 | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Solar PV + Battery Storage | 1250 | No | 0 | 0 |  | 28
GFID100977 | SCE | 92240 | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Solar PV + Battery Storage | 839 | No | 0 |  |  | 2 | [6 empty] | 0 | Initial Review Cost Report
GFID100978 | SCE | 92678 | Non-NEM | Rule 21 Non-Export | Resolved-Withdrawn | Battery Storage | 280 | No | 0 | 4
GFID100979 | SCE | 90274 | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 10 | No | 0 | 8 | 14 | [7 empty] | 0 | Fast Track Initial Review | 93
GFID100981 | SCE | 92660 | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 10 | No | 0 | 9 | 13 | [7 empty] | 0 | Fast Track Initial Review | 39
GFID100982 | SCE | 93022 | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 10 | No | 0 | 2 | 13 | [7 empty] | 0 | Fast Track Initial Review | 91
GFID100988 | SCE | 93060 | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Battery Storage | 116 | No | 0 | 4 | 15
GFID100989 | SCE | 93060 | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Battery Storage | 174 | No | 0 | 8 | 13
GFID100990 | SCE | 93060 | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Battery Storage | 116 | No | 0 | 7 | 19
GFID100991 | SCE | 93060 | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Battery Storage | 174 | No | 0 |  | 15
GFID100992 | SCE | 91360 | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 10 | No | 0 | 2 | 15 | [7 empty] | 0 | Fast Track Initial Review | 34 |  | 87
GFID100993 | SCE | 92408 | Non-NEM | Rule 21 Non-Export | Resolved-Withdrawn | Battery Storage | 375.5 | No | 0 | 5
GFID100994 | SCE | 92583 | Non-NEM | Rule 21 Non-Export | Pending-InitialReview | Battery Storage | 357.5 | No | 0 | 1
GFID100995 | SCE | 92408 | Non-NEM | Rule 21 Non-Export | Pending-InitialReview | Battery Storage | 210 | No | 0 | 7
GFID101000 | SCE | 92549 | Non-NEM | Rule 21 Non-Export | Pending-InitialReview | Battery Storage | 10 | No | 0 | 1
GFID101005 | SCE | 91320 | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Battery Storage | 10 | No | 0 | 4 | 10 | [7 empty] | 1 | Fast Track Initial Review
GFID101009 | SCE | 93105 | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 10 | No | 0 | 2 | 11 | [7 empty] | 0 | Fast Track Initial Review | 50
GFID101013 | SCE | 93065 | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 10 | No | 0 | #VALUE! | 21 | [7 empty] | 0 | Fast Track Initial Review | 17
GFID101014 | SCE | 91320 | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 10 | No | 0 | 10 | 14 | [7 empty] | 0 | Fast Track Initial Review | 71
GFID101015 | SCE | 92883 | Non-NEM | Rule 21 Non-Export | Pending-CommissioningTest | Battery Storage | 5 | No | 0 | 5 | 11 | [7 empty] | 0 | Fast Track Initial Review |  |  | 0
GFID101016 | SCE | 93063 | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 10 | No | 0 | 1 | 13 | [7 empty] | 0 | Fast Track Initial Review | 36 |  | 73
GFID101017 | SCE | 93105 | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Battery Storage | 10 | No | 0 | 4 | 12 | [7 empty] | 0 | Fast Track Initial Review
GFID101018 | SCE | 93105 | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 10 | No | 0 |  | 12 | [7 empty] | 0 | Fast Track Initial Review | 48 |  | 95
GFID101019 | SCE | 93111 | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 15 | No | 0 | 6 | 11 | [7 empty] | 7 | Fast Track Initial Review | 4
GFID101020 | SCE | 93108 | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 10 | No | 0 | 93 | 12 | [7 empty] | 0 | Fast Track Initial Review | 42
GFID101021 | SCE | 93108 | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 10 | No | 0 | 1 | 8 | [7 empty] | 0 | Fast Track Initial Review | 48
GFID101022 | SCE | 91320 | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 10 | No | 0 | 0 | 12 | [7 empty] | 1 | Fast Track Initial Review | 11
GFID101024 | SCE | 93105 | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 10 | No | 0 | 40 | 14 | [7 empty] | 0 | Fast Track Initial Review | 49
GFID101025 | SCE | 93105 | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Battery Storage | 10 | No | 0 | 0 | 13 | [7 empty] | 0 | Fast Track Initial Review
GFID101027 | SCE | 92571 | Non-NEM | Rule 21 Non-Export | Resolved-Withdrawn | Solar PV | 24.9165 | No | 0 | 4
GFID101028 | SCE | 93664 | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Battery Storage | 10 | No | 0 | 3 | 10 | [7 empty] | 0 | Fast Track Initial Review
GFID101031 | SCE | 92679 | Non-NEM | Rule 21 Non-Export | Pending-Resubmission | Battery Storage | 7.6 | No | 0 | 6
GFID101037 | SCE | 93105 | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 15 | No | 0 | 4 | 13 | [7 empty] | 3 | Fast Track Initial Review | 26
GFID101039 | SCE | 93117 | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 10 | No | 0 | 4 | 12 | [7 empty] | 0 | Fast Track Initial Review | 34 |  | 83
GFID101042 | SCE | 92358 | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 7.6 | No | 0 | 0 | 13 | [7 empty] | 3 | Fast Track Initial Review | 26
GFID101043 | SCE | 93108 | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 10 | No | 0 | 8 | 13 | [7 empty] | 0 | Fast Track Initial Review | 36
GFID101044 | SCE | 91320 | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 10 | No | 0 |  | 10 | [7 empty] | 0 | Fast Track Initial Review | 26
GFID101052 | SCE | 92691 | Non-NEM | Rule 21 Non-Export | Resolved-Withdrawn | Solar PV | 16 | No | 0
GFID101054 | SCE | 93063 | Non-NEM | Rule 21 Non-Export | Pending-Withdrawn | Battery Storage | 18 | No | 0 | 3
GFID101055 | SCE | 93063 | Non-NEM | Rule 21 Non-Export | Resolved-Withdrawn | Battery Storage | 18 | No | 0
GFID101059 | SCE | 93108 | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 10 | No | 0 | 9 | 10 | [7 empty] | 0 | Fast Track Initial Review | 32
GFID101062 | SCE | 90245 | Non-NEM | Rule 21 Non-Export | Pending-MomentaryParallel Review | Internal Combustion Engine | 2750 | No | 0
GFID101064 | SCE | 93105 | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Battery Storage | 10 | No | 0 | 2 | 12 | [7 empty] | 1 | Fast Track Initial Review |  |  | 0
GFID101070 | SCE | 91007 | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Battery Storage | 210 | No | 0 |  | 11
GFID101075 | SCE | 93063 | Non-NEM | Rule 21 Non-Export | Pending-Resubmission | Solar PV + Battery Storage | 382.16 | No | 0
GFID101077 | SCE | 93561 | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 10 | No | 0 | 3 | 13 | [7 empty] | 0 | Fast Track Initial Review | 22
GFID101079 | SCE | 93108 | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 10 | No | 0 | 7 | 12 | [7 empty] | 2 | Fast Track Initial Review | 15
GFID101082 | SCE | 90720 | Non-NEM | Rule 21 Non-Export | Pending-CommissioningTest | Solar PV + Battery Storage + Internal Combustion Engine | 31152.44 | No | 0 | [13 empty] | 0
GFID101084 | SCE | 93001 | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 10 | No | 0 |  | 15 | [7 empty] | 3 | Fast Track Initial Review |  |  | 0
GFID101085 | SCE | 92223 | Non-NEM | Rule 21 Non-Export | Pending-Withdrawn | Battery Storage | 1072.5 | No | 0 | 10 | [12 empty] | 0
GFID101089 | SCE | 93065 | Non-NEM | Rule 21 Non-Export | Pending-InitialReview | Battery Storage | 10 | No | 0
GFID101090 | SCE | 91302 | Non-NEM | Rule 21 Non-Export | Pending Review | Battery Storage | 10 | No | 0 | 1
GFID101091 | SCE | 91362 | Non-NEM | Rule 21 Non-Export | Pending-Resubmission | Battery Storage | 429 | No | 0 | 10
GFID101092 | SCE | 90266 | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Battery Storage | 15 | No | 0 | 1 | 13 | [7 empty] | 0 | Fast Track Initial Review |  |  | 0
GFID101094 | SCE | 91360 | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 10 | No | 0 | 0 | 11 | [7 empty] | 0 | Fast Track Initial Review |  |  | 0
GFID101098 | SCE | 90740 | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Battery Storage | 210 | No | 0 |  | 12 | [7 empty] | 1 | Fast Track Initial Review |  |  | 0
GFID101100 | SCE | 91731 | Non-NEM | Rule 21 Non-Export | Pending-Resubmission | Battery Storage | 500 | No | 0
GFID101102 | SCE | 91733 | Non-NEM | Rule 21 Non-Export | Pending-Resubmission | Battery Storage | 250 | No | 0 | 4
GFID101105 | SCE | 91362 | Non-NEM | Rule 21 Non-Export | Pending Review | Battery Storage | 180 | No | 0 | 0
GFID101113 | SCE | 93534 | Non-NEM | Rule 21 Non-Export | Pending-Withdrawn | Solar PV + Battery Storage | 750 | No | 0 | 4
GFID101116 | SCE | 91304 | Non-NEM | Rule 21 Non-Export | Pending-InitialReview | Battery Storage | 15 | No | 0 | 6
GFID101118 | SCE | 92688 | Non-NEM | Rule 21 Non-Export | Pending-Resubmission | Battery Storage | 572 | No | 0 | 3
GFID101125 | SCE | 92313 | Non-NEM | Rule 21 Non-Export | Pending-Withdrawn | Battery Storage | 572 | No | 0 | 3
GFID101140 | SCE | 93063 | Non-NEM | Rule 21 Non-Export | Pending-Resubmission | Solar PV + Battery Storage | 448.2 | No | 0
GFID101141 | SCE | 93063 | Non-NEM | Rule 21 Non-Export | Pending-Resubmission | Solar PV + Battery Storage | 1160 | No | 0 | 16
GFID101142 | SCE | 93010 | Non-NEM | Rule 21 Non-Export | Pending-InitialReview | Battery Storage | 7.6 | No | 0 | 8
GFID101143 | SCE | 91362 | Non-NEM | Rule 21 Non-Export | Pending-InitialReview | Battery Storage | 10 | No | 0 | 4
GFID101145 | SCE | 92688 | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Battery Storage | 357.5 | No | 0 | 2
GFID101147 | SCE | 91362 | Non-NEM | Rule 21 Non-Export | Pending Review | Battery Storage | 286 | No | 0 | 19
GFID101156 | SCE | 93060 | Non-NEM | Rule 21 Non-Export | Pending-Resubmission | Battery Storage | 643 | No | 0
GFID101157 | SCE | 92867 | Non-NEM | Rule 21 Non-Export | Pending-Withdrawn | Solar PV | 50 | No | 0 | 1
GFID101158 | SCE | 93105 | Non-NEM | Rule 21 Non-Export | Pending-InitialReview | Battery Storage | 490 | No | 0
GFID101160 | SCE | 93105 | Non-NEM | Rule 21 Non-Export | Pending-Resubmission | Battery Storage | 429 | No | 0 | 4
GFID101162 | SCE | 91362 | Non-NEM | Rule 21 Non-Export | Pending-Resubmission | Battery Storage | 214.5 | No | 0 | 9
GFID101170 | SCE | 92256 | Non-NEM | Rule 21 Non-Export | Pending Review | Battery Storage | 10 | No | 0
GFID101178 | SCE | 93063 | Non-NEM | Rule 21 Non-Export | Pending-Resubmission | Battery Storage | 20 | No | 0 | 13
GFID101181 | SCE | 91320 | Non-NEM | Rule 21 Non-Export | Pending Review | Battery Storage | 429 | No | 0 | 2
GFID8745 | SCE | 92377 | Non-NEM | Rule 21 Non-Export | Application Review In Progress | Internal Combustion Engine | 4 | No | 0 | 3
GFID8748 | SCE | 92596 | Non-NEM | Rule 21 Non-Export | IA Negotiation | Battery Storage | 0 | No | 0 | 6 | 20 | [7 empty] | 14 | Fast Track Initial Review
GFID8754 | SCE | 92346 | Non-NEM | Rule 21 Export | IA Negotiation |  | 2.25 | No | 2 |  | 16 |  |  | 34
GFID8755 | SCE | 90802 | Non-NEM | Rule 21 Non-Export | IA Negotiation | Battery Storage | 0.3 | No | 3 | 6 | 15 | [7 empty] | 15 | Fast Track Initial Review
GFID8758 | SCE | 93108 | Non-NEM | QF Conversion | In-Service | Other (Hydroelectric) | 0.13 | No | 0 | [9 empty] | 12 |  | 12 |  | 66
GFID8763 | SCE | 90815 | Non-NEM | Rule 21 Export | IA Negotiation |  | 0 | No | 0 | 3 | 13 | [7 empty] | 14 | Fast Track Initial Review
GFID8766 | SCE | #N/A | Non-NEM | Rule 21 Non-Export | Cancelled-Intake |  | 0 | No |  | 4
GFID8767 | SCE | #N/A | Non-NEM | Rule 21 Non-Export | Application Review In Progress |  | 0 | No |  | 10
GFID8768 | SCE | #N/A | Non-NEM | Rule 21 Non-Export | Application Review In Progress |  | 0 | No |  | 7
GFID8769 | SCE | 93543 | Non-NEM | Rule 21 Export | Supplemental Review Complete |  | 0.4815 | No | 0 | 4 | 14 |  |  | 36
GFID8770 | SCE | 93527 | Non-NEM | Rule 21 Export | Withdrawn |  | 0 | No | 0 |  | 14 |  | 17
GFID8771 | SCE | 93527 | Non-NEM | Rule 21 Export | Withdrawn |  | 0 | No | 1 |  | 14 |  | 17
GFID8775 | SCE | 92311 | Non-NEM | Rule 21 Export | System Impact Study In Progress |  | 3.49 | No | 3 | 5
GFID8776 | SCE | 90222 | Non-NEM | Rule 21 Export | Application Review In Progress |  | 0 | No
GFID8777 | SCE | 90222 | Non-NEM | Rule 21 Export | Application Review In Progress |  | 0 | No |  | 54
GFID8778 | SCE | 90222 | Non-NEM | Rule 21 Export | Application Review In Progress |  | 0 | No | [14 empty] | 0
GFID8779 | SCE | 93562 | Non-NEM | Rule 21 Export | Supplemental Review Complete |  | 0 | No | 2 | 16 | 2 |  | 2
GFID8781 | SCE | #N/A | Non-NEM | Rule 21 Export | Fast Track Initial Review Complete |  | 0 | No | 1 | 2
NST-137551 | SCE | 92865 | NEM | NEM | Engineering Study In Progress | Solar PV + Battery Storage | 0.603 | No | 0 | 6 | [8 empty] | 28 |  | 43
NST-147897 | SCE | 93274 | NEM | NEMA | SCE Engineer Review. Pending SCE System Upgrades | Solar PV | 128.752 | No | 0 | 8
NST-147897 | SCE | 93274 | NEM | NEM Aggregation | Construction |  | 128.752 | No | 0 | 4
NST-149934 | SCE | 92562 | NEM | NEM-ST | Application Review In Progress | Solar PV | 0 | No | 0
NST-155960 | SCE | 93257 | NEM | NEM Aggregation | IA Negotiation | Solar PV | 0 | No | 0 | 8 | 0 |  |  | 35
NST-164580 | SCE | 7656 | NEM | VNEM | Withdrawn | Solar PV | 503.303 | No | 0 | 13
NST-165244 | SCE | 93555 | NEM | NEM | Pending PTO | Solar PV | 0.15 | No | 0 |  |  | 6 | [6 empty] | 2 | Initial Review Cost Report | 22
NST-167710 | SCE | 92408 | NEM | NEM Aggregation | Pending PTO | Solar PV | 2.5 | No | 0 | 11 | 14 |  | 20 |  | 18 |  |  |  | 4 | Supplemental Review | 46
NST-167713 | SCE | 92316 | NEM | NEM Aggregation | In-Service | Solar PV | 2.6 | No | 0 | 11 |  | 28 | [6 empty] | 4 | Initial Review Cost Report | 52
NST-167897 | SCE | 93030 | NEM | NEM-ST | Construction |  | 2.5 | No | 0 | 13 | 13 |  |  |  | 18 | 2 | 22 | 49
NST-167898 | SCE | 93030 | NEM | NEM Aggregation | Construction | Solar PV | 2.5 | No | 0 | 5 | 35 |  |  |  | 18 | 2 | 22 | 49
NST-173645 | SCE | 93272 | NEM | NEM Aggregation | Application Review Complete | Solar PV | 1.8 | No | 0 | 7 | 15 |  |  |  | 5 |  |  | 63
NST-173746 | SCE | 92346 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 34.066 | No | 0 | 2 | [12 empty] | 2
NST-174421 | SCE | 93215 | NEM | NEMA | SCE Engineer Review. Pending Applicant Construction | Solar PV | 265.971 | No | 0 | 8
NST-177459 | SCE | 91711 | NEM | NEM Aggregation | Pending PTO | Solar PV | 0.59665 | No | 0 | 30 |  | 0 | [6 empty] | 1 | Initial Review Cost Report | 49
NST-177527 | SCE | 92345 | NEM | NEM | In-Service | Solar PV | 0.03 | No | 0 | 6 |  | 16 | [6 empty] | 9 | Initial Review Cost Report | 32
NST-177735 | SCE | 93291 | NEM | NEM Aggregation | Construction | Solar PV | 3.75 | No | 0 | 7 | 14 |  |  | 32 |  |  |  |  | 13 | Supplemental Review Cost Report | 43
NST-178155 | SCE | 91768 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 32.591 | No | 0 | 1 | [12 empty] | 24
NST-178193 | SCE | 91766 | NEM | NEMA | Withdrawn | Solar PV | 41.336 | No | 0 | 12
NST-178235 | SCE | 92408 | NEM | NEMA | Withdrawn | Solar PV | 291.975 | No | 0
NST-178278 | SCE | 92354 | NEM | NEM Aggregation | Construction | Solar PV | 0 | No | 0 | 22 |  | 29 | [6 empty] | 16 | Initial Review Cost Report | 22
NST-178295 | SCE | 92354 | NEM | NEMA | SCE System Upgrades. Pending Local Planner Process | Solar PV | 114.05 | No | 0 | 7
NST-178295 | SCE | 92354 | NEM | NEM Aggregation | Construction | Solar PV | 114.05 | No | 0 | 3
NST-178439 | SCE | 93292 | NEM | NEM Aggregation | Transferred to NEM | Solar PV | 0 | No | 0 | 3
NST-178602 | SCE | 93105 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 30 | No | 0 | [13 empty] | 122
NST-178637 | SCE | 92503 | NEM | NEMA | Withdrawn | Solar PV | 46.639 | No | 0
NST-178787 | SCE | 92320 | NEM | NEMA | Withdrawn | Solar PV | 55.2 | No | 0
NST-178962 | SCE | 92688 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 41.611 | No | 0 | [13 empty] | 90
NST-178986 | SCE | 92225 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 286.806 | No | 0 | 5 | [12 empty] | 161
NST-179136 | SCE | 91789 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 167.982 | No | 0 | [13 empty] | 420
NST-179182 | SCE | 92780 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 158.155 | No | 0 | 8 | [12 empty] | 82
NST-179344 | SCE | 92620 | NEM | VNEM | NGOM Installation. Pending ESR Violation Corrections | Solar PV | 82.879 | No | 0 | #VALUE! | [16 empty] | 5
NST-179352 | SCE | 92620 | NEM | VNEM | NGOM Installation. Pending ESR Violation Corrections | Solar PV | 70.467 | No | 0 | 3 | [16 empty] | 5
NST-179530 | SCE | 92270 | NEM | NEMA | Withdrawn | Solar PV + Battery Storage | 55.696 | No | 0
NST-179663 | SCE | 93014 | NEM | Other-MT | NEMI - PTO Issued | Solar PV | 165.396 | No | 0 | 8 | [12 empty] | 230
NST-179671 | SCE | 93063 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 680.828 | No | 0 | 10 | [12 empty] | 244
NST-179730 | SCE | 93060 | NEM | NEMA | Withdrawn | Solar PV | 182.069 | No | 0
NST-179880 | SCE | 93230 | NEM | NEMA | Withdrawn | Solar PV | 2867.296 | No | 0
NST-179880 | SCE | 93230 | NEM | NEM-ST | Withdrawn | Solar PV | 2867.296 | No | 0 | 7 | 14 |  |  | 35
NST-180019 | SCE | 92887 | NEM | VNEM | NEMI - PTO Issued | Solar PV | 205.067 | No | 0 | 4 | [12 empty] | 235 |  |  |  | 37 | 0
NST-180252 | SCE | 92841 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 33.561 | No | 0 |  | 3 | [11 empty] | 49
NST-180317 | SCE | 92688 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 220.502 | No | 0 | 0 | [12 empty] | 121
NST-180450 | SCE | 90222 | NEM | NEM-FC | NEMI - PTO Issued | Fuel Cell - Renewable | 787.5 | No | 0 | 4 | [12 empty] | 113
NST-180450 | SCE | 90222 | NEM | NEM | Transferred to NEM | Fuel Cell | 787.5 | No | 2 | [13 empty] | 100
NST-180659 | SCE | 92241 | NEM | NEM | Construction | Solar PV | 214.249 | No | 0 | 14 | 15 |  |  | 21 |  |  |  |  | 14 | Supplemental Review Cost Report | 69
NST-180659 | SCE | 92241 | NEM | NEMA | SCE Engineer Review. Pending SCE System Upgrades | Solar PV | 214.249 | No | 0
NST-180728 | SCE | 90230 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 32.616 | No | 0 | 11 | [12 empty] | 51
NST-181017 | SCE | 93265 | NEM | NEMA | Cancelled By Applicant | Solar PV + Battery Storage | 243.4 | No | 0 |  | 5
NST-181189 | SCE | 92210 | NEM | NEMA | NEMI - PTO Issued | Solar PV + Battery Storage | 34.42 | No | 0 | [13 empty] | 19
NST-181290 | SCE | 91748 | NEM | NEMA | Withdrawn | Solar PV | 235.488 | No | 0 | 6
NST-181433 | SCE | 92704 | NEM | NEMA | Withdrawn | Solar PV | 64.212 | No | 0 | 5
NST-181442 | SCE | 93230 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 59.285 | No | 0 | #VALUE! | [12 empty] | 232
NST-181602 | SCE | 92210 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 30.965 | No | 0 | 9 | [12 empty] | 71
NST-181721 | SCE | 92602 | NEM | VNEM | NGOM Installation. Pending AHJ Panel Permit | Solar PV | 62.484 | No | 0 | 3 | [16 empty] | 140
NST-181726 | SCE | 92602 | NEM | VNEM | NGOM Installation. Pending AHJ Panel Permit | Solar PV | 111.746 | No | 0 | 4 | [16 empty] | 141
NST-181731 | SCE | 92602 | NEM | VNEM | NGOM Installation. Pending AHJ Panel Permit | Solar PV | 113.586 | No | 0 | [17 empty] | 105
NST-181893 | SCE | 90250 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 65.126 | No | 0 | 4 | [12 empty] | 187
NST-182021 | SCE | 93257 | NEM | NEMA | Withdrawn | Solar PV | 31.853 | No | 0
NST-182036 | SCE | 93230 | NEM | NEMA | SCE Engineer Review. Pending SCE System Upgrades | Solar PV | 2867.296 | No | 0 | 4
NST-182036 | SCE | 93230 | NEM | NEM-ST | In-Service | Solar PV | 2867.296 | No | 0 | 3 | 14 |  |  | 35 |  |  |  |  | 14 | Supplemental Review Cost Report | 36
NST-182245 | SCE | 93519 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 35.591 | No | 0 | [13 empty] | 5
NST-182426 | SCE | 90640 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 66.6 | No | 0 | 1 | [12 empty] | 25
NST-182430 | SCE | 90640 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 66.6 | No | 0 | [13 empty] | 35
NST-182576 | SCE | 91744 | NEM | NEMA | Withdrawn | Solar PV | 133.349 | No | 0 | 55 | [12 empty] | 17
NST-182712 | SCE | 93516 | NEM | NEMA | Withdrawn | Solar PV | 407.95 | No | 0
NST-183066 | SCE | 92557 | NEM | NEMA | Withdrawn | Solar PV | 30.665 | No | 0
NST-183344 | SCE | 92376 | NEM | VNEM | NGOM Requirements Met. Pending Local Planner SO Release | Solar PV | 98.412 | No | 0
NST-183381 | SCE | 90242 | NEM | VNEM | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 48.435 | No | 0
NST-183386 | SCE | 90605 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 40.028 | No | 0 | 30 | [12 empty] | 91
NST-183547 | SCE | 93219 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 35.502 | No | 0 | [13 empty] | 140
NST-183549 | SCE | 90242 | NEM | VNEM | Withdrawn | Solar PV | 46.598 | No | 0
NST-183551 | SCE | 90242 | NEM | VNEM | Withdrawn | Solar PV | 47.317 | No | 0 | 7
NST-183554 | SCE | 90242 | NEM | VNEM-SOMAH | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 75.123 | No | 0 | 1
NST-183613 | SCE | 93555 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 763 | No | 0 | [13 empty] | 122
NST-183613 | SCE | 93555 | NEM | NEM-ST | In-Service | Solar PV | 763 | No | 0 | 6 | 0 | [7 empty] | 0 | Fast Track Initial Review | 43 |  | 122
NST-183676 | SCE | 92284 | NEM | VNEM | Meter Request Released. Pending NGOM installation | Solar PV | 81.365 | No | 0
NST-183680 | SCE | 92284 | NEM | VNEM | NGOM Installation. Pending New Service Request and AHJ Panel Permit | Solar PV | 87.588 | No | 0
NST-184015 | SCE | 92320 | NEM | NEMA | Withdrawn | Solar PV | 50.061 | No | 0
NST-184127 | SCE | 90022 | NEM | VNEM | NGOM Installation. Pending AHJ Panel Permit | Solar PV | 114.919 | No | 0 | 4
NST-184151 | SCE | 92270 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 33.545 | No | 0 | 16 | [12 empty] | 34
NST-184165 | SCE | 92234 | NEM | VNEM | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 37.2 | No | 0 | 41
NST-184172 | SCE | 92234 | NEM | VNEM | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 96 | No | 0 | 6
NST-184175 | SCE | 92234 | NEM | VNEM | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 31.6 | No | 0 | 6
NST-184177 | SCE | 92234 | NEM | VNEM | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 54 | No | 0 | 2
NST-184435 | SCE | 93230 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 269.851 | No | 0 | 48 | [12 empty] | 352
NST-184642 | SCE | 90503 | NEM | NEMA | NEMI - Returned from Engineering | Solar PV | 68.816 | No | 0 | 3
NST-184733 | SCE | 91746 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 64.36 | No | 0 | [13 empty] | 84
NST-184818 | SCE | 93539 | NEM | NEMA | Withdrawn | Solar PV | 69.017 | No | 0
NST-185013 | SCE | 91024 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 31.002 | No | 0 | 1 | 4 | [11 empty] | 163
NST-185057 | SCE | 93230 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 333.058 | No | 0 | 17 | [12 empty] | 339
NST-185072 | SCE | 91770 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 995.253 | No | 0 | 8 | [12 empty] | 156
NST-185130 | SCE | 92840 | NEM | VNEM | NGOM Installation. Pending AHJ Panel Permit | Solar PV | 75.864 | No | 0 | 2 | [16 empty] | 132
NST-185356 | SCE | 90266 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 170.071 | No | 0 | 8 | 4 | [11 empty] | 77
NST-185361 | SCE | 92260 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 37.333 | No | 0 | 5 | [12 empty] | 15
NST-185620 | SCE | 91764 | NEM | NEMA | SCE Engineer. Supplemental Review In Progress | Solar PV | 2226.453 | No | 0 | 0
NST-185620 | SCE | 91764 | NEM | NEM-ST | Withdrawn | Solar PV | 2226.453 | No | 0 | 3
NST-185673 | SCE | 92410 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 266.048 | No | 0 | 0 | [12 empty] | 217
NST-185905 | SCE | 92562 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 32.09 | No | 0 | 34 | [12 empty] | 14
NST-185916 | SCE | 92627 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 79.408 | No | 0 | 6 | [12 empty] | 21
NST-186160 | SCE | 91730 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 165.319 | No | 0 | 8 | [12 empty] | 367
NST-186173 | SCE | 92840 | NEM | NEM-ST | Transferred to NEM | Solar PV | 0 | No | 0
NST-186189 | SCE | 91766 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 41.336 | No | 0 | 30 | [12 empty] | 26
NST-186196 | SCE | 90630 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV + Battery Storage | 341.25 | No | 0 | 1
NST-186216 | SCE | 92336 | NEM | VNEM | NEMI - PTO Issued | Solar PV | 45.172 | No | 0 | [13 empty] | 354 |  |  |  | 94
NST-186287 | SCE | 92408 | NEM | NEMA | Withdrawn | Solar PV | 43.991 | No | 0
NST-186495 | SCE | 91763 | NEM | VNEM | SCE System Upgrades. Pending Local Planner Process | Solar PV | 410.612 | No | 0 | 5
NST-186495 | SCE | 91763 | NEM | NEM-ST | Construction | Solar PV | 410.612 | No | 0 |  |  | 20 | [6 empty] | 3 | Initial Review Cost Report | 21
NST-186511 | SCE | 92553 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 137.035 | No | 0
NST-186828 | SCE | 90250 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 77.371 | No | 0 | 8 | [12 empty] | 224
NST-186860 | SCE | 90040 | NEM | NEMA | Withdrawn | Solar PV + Battery Storage | 725.873 | No | 0
NST-186949 | SCE | 92240 | NEM | VNEM | NEMI - PTO Issued | Solar PV | 30.832 | No | 0 | [13 empty] | 400
NST-186951 | SCE | 92240 | NEM | VNEM | NEMI - PTO Issued | Solar PV | 46.248 | No | 0 | 3 | [12 empty] | 376
NST-186961 | SCE | 92240 | NEM | VNEM | NEMI - PTO Issued | Solar PV | 30.832 | No | 0 | [13 empty] | 369
NST-186964 | SCE | 92240 | NEM | VNEM | NEMI - PTO Issued | Solar PV | 30.832 | No | 0 | 5 | [12 empty] | 376
NST-186968 | SCE | 92240 | NEM | VNEM | NEMI - PTO Issued | Solar PV | 30.832 | No | 0 | [13 empty] | 372
NST-186970 | SCE | 92240 | NEM | VNEM | NEMI - PTO Issued | Solar PV | 30.832 | No | 0 | 6 | [12 empty] | 383
NST-186974 | SCE | 92240 | NEM | VNEM | NEMI - PTO Issued | Solar PV | 30.832 | No | 0 | [13 empty] | 370
NST-187024 | SCE | 90805 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 248.003 | No | 0 | [13 empty] | 144
NST-187270 | SCE | 90044 | NEM | VNEM | NGOM Installation. Pending AHJ Panel Permit | Solar PV | 106.734 | No | 0
NST-187386 | SCE | 92704 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 64.212 | No | 0 | 3 | [12 empty] | 52
NST-187426 | SCE | 91763 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 380.485 | No | 0 | 5 | [12 empty] | 220
NST-187430 | SCE | 91763 | NEM | VNEM | Withdrawn | Solar PV | 239.953 | No | 0
NST-187547 | SCE | 93550 | NEM | VNEM | Withdrawn | Solar PV | 81.045 | No | 0
NST-187553 | SCE | 93550 | NEM | VNEM | Withdrawn | Solar PV | 94.667 | No | 0 | 4
NST-187580 | SCE | 92411 | NEM | NEMA | SCE Engineer Review. Pending Applicant Construction | Solar PV | 333.927 | No | 0 | 13
NST-187582 | SCE | 92404 | NEM | NEMA | SCE Engineer Review. Pending Applicant Construction | Solar PV | 459.15 | No | 0 | 6
NST-187587 | SCE | 92407 | NEM | NEMA | SCE Engineer Review. Pending Applicant Construction | Solar PV | 822.296 | No | 0
NST-187589 | SCE | 92346 | NEM | NEMA | Withdrawn | Solar PV | 2489.614 | No | 0
NST-187641 | SCE | 90401 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 93.203 | No | 0 | 4 | [12 empty] | 169
NST-187650 | SCE | 90404 | NEM | NEMA | Withdrawn | Solar PV | 33.42 | No | 0
NST-187661 | SCE | 90404 | NEM | NEMA | Withdrawn | Solar PV | 79.862 | No | 0
NST-187732 | SCE | 90241 | NEM | VNEM | Meter Request Released. Pending NGOM installation | Solar PV | 47.397 | No | 0 | 7
NST-187750 | SCE | 92562 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 154.225 | No | 0 | 10 | [12 empty] | 10
NST-187773 | SCE | 93001 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 33.349 | No | 0 | #VALUE! | [12 empty] | 21
NST-188311 | SCE | 93291 | NEM | NEM Aggregation | Construction | Solar PV | 981.745 | No | 0 |  | 14 |  |  | 24 |  |  |  |  | 12 | Supplemental Review Cost Report | 40
NST-188311 | SCE | 93291 | NEM | NEMA | SCE Engineer Review. Pending SCE System Upgrades | Solar PV | 981.745 | No | 0 | 30
NST-188321 | SCE | 92590 | NEM | VNEM | NGOM Installation. Pending AHJ Panel Permit | Solar PV | 94.208 | No | 0 | 3 | [16 empty] | 104
NST-188322 | SCE | 92590 | NEM | VNEM | NGOM Installation. Pending AHJ Panel Permit | Solar PV | 93.484 | No | 0 | 3 | [16 empty] | 104
NST-188324 | SCE | 92590 | NEM | VNEM | NGOM Installation. Pending AHJ Panel Permit | Solar PV | 88.411 | No | 0 | 4 | [16 empty] | 104
NST-188375 | SCE | 91016 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 57.825 | No | 0 | 8 | [12 empty] | 153
NST-188376 | SCE | 90305 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 61.441 | No | 0 | [13 empty] | 110
NST-188456 | SCE | 92780 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 34.855 | No | 0 | 0 | [12 empty] | 38
NST-188481 | SCE | 90255 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 643.61 | No | 0 | [13 empty] | 327
NST-188491 | SCE | 92408 | NEM | NEMA | SCE System Upgrades. Pending Local Planner Process | Solar PV | 291.975 | No | 0
NST-188491 | SCE | 92408 | NEM | NEM-ST | Construction | Solar PV | 291.975 | No | 0 |  | 12 |  |  | 20
NST-188493 | SCE | 93247 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 108.246 | No | 0 | 15 | [12 empty] | 334
NST-188565 | SCE | 92405 | NEM | NEMA | SCE Engineer Review. Pending Applicant Construction | Solar PV | 869.602 | No | 0 | 3
NST-188568 | SCE | 92405 | NEM | NEMA | NEMI - Conditional PTO | Solar PV | 445.236 | No | 0 | [13 empty] | 397
NST-188579 | SCE | 93274 | NEM | NEMA | SCE Engineer Assigned. Pending Technical Review | Solar PV | 666.116 | No | 0 | 9
NST-188579 | SCE | 93274 | NEM | NEM Aggregation | Supplemental Review Complete | Solar PV | 666.116 | No | 0 | 6 | 10
NST-188585 | SCE | 92504 | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 797.56 | No | 0 | 11
NST-188590 | SCE | 91763 | NEM | NEMA | Withdrawn | Solar PV | 38.757 | No | 0 | 15
NST-188646 | SCE | 93021 | NEM | NEMA | NGOM Installation. Pending AHJ Panel Permit | Solar PV | 50.454 | No | 0 | [17 empty] | 81
NST-188795 | SCE | 92701 | NEM | NEMA | NGOM Installation. Pending Local Planner Process | Solar PV + Battery Storage | 807.788 | No | 0 | 11 | [16 empty] | 12
NST-188839 | SCE | 92701 | NEM | NEMA | Applicant Response Received. Pending SCE Engineer Review | Solar PV + Battery Storage | 185.223 | No | 0 | 2
NST-188840 | SCE | 92705 | NEM | NEMA | Cancelled By Applicant | Solar PV + Battery Storage | 207.968 | No | 0 | 5
NST-188957 | SCE | 92821 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 299.466 | No | 0 | 3 | [12 empty] | 72
NST-189093 | SCE | 93108 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 162.777 | No | 0 | 10 | [12 empty] | 69
NST-189148 | SCE | 93021 | NEM | NEM-ST | Construction | Solar PV | 511.33 | No | 0 |  | 14 | [7 empty] | 10 | Fast Track Initial Review | 22
NST-189148 | SCE | 93021 | NEM | VNEM | SCE Engineer Review. Pending Applicant Construction | Solar PV | 511.33 | No | 0 | 5
NST-189219 | SCE | 90404 | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 77.49 | No | 0 | 5
NST-189439 | SCE | 92782 | NEM | NEMA | Withdrawn | Solar PV | 238.591 | No | 0
NST-189532 | SCE | 91320 | NEM | NEMA | Withdrawn | Solar PV | 31.461 | No | 0
NST-189535 | SCE | 91360 | NEM | NEMA | Withdrawn | Solar PV | 43.79 | No | 0
NST-189675 | SCE | 90601 | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 942.055 | No | 0 | 5
NST-189710 | SCE | 92376 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 456.53 | No | 0 | 12 | [12 empty] | 329
NST-189770 | SCE | 90220 | NEM | VNEM | Withdrawn | Solar PV | 30.28 | No | 0 | 3
NST-189800 | SCE | 92408 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 43.991 | No | 0 | 3 | [12 empty] | 73
NST-189869 | SCE | 92843 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 78.295 | No | 0 | 7 | [12 empty] | 194
NST-189999 | SCE | 92701 | NEM | Other-MT | SCE Engineer Review. Pending Applicant Response | Solar PV + Battery Storage | 340.269 | No | 0 | 9
NST-190031 | SCE | 92586 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 697.32 | No | 0
NST-190261 | SCE | 91362 | NEM | NEMA | Withdrawn | Solar PV | 54.737 | No | 0 | 4
NST-190296 | SCE | 92405 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 480.021 | No | 0 | 22
NST-190308 | SCE | 92407 | NEM | NEMA | SCE Engineer Review. Pending Applicant Construction | Solar PV | 403.496 | No | 0 | 23
NST-190313 | SCE | 92415 | NEM | NEMA | SCE Engineer Review. Pending Applicant Construction | Solar PV | 271.316 | No | 0 | 2
NST-190316 | SCE | 92346 | NEM | NEMA | SCE Engineer Review. Pending Applicant Construction | Solar PV | 396.539 | No | 0 | 3
NST-190334 | SCE | 92210 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 68.448 | No | 0 | [13 empty] | 142
NST-190581 | SCE | 91733 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 40.36 | No | 0 | 6 | [12 empty] | 57
NST-190590 | SCE | 92373 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 110.822 | No | 0 | 9 | [12 empty] | 202
NST-190683 | SCE | 92509 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 443.42 | No | 0 | 9 | [12 empty] | 162
NST-190820 | SCE | 92583 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 158.647 | No | 0 | [13 empty] | 42
NST-190880 | SCE | 90266 | NEM | NEMA | Withdrawn | Solar PV | 59.525 | No | 0 | [13 empty] | 71
NST-190914 | SCE | 92870 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 154.481 | No | 0 | 2 | [12 empty] | 20
NST-191034 | SCE | 92074 | NEM | NEMA | Withdrawn | Solar PV | 33.849 | No | 0
NST-191044 | SCE | 92335 | NEM | NEMA | NEMI - Transferred to GICD | Solar PV | 130.759 | No | 0 | 1
NST-191044 | SCE | 92335 | NEM | NEM-ST | Pending PTO |  | 130.759 | No | 0
NST-191106 | SCE | 92320 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 50.061 | No | 0 | 15 | [12 empty] | 4
NST-191170 | SCE | 92270 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 32.051 | No | 0 | [13 empty] | 20
NST-191185 | SCE | 92583 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 158.647 | No | 0 | 4 | [12 empty] | 327
NST-191186 | SCE | 92582 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 122.704 | No | 0 | 6 | [12 empty] | 350
NST-191188 | SCE | 92583 | NEM | NEMA | Withdrawn | Solar PV | 332.023 | No | 0
NST-191189 | SCE | 93561 | NEM | NEMA | SCE Engineer Review. Pending Applicant Construction | Solar PV | 180.447 | No | 0 | 6
NST-191193 | SCE | 93561 | NEM | NEMA | SCE Engineer Review. Pending Applicant Construction | Solar PV | 137.14 | No | 0 | 2
NST-191194 | SCE | 93561 | NEM | NEMA | SCE Engineer Review. Pending Applicant Construction | Solar PV | 492.162 | No | 0
NST-191196 | SCE | 93561 | NEM | NEMA | Pending Agreement Approval/Execution | Solar PV + Battery Storage | 750.66 | No | 0 | 0
NST-191197 | SCE | 93561 | NEM | NEMA | SCE Engineer Review. Pending Applicant Construction | Solar PV | 151.576 | No | 0 | 6
NST-191201 | SCE | 92277 | NEM | NEMA | Withdrawn | Solar PV | 40.611 | No | 0 | 4
NST-191203 | SCE | 92277 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 150.26 | No | 0 | 2 | [12 empty] | 108
NST-191227 | SCE | 93546 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 75.679 | No | 0 | 0 | [12 empty] | 56
NST-191278 | SCE | 93257 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 31.853 | No | 0 | 5 | [12 empty] | 95
NST-191314 | SCE | 91355 | NEM | NEMA | Withdrawn | Solar PV | 318.515 | No | 0 | 2 | [12 empty] | 59
NST-191346 | SCE | 92647 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 52.299 | No | 0 | 1 | [12 empty] | 179 |  |  |  | 14
NST-191397 | SCE | 93291 | NEM | NEMA | SCE Engineer Assigned. Pending Technical Review | Solar PV | 1783.78 | No | 0
NST-191397 | SCE | 93291 | NEM | NEM Aggregation | Construction | Solar PV | 1783.78 | No | 0 | 5 | 13 |  |  | 37
NST-191399 | SCE | 92708 | NEM | NEMA | NEMI - PTO Issued | Solar PV + Battery Storage | 138.314 | No | 0 | 8 | [12 empty] | 183
NST-191584 | SCE | 91762 | NEM | NEMA | Withdrawn | Solar PV | 6062.846 | No | 0
NST-191628 | SCE | 92313 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 30.493 | No | 0 | [13 empty] | 323
NST-191683 | SCE | 93555 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 119.663 | No | 0 | 0 | [12 empty] | 9
NST-191752 | SCE | 93256 | NEM | NEMA | NEMI - Transferred to GICD | Solar PV | 1821.492 | No | 0
NST-191752 | SCE | 93256 | NEM | NEM Aggregation | System Impact Study Complete | Solar PV | 1821.492 | No | 0 | 7 |  |  |  |  | 14
NST-191790 | SCE | 92561 | NEM | NEMA | Withdrawn | Solar PV | 229.615 | No | 0 | 3
NST-191821 | SCE | 92313 | NEM | NEMA | Withdrawn | Solar PV | 94.577 | No | 0 | 13
NST-191903 | SCE | 92240 | NEM | NEMA | NEMI - Equipment Change Submitted | Solar PV | 727.784 | No | 0 | 4
NST-191954 | SCE | 91768 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 337.3 | No | 0 | 9 | [12 empty] | 175
NST-191969 | SCE | 92843 | NEM | NEMA | Withdrawn | Solar PV | 72.02 | No | 0 | 5
NST-192012 | SCE | 92701 | NEM | NEMA | NEMI - Load Justification Reviewed | Solar PV | 54.551 | No | 0 | 6
NST-192113 | SCE | 92337 | NEM | NEM-ST | IA Negotiation | Solar PV | 1282.236 | No | 0 | 49 | 15
NST-192113 | SCE | 92337 | NEM | NEMA | SCE Engineer Assigned. Pending Technical Review | Solar PV | 1282.236 | No | 0 | 4
NST-192226 | SCE | 92410 | NEM | VNEM | Withdrawn | Solar PV | 619.865 | No | 0 | 4
NST-192300 | SCE | 93536 | NEM | NEMA | Withdrawn | Solar PV | 48.541 | No | 0
NST-192359 | SCE | 90802 | NEM | NEMA | SCE Engineer. Initial Review Complete | Solar PV | 189.541 | No | 0
NST-192359 | SCE | 90802 | NEM | NEM-ST | Pending PTO | Solar PV | 189.541 | No | 0 |  | 6 | [7 empty] | 15 | Fast Track Initial Review
NST-192504 | SCE | 91362 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 57.927 | No | 0 | [13 empty] | 46
NST-192510 | SCE | 92630 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 46.141 | No | 0 | [13 empty] | 45
NST-192701 | SCE | 93023 | NEM | NEMA | NEMI - PTO Issued | Solar PV + Battery Storage | 128.082 | No | 0 | 3 | [12 empty] | 114
NST-192885 | SCE | 92590 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 36.653 | No | 0 | 4 | [12 empty] | 1
NST-193092 | SCE | 92571 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 66.517 | No | 0 | #VALUE! | [12 empty] | 90
NST-193123 | SCE | 90660 | NEM | NEMA | Withdrawn | Solar PV | 62.568 | No | 0
NST-193178 | SCE | 93065 | NEM | NEMA | Withdrawn | Solar PV | 331.58 | No | 0
NST-193331 | SCE | 92651 | NEM | NEM-ST | Withdrawn | Solar PV | 0 | No | 0
NST-193452 | SCE | 91006 | NEM | NEMA | NEMI - PTO Issued | Solar PV + Battery Storage | 40.002 | No | 0 | [13 empty] | 29
NST-193645 | SCE | 90745 | NEM | NEMA | Cancelled By Applicant | Solar PV | 340.11 | No | 0
NST-193648 | SCE | 90720 | NEM | NEMA | Withdrawn | Solar PV | 41.266 | No | 0
NST-193674 | SCE | 92503 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 46.639 | No | 0 | 8 | [12 empty] | 24
NST-193743 | SCE | 93001 | NEM | VNEM | NEMI - PTO Issued | Solar PV | 48.064 | No | 0 | 0 | [12 empty] | 302 |  |  |  | 20
NST-193744 | SCE | 93001 | NEM | VNEM | NEMI - PTO Issued | Solar PV | 57.676 | No | 0 | 6 | [12 empty] | 301 |  |  |  | 20
NST-193796 | SCE | 93539 | NEM | NEMA | Withdrawn | Solar PV | 69.017 | No | 0 | 18
NST-193836 | SCE | 92342 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 77.063 | No | 0 | [13 empty] | 99
NST-193956 | SCE | 92394 | NEM | NEMA | SCE Engineer Assigned. Pending Technical Review | Solar PV | 34319.856 | No | 0
NST-193956 | SCE | 92394 | NEM | NEM Aggregation | IA Negotiation | Solar PV | 34319.856 | No | 0 | 9
NST-194237 | SCE | 91748 | NEM | NEMA | Withdrawn | Solar PV | 235.488 | No | 0 | 17
NST-194276 | SCE | 93555 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 143.503 | No | 0 | 3 | [12 empty] | 163
NST-194404 | SCE | 92557 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 30.665 | No | 0 | 51 | [12 empty] | 279
NST-194428 | SCE | 92336 | NEM | NEMA | Withdrawn | Solar PV | 457.644 | No | 0 | 3
NST-194496 | SCE | 93230 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 333.058 | No | 0 | [13 empty] | 181
NST-194583 | SCE | 91360 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 43.214 | No | 0 | 4 | [12 empty] | 34
NST-194634 | SCE | 91706 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 54.615 | No | 0 | 8 | [12 empty] | 26
NST-194659 | SCE | 92262 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 36.832 | No | 0 | 14 | [12 empty] | 16
NST-194756 | SCE | 90704 | NEM | NEMA | SCE Engineer Assigned. Pending Technical Review | Solar PV + Battery Storage | 632.432 | No | 0
NST-194756 | SCE | 90704 | NEM | NEM-ST | On Hold |  | 632.432 | No | 0
NST-194764 | SCE | 93230 | NEM | NEM Aggregation | Withdrawn | Solar PV | 0 | No | 0
NST-194977 | SCE | 90755 | NEM | Other-NEM-V | NEMI - PTO Issued | Solar PV | 46.155 | No | 0 | [13 empty] | 77
NST-195095 | SCE | 90805 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 303.348 | No | 0 | 2
NST-195132 | SCE | 93215 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 132.698 | No | 0 | 9 | [12 empty] | 150
NST-195313 | SCE | 93274 | NEM | NEMA | SCE Engineer. Supplemental Review Complete | Solar PV | 2888.109 | No | 0 | 4
NST-195313 | SCE | 93274 | NEM | NEM-ST | Application Review In Progress | Solar PV | 2888.109 | No | 0
NST-195484 | SCE | 91762 | NEM | NEMA | Withdrawn | Solar PV | 6062.846 | No | 0 | 0
NST-195562 | SCE | 93277 | NEM | NEMA | Meter Request Released. Pending NGOM installation | Solar PV | 322.637 | No | 0 | 0
NST-195562 | SCE | 93277 | NEM | NEM-ST | Construction | Solar PV | 322.637 | No | 0 | [9 empty] | 2
NST-195661 | SCE | 92374 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 35.483 | No | 0 | 6 | [12 empty] | 56
NST-195808 | SCE | 90266 | NEM | NEMA | NEMI - Pending Permanent Service | Solar PV + Battery Storage | 34.142 | No | 0 | 6
NST-195934 | SCE | 90201 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 54.666 | No | 0 | 13 | [12 empty] | 175
NST-196012 | SCE | 93013 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 233.246 | No | 0 | 2 | [12 empty] | 160
NST-196126 | SCE | 92835 | NEM | NEMA | Withdrawn | Solar PV | 275.571 | No | 0 | 3
NST-196192 | SCE | 91320 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 31.461 | No | 0 | 1 | [12 empty] | 25
NST-196195 | SCE | 91362 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 54.737 | No | 0 | 14 | [12 empty] | 33
NST-196218 | SCE | 90040 | NEM | NEMA | NEMI - PTO Issued | Solar PV + Battery Storage | 342.455 | No | 0 | 6 | [12 empty] | 318
NST-196299 | SCE | 92074 | NEM | NEMA | Withdrawn | Solar PV | 33.849 | No | 0
NST-196306 | SCE | 93510 | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 34.396 | No | 0 | 6
NST-196317 | SCE | 93065 | NEM | NEMA | NEMI - Equipment Change Submitted | Solar PV | 140.143 | No | 0 | 5
NST-196394 | SCE | 92614 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 878.495 | No | 0 | [13 empty] | 171
NST-196494 | SCE | 91763 | NEM | VNEM | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 53.755 | No | 0
NST-196563 | SCE | 93277 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 860.628 | No | 0 | [13 empty] | 297
NST-196626 | SCE | 91355 | NEM | VNEM | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 74.891 | No | 0 | 4 | [16 empty] | 71
NST-196646 | SCE | 93110 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 332.4 | No | 0 | 0
NST-196660 | SCE | 91355 | NEM | VNEM | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 55.248 | No | 0 | 5 | [16 empty] | 71
NST-196662 | SCE | 91355 | NEM | VNEM | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 60.159 | No | 0 | 3 | [16 empty] | 73
NST-196668 | SCE | 91355 | NEM | VNEM | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 77.347 | No | 0 | [17 empty] | 71
NST-196790 | SCE | 93277 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 187.176 | No | 0 | 6 | [12 empty] | 296
NST-196800 | SCE | 93291 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 187.176 | No | 0 | 5 | [12 empty] | 315
NST-196887 | SCE | 92376 | NEM | NEMA | SCE Engineer Review. Pending Applicant Construction | Solar PV | 624.316 | No | 0 | 4
NST-197118 | SCE | 92530 | NEM | VNEM | Cancelled By Applicant | Solar PV | 331.66 | No | 0
NST-197147 | SCE | 91763 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 38.757 | No | 0 | 3
NST-197171 | SCE | 92553 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 94.49 | No | 0 | 4
NST-197197 | SCE | 90745 | NEM | VNEM | NGOM Installation. Pending New Service Request and AHJ Panel Permit | Solar PV | 40.268 | No | 0 | 6 | [16 empty] | 78
NST-197227 | SCE | 92407 | NEM | NEMA | SCE Engineer Review. Pending Applicant Construction | Solar PV | 313.057 | No | 0
NST-197230 | SCE | 92407 | NEM | NEMA | SCE Engineer Review. Pending Applicant Construction | Solar PV | 187.834 | No | 0 | 1
NST-197236 | SCE | 92407 | NEM | NEMA | SCE Engineer Review. Pending Applicant Construction | Solar PV | 211.024 | No | 0 | 1
NST-197341 | SCE | 93272 | NEM | NEMA | NEMI - Sent to Engineering | Solar PV | 800.715 | No | 0 | #VALUE!
NST-197341 | SCE | 93272 | NEM | NEM Aggregation | Construction | Solar PV | 800.715 | No | 0 | 0 | 9 |  |  | 31 |  |  |  |  | 5 | Supplemental Review Cost Report | 22
NST-197515 | SCE | 92262 | NEM | NEMA | Withdrawn | Solar PV | 31.536 | No | 0 | [13 empty] | 3
NST-197545 | SCE | 92663 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 31.827 | No | 0 | 35
NST-197557 | SCE | 92596 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 132.549 | No | 0 | 5
NST-197794 | SCE | 91763 | NEM | NEM-ST | Construction | Solar PV | 80.632 | No | 0 | 0 | [8 empty] | 4 |  | 52
NST-197794 | SCE | 91763 | NEM | VNEM | SCE Engineer Review. Pending SCE System Upgrades | Solar PV | 80.632 | No | 0 | 0
NST-197857 | SCE | 91763 | NEM | VNEM | SCE Engineer Review. Pending SCE System Upgrades | Solar PV | 106.669 | No | 0 | 9
NST-197886 | SCE | 92610 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 337.896 | No | 0 | 3 | [12 empty] | 304
NST-197957 | SCE | 92880 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 148.762 | No | 0 | 4 | [12 empty] | 162
NST-198052 | SCE | 91730 | NEM | NEMA | Applicant Response Received. Pending SCE Engineer Review | Solar PV | 866.874 | No | 0 | 5
NST-198058 | SCE | 91730 | NEM | NEMA | Applicant Response Received. Pending SCE Engineer Review | Solar PV | 121.362 | No | 0
NST-198066 | SCE | 93065 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 316.1 | No | 0 | 3 | [12 empty] | 142
NST-198231 | SCE | 91780 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 41.363 | No | 0 | 2 | [12 empty] | 57
NST-198252 | SCE | 90810 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 301.746 | No | 0 | 6
NST-198270 | SCE | 92392 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 50 | No | 0 | #VALUE! | [12 empty] | 77
NST-198436 | SCE | 90660 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 62.568 | No | 0 | [13 empty] | 33
NST-198538 | SCE | 91710 | NEM | NEMA | SCE Engineer Assigned. Pending Technical Review | Solar PV | 3740.773 | No | 0 | 9
NST-198538 | SCE | 91710 | NEM | NEM-ST | IA Negotiation | Solar PV | 3740.773 | No | 0 | [5 empty] | 22 | 0 | 7 | 62
NST-198742 | SCE | 92392 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 50 | No | 0 | [13 empty] | 95
NST-198752 | SCE | 91744 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 137.073 | No | 0 | 6 | [12 empty] | 27
NST-198827 | SCE | 91764 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 1641.354 | No | 0 | 5
NST-198827 | SCE | 91764 | NEM | NEM-ST | IA Negotiation | Solar PV | 1641.354 | No | 0 | 7 | 16 |  |  | 35
NST-198832 | SCE | 92260 | NEM | Other-NEM-V | NEMI - Conditional PTO | Solar PV | 85.937 | No | 0 | [13 empty] | 290
NST-199009 | SCE | 91708 | NEM | NEM-ST | Construction | Solar PV | 575.484 | No | 0 | 0 | [8 empty] | 15 |  | 28
NST-199009 | SCE | 91708 | NEM | NEMA | NEMI - Returned from Engineering | Solar PV | 575.484 | No | 0 | 3
NST-199024 | SCE | 90040 | NEM | NEM-ST | IA Negotiation | Solar PV | 725.873 | No | 0 | 0 | 0 |  |  | 34
NST-199024 | SCE | 90040 | NEM | NEMA | SCE Engineer. Supplemental Review Complete | Solar PV + Battery Storage | 725.873 | No | 0
NST-199260 | SCE | 92544 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 690.54 | No | 0 | 4 | [12 empty] | 115
NST-199299 | SCE | 92410 | NEM | VNEM | Meter Request Released. Pending NGOM installation | Solar PV | 42.03 | No | 0 | 7 | [16 empty] | 20
NST-199306 | SCE | 93108 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV + Battery Storage | 57.512 | No | 0 | 4
NST-199341 | SCE | 91011 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 57.533 | No | 0 | 1
NST-199389 | SCE | 92234 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 276.258 | No | 0 | 0 | [12 empty] | 323
NST-199579 | SCE | 92260 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 119.693 | No | 0 | #VALUE! | [12 empty] | 153
NST-199608 | SCE | 92234 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 163.882 | No | 0 | 4 | [12 empty] | 322
NST-199613 | SCE | 91710 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 525.855 | No | 0 | #VALUE! | [12 empty] | 99
NST-199653 | SCE | 91006 | NEM | NEMA | Withdrawn | Solar PV | 39.379 | No | 0
NST-199706 | SCE | 91762 | NEM | NEMA | SCE Engineer. Initial Review Complete | Solar PV | 6062.846 | No | 0 | 3
NST-199706 | SCE | 91762 | NEM | NEM-ST | Phase I Complete | Solar PV | 6062.846 | No | 0 | 4 |  |  |  |  | 20 | 16 | 16 | 63
NST-199716 | SCE | 93291 | NEM | NEMA | Pending Agreement Approval/Execution | Solar PV | 2378.373 | No | 0 | 8
NST-199716 | SCE | 93291 | NEM | NEM-ST | Construction | Solar PV | 2378.373 | No | 0 |  | 13 |  |  | 37
NST-199736 | SCE | 91362 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 48.399 | No | 0 | [13 empty] | 43
NST-200073 | SCE | 93271 | NEM | NEM-ST | Transferred to NEM | Solar PV | 0 | No | 0
NST-200175 | SCE | 93230 | NEM | NEMA | SCE Engineer Review. Pending SCE System Upgrades | Solar PV | 2907.78 | No | 0 | 4
NST-200175 | SCE | 93230 | NEM | NEM Aggregation | Construction | Solar PV | 2907.78 | No | 0 | 0 | 15 |  |  | 34 |  |  |  |  | 10 | Supplemental Review Cost Report | 99
NST-200251 | SCE | 91360 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 98 | No | 0 | #VALUE! | [12 empty] | 78
NST-200259 | SCE | 92410 | NEM | VNEM | NGOM Requirements Met. Pending Local Planner SO Release | Solar PV | 51.37 | No | 0 | [17 empty] | 20
NST-200293 | SCE | 90220 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 41.101 | No | 0 | 1 | [12 empty] | 148
NST-200315 | SCE | 90265 | NEM | NEMA | Withdrawn | Solar PV + Battery Storage | 81 | No | 0 | 4
NST-200329 | SCE | 92821 | NEM | NEMA | Withdrawn | Solar PV | 317.739 | No | 0 | 12
NST-200341 | SCE | 92865 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV + Battery Storage | 529.334 | No | 0 | 2
NST-200347 | SCE | 93230 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 257.41 | No | 0 | 36 | [12 empty] | 284
NST-200411 | SCE | 93230 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 174.211 | No | 0 | 8 | [12 empty] | 282
NST-200414 | SCE | 93230 | NEM | NEMA | NEMI - Returned from Engineering | Solar PV | 152.733 | No | 0
NST-200454 | SCE | 93021 | NEM | NEM-ST | Withdrawn | Solar PV | 1583.53 | No | 0 | 9
NST-200454 | SCE | 93021 | NEM | NEMA | Withdrawn | Solar PV + Battery Storage | 1583.53 | No | 0 | 6
NST-200473 | SCE | 93256 | NEM | NEMA | Pending Agreement Approval/Execution | Solar PV | 1124.734 | No | 0 | 5
NST-200473 | SCE | 93256 | NEM | NEM-ST | Pending PTO | Solar PV | 1124.734 | No | 0 | 5 | 15 |  |  | 34 |  |  |  |  | 3 | Supplemental Review Cost Report | 29
NST-200525 | SCE | 92835 | NEM | NEMA | Applicant Response Received. Pending SCE Engineer Review | Solar PV | 275.571 | No | 0 | 2
NST-200574 | SCE | 90401 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 51.297 | No | 0 | 4
NST-200654 | SCE | 93230 | NEM | NEMA | Withdrawn | Solar PV | 31.34 | No | 0
NST-200678 | SCE | 93247 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 63.644 | No | 0 | [13 empty] | 108
NST-200860 | SCE | 91387 | NEM | NEMA | Withdrawn | Solar PV | 70.996 | No | 0
NST-200907 | SCE | 90022 | NEM | NEMA | SCE Engineer Review. Pending Applicant Construction | Solar PV | 144.307 | No | 0
NST-200986 | SCE | 91362 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 59.4 | No | 0 | 0 | [12 empty] | 48
NST-201002 | SCE | 91006 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 37.948 | No | 0 | [13 empty] | 35
NST-201083 | SCE | 93516 | NEM | NEMA | Withdrawn | Solar PV | 407.95 | No | 0 | 3
NST-201222 | SCE | 91745 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 33.576 | No | 0 | 8 | [12 empty] | 46
NST-201244 | SCE | 92240 | NEM | NEMA | Withdrawn | Solar PV | 89.208 | No | 0
NST-201770 | SCE | 93277 | NEM | NEMA | Applicant Response Received. Pending SCE Engineer Review | Solar PV | 999.174 | No | 0 | #VALUE!
NST-201770 | SCE | 93277 | NEM | NEM Aggregation | Construction | Solar PV | 999.174 | No | 0 |  | 13 |  |  | 31
NST-201854 | SCE | 92614 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 52.021 | No | 0 | 3 | [12 empty] | 135
NST-201925 | SCE | 92335 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 34.809 | No | 0 | 9 | [12 empty] | 37
NST-201927 | SCE | 92544 | NEM | NEMA | Withdrawn | Solar PV | 30.716 | No | 0 | 3
NST-201936 | SCE | 92562 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 34.33 | No | 0 | 0 | [12 empty] | 9
NST-201942 | SCE | 91801 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 54.899 | No | 0 | [13 empty] | 52
NST-201978 | SCE | 93274 | NEM | NEMA | Applicant Response Received. Pending SCE Engineer Review | Solar PV | 905.878 | No | 0 | 8
NST-201978 | SCE | 93274 | NEM | NEM Aggregation | Construction | Solar PV | 905.878 | No | 0 | 1 | 15 |  | 20 | [5 empty] | 19 | Supplemental Review | 53
NST-202268 | SCE | 93292 | NEM | NEMA | Pending Agreement Approval/Execution | Solar PV | 333.058 | No | 0 | 8
NST-202268 | SCE | 93292 | NEM | NEM Aggregation | Pending PTO | Solar PV | 333.058 | No | 0 | 2 |  | 14 | [6 empty] | 5 | Initial Review Cost Report | 50
NST-202288 | SCE | 93256 | NEM | NEMA | Withdrawn | Solar PV | 136.614 | No | 0
NST-202352 | SCE | 91706 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 38.668 | No | 0 | 1 | [12 empty] | 50
NST-202386 | SCE | 90241 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 344.163 | No | 0 | 8 | [12 empty] | 13
NST-202800 | SCE | 92336 | NEM | NEM Aggregation | Transferred to NEM | Solar PV | 0.024951 | No | 0
NST-202821 | SCE | 91723 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 95.01 | No | 0 | 3 | [12 empty] | 137
NST-202824 | SCE | 93277 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 122.263 | No | 0 | [13 empty] | 265
NST-202829 | SCE | 93277 | NEM | NEMA | Withdrawn | Solar PV | 156.052 | No | 0
NST-202901 | SCE | 91748 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 235.488 | No | 0 | 0 | [12 empty] | 86
NST-202908 | SCE | 92392 | NEM | Other-NEM-V | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 139.168 | No | 0 | 10
NST-202910 | SCE | 92392 | NEM | Other-NEM-V | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 125.966 | No | 0
NST-202911 | SCE | 92392 | NEM | Other-NEM-V | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 88.867 | No | 0 | 3
NST-202912 | SCE | 92392 | NEM | Other-NEM-V | Withdrawn | Solar PV | 167.998 | No | 0 | #VALUE!
NST-202961 | SCE | 91791 | NEM | NEMA | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 66.227 | No | 0 | 3
NST-202964 | SCE | 91791 | NEM | NEMA | Withdrawn | Solar PV | 64.256 | No | 0
NST-202966 | SCE | 91791 | NEM | NEMA | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 61.496 | No | 0 | 0
NST-202968 | SCE | 91791 | NEM | NEMA | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 62.285 | No | 0 | #VALUE!
NST-202986 | SCE | 91791 | NEM | NEMA | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 63.467 | No | 0 | 0
NST-202989 | SCE | 91791 | NEM | NEMA | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 62.679 | No | 0
NST-203056 | SCE | 93551 | NEM | Other-NEM-V | SCE Engineer Review. Pending SCE System Upgrades | Solar PV | 93.513 | No | 0 | 0
NST-203061 | SCE | 93551 | NEM | Other-NEM-V | NGOM Installation. Pending AHJ Panel Permit | Solar PV | 88.758 | No | 0 | 10
NST-203063 | SCE | 93551 | NEM | Other-NEM-V | NGOM Installation. Pending AHJ Panel Permit | Solar PV | 80.833 | No | 0 | 9
NST-203068 | SCE | 93551 | NEM | Other-NEM-V | NGOM Installation. Pending AHJ Panel Permit | Solar PV | 53.096 | No | 0 | 25
NST-203070 | SCE | 93551 | NEM | Other-NEM-V | NGOM Installation. Pending AHJ Panel Permit | Solar PV | 66.568 | No | 0 | 8
NST-203355 | SCE | 93065 | NEM | NEMA | Withdrawn | Solar PV | 430.855 | No | 0 | 4
NST-203422 | SCE | 93291 | NEM | NEM Aggregation | Construction | Solar PV | 52.613 | No | 0 |  | 15 | [7 empty] | 1 | Fast Track Initial Review | 9
NST-203422 | SCE | 93291 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 52.613 | No | 0
NST-203530 | SCE | 91733 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 48.941 | No | 0 | 4 | [12 empty] | 34
NST-203829 | SCE | 92211 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 73.34 | No | 0 | 8 | [12 empty] | 50
NST-203847 | SCE | 92223 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 77.639 | No | 0 | 2 | [12 empty] | 93
NST-203851 | SCE | 93505 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 139.365 | No | 0 | 7
NST-203980 | SCE | 91761 | NEM | NEMA | NEMI - PTO Issued | Solar PV + Battery Storage | 795.781 | No | 0 | 8 | [12 empty] | 110 |  |  |  | 0 | 15
NST-204012 | SCE | 93117 | NEM | NEMA | Withdrawn | Solar PV | 160.234 | No | 0 | 13
NST-204045 | SCE | 91789 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 57.787 | No | 0 | [13 empty] | 66
NST-204050 | SCE | 92234 | NEM | NEM Aggregation | Withdrawn | Solar PV | 346.581 | No | 0 | 4
NST-204050 | SCE | 92234 | NEM | NEMA | Withdrawn | Solar PV | 346.581 | No | 0
NST-204149 | SCE | 90249 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 390.647 | No | 0
NST-204228 | SCE | 93534 | NEM | NEMA | Withdrawn | Solar PV | 911 | No | 0
NST-204510 | SCE | 90631 | NEM | NEMA | Withdrawn | Solar PV | 233.842 | No | 0 | 18
NST-204597 | SCE | 91764 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 103.184 | No | 0 | 12
NST-204659 | SCE | 91762 | NEM | NEMA | Withdrawn | Solar PV | 259.057 | No | 0
NST-204787 | SCE | 92606 | NEM | NEMA | NEMI - Pending Final Documents | Solar PV + Battery Storage | 1935.784 | No | 0
NST-205131 | SCE | 92831 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 52.279 | No | 0 | 0 | [12 empty] | 124
NST-205265 | SCE | 92653 | NEM | NEMA | Withdrawn | Solar PV + Battery Storage | 395.416 | No | 0 | 4
NST-205352 | SCE | 93535 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 69.017 | No | 0 | 5 | [12 empty] | 109
NST-205416 | SCE | 91752 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 779.056 | No | 0
NST-205421 | SCE | 91752 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 483.015 | No | 0
NST-205650 | SCE | 93230 | NEM | NEMA | Pending Agreement Approval/Execution | Solar PV | 582.338 | No | 0 | 7
NST-205650 | SCE | 93230 | NEM | NEM Aggregation | IA Negotiation | Solar PV | 582.338 | No | 0 | 6 |  | 50 | 20
NST-205900 | SCE | 93105 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 89.002 | No | 0 | 6
NST-206051 | SCE | 93117 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 226.371 | No | 0 | 5
NST-206127 | SCE | 93110 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 187.881 | No | 0 | 8
NST-206142 | SCE | 93101 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 109.756 | No | 0 | 3
NST-206224 | SCE | 92545 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 464.71 | No | 0
NST-206395 | SCE | 93003 | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 31.884 | No | 0
NST-206412 | SCE | 91302 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 35.638 | No | 0 | 4 | [12 empty] | 24
NST-206453 | SCE | 90405 | NEM | NEMA | NGOM Requirements Met. Pending Local Planner SO Release | Solar PV | 309.987 | No | 0 | 5
NST-206469 | SCE | 93274 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 65.136 | No | 0 | 3 | [12 empty] | 61
NST-206601 | SCE | 92225 | NEM | VNEM-SOMAH | NGOM Installation. Pending AHJ Panel Permit | Solar PV | 41.525 | No | 0
NST-206603 | SCE | 92225 | NEM | VNEM-SOMAH | NGOM Installation. Pending AHJ Panel Permit | Solar PV | 38.757 | No | 0 | 5
NST-206608 | SCE | 92225 | NEM | VNEM-SOMAH | NGOM Installation. Pending AHJ Panel Permit | Solar PV | 42.448 | No | 0 | 6
NST-206610 | SCE | 92225 | NEM | VNEM-SOMAH | NGOM Installation. Pending AHJ Panel Permit | Solar PV | 41.525 | No | 0 | 2
NST-206611 | SCE | 92225 | NEM | VNEM-SOMAH | NGOM Installation. Pending AHJ Panel Permit | Solar PV | 32.912 | No | 0 | 7
NST-206616 | SCE | 92225 | NEM | VNEM-SOMAH | NGOM Installation. Pending AHJ Panel Permit | Solar PV | 35.066 | No | 0 | 64
NST-206659 | SCE | 93560 | NEM | NEM-ST | Withdrawn |  | 178.5 | No | 0 | 0 | 29
NST-206659 | SCE | 93560 | NEM | Other-MT-ST | NEMI - Application Returned. Pending Applicant Corrections | Solar PV | 178.5 | No | 0 | 12
NST-206698 | SCE | 92240 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 89.208 | No | 0 | [13 empty] | 11
NST-206760 | SCE | 91730 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 642.3 | No | 0 | 2 | [12 empty] | 10
NST-206822 | SCE | 93501 | NEM | NEM-Military (SB-83) | Pending PTO |  | 0.235 | No | 0 | 10 | 12 | [7 empty] | 14 | Fast Track Initial Review | 35
NST-206863 | SCE | 91730 | NEM | VNEM-SOMAH | NEMI - PTO Issued | Solar PV | 90.953 | No | 0 | [13 empty] | 0
NST-207061 | SCE | 92704 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV + Battery Storage | 183.506 | No | 0 | 3
NST-207064 | SCE | 92704 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV + Battery Storage | 232.492 | No | 0
NST-207068 | SCE | 92707 | NEM | NEMA | Applicant Response Received. Pending SCE Engineer Review | Solar PV + Battery Storage | 183.538 | No | 0 | 2
NST-207070 | SCE | 92701 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV + Battery Storage | 91.611 | No | 0 | 4
NST-207071 | SCE | 92706 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV + Battery Storage | 244.707 | No | 0 | 10
NST-207073 | SCE | 92703 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV + Battery Storage | 507.704 | No | 0 | 2
NST-207078 | SCE | 92703 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV + Battery Storage | 350.523 | No | 0 | #VALUE!
NST-207080 | SCE | 92705 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV + Battery Storage | 246.297 | No | 0 | 30
NST-207081 | SCE | 92701 | NEM | NEMA | Applicant Response Received. Pending SCE Engineer Review | Solar PV + Battery Storage | 370.445 | No | 0
NST-207127 | SCE | 93277 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 156.052 | No | 0 | 2 | [12 empty] | 275
NST-207154 | SCE | 93101 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV + Battery Storage | 246.951 | No | 0 | 1
NST-207163 | SCE | 90701 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 135.121 | No | 0 | 54
NST-207170 | SCE | 90405 | NEM | VNEM-SOMAH | NGOM Installation. Pending AHJ Panel Permit | Solar PV | 47.462 | No | 0 | [17 empty] | 25
NST-207206 | SCE | 93109 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 96.524 | No | 0 | 76
NST-207227 | SCE | 91730 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 127.774 | No | 0
NST-207269 | SCE | 93103 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 41.367 | No | 0 | 3
NST-207292 | SCE | 92545 | NEM | NEMA | Withdrawn | Solar PV | 624.255 | No | 0
NST-207400 | SCE | 93516 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 407.95 | No | 0 | 9 | [12 empty] | 41
NST-207414 | SCE | 93117 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 263.982 | No | 0 | [13 empty] | 225
NST-207456 | SCE | 92336 | NEM | NEMA | Withdrawn | Solar PV | 457.644 | No | 0
NST-207551 | SCE | 91780 | NEM | NEMA | NEMI - PTO Issued | Solar PV + Battery Storage | 54.006 | No | 0 | 5 | [12 empty] | 110
NST-207763 | SCE | 92346 | NEM | NEMA | SCE Engineer Review. Pending Applicant Construction | Solar PV | 211.232 | No | 0 | 40
NST-207772 | SCE | 92410 | NEM | NEMA | SCE Engineer Review. Pending Applicant Construction | Solar PV | 354.798 | No | 0 | 0
NST-207778 | SCE | 92405 | NEM | NEMA | SCE Engineer Review. Pending Applicant Construction | Solar PV | 229.575 | No | 0 | 3
NST-207787 | SCE | 92410 | NEM | NEMA | SCE Engineer Review. Pending Applicant Construction | Solar PV | 229.575 | No | 0 | 10
NST-207874 | SCE | 93101 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV + Battery Storage | 123.475 | No | 0 | 4
NST-207892 | SCE | 93103 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 198.932 | No | 0
NST-207929 | SCE | 93291 | NEM | NEMA | Withdrawn | Solar PV + Battery Storage | 3160.29 | No | 0
NST-207999 | SCE | 92376 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 253.422 | No | 0 | 11
NST-208000 | SCE | 92270 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 75.9 | No | 0 | 3 | [12 empty] | 43
NST-208001 | SCE | 92376 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 92.221 | No | 0 | 14
NST-208079 | SCE | 92606 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 276.965 | No | 0
NST-208665 | SCE | 92374 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 184.321 | No | 0 | 6
NST-208666 | SCE | 92374 | NEM | NEMA | Withdrawn | Solar PV | 92.236 | No | 0 | 3
NST-208906 | SCE | 92399 | NEM | Other-MT-ST | NEMI - Equipment Change Submitted | Solar PV + Battery Storage | 2482.964 | No | 0 | 4
NST-208913 | SCE | 92393 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 99.235 | No | 0 | [13 empty] | 53
NST-208965 | SCE | 92399 | NEM | NEM-ST | Application Review In Progress | Solar PV | 2222.448 | No | 0 | 3
NST-208965 | SCE | 92399 | NEM | Other-MT-ST | SCE Engineer Review. Pending Applicant Response | Solar PV + Battery Storage | 2222.448 | No | 0 | 2
NST-209334 | SCE | 91387 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 70.996 | No | 0 | 4 | [12 empty] | 42
NST-209489 | SCE | 91746 | NEM | NEMA | Withdrawn | Solar PV | 469.342 | No | 0
NST-209643 | SCE | 92399 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 51.527 | No | 0 | 4 | [12 empty] | 43
NST-209765 | SCE | 92701 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 45.921 | No | 0 | 5 | [12 empty] | 87
NST-210226 | SCE | 93117 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 160.23 | No | 0 | 7 | [12 empty] | 264
NST-210290 | SCE | 90746 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 790.146 | No | 0
NST-210399 | SCE | 92377 | NEM | NEMA | Withdrawn | Solar PV | 460.734 | No | 0 | 17
NST-210501 | SCE | 91007 | NEM | NEMA | Withdrawn | Solar PV | 31.695 | No | 0
NST-210608 | SCE | 92583 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 335.937 | No | 0 | 0 | [12 empty] | 259
NST-211268 | SCE | 90631 | NEM | NEMA | Withdrawn | Solar PV | 233.842 | No | 0 | 14
NST-211302 | SCE | 92596 | NEM | NEMA | NEMI - Pending Permanent Service | Solar PV | 161.585 | No | 0 | 6
NST-211422 | SCE | 92401 | NEM | NEMA | Withdrawn | Solar PV + Battery Storage | 45.441 | No | 0
NST-211777 | SCE | 90201 | NEM | VNEM-SOMAH | Withdrawn | Solar PV | 65.769 | No | 0
NST-211902 | SCE | 91762 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 259.211 | No | 0 | [13 empty] | 44
NST-212562 | SCE | 91387 | NEM | NEMA | NEMI - PTO Issued | Solar PV + Battery Storage | 36.69 | No | 0 | 9 | [12 empty] | 92
NST-213005 | SCE | 92833 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 80.312 | No | 0 | 2 | [12 empty] | 41
NST-213190 | SCE | 92270 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 35.202 | No | 0 | 8 | [12 empty] | 79
NST-213277 | SCE | 92782 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 238.591 | No | 0 | [13 empty] | 190
NST-213463 | SCE | 91761 | NEM | NEM-ST | Supplemental Review Complete |  | 2845.108 | No | 0 | 3 | 13 |  |  | 43
NST-213463 | SCE | 91761 | NEM | NEMA | SCE Engineer. Supplemental Review Complete | Solar PV + Battery Storage | 2845.108 | No | 0 | 4
NST-213573 | SCE | 90266 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 162.639 | No | 0 | [13 empty] | 18
NST-213818 | SCE | 92335 | NEM | NEMA | Withdrawn | Solar PV + Battery Storage | 145.686 | No | 0 | 3
NST-213822 | SCE | 90720 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 225.868 | No | 0 | [13 empty] | 62
NST-213847 | SCE | 90720 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 288.672 | No | 0 | [13 empty] | 45
NST-213890 | SCE | 91387 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 39.518 | No | 0 | 4 | [12 empty] | 76
NST-214173 | SCE | 91711 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 157.156 | No | 0 | [13 empty] | 178
NST-214208 | SCE | 92410 | NEM | NEMA | SCE Engineer Review. Pending Applicant Construction | Solar PV | 133.78 | No | 0 | 3
NST-214235 | SCE | 92411 | NEM | NEMA | SCE Engineer Review. Pending Applicant Construction | Solar PV | 239.396 | No | 0 | 2
NST-214244 | SCE | 92410 | NEM | NEMA | SCE Engineer Review. Pending Applicant Construction | Solar PV | 267.56 | No | 0
NST-214250 | SCE | 93023 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV + Battery Storage | 49.498 | No | 0
NST-214809 | SCE | 91789 | NEM | NEMA | Withdrawn | Solar PV | 111.034 | No | 0
NST-214836 | SCE | 92313 | NEM | NEMA | Withdrawn | Solar PV | 94.577 | No | 0 | 3
NST-214921 | SCE | 92239 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 110.87 | No | 0 | 6
NST-215027 | SCE | 93117 | NEM | NEMA | SCE Engineer. Supplemental Review In Progress | Solar PV + Battery Storage | 999.235 | No | 0 | 9
NST-215031 | SCE | 92307 | NEM | NEMA | Withdrawn | Solar PV | 43.194 | No | 0 | 25
NST-215307 | SCE | 92591 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 126.748 | No | 0 | 3 | [12 empty] | 42
NST-215473 | SCE | 93230 | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 521.34 | No | 0 | 2
NST-215591 | SCE | 92401 | NEM | NEMA | Withdrawn | Solar PV + Battery Storage | 45.441 | No | 0 | 9
NST-215645 | SCE | 92618 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 282.95 | No | 0 | 5
NST-215657 | SCE | 93230 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 333.058 | No | 0
NST-215685 | SCE | 91321 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 126.626 | No | 0 | 3 | [12 empty] | 8
NST-215783 | SCE | 91320 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 327.78 | No | 0
NST-215801 | SCE | 93230 | NEM | VNEM-SOMAH | Withdrawn | Solar PV | 186.707 | No | 0 | 3
NST-215837 | SCE | 92618 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 78.253 | No | 0 | 8 | [12 empty] | 21
NST-216134 | SCE | 93103 | NEM | NEM-ST | Application Review In Progress |  | 561.872 | No | 0 | 0
NST-216134 | SCE | 93103 | NEM | NEMA | NEMI - Transferred to GICD | Solar PV + Battery Storage | 561.872 | No | 0
NST-216275 | SCE | 93277 | NEM | NEMA | Withdrawn | Solar PV | 42.29 | No | 0
NST-216299 | SCE | 91789 | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 142.661 | No | 0 | 11
NST-216352 | SCE | 92637 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 118.17 | No | 0 | 8
NST-216585 | SCE | 93291 | NEM | NEMA | Withdrawn | Solar PV | 46.76 | No | 0 | 4
NST-216624 | SCE | 92376 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 948.028 | No | 0 | 3
NST-216837 | SCE | 92881 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 33.184 | No | 0 | 2 | [12 empty] | 61
NST-216914 | SCE | 92399 | NEM | NEM-ST | Application Review In Progress | Solar PV | 5430.038 | No | 0 | 4
NST-216914 | SCE | 92399 | NEM | Other-MT-ST | Applicant Response Received. Pending SCE Engineer Review | Solar PV + Battery Storage | 5430.038 | No | 0
NST-216933 | SCE | 91350 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 44.255 | No | 0 | 3 | [12 empty] | 6
NST-216981 | SCE | 91361 | NEM | NEMA | NEMI - PTO Issued | Solar PV + Battery Storage | 33.111 | No | 0 | [13 empty] | 19
NST-217100 | SCE | 92651 | NEM | NEM-ST | Application Review In Progress |  | 0.011337 | No | 0 | 4 | [8 empty] | 2 |  | 0
NST-217154 | SCE | 92377 | NEM | NEMA | NEMI - Pending Final NEM Review | Solar PV | 460.734 | No | 0 | 1
NST-217243 | SCE | 93535 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 909.719 | No | 0 | 3
NST-217243 | SCE | 93535 | NEM | NEM Aggregation | Application Review In Progress |  | 909.719 | No | 0
NST-217294 | SCE | 90715 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 674.324 | No | 0 | 1
NST-217310 | SCE | 90703 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 515.257 | No | 0 | 25
NST-218066 | SCE | 90249 | NEM | NEMA | Withdrawn | Solar PV | 91.095 | No | 0 | 5
NST-218257 | SCE | 91723 | NEM | NEMA | SCE Engineer. Initial Review Complete | Solar PV + Battery Storage | 1932.248 | No | 0
NST-218783 | SCE | 93230 | NEM | NEM-FC | SCE Engineer Review. Pending Applicant Response | Fuel Cell - Renewable | 400 | No | 0 | 4
NST-218793 | SCE | 92346 | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 71.528 | No | 0 | 11
NST-218970 | SCE | 92335 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV + Battery Storage | 168.97 | No | 0 | 4
NST-218971 | SCE | 90703 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 128.493 | No | 0 | 2
NST-218974 | SCE | 92561 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 229.615 | No | 0 | 3
NST-218975 | SCE | 90703 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 103.08 | No | 0 | 4
NST-218978 | SCE | 90716 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 160.086 | No | 0
NST-218981 | SCE | 90715 | NEM | NEMA | Withdrawn | Solar PV | 95.661 | No | 0 | 2
NST-218984 | SCE | 90703 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 177.429 | No | 0 | 2
NST-218989 | SCE | 90703 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 172.244 | No | 0 | 6
NST-218994 | SCE | 90703 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 154.441 | No | 0 | 11
NST-219028 | SCE | 93543 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 100.855 | No | 0 | 2
NST-219138 | SCE | 92630 | NEM | NEM-ST | In-Service (Conditional PTO) |  | 1124.354 | No | 0 | 5 | 7 |  | 19 | [5 empty] | 7 | Supplemental Review | 105
NST-219138 | SCE | 92630 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 1124.354 | No | 0 | 15
NST-219258 | SCE | 90704 | NEM | NEM-ST | Transferred to NEM |  | 153.159 | No | 0
NST-219258 | SCE | 90704 | NEM | Other-NEM-V | SCE Engineer Review. Pending Applicant Response | Solar PV | 153.159 | No | 0
NST-219556 | SCE | 90274 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 33.849 | No | 0 | #VALUE! | [12 empty] | 51
NST-219644 | SCE | 92821 | NEM | NEMA | NGOM Installation. Pending AHJ Panel Permit | Solar PV + Battery Storage | 317.739 | No | 0 | 9
NST-219944 | SCE | 90716 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 152.099 | No | 0 | 4
NST-219965 | SCE | 90703 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 491.582 | No | 0
NST-219973 | SCE | 91746 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 469.342 | No | 0 | 7 | [12 empty] | 53
NST-220174 | SCE | 92270 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV + Battery Storage | 37.95 | No | 0 | 4
NST-220427 | SCE | 92591 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 53.907 | No | 0 | 6 | [12 empty] | 45
NST-220470 | SCE | 93536 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 184.398 | No | 0 | 0 | [12 empty] | 189
NST-220495 | SCE | 90250 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 496.475 | No | 0 | [13 empty] | 44
NST-220503 | SCE | 91350 | NEM | NEMA | Withdrawn | Solar PV | 37.089 | No | 0 | 37
NST-220653 | SCE | 92562 | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 37.923 | No | 0 | 4
NST-220790 | SCE | 93518 | NEM | NEMA | Withdrawn | Solar PV | 37.207 | No | 0
NST-220885 | SCE | 92376 | NEM | NEMA | Withdrawn | Solar PV | 3227.722 | No | 0 | 6
NST-221339 | SCE | 91789 | NEM | NEMA | SCE Engineer Review. Pending Applicant Construction | Solar PV | 494.247 | No | 0 | 11
NST-221368 | SCE | 92587 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 76.417 | No | 0 | 17
NST-221381 | SCE | 92587 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 91.207 | No | 0
NST-221402 | SCE | 92587 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 394.41 | No | 0 | 4
NST-221425 | SCE | 93012 | NEM | NEMA | Withdrawn | Solar PV + Battery Storage | 80.471 | No | 0
NST-221476 | SCE | 92408 | NEM | NEMA | NGOM Installation. Pending Invoice Payment and AHJ Panel Permit | Solar PV | 129.62 | No | 0 | 3
NST-221480 | SCE | 91761 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 122.902 | No | 0
NST-221483 | SCE | 90670 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 233.157 | No | 0
NST-221567 | SCE | 92562 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 30.712 | No | 0 | [13 empty] | 34
NST-221650 | SCE | 90230 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV + Battery Storage | 32.616 | No | 0
NST-221966 | SCE | 92307 | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 44.085 | No | 0 | 8
NST-222023 | SCE | 92562 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 45.676 | No | 0 | 3 | [12 empty] | 31
NST-222059 | SCE | 92336 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV + Battery Storage | 231.64 | No | 0
NST-222199 | SCE | 90504 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 118.417 | No | 0 | 3
NST-222224 | SCE | 93021 | NEM | NEMA | Withdrawn | Solar PV | 177.111 | No | 0 | 5
NST-222295 | SCE | 93291 | NEM | NEM-ST | IA Negotiation |  | 3160.29 | No | 0 | 4 | 8 |  |  | 29
NST-222295 | SCE | 93291 | NEM | NEMA | SCE Engineer. Supplemental Review Complete | Solar PV + Battery Storage | 3160.29 | No | 0
NST-222464 | SCE | 92831 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV + Battery Storage | 418.132 | No | 0 | 3
NST-222541 | SCE | 92410 | NEM | NEM-ST | Supplemental Review Complete |  | 616.224 | No | 0 | 0 | 15 |  | 25
NST-222541 | SCE | 92410 | NEM | VNEM-SOMAH | NEMI - Transferred to GICD | Solar PV | 616.224 | No | 0
NST-222571 | SCE | 91801 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 57.509 | No | 0 | 11
NST-222572 | SCE | 93065 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 58.185 | No | 0
NST-222653 | SCE | 90404 | NEM | VNEM-SOMAH | Withdrawn | Solar PV | 48.499 | No | 0
NST-222654 | SCE | 93103 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 164.634 | No | 0
NST-222693 | SCE | 95765 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 992.334 | No | 0 | 0
NST-222697 | SCE | 90404 | NEM | VNEM-SOMAH | Withdrawn | Solar PV | 48.843 | No | 0 | 4
NST-223043 | SCE | 91748 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 42.398 | No | 0 | 0 | [12 empty] | 20
NST-223259 | SCE | 92509 | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 71.217 | No | 0 | 5
NST-223309 | SCE | 91340 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 50.073 | No | 0
NST-223453 | SCE | 92211 | NEM | NEM-ST | Application Review In Progress |  | 1271.853 | No | 0 | 2
NST-223453 | SCE | 92211 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV + Battery Storage | 1271.853 | No | 0
NST-223606 | SCE | 93550 | NEM | NEMA | Withdrawn | Solar PV | 52.17 | No | 0 | 19
NST-223693 | SCE | 91010 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 73.271 | No | 0 | 2 | [12 empty] | 174
NST-223694 | SCE | 92392 | NEM | Other-NEM-V | NGOM Installation. Pending AHJ Panel Permit | Solar PV | 173.702 | No | 0 | 14
NST-223828 | SCE | 92544 | NEM | NEMA | Withdrawn | Solar PV | 30.716 | No | 0 | 10
NST-223930 | SCE | 91790 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 938.859 | No | 0 | 10
NST-224237 | SCE | 92401 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 207.925 | No | 0 | 2 | [12 empty] | 21
NST-224243 | SCE | 92509 | NEM | NEM-ST | Application Review In Progress |  | 2017.36 | No | 0
NST-224243 | SCE | 92509 | NEM | NEMA | Applicant Response Received. Pending SCE Engineer Review | Solar PV + Battery Storage | 2017.36 | No | 0
NST-224291 | SCE | 92509 | NEM | NEM | Application Review In Progress |  | 666.05 | No | 0
NST-224291 | SCE | 92509 | NEM | NEMA | Applicant Response Received. Pending SCE Engineer Review | Solar PV | 666.05 | No | 0
NST-224292 | SCE | 92509 | NEM | NEM-ST | Application Review In Progress |  | 762.47 | No | 0
NST-224292 | SCE | 92509 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 762.47 | No | 0
NST-224342 | SCE | 92408 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 67.252 | No | 0 | 6 | [12 empty] | 153
NST-224404 | SCE | 93065 | NEM | NEMA | Withdrawn | Solar PV | 306.623 | No | 0 | 4
NST-224453 | SCE | 93043 | NEM | NEMA | SCE Engineer. Initial Review In Progress | Solar PV | 609.029 | No | 0 | 0
NST-224453 | SCE | 93043 | NEM | NEM-Military (SB-83) | Application Review In Progress |  | 609.029 | No | 0
NST-224456 | SCE | 92210 | NEM | NEMA | Withdrawn | Solar PV + Battery Storage | 77.176 | No | 0 | 3
NST-224734 | SCE | 93013 | NEM | NEMA | Applicant Response Received. Pending SCE Engineer Review | Solar PV | 591.515 | No | 0 | 0
NST-224785 | SCE | 92395 | NEM | NEMA | Withdrawn | Solar PV | 299.298 | No | 0
NST-224796 | SCE | 93292 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 172.073 | No | 0 | 3
NST-224954 | SCE | 92583 | NEM | NEMA | NGOM Installation. Pending Invoice Payment and AHJ Panel Permit | Solar PV + Battery Storage | 45.622 | No | 0 | 37
NST-225062 | SCE | 90703 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 119.479 | No | 0 | 8
NST-225068 | SCE | 90703 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 236.615 | No | 0 | 15
NST-225078 | SCE | 90715 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 98.394 | No | 0 | 22
NST-225090 | SCE | 90701 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 145.071 | No | 0 | 4
NST-225094 | SCE | 90703 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 145.071 | No | 0 | 3
NST-225111 | SCE | 90703 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 142.502 | No | 0 | 8
NST-225124 | SCE | 90703 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 133.757 | No | 0 | 0
NST-225366 | SCE | 93518 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 37.055 | No | 0 | 0 | [12 empty] | 12
NST-225471 | SCE | 92345 | NEM | NEMA | Withdrawn | Solar PV | 40.88 | No | 0
NST-225637 | SCE | 92374 | NEM | NEMA | Withdrawn | Solar PV | 296.582 | No | 0
NST-225695 | SCE | 92570 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 997.192 | No | 0 | 7
NST-225702 | SCE | 92571 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 483.015 | No | 0
NST-225748 | SCE | 91761 | NEM | NEMA | Withdrawn | Solar PV | 997.192 | No | 0
NST-225752 | SCE | 91761 | NEM | NEMA | SCE Engineer. Initial Review Complete | Solar PV | 997.192 | No | 0 | 29
NST-226207 | SCE | 93654 | NEM | NEMA | Withdrawn | Solar PV | 551.919 | No | 0 | 8
NST-226404 | SCE | 92301 | NEM | NEMA | Withdrawn | Solar PV | 6005.196 | No | 0
NST-226614 | SCE | 92843 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 68.245 | No | 0 | [13 empty] | 27
NST-226637 | SCE | 92618 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 37.093 | No | 0 | 0 | [12 empty] | 26
NST-226900 | SCE | 92395 | NEM | NEMA | NEMI - 1.0 Expansion Ineligible | Solar PV | 31.394 | No | 0
NST-226928 | SCE | 90266 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 301.627 | No | 0 | 30 | [12 empty] | 127
NST-227017 | SCE | 92701 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 271.625 | No | 0 | [13 empty] | 201
NST-227190 | SCE | 93065 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 51.486 | No | 0 | 8 | [12 empty] | 6
NST-227289 | SCE | 90602 | NEM | Other-NEM-V | Withdrawn | Solar PV | 57.534 | No | 0
NST-227416 | SCE | 90680 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 224.606 | No | 0 | [13 empty] | 205
NST-227529 | SCE | 91007 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 31.695 | No | 0 | 6
NST-227638 | SCE | 92630 | NEM | NEMA | Applicant Response Received. Pending SCE Engineer Review | Solar PV | 204.951 | No | 0
NST-227638 | SCE | 92630 | NEM | NEM-ST | Application Review In Progress |  | 204.951 | No | 0
NST-227998 | SCE | 91350 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 165.052 | No | 0 | 20
NST-228797 | SCE | 92614 | NEM | NEMA | Withdrawn | Solar PV | 129.672 | No | 0
NST-228865 | SCE | 93277 | NEM | NEMA | Withdrawn | Solar PV | 42.29 | No | 0
NST-228992 | SCE | 90301 | NEM | NEMA | NEMI - 1.0 Expansion Ineligible | Solar PV | 30 | No | 0
NST-229047 | SCE | 92882 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 31.663 | No | 0 | 2 | [12 empty] | 21
NST-229209 | SCE | 93274 | NEM | NEM Aggregation | Transferred to NEM |  | 354.405 | No | 0
NST-229209 | SCE | 93274 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 354.405 | No | 0
NST-229327 | SCE | 93227 | NEM | NEMA | Withdrawn | Solar PV | 4547.958 | No | 0 | 0
NST-229327 | SCE | 93227 | NEM | NEM Aggregation | Withdrawn |  | 4547.958 | No | 0 | 10
NST-229578 | SCE | 90802 | NEM | Other-NEM-V | NEMI - 1.0 Expansion Ineligible | Solar PV | 241.532 | No | 0
NST-229582 | SCE | 93012 | NEM | NEMA | NEMI - Equipment Change Submitted | Solar PV | 209.759 | No | 0 | 1
NST-229630 | SCE | 92376 | NEM | NEM-ST | Application Review In Progress |  | 2423.25 | No | 0
NST-229630 | SCE | 92376 | NEM | NEMA | Applicant Response Received. Pending SCE Engineer Review | Solar PV | 2423.25 | No | 0
NST-229728 | SCE | 91354 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 125.643 | No | 0
NST-229858 | SCE | 93230 | NEM | VNEM-SOMAH | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 45.215 | No | 0 | 0
NST-229861 | SCE | 93230 | NEM | VNEM-SOMAH | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 50.111 | No | 0
NST-229865 | SCE | 93230 | NEM | VNEM-SOMAH | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 46.079 | No | 0
NST-229908 | SCE | 92879 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 131.4 | No | 0 | [13 empty] | 11
NST-229916 | SCE | 93230 | NEM | VNEM-SOMAH | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 44.639 | No | 0
NST-230091 | SCE | 92780 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 66.734 | No | 0 | [13 empty] | 162
NST-230377 | SCE | 91354 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 276.258 | No | 0
NST-230385 | SCE | 92376 | NEM | NEM-ST | Application Review In Progress |  | 1199.13 | No | 0
NST-230385 | SCE | 92376 | NEM | NEMA | Applicant Response Received. Pending SCE Engineer Review | Solar PV + Battery Storage | 1199.13 | No | 0
NST-230387 | SCE | 92374 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 102.549 | No | 0 | 7
NST-230435 | SCE | 91355 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 715.752 | No | 0 | 7 | [12 empty] | 7
NST-230628 | SCE | 91791 | NEM | Other-NEM-V | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 66.78 | No | 0 | 9
NST-230810 | SCE | 91011 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 30.571 | No | 0 | 5 | [12 empty] | 7
NST-230846 | SCE | 93277 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 34.224 | No | 0 | [13 empty] | 9
NST-231067 | SCE | 92562 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 32.17 | No | 0 | [13 empty] | 52
NST-231287 | SCE | 93110 | NEM | NEM-ST | Application Review In Progress |  | 646.721 | No | 0
NST-231287 | SCE | 93110 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV + Battery Storage | 646.721 | No | 0 | 3
NST-231715 | SCE | 90505 | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 81.22 | No | 0
NST-231810 | SCE | 93030 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 84.45 | No | 0 | 11 | [12 empty] | 139
NST-231824 | SCE | 90806 | NEM | NEMA | Withdrawn | Solar PV | 127.476 | No | 0 | 12
NST-231836 | SCE | 90806 | NEM | NEMA | Withdrawn | Solar PV | 167.156 | No | 0 | 11
NST-231856 | SCE | 90806 | NEM | NEMA | Withdrawn | Solar PV | 83.578 | No | 0 | 6
NST-231870 | SCE | 90806 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 541.46 | No | 0
NST-231895 | SCE | 90806 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 427.458 | No | 0
NST-231909 | SCE | 92210 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 36.715 | No | 0 | [13 empty] | 1
NST-231986 | SCE | 90807 | NEM | NEMA | Withdrawn | Solar PV | 44.06 | No | 0
NST-232042 | SCE | 93215 | NEM | NEMA | Withdrawn | Solar PV | 30.777 | No | 0 | 7
NST-232069 | SCE | 90807 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 93.745 | No | 0
NST-232122 | SCE | 93117 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 44.306 | No | 0 | 4 | [12 empty] | 118
NST-232124 | SCE | 92879 | NEM | NEMA | NGOM Installation. Pending AHJ Panel Permit | Solar PV | 78.246 | No | 0
NST-232139 | SCE | 93065 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 306.623 | No | 0
NST-232143 | SCE | 91791 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 81.905 | No | 0 | 9
NST-232232 | SCE | 93063 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 124.347 | No | 0 | 0
NST-232348 | SCE | 90069 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 60.945 | No | 0 | 9 | [12 empty] | 4
NST-232379 | SCE | 92627 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 75.28 | No | 0
NST-232380 | SCE | 92620 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 53.974 | No | 0 | 4
NST-232543 | SCE | 92637 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 59.656 | No | 0 | 12 | [12 empty] | 141
NST-232550 | SCE | 92630 | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 59.656 | No | 0
NST-232563 | SCE | 90720 | NEM | NEM-ST | Application Review In Progress |  | 220.216 | No | 0 | 5
NST-232563 | SCE | 90720 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 220.216 | No | 0
NST-232584 | SCE | 90720 | NEM | NEMA | NEMI - Sent to Engineering | Solar PV | 161.305 | No | 0
NST-232584 | SCE | 90720 | NEM | NEM-ST | Application Review In Progress |  | 161.305 | No | 0 | 4
NST-232590 | SCE | 90720 | NEM | NEMA | NEMI - Sent to Engineering | Solar PV | 145.074 | No | 0 | 5
NST-232590 | SCE | 90720 | NEM | NEM-ST | Application Review In Progress |  | 145.074 | No | 0
NST-232595 | SCE | 92867 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 54.475 | No | 0
NST-232601 | SCE | 90720 | NEM | NEMA | NEMI - Sent to Engineering | Solar PV | 173.009 | No | 0
NST-232601 | SCE | 90720 | NEM | NEM-ST | Application Review In Progress |  | 173.009 | No | 0 | 3
NST-232607 | SCE | 92867 | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 71.019 | No | 0 | 4
NST-232609 | SCE | 90720 | NEM | NEM-ST | Supplemental Review In Progress |  | 1007.193 | No | 0 |  | 14
NST-232609 | SCE | 90720 | NEM | NEMA | SCE Engineer Assigned. Pending Technical Review | Solar PV + Battery Storage | 1007.193 | No | 0
NST-232626 | SCE | 90720 | NEM | NEMA | NEMI - Sent to Engineering | Solar PV | 316.089 | No | 0 | 0
NST-232626 | SCE | 90720 | NEM | NEM-ST | Application Review In Progress |  | 316.089 | No | 0 | 4
NST-232635 | SCE | 90740 | NEM | NEMA | Withdrawn | Solar PV | 198.604 | No | 0 | 17
NST-232641 | SCE | 90720 | NEM | NEMA | Withdrawn | Solar PV | 290.145 | No | 0 | #VALUE!
NST-232650 | SCE | 90720 | NEM | NEMA | NEMI - Sent to Engineering | Solar PV | 145.074 | No | 0
NST-232650 | SCE | 90720 | NEM | NEM-ST | Intake |  | 145.074 | No | 0
NST-232660 | SCE | 90720 | NEM | NEMA | Withdrawn | Solar PV | 163.642 | No | 0 | 19
NST-232696 | SCE | 91350 | NEM | NEMA | Withdrawn | Solar PV | 37.089 | No | 0
NST-232697 | SCE | 92371 | NEM | NEMA | Withdrawn | Solar PV | 32.331 | No | 0 | 13
NST-232699 | SCE | 91732 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV + Battery Storage | 675.834 | No | 0 | 16
NST-232708 | SCE | 91770 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV + Battery Storage | 499.758 | No | 0 | 5
NST-232735 | SCE | 92701 | NEM | NEMA | Withdrawn | Solar PV | 113.32 | No | 0 | 9
NST-232792 | SCE | 92301 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 265.196 | No | 0 | 3 | [12 empty] | 2
NST-232996 | SCE | 91770 | NEM | NEMA | Applicant Response Received. Pending SCE Engineer Review | Solar PV + Battery Storage | 426.064 | No | 0 | 4
NST-233019 | SCE | 91733 | NEM | NEMA | SCE Engineer. Initial Review Complete | Solar PV + Battery Storage | 749.966 | No | 0 | 3
NST-233019 | SCE | 91733 | NEM | NEM-ST | IA Negotiation |  | 749.966 | No | 0 | 3 |  | 13
NST-233223 | SCE | 91790 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 158.582 | No | 0 | #VALUE!
NST-233264 | SCE | 92374 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 296.582 | No | 0
NST-233290 | SCE | 90505 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 41.501 | No | 0 | #VALUE! | [12 empty] | 1
NST-233382 | SCE | 93536 | NEM | NEMA | SCE Engineer. Detail Study In Progress | Solar PV | 1492.488 | No | 0 | 7
NST-233382 | SCE | 93536 | NEM | NEM-ST | System Impact Study In Progress |  | 1492.488 | No | 0 |  | 13 |  |  |  | 9
NST-233467 | SCE | 92284 | NEM | NEM-ST | Construction |  | 0.0142 | No | 0 |  | 4 | [7 empty] | 18 | Fast Track Initial Review | 29
NST-233633 | SCE | 90404 | NEM | NEM-ST | In-Service |  | 162.607 | No | 0 | 4 |  | 40
NST-233633 | SCE | 90404 | NEM | NEMA | SCE Engineer Assigned. Pending Technical Review | Solar PV | 162.607 | No | 0
NST-233878 | SCE | 92618 | NEM | VNEM-SOMAH | NGOM Installation. Pending AHJ Panel Permit | Solar PV | 46.387 | No | 0 | 3
NST-233880 | SCE | 92618 | NEM | VNEM-SOMAH | NGOM Installation. Pending AHJ Panel Permit | Solar PV | 72.514 | No | 0 | 95
NST-234059 | SCE | 92395 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 31.394 | No | 0
NST-234148 | SCE | 91763 | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 40.127 | No | 0
NST-234149 | SCE | 92780 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 74.308 | No | 0 | #VALUE!
NST-234157 | SCE | 91340 | NEM | NEMA | Withdrawn | Solar PV | 66.757 | No | 0 | 13
NST-234158 | SCE | 90815 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 31.21 | No | 0
NST-234159 | SCE | 91362 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 87.312 | No | 0 | 3
NST-234160 | SCE | 92656 | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 42.727 | No | 0 | 6
NST-234161 | SCE | 93551 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 51.91 | No | 0 | 6
NST-234162 | SCE | 90660 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 51.91 | No | 0
NST-234163 | SCE | 91011 | NEM | NEMA | Withdrawn | Solar PV | 76.538 | No | 0
NST-234164 | SCE | 93003 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 54.511 | No | 0
NST-234165 | SCE | 90210 | NEM | NEMA | Withdrawn | Solar PV | 86.941 | No | 0 | 13
NST-234166 | SCE | 90630 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 47.316 | No | 0
NST-234167 | SCE | 90274 | NEM | NEMA | Withdrawn | Solar PV | 48.191 | No | 0
NST-234291 | SCE | 90715 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 95.661 | No | 0
NST-234467 | SCE | 90745 | NEM | VNEM-SOMAH | SCE Engineer Review. Pending Applicant Response | Solar PV | 32.806 | No | 0 | 4
NST-234508 | SCE | 90249 | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 253.667 | No | 0
NST-234681 | SCE | 92234 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 346.581 | No | 0 | 1
NST-234735 | SCE | 92234 | NEM | VNEM-SOMAH | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 34.588 | No | 0
NST-234744 | SCE | 92234 | NEM | VNEM-SOMAH | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 47.609 | No | 0 | 4
NST-234776 | SCE | 92544 | NEM | NEMA | Withdrawn | Solar PV + Battery Storage | 230 | No | 0
NST-234819 | SCE | 92544 | NEM | NEMA | Withdrawn | Solar PV + Battery Storage | 230 | No | 0
NST-235155 | SCE | 93021 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 177.095 | No | 0 | 1
NST-235155 | SCE | 93021 | NEM | NEM Aggregation | Transferred to NEM |  | 177.095 | No | 0
NST-235240 | SCE | 90040 | NEM | NEMA | SCE Engineer Review. Pending SCE System Upgrades | Solar PV | 400.546 | No | 0 | 5
NST-235240 | SCE | 90040 | NEM | NEM-ST | Transferred to NEM |  | 400.546 | No | 0
NST-235259 | SCE | 92345 | NEM | NEMA | Withdrawn | Solar PV | 51.402 | No | 0 | 12
NST-235366 | SCE | 91768 | NEM | VNEM-SOMAH | NGOM Installation. Pending New Service Request and AHJ Panel Permit | Solar PV | 123.995 | No | 0 | 0
NST-235385 | SCE | 91763 | NEM | VNEM-SOMAH | Withdrawn | Solar PV | 99.785 | No | 0
NST-235478 | SCE | 92260 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 33.788 | No | 0 | 2 | [12 empty] | 34
NST-235512 | SCE | 92373 | NEM | NEM-FC | NEMI - Conditional PTO | Fuel Cell - Renewable | 1100 | No | 0 | [13 empty] | 148
NST-235512 | SCE | 92373 | NEM | NEM-ST | IA Negotiation |  | 1100 | No | 0 | [13 empty] | 140
NST-235698 | SCE | 92880 | NEM | NEMA | Withdrawn | Solar PV | 290.845 | No | 0
NST-236173 | SCE | 90807 | NEM | NEM-ST | Application Review In Progress |  | 1305 | No | 0
NST-236173 | SCE | 90807 | NEM | Other-MT-ST | SCE Engineer Assigned. Pending Technical Review | Other | 1305 | No | 0
NST-236463 | SCE | 93277 | NEM | NEM Aggregation | Application Review In Progress |  | 147.915 | No | 0 | 8
NST-236463 | SCE | 93277 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 147.915 | No | 0 | 0
NST-236933 | SCE | 92223 | NEM | NEMA | Withdrawn | Solar PV | 63.547 | No | 0
NST-236987 | SCE | 93277 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 32.324 | No | 0
NST-237191 | SCE | 92260 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 38.311 | No | 0 | 1
NST-237236 | SCE | 91764 | NEM | NEMA | NEMI - Sent to Engineering | Solar PV + Battery Storage | 1462.698 | No | 0 | 7
NST-237236 | SCE | 91764 | NEM | NEM-ST | Withdrawn |  | 1462.698 | No | 0
NST-237346 | SCE | 92629 | NEM | NEMA | Withdrawn | Solar PV | 428.831 | No | 0
NST-237456 | SCE | 90706 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 31.064 | No | 0 | [13 empty] | 152
NST-237462 | SCE | 90706 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 46.079 | No | 0 | 5 | [12 empty] | 152
NST-237530 | SCE | 92614 | NEM | NEMA | Withdrawn | Solar PV | 123.891 | No | 0
NST-237681 | SCE | 92210 | NEM | NEMA | NEMI - PTO Issued | Solar PV + Battery Storage | 76.852 | No | 0 | [13 empty] | 122
NST-237751 | SCE | 92262 | NEM | NEMA | Withdrawn | Solar PV | 68.086 | No | 0
NST-237802 | SCE | 90723 | NEM | Other-NEM-V | SCE Engineer Review. Pending Applicant Response | Solar PV | 710.48 | No | 0 | 14
NST-237830 | SCE | 92307 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 30.236 | No | 0 | 3 | [12 empty] | 17
NST-237887 | SCE | 93550 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 52.17 | No | 0 | 19 | [12 empty] | 98
NST-238138 | SCE | 92374 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 146.577 | No | 0 | 0 | [12 empty] | 44
NST-238201 | SCE | 90670 | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 159.041 | No | 0
NST-238228 | SCE | 93256 | NEM | NEMA | SCE Engineer. Initial Review Complete | Solar PV | 998.341 | No | 0 | 11
NST-238337 | SCE | 90265 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 31.319 | No | 0 | [13 empty] | 95
NST-238443 | SCE | 90245 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 125.954 | No | 0
NST-238451 | SCE | 92886 | NEM | VNEM-SOMAH | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 58.702 | No | 0 | 8
NST-238452 | SCE | 92886 | NEM | VNEM-SOMAH | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 39.655 | No | 0 | 3
NST-238453 | SCE | 92886 | NEM | VNEM-SOMAH | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 84.931 | No | 0 | 9
NST-238578 | SCE | 93021 | NEM | NEMA | Withdrawn | Solar PV + Battery Storage | 1584.307 | No | 0
NST-238954 | SCE | 93277 | NEM | NEMA | Withdrawn | Solar PV | 42.509 | No | 0 | 5
NST-238961 | SCE | 92626 | NEM | NEM-ST | Application Review In Progress |  | 1055.194 | No | 0
NST-238961 | SCE | 92626 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 1055.194 | No | 0 | 5
NST-238971 | SCE | 92704 | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 104.128 | No | 0
NST-239276 | SCE | 92651 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 49.887 | No | 0
NST-239366 | SCE | 93274 | NEM | NEM Aggregation | Application Review In Progress |  | 1217.025 | No | 0 | 6
NST-239366 | SCE | 93274 | NEM | NEMA | SCE Engineer Assigned. Pending Technical Review | Solar PV | 1217.025 | No | 0 | 8
NST-239682 | SCE | 91355 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 142.111 | No | 0
NST-23972 | SCE | 90703 | NEM | NEMA | Withdrawn | Solar PV | 142.502 | No | 0 | 1
NST-23977 | SCE | 90703 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 153.308 | No | 0 | 10
NST-239800 | SCE | 91361 | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 31.329 | No | 0 | #VALUE!
NST-239870 | SCE | 92316 | NEM | NEMA | Withdrawn | Solar PV | 110.039 | No | 0
NST-239917 | SCE | 91745 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 31.615 | No | 0 | 4 | [12 empty] | 10
NST-240125 | SCE | 90720 | NEM | NEMA | NEMI - Sent to Engineering | Solar PV | 290.145 | No | 0 | 3
NST-240125 | SCE | 90720 | NEM | NEM-ST | Application Review In Progress |  | 290.145 | No | 0
NST-240332 | SCE | 92780 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 38.206 | No | 0 | 16 | [12 empty] | 140
NST-240381 | SCE | 90305 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 33.579 | No | 0 | 5 | [12 empty] | 44
NST-240504 | SCE | 91355 | NEM | NEMA | NEMI - 1.0 Expansion Ineligible | Solar PV | 760.466 | No | 0
NST-240650 | SCE | 91763 | NEM | VNEM-SOMAH | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 99.785 | No | 0
NST-240738 | SCE | 93274 | NEM | NEMA | Withdrawn | Solar PV | 250.83 | No | 0 | 21
NST-240808 | SCE | 93274 | NEM | VNEM-SOMAH | NGOM Installation. Pending Local Planner Process | Solar PV | 60.576 | No | 0 | 6
NST-240813 | SCE | 93274 | NEM | VNEM-SOMAH | SCE System Upgrades. Pending Local Planner Process | Solar PV | 82.745 | No | 0 | 3
NST-240816 | SCE | 93274 | NEM | VNEM-SOMAH | NGOM Installation. Pending Local Planner Process | Solar PV | 88.053 | No | 0 | 7
NST-240821 | SCE | 92708 | NEM | Other-NEM-V | NGOM Installation. Pending New Service Request and AHJ Panel Permit | Solar PV | 39.039 | No | 0 | 5
NST-240822 | SCE | 92708 | NEM | Other-NEM-V | NGOM Installation. Pending New Service Request and AHJ Panel Permit | Solar PV | 60.638 | No | 0 | #VALUE!
NST-240828 | SCE | 92210 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 36.867 | No | 0 | [13 empty] | 7
NST-240907 | SCE | 92880 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 290.796 | No | 0 | 30 | [12 empty] | 6
NST-241058 | SCE | 91351 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 174.473 | No | 0 | 4
NST-241064 | SCE | 91350 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 98.009 | No | 0 | 13
NST-241068 | SCE | 91390 | NEM | NEMA | Withdrawn | Solar PV | 71.796 | No | 0
NST-241097 | SCE | 92399 | NEM | NEM-ST | Supplemental Review In Progress |  | 2206.415 | No | 0 | 8 | 16
NST-241097 | SCE | 92399 | NEM | NEMA | SCE Engineer. Initial Review Complete | Solar PV + Battery Storage | 2206.415 | No | 0 | 6
NST-241122 | SCE | 92395 | NEM | NEMA | NEMI - Application Re-Submitted | Solar PV | 127 | No | 0 | 4
NST-241130 | SCE | 93267 | NEM | NEMA | Withdrawn | Solar PV | 522.149 | No | 0
NST-24116 | SCE | 90715 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 98.394 | No | 0
NST-24117 | SCE | 90715 | NEM | NEMA | Withdrawn | Solar PV | 838.315 | No | 0 | 4
NST-24118 | SCE | 90703 | NEM | NEMA | Withdrawn | Solar PV | 208.086 | No | 0
NST-24119 | SCE | 90701 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 107.218 | No | 0
NST-24120 | SCE | 90703 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 99.06 | No | 0 | 1
NST-24121 | SCE | 90703 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 54.273 | No | 0 | 5
NST-24122 | SCE | 90703 | NEM | NEMA | Withdrawn | Solar PV | 135.121 | No | 0
NST-24123 | SCE | 90703 | NEM | NEMA | Withdrawn | Solar PV | 119.479 | No | 0
NST-24124 | SCE | 90703 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 783.877 | No | 0 | 5
NST-24125 | SCE | 90703 | NEM | NEMA | Withdrawn | Solar PV | 491.582 | No | 0
NST-24126 | SCE | 90703 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 63.254 | No | 0 | 6
NST-24127 | SCE | 90716 | NEM | NEMA | Withdrawn | Solar PV | 201.902 | No | 0
NST-24129 | SCE | 90716 | NEM | NEMA | Withdrawn | Solar PV | 152.099 | No | 0 | 11
NST-24130 | SCE | 90703 | NEM | NEMA | Withdrawn | Solar PV | 549.369 | No | 0 | 3
NST-24131 | SCE | 90703 | NEM | NEMA | Withdrawn | Solar PV | 196.789 | No | 0
NST-24132 | SCE | 90703 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 126.507 | No | 0 | 8
NST-24133 | SCE | 90716 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 107.218 | No | 0 | 5
NST-24135 | SCE | 90701 | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 91.188 | No | 0
NST-24136 | SCE | 90703 | NEM | NEMA | Withdrawn | Solar PV | 126.507 | No | 0
NST-241362 | SCE | 91351 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 103.011 | No | 0
NST-24137 | SCE | 90715 | NEM | NEMA | Withdrawn | Solar PV | 107.765 | No | 0
NST-24138 | SCE | 90701 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 163.812 | No | 0 | 9
NST-24139 | SCE | 90703 | NEM | NEMA | Withdrawn | Solar PV | 236.615 | No | 0
NST-24140 | SCE | 90715 | NEM | NEMA | Withdrawn | Solar PV | 98.394 | No | 0 | 3
NST-24141 | SCE | 90701 | NEM | NEMA | Withdrawn | Solar PV | 145.071 | No | 0 | 4
NST-24142 | SCE | 90703 | NEM | NEMA | Withdrawn | Solar PV | 145.071 | No | 0
NST-24143 | SCE | 90703 | NEM | NEMA | Withdrawn | Solar PV | 196.789 | No | 0 | 6
NST-24144 | SCE | 90703 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 565.802 | No | 0 | 8
NST-24145 | SCE | 90715 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 100.737 | No | 0 | 0
NST-24146 | SCE | 90703 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 208.122 | No | 0
NST-241670 | SCE | 91016 | NEM | NEMA | SCE Engineer Assigned. Pending Technical Review | Solar PV | 657.826 | No | 0 | 5
NST-241670 | SCE | 91016 | NEM | NEM Aggregation | Application Review In Progress |  | 657.826 | No | 0 | 6
NST-241773 | SCE | 92688 | NEM | NEMA | Withdrawn | Solar PV | 1348.361 | No | 0
NST-241773 | SCE | 92688 | NEM | NEM-ST | Withdrawn |  | 1348.361 | No | 0
NST-241941 | SCE | 92590 | NEM | NEMA | NEMI - Application Re-Submitted | Solar PV | 48.95 | No | 0 | 17
NST-242130 | SCE | 93654 | NEM | NEMA | Withdrawn | Solar PV | 552.589 | No | 0
NST-242477 | SCE | 91709 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 70.278 | No | 0
NST-242488 | SCE | 91709 | NEM | NEMA | NEMI - Returned from Engineering | Solar PV | 61.4 | No | 0 | 3
NST-242500 | SCE | 90631 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 74.963 | No | 0
NST-242543 | SCE | 90638 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 117.378 | No | 0
NST-242656 | SCE | 92653 | NEM | NEMA | Withdrawn | Solar PV | 395.416 | No | 0 | #VALUE!
NST-242762 | SCE | 91762 | NEM | Other-NEM-V | SCE Engineer Assigned. Pending Technical Review | Solar PV | 42.995 | No | 0
NST-242821 | SCE | 91730 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 31.911 | No | 0 | [13 empty] | 66
NST-242822 | SCE | 91730 | NEM | NEM-ST | System Impact Study Complete |  | 2134.879 | No | 0 | 4 | 21 |  | 23
NST-242822 | SCE | 91730 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV + Battery Storage | 2134.879 | No | 0
NST-242966 | SCE | 92618 | NEM | NEMA | NGOM Installation. Pending Invoice Payment and AHJ Panel Permit | Solar PV + Battery Storage | 59.986 | No | 0
NST-242968 | SCE | 93108 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 112.5 | No | 0 | 10
NST-242974 | SCE | 90638 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 259.874 | No | 0 | 6
NST-243141 | SCE | 92399 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 368.355 | No | 0 | 0
NST-243152 | SCE | 93101 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 241.939 | No | 0 | 7
NST-243421 | SCE | 92401 | NEM | NEMA | Withdrawn | Solar PV + Battery Storage | 45.441 | No | 0
NST-243443 | SCE | 91764 | NEM | NEM-ST | Application Review In Progress |  | 0 | No | 0 | 45
NST-243564 | SCE | 93247 | NEM | VNEM-SOMAH | NGOM Installation. Pending New Service Request and AHJ Panel Permit | Solar PV | 50.584 | No | 0 | 3
NST-243566 | SCE | 93247 | NEM | VNEM-SOMAH | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 66.508 | No | 0
NST-243636 | SCE | 90404 | NEM | VNEM-SOMAH | SCE Engineer Review. Pending Applicant Response | Solar PV | 48.499 | No | 0 | 4
NST-243976 | SCE | 92354 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 155.051 | No | 0
NST-244089 | SCE | 93291 | NEM | NEMA | Withdrawn | Solar PV | 32.398 | No | 0
NST-244376 | SCE | 92882 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 83.417 | No | 0 | 6
NST-244608 | SCE | 92503 | NEM | NEMA | Withdrawn | Solar PV | 147.494 | No | 0 | 4
NST-244631 | SCE | 92879 | NEM | NEMA | SCE Engineer Assigned. Pending Technical Review | Solar PV | 114.717 | No | 0 | 4
NST-245073 | SCE | 92270 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 52.177 | No | 0
NST-245164 | SCE | 93551 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 196.61 | No | 0 | 5
NST-245180 | SCE | 93551 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 236.27 | No | 0
NST-245183 | SCE | 93551 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 247.574 | No | 0 | 10
NST-245188 | SCE | 93536 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 114.793 | No | 0 | 9
NST-245190 | SCE | 93551 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 147.592 | No | 0 | 18
NST-245195 | SCE | 93536 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 226.091 | No | 0
NST-245201 | SCE | 93536 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 206.16 | No | 0
NST-245205 | SCE | 93536 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 463.859 | No | 0 | 6
NST-245223 | SCE | 90404 | NEM | VNEM-SOMAH | SCE Engineer Review. Pending Applicant Response | Solar PV | 48.843 | No | 0 | 6
NST-245315 | SCE | 92252 | NEM | NEMA | Withdrawn | Solar PV | 306.535 | No | 0
NST-245380 | SCE | 92584 | NEM | NEMA | Withdrawn | Solar PV | 325.146 | No | 0 | 4
NST-245384 | SCE | 90232 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 361.213 | No | 0 | 35
NST-245563 | SCE | 93063 | NEM | NEMA | Withdrawn | Solar PV | 634.205 | No | 0
NST-245576 | SCE | 91737 | NEM | VNEM-SOMAH | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 71.504 | No | 0 | 9
NST-245578 | SCE | 91737 | NEM | VNEM-SOMAH | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 31.512 | No | 0
NST-245586 | SCE | 91737 | NEM | VNEM-SOMAH | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 39.655 | No | 0
NST-245590 | SCE | 91737 | NEM | VNEM-SOMAH | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 76.188 | No | 0
NST-245592 | SCE | 91737 | NEM | VNEM-SOMAH | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 48.086 | No | 0 | 7
NST-245593 | SCE | 91737 | NEM | VNEM-SOMAH | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 31.849 | No | 0 | 1
NST-245661 | SCE | 91708 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 872.587 | No | 0 | 5
NST-245662 | SCE | 91708 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 959.183 | No | 0
NST-245749 | SCE | 91340 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 110.719 | No | 0 | 3
NST-245752 | SCE | 91340 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 110.758 | No | 0
NST-245927 | SCE | 91340 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 110.917 | No | 0 | 5
NST-246045 | SCE | 92614 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 129.672 | No | 0
NST-246066 | SCE | 90638 | NEM | NEMA | Applicant Response Received. Pending SCE Engineer Review | Solar PV + Battery Storage | 3527.933 | No | 0 | 2
NST-246066 | SCE | 90638 | NEM | NEM-ST | Application Review In Progress |  | 3527.933 | No | 0 | 5
NST-246469 | SCE | 90806 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 118.943 | No | 0 | 4
NST-246590 | SCE | 91108 | NEM | NEMA | Withdrawn | Solar PV | 32.59 | No | 0
NST-246891 | SCE | 91761 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 372.488 | No | 0
NST-24690 | SCE | 90631 | NEM | NEM-ST | Application Review In Progress |  | 0 | No | 0 | 0
NST-246972 | SCE | 91761 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 345.274 | No | 0 | 4
NST-247220 | SCE | 93105 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 32.761 | No | 0 | [13 empty] | 45
NST-247251 | SCE | 91362 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 36.133 | No | 0 | [13 empty] | 28
NST-247374 | SCE | 92532 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 59.568 | No | 0 | 4 | [12 empty] | 119
NST-247510 | SCE | 93291 | NEM | NEMA | Withdrawn | Solar PV | 33.773 | No | 0
NST-247523 | SCE | 93561 | NEM | VNEM-SOMAH | SCE Engineer Review. Pending Applicant Response | Solar PV | 34.972 | No | 0 | 4
NST-247620 | SCE | 92404 | NEM | VNEM-SOMAH | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 32.318 | No | 0 | 4
NST-247731 | SCE | 93033 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 180 | No | 0 | 6
NST-247776 | SCE | 93110 | NEM | NEMA | Withdrawn | Solar PV | 144.401 | No | 0 | 5
NST-24778 | SCE | 90620 | NEM | NEM-ST | Application Review In Progress |  | 0.54726 | No | 0
NST-247811 | SCE | 93274 | NEM | NEM Aggregation | IA Negotiation |  | 250.83 | No | 0 | 0 |  | 23
NST-247811 | SCE | 93274 | NEM | NEMA | SCE Engineer. Initial Review Complete | Solar PV | 250.83 | No | 0
NST-247920 | SCE | 91730 | NEM | NEMA | Withdrawn | Solar PV | 76.848 | No | 0 | 19
NST-247976 | SCE | 91302 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 32.153 | No | 0 | 30 | [12 empty] | 12
NST-247999 | SCE | 91764 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 679.237 | No | 0 | 4
NST-248292 | SCE | 92404 | NEM | VNEM-SOMAH | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 44.887 | No | 0 | 2
NST-248303 | SCE | 92404 | NEM | VNEM-SOMAH | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 32.318 | No | 0 | 5
NST-248322 | SCE | 92404 | NEM | VNEM-SOMAH | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 39.5 | No | 0 | 1
NST-248344 | SCE | 92404 | NEM | VNEM-SOMAH | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 39.5 | No | 0 | 0
NST-248351 | SCE | 92404 | NEM | VNEM-SOMAH | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 46.323 | No | 0
NST-248360 | SCE | 92404 | NEM | VNEM-SOMAH | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 40.937 | No | 0 | 6
NST-248376 | SCE | 92604 | NEM | VNEM-SOMAH | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 47.4 | No | 0 | 2
NST-248378 | SCE | 92404 | NEM | VNEM-SOMAH | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 40.219 | No | 0 | 4
NST-248694 | SCE | 93277 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 42.29 | No | 0 | 2 | [12 empty] | 59
NST-248702 | SCE | 92870 | NEM | NEMA | NEMI - Equipment Change Submitted | Solar PV | 200 | No | 0 | 4
NST-248756 | SCE | 90501 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 605.75 | No | 0 | 0
NST-248761 | SCE | 90501 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 381.67 | No | 0 | 7
NST-248982 | SCE | 91706 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 46.791 | No | 0 | [13 empty] | 98
NST-249052 | SCE | 92316 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 358.366 | No | 0
NST-249066 | SCE | 93230 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 129.671 | No | 0
NST-249069 | SCE | 90066 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 43.136 | No | 0 | 4 | [12 empty] | 117
NST-249104 | SCE | 92591 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 479.565 | No | 0
NST-249442 | SCE | 92311 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 42.726 | No | 0 | 0 | [12 empty] | 35
NST-249654 | SCE | 93274 | NEM | NEM Aggregation | Supplemental Review Complete |  | 1497.511 | No | 0 |  | 15 |  |  | 35
NST-249654 | SCE | 93274 | NEM | NEMA | SCE Engineer. Supplemental Review Complete | Solar PV | 1497.511 | No | 0 | 2
NST-249655 | SCE | 90249 | NEM | NEMA | Applicant Response Received. Pending SCE Engineer Review | Solar PV | 65.598 | No | 0 | 5
NST-249656 | SCE | 90247 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 111.144 | No | 0 | 9
NST-249750 | SCE | 92571 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 334.994 | No | 0
NST-249844 | SCE | 91706 | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 565.268 | No | 0 | 5
NST-249894 | SCE | 93103 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 121.494 | No | 0
NST-250098 | SCE | 92780 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 65.38 | No | 0 | 1 | [12 empty] | 59
NST-250102 | SCE | 92683 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 127.067 | No | 0
NST-250114 | SCE | 93230 | NEM | NEMA | NEMI - Sent to Engineering | Solar PV + Battery Storage | 784.207 | No | 0 | 3
NST-250268 | SCE | 91390 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 71.796 | No | 0
NST-250284 | SCE | 93230 | NEM | NEMA | NEMI - Sent to Engineering | Solar PV + Battery Storage | 688.819 | No | 0 | 4
NST-250431 | SCE | 91801 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 206.05 | No | 0 | 4
NST-250433 | SCE | 91803 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 332.66 | No | 0 | 11
NST-250437 | SCE | 91801 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 126.609 | No | 0
NST-250438 | SCE | 91803 | NEM | NEMA | Withdrawn | Solar PV | 126.609 | No | 0
NST-250442 | SCE | 91754 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 218.463 | No | 0
NST-250447 | SCE | 91803 | NEM | NEMA | Withdrawn | Solar PV | 130.56 | No | 0 | 4
NST-250448 | SCE | 91801 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 677.732 | No | 0 | 4
NST-250451 | SCE | 91801 | NEM | NEM-ST | Application Review In Progress |  | 1052.595 | No | 0
NST-250451 | SCE | 91801 | NEM | NEMA | SCE Engineer Assigned. Pending Technical Review | Solar PV | 1052.595 | No | 0 | 0
NST-250455 | SCE | 91801 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 119.162 | No | 0 | 9
NST-250460 | SCE | 91754 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 158.882 | No | 0 | 8
NST-250465 | SCE | 91776 | NEM | NEMA | Withdrawn | Solar PV | 1108.866 | No | 0 | 6
NST-250467 | SCE | 91803 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 129.092 | No | 0 | 4
NST-250722 | SCE | 92606 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 99.427 | No | 0
NST-250730 | SCE | 93001 | NEM | Other-NEM-V | Withdrawn | Solar PV | 362.024 | No | 0
NST-250915 | SCE | 92530 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 122.423 | No | 0 | 0 | [12 empty] | 70
NST-251046 | SCE | 92614 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 123.891 | No | 0 | 1 | [12 empty] | 98
NST-251093 | SCE | 92408 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 371.208 | No | 0
NST-251099 | SCE | 92210 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 37.669 | No | 0 | 11 | [12 empty] | 112
NST-251193 | SCE | 93101 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 148.858 | No | 0 | 4
NST-251197 | SCE | 90241 | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 72.318 | No | 0
NST-251212 | SCE | 90806 | NEM | NEMA | Withdrawn | Solar PV | 52.487 | No | 0 | 21
NST-251304 | SCE | 91702 | NEM | NEM-ST | System Impact Study In Progress |  | 4922.188 | No | 0 | 3 |  |  |  |  | 6 | [7 empty] | 0
NST-251304 | SCE | 91702 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 4922.188 | No | 0 | 8 | [12 empty] | 0
NST-251393 | SCE | 92374 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 117.412 | No | 0
NST-251430 | SCE | 92880 | NEM | NEMA | Withdrawn | Solar PV | 492.08 | No | 0 | 15
NST-251502 | SCE | 92708 | NEM | NEMA | Withdrawn | Solar PV | 397 | No | 0
NST-251585 | SCE | 92880 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 110.436 | No | 0
NST-251718 | SCE | 91724 | NEM | Other-NEM-V | Withdrawn | Solar PV | 105.284 | No | 0
NST-251787 | SCE | 93235 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 991.559 | No | 0 | 8
NST-251803 | SCE | 93230 | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 38.241 | No | 0 | 0
NST-251838 | SCE | 92840 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 49.433 | No | 0 | 5
NST-251846 | SCE | 93274 | NEM | NEMA | Withdrawn | Solar PV | 994.866 | No | 0 | 7
NST-251914 | SCE | 93012 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 35.957 | No | 0 | 4
NST-251924 | SCE | 92335 | NEM | NEMA | Withdrawn | Solar PV | 77.303 | No | 0 | 18
NST-251942 | SCE | 90810 | NEM | NEMA | Withdrawn | Solar PV | 79.721 | No | 0 | 1
NST-251948 | SCE | 90232 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 32.604 | No | 0
NST-251959 | SCE | 92656 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 69.708 | No | 0 | 4
NST-251984 | SCE | 92571 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 997.192 | No | 0
NST-252007 | SCE | 93272 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 781.228 | No | 0 | 5
NST-252032 | SCE | 90505 | NEM | NEMA | Withdrawn | Solar PV | 53.18 | No | 0
NST-252034 | SCE | 90032 | NEM | NEMA | Withdrawn | Solar PV | 59.396 | No | 0
NST-252037 | SCE | 91387 | NEM | NEMA | Withdrawn | Solar PV | 70.669 | No | 0
NST-252039 | SCE | 90250 | NEM | NEMA | Withdrawn | Solar PV | 82.091 | No | 0 | 4
NST-252041 | SCE | 91763 | NEM | NEMA | Withdrawn | Solar PV | 97.438 | No | 0
NST-252046 | SCE | 90403 | NEM | NEMA | Withdrawn | Solar PV | 60.011 | No | 0
NST-252049 | SCE | 91748 | NEM | NEMA | Withdrawn | Solar PV | 82.448 | No | 0 | 4
NST-252050 | SCE | 92260 | NEM | NEMA | Withdrawn | Solar PV | 110.644 | No | 0
NST-252051 | SCE | 91730 | NEM | NEMA | Withdrawn | Solar PV | 102.792 | No | 0 | 4
NST-252098 | SCE | 92883 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 42.415 | No | 0 | 4
NST-252150 | SCE | 92880 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 42.415 | No | 0 | 4
NST-252151 | SCE | 92882 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 42.415 | No | 0 | 9
NST-252152 | SCE | 92881 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 42.415 | No | 0 | #VALUE!
NST-252153 | SCE | 92882 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 42.415 | No | 0 | 1
NST-252154 | SCE | 92882 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 42.8 | No | 0 | 10
NST-252191 | SCE | 92882 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 42.415 | No | 0 | 4
NST-252195 | SCE | 92879 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 42.415 | No | 0 | 18
NST-252235 | SCE | 92880 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 42.415 | No | 0 | 24
NST-252244 | SCE | 91355 | NEM | NEMA | Applicant Response Received. Pending SCE Engineer Review | Solar PV | 376.508 | No | 0 | 7
NST-252245 | SCE | 92860 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 42.415 | No | 0
NST-252291 | SCE | 92879 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 42.415 | No | 0 | 6
NST-252297 | SCE | 92880 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 42.415 | No | 0 | 6
NST-252301 | SCE | 92882 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 42.415 | No | 0
NST-252305 | SCE | 92882 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 42.415 | No | 0 | 11
NST-252306 | SCE | 92882 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 42.415 | No | 0 | 4
NST-252311 | SCE | 92881 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 42.415 | No | 0 | 3
NST-252314 | SCE | 92881 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 42.415 | No | 0 | 11
NST-252316 | SCE | 92882 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 42.415 | No | 0
NST-252334 | SCE | 92879 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 42.415 | No | 0 | 4
NST-252400 | SCE | 92860 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 42.415 | No | 0 | 3
NST-252401 | SCE | 92881 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 42.415 | No | 0
NST-252402 | SCE | 92879 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 41.855 | No | 0 | 7
NST-252407 | SCE | 92879 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 42.415 | No | 0 | 36
NST-252408 | SCE | 92879 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 42.415 | No | 0
NST-252411 | SCE | 92882 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 42.415 | No | 0 | 16
NST-252414 | SCE | 92879 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 42.415 | No | 0 | 25
NST-252420 | SCE | 92860 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 42.415 | No | 0
NST-252425 | SCE | 92860 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 42.415 | No | 0
NST-252427 | SCE | 92860 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 42.415 | No | 0
NST-252450 | SCE | 90640 | NEM | NEM-ST | Fast Track Initial Review In Progress |  | 2051.039 | No | 0 | 10
NST-252450 | SCE | 90640 | NEM | NEMA | SCE Engineer. Initial Review In Progress | Solar PV + Battery Storage | 2051.039 | No | 0 | 4
NST-252457 | SCE | 93274 | NEM | NEMA | Withdrawn | Solar PV | 87.041 | No | 0 | 1
NST-252462 | SCE | 91748 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 606.981 | No | 0 | 2
NST-252468 | SCE | 93277 | NEM | NEMA | Withdrawn | Solar PV | 187.057 | No | 0 | 3
NST-252501 | SCE | 93272 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 781.228 | No | 0 | 6
NST-252517 | SCE | 92883 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 42.415 | No | 0
NST-252526 | SCE | 92860 | NEM | NEMA | Withdrawn | Solar PV | 42.415 | No | 0
NST-252535 | SCE | 93291 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 32.388 | No | 0 | #VALUE! | [12 empty] | 66
NST-252543 | SCE | 92880 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 42.415 | No | 0
NST-252547 | SCE | 92882 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 42.415 | No | 0
NST-252559 | SCE | 93235 | NEM | NEMA | Withdrawn | Solar PV | 991.559 | No | 0
NST-252560 | SCE | 92881 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 42.415 | No | 0 | 11
NST-252575 | SCE | 92886 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 248.953 | No | 0 | 10
NST-252618 | SCE | 92653 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 428.831 | No | 0 | 5
NST-252730 | SCE | 93561 | NEM | VNEM-SOMAH | NGOM Installation. Pending Local Planner Process | Solar PV | 42.153 | No | 0 | 5
NST-252877 | SCE | 92701 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 111.575 | No | 0 | [13 empty] | 62
NST-252883 | SCE | 90045 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 238.307 | No | 0 | 1
NST-252884 | SCE | 90045 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 302.274 | No | 0
NST-252884 | SCE | 90045 | NEM | NEM-ST | Application Review In Progress |  | 302.274 | No | 0
NST-253322 | SCE | 92509 | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 92.471 | No | 0
NST-253425 | SCE | 91752 | NEM | NEMA | SCE Engineer Review. Pending Applicant Construction | Solar PV | 997.456 | No | 0
NST-253488 | SCE | 91350 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 143.869 | No | 0
NST-253627 | SCE | 91340 | NEM | NEMA | Withdrawn | Solar PV | 30.191 | No | 0 | 5
NST-253693 | SCE | 92316 | NEM | NEMA | SCE Engineer Assigned. Pending Technical Review | Solar PV + Battery Storage | 1706.443 | No | 0 | 4
NST-253693 | SCE | 92316 | NEM | NEM-ST | Application Review In Progress |  | 1706.443 | No | 0 | 4
NST-253723 | SCE | 92708 | NEM | NEM Aggregation | Application Review In Progress |  | 1075.526 | No | 0 | [13 empty] | 0
NST-253723 | SCE | 92708 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 1075.526 | No | 0 | [13 empty] | 0
NST-253725 | SCE | 93724 | NEM | VNEM-SOMAH | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 94.611 | No | 0 | 9
NST-253790 | SCE | 90740 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 232.795 | No | 0 | 7
NST-254114 | SCE | 90807 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 44.06 | No | 0 | 5 | [12 empty] | 64
NST-254163 | SCE | 93065 | NEM | NEM-ST | Application Review In Progress |  | 16500 | No | 0 | 4
NST-254163 | SCE | 93065 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 16500 | No | 0
NST-254256 | SCE | 91387 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 33.646 | No | 0 | 10 | [12 empty] | 1
NST-254377 | SCE | 93066 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 884.458 | No | 0
NST-254405 | SCE | 93247 | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 37.198 | No | 0 | 8
NST-254415 | SCE | 93117 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 234.917 | No | 0 | 3 | [12 empty] | 43
NST-254435 | SCE | 92337 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 413.639 | No | 0 | 7
NST-254490 | SCE | 92301 | NEM | NEMA | Withdrawn | Solar PV | 101.853 | No | 0
NST-254511 | SCE | 93219 | NEM | NEMA | Withdrawn | Solar PV | 208.306 | No | 0 | 2
NST-254546 | SCE | 92223 | NEM | NEMA | Withdrawn | Solar PV | 456.123 | No | 0
NST-254613 | SCE | 92821 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 177.793 | No | 0 | 88
NST-254677 | SCE | 92313 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 94.577 | No | 0 | 6 | [12 empty] | 65
NST-254817 | SCE | 92591 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 243.043 | No | 0 | 7
NST-254843 | SCE | 91302 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 895.332 | No | 0 | 4
NST-254882 | SCE | 90630 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 184.41 | No | 0
NST-254968 | SCE | 93546 | NEM | NEM-ST | Application Review In Progress |  | 869.26 | No | 0 | 8
NST-254968 | SCE | 93546 | NEM | Other-MT | Pending Agreement Approval/Execution | Solar PV + Battery Storage | 869.26 | No | 0 | 7
NST-255071 | SCE | 92277 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 34.136 | No | 0
NST-255104 | SCE | 92270 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 61.389 | No | 0 | 28 | [12 empty] | 22
NST-255153 | SCE | 90242 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 176.347 | No | 0
NST-255191 | SCE | 91016 | NEM | Other-NEM-V | NEMI - Load Justification Reviewed | Solar PV | 502.288 | No | 0
NST-255282 | SCE | 91730 | NEM | NEMA | Withdrawn | Solar PV | 76.848 | No | 0 | 4
NST-255297 | SCE | 93257 | NEM | VNEM | SCE Engineer Review. Pending Applicant Response | Solar PV | 120.815 | No | 0 | 6
NST-255301 | SCE | 93257 | NEM | VNEM | SCE Engineer Review. Pending Applicant Response | Solar PV | 64.586 | No | 0 | 7
NST-255315 | SCE | 92223 | NEM | NEMA | Withdrawn | Solar PV | 683.774 | No | 0 | 5
NST-255319 | SCE | 93063 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 634.629 | No | 0 | 3
NST-255359 | SCE | 90220 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 931.18 | No | 0 | 4
NST-255404 | SCE | 91711 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 84.194 | No | 0 | 3
NST-255429 | SCE | 91711 | NEM | NEMA | Withdrawn | Solar PV | 92.774 | No | 0
NST-255516 | SCE | 92627 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 172.666 | No | 0 | 3
NST-255533 | SCE | 92210 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 30.628 | No | 0 | [13 empty] | 37
NST-255603 | SCE | 93274 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 143.83 | No | 0 | 16
NST-255692 | SCE | 93277 | NEM | NEMA | Withdrawn | Solar PV | 36.2563 | No | 0
NST-255734 | SCE | 90242 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 136.916 | No | 0 | 4
NST-255739 | SCE | 90241 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 372.128 | No | 0
NST-255739 | SCE | 90241 | NEM | NEM-ST | Application Review In Progress |  | 372.128 | No | 0 | 9
NST-255743 | SCE | 90241 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 322.584 | No | 0
NST-255747 | SCE | 90241 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 176.319 | No | 0 | 0
NST-255749 | SCE | 90240 | NEM | NEM-ST | Application Review In Progress |  | 317.079 | No | 0
NST-255749 | SCE | 90240 | NEM | NEMA | Applicant Response Received. Pending SCE Engineer Review | Solar PV | 317.079 | No | 0
NST-255795 | SCE | 93030 | NEM | NEM-ST | Application Review In Progress |  | 1871.21 | No | 0 | 4
NST-255795 | SCE | 93030 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 1871.21 | No | 0
NST-255801 | SCE | 93030 | NEM | NEM-ST | Application Review In Progress |  | 1876.208 | No | 0 | 5
NST-255801 | SCE | 93030 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 1876.208 | No | 0
NST-255852 | SCE | 92374 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 178.414 | No | 0 | 5
NST-255875 | SCE | 90670 | NEM | VNEM-SOMAH | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 143.535 | No | 0 | 0
NST-255876 | SCE | 90670 | NEM | VNEM-SOMAH | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 78.32 | No | 0 | 0
NST-255877 | SCE | 90670 | NEM | VNEM-SOMAH | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 34.877 | No | 0 | 0
NST-255881 | SCE | 91010 | NEM | VNEM-SOMAH | NGOM Installation. Pending Local Planner Process | Solar PV | 70.618 | No | 0 | 5
NST-255883 | SCE | 92882 | NEM | VNEM-SOMAH | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 112.891 | No | 0 | 16
NST-255972 | SCE | 91710 | NEM | NEM-ST | Application Review In Progress |  | 2065.994 | No | 0
NST-255972 | SCE | 91710 | NEM | NEMA | SCE Engineer Assigned. Pending Technical Review | Solar PV + Battery Storage | 2065.994 | No | 0 | 15
NST-255973 | SCE | 90603 | NEM | NEMA | Applicant Response Received. Pending SCE Engineer Review | Solar PV | 907.796 | No | 0
NST-255989 | SCE | 90670 | NEM | Other-NEM-V | SCE Engineer Review. Pending Applicant Response | Solar PV | 344.776 | No | 0 | #VALUE!
NST-256038 | SCE | 92324 | NEM | Other-NEM-V | NEMI - Application Returned. Pending Applicant Corrections | Solar PV | 113.427 | No | 0 | 6
NST-256047 | SCE | 90241 | NEM | NEMA | Applicant Response Received. Pending SCE Engineer Review | Solar PV | 758.201 | No | 0 | 8 | [12 empty] | 0
NST-256047 | SCE | 90241 | NEM | NEM-ST | Application Review In Progress |  | 758.201 | No | 0 | [13 empty] | 0
NST-256051 | SCE | 90241 | NEM | NEM-ST | Application Review In Progress |  | 739.852 | No | 0 | [13 empty] | 0
NST-256051 | SCE | 90241 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 739.852 | No | 0 | 15 | [12 empty] | 0
NST-256052 | SCE | 90241 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 171.966 | No | 0 | 8
NST-256053 | SCE | 90242 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 173.061 | No | 0 | [13 empty] | 0
NST-256053 | SCE | 90242 | NEM | NEM-ST | Application Review In Progress |  | 173.061 | No | 0 | [13 empty] | 0
NST-256054 | SCE | 90706 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 101.865 | No | 0
NST-256056 | SCE | 92324 | NEM | Other-NEM-V | NEMI - Application Returned. Pending Applicant Corrections | Solar PV | 95.708 | No | 0 | 3
NST-256057 | SCE | 90240 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 173.061 | No | 0 | 20
NST-256057 | SCE | 90240 | NEM | NEM-ST | Application Review In Progress |  | 173.061 | No | 0
NST-256059 | SCE | 90670 | NEM | Other-NEM-V | Withdrawn | Solar PV | 91.471 | No | 0
NST-256065 | SCE | 90241 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 171.966 | No | 0
NST-256070 | SCE | 90670 | NEM | Other-NEM-V | Withdrawn | Solar PV | 147.761 | No | 0
NST-256102 | SCE | 91010 | NEM | VNEM-SOMAH | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 50.573 | No | 0 | 4
NST-256182 | SCE | 93256 | NEM | NEMA | Withdrawn | Solar PV | 531.222 | No | 0 | 8
NST-256216 | SCE | 90740 | NEM | Other-NEM-V | NEMI - Application Re-Submitted | Solar PV | 1367.053 | No | 0
NST-256229 | SCE | 93536 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 33.152 | No | 0 | 0 | [12 empty] | 34
NST-256285 | SCE | 93256 | NEM | NEMA | Withdrawn | Solar PV | 334.056 | No | 0
NST-256295 | SCE | 90232 | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 46.086 | No | 0 | 5
NST-256306 | SCE | 90242 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 131.439 | No | 0
NST-256312 | SCE | 90241 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 171.966 | No | 0 | 6
NST-256318 | SCE | 90242 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 376.532 | No | 0 | 4
NST-256325 | SCE | 90242 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 262.031 | No | 0 | 1
NST-256327 | SCE | 92373 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 123.621 | No | 0 | 2
NST-256331 | SCE | 90241 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 86.977 | No | 0 | 8
NST-256333 | SCE | 92882 | NEM | NEMA | Withdrawn | Solar PV | 90.335 | No | 0
NST-256335 | SCE | 90240 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 177.442 | No | 0
NST-256337 | SCE | 92882 | NEM | NEMA | Withdrawn | Solar PV | 170.904 | No | 0
NST-256339 | SCE | 90241 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 132.534 | No | 0 | 5
NST-256342 | SCE | 91016 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 65.493 | No | 0 | 11
NST-256344 | SCE | 90241 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 770.679 | No | 0 | 15 | [12 empty] | 0
NST-256344 | SCE | 90241 | NEM | NEM-ST | Application Review In Progress |  | 770.679 | No | 0 | 5 | [12 empty] | 0
NST-256347 | SCE | 90241 | NEM | NEM-ST | Fast Track Initial Review In Progress |  | 713.429 | No | 0 | 4
NST-256347 | SCE | 90241 | NEM | NEMA | SCE Engineer. Initial Review In Progress | Solar PV | 713.429 | No | 0
NST-256350 | SCE | 92867 | NEM | NEMA | Withdrawn | Solar PV | 66.751 | No | 0
NST-256351 | SCE | 90242 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 176.347 | No | 0 | 3
NST-256360 | SCE | 90802 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 136.727 | No | 0
NST-256362 | SCE | 90241 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 373.596 | No | 0 | 4
NST-256366 | SCE | 90241 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 264.233 | No | 0 | 5
NST-256371 | SCE | 90242 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 135.82 | No | 0 | 9
NST-256384 | SCE | 92780 | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 45.527 | No | 0 | 8
NST-256407 | SCE | 90630 | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 35.578 | No | 0 | 7
NST-256408 | SCE | 90242 | NEM | NEMA | Withdrawn | Solar PV | 235.093 | No | 0 | 4
NST-256428 | SCE | 90242 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 221.011 | No | 0 | 11
NST-256437 | SCE | 90242 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 188.153 | No | 0 | 1
NST-256462 | SCE | 90670 | NEM | NEMA | Withdrawn | Solar PV | 76.239 | No | 0 | 4
NST-256476 | SCE | 90802 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 943.859 | No | 0 | 8
NST-256510 | SCE | 92504 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 174.756 | No | 0 | 7
NST-256514 | SCE | 92503 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 260.135 | No | 0
NST-256516 | SCE | 92507 | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 186.892 | No | 0 | 1
NST-256529 | SCE | 92882 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 41.37 | No | 0 | 17
NST-256560 | SCE | 90242 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 146.298 | No | 0 | 4
NST-256565 | SCE | 90242 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 232.783 | No | 0 | 2
NST-256569 | SCE | 90242 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 211.918 | No | 0 | 2
NST-256606 | SCE | 92618 | NEM | NEMA | Withdrawn | Solar PV | 33.734 | No | 0
NST-256677 | SCE | 91746 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 987.579 | No | 0 | 5
NST-256727 | SCE | 92841 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 238.157 | No | 0 | 6
NST-256754 | SCE | 93514 | NEM | NEM-ST | Application Review In Progress |  | 0.024726 | No | 0
NST-256785 | SCE | 93215 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 30.561 | No | 0 | 1
NST-256817 | SCE | 92867 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 35.88 | No | 0
NST-256866 | SCE | 90640 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 506.61 | No | 0
NST-256869 | SCE | 90040 | NEM | NEMA | Withdrawn | Solar PV | 149.906 | No | 0
NST-256872 | SCE | 90640 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 372.493 | No | 0 | 4
NST-256967 | SCE | 90250 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 517.99 | No | 0 | 8
NST-256971 | SCE | 90260 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 579.95 | No | 0 | 7
NST-256984 | SCE | 92508 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 38.302 | No | 0 | #VALUE!
NST-257005 | SCE | 90245 | NEM | NEMA | NEMI - Application Returned 2nd Time. Pending Applicant Corrections | Solar PV | 491.583 | No | 0 | 14
NST-257010 | SCE | 93247 | NEM | NEMA | SCE Engineer. Supplemental Review Complete | Solar PV | 84.745 | No | 0 | 6 | [12 empty] | 0
NST-257010 | SCE | 93247 | NEM | NEM-ST | Application Review In Progress |  | 84.745 | No | 0 | [13 empty] | 0
NST-257365 | SCE | 93292 | NEM | NEMA | Applicant Response Received. Pending SCE Engineer Review | Solar PV | 66.295 | No | 0 | 11
NST-257394 | SCE | 93291 | NEM | NEMA | Withdrawn | Solar PV | 35.723 | No | 0
NST-257474 | SCE | 91724 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 105.284 | No | 0
NST-257513 | SCE | 90280 | NEM | NEMA | NEMI - 1.0 Expansion Ineligible | Solar PV | 447.454 | No | 0 | 10
NST-257572 | SCE | 93550 | NEM | NEMA | Withdrawn | Solar PV | 263.235 | No | 0
NST-257662 | SCE | 90807 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 86.188 | No | 0
NST-257779 | SCE | 93109 | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 48.655 | No | 0 | 8
NST-257786 | SCE | 90802 | NEM | NEMA | Withdrawn | Solar PV | 1894.456 | No | 0 | 2
NST-257922 | SCE | 92571 | NEM | NEMA | Withdrawn | Solar PV | 997.192 | No | 0 | 7
NST-257972 | SCE | 93230 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 896.1482 | No | 0 | [13 empty] | 33
NST-258041 | SCE | 92260 | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 34.588 | No | 0 | 14
NST-258042 | SCE | 91741 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 101.589 | No | 0 | 5 | [12 empty] | 6
NST-258155 | SCE | 93561 | NEM | NEMA | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 32.161 | No | 0
NST-258182 | SCE | 92833 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 82.216 | No | 0 | 2
NST-258360 | SCE | 92821 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 388.4 | No | 0 | 10
NST-258409 | SCE | 92352 | NEM | NEM-ST | Transferred to NEM |  | 0 | No | 0 | [13 empty] | 0
NST-258442 | SCE | 93291 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 113.595 | No | 0 | 4
NST-258449 | SCE | 90621 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 372.109 | No | 0 | 0
NST-258455 | SCE | 90620 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 423.819 | No | 0
NST-258464 | SCE | 90620 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 196.361 | No | 0 | 3
NST-258471 | SCE | 92821 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 200.5 | No | 0
NST-258474 | SCE | 90621 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 215.328 | No | 0
NST-258479 | SCE | 90621 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 266.642 | No | 0
NST-258481 | SCE | 92821 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 388.4 | No | 0 | 4
NST-258486 | SCE | 92821 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 432.3 | No | 0
NST-258487 | SCE | 90621 | NEM | NEMA | Withdrawn | Solar PV | 205.755 | No | 0
NST-258493 | SCE | 92657 | NEM | NEMA | NEMI - Pending Permanent Service | Solar PV | 39.752 | No | 0 | 13
NST-258583 | SCE | 93277 | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 30.824 | No | 0 | 2
NST-258587 | SCE | 92313 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 284.657 | No | 0 | 4
NST-258592 | SCE | 92313 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 234.09 | No | 0
NST-258674 | SCE | 93023 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 46.533 | No | 0 | 3
NST-258679 | SCE | 93023 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 85.284 | No | 0 | 2
NST-258682 | SCE | 93024 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 348.444 | No | 0 | 10
NST-259231 | SCE | 90703 | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 41.753 | No | 0 | 3
NST-259299 | SCE | 92646 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 95.027 | No | 0 | 5
NST-259319 | SCE | 92618 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 804.698 | No | 0 | 6
NST-259325 | SCE | 92618 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 56.898 | No | 0 | 22
NST-259329 | SCE | 92618 | NEM | NEMA | Withdrawn | Solar PV | 450.324 | No | 0 | 9
NST-259334 | SCE | 92618 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 136.961 | No | 0 | 0
NST-259346 | SCE | 93274 | NEM | NEMA | SCE Engineer. Supplemental Review In Progress | Solar PV | 994.866 | No | 0
NST-259346 | SCE | 93274 | NEM | NEM-ST | Application Review In Progress |  | 994.866 | No | 0
NST-259348 | SCE | 92683 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 366.779 | No | 0 | 26
NST-259356 | SCE | 91803 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 130.56 | No | 0 | 4
NST-259362 | SCE | 91803 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 126.609 | No | 0 | 0
NST-259409 | SCE | 92866 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 33.793 | No | 0 | 2 | [12 empty] | 47
NST-259526 | SCE | 93274 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 713.342 | No | 0 | #VALUE!
NST-259571 | SCE | 93291 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 46.76 | No | 0 | 6 | [12 empty] | 15
NST-259754 | SCE | 92647 | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 85.422 | No | 0 | 4
NST-260062 | SCE | 90640 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 65.426 | No | 0
NST-260385 | SCE | 90220 | NEM | NEMA | NEMI - Equipment Change Submitted | Solar PV | 316.373 | No | 0
NST-260575 | SCE | 91340 | NEM | NEMA | Withdrawn | Solar PV | 415.276 | No | 0 | 4
NST-260607 | SCE | 92866 | NEM | NEMA | Withdrawn | Solar PV | 130.234 | No | 0 | 4
NST-260676 | SCE | 91776 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 897.851 | No | 0
NST-260781 | SCE | 93230 | NEM | NEM Aggregation | Withdrawn |  | 781.056 | No | 0 |  | 15 | [11 empty] | 0
NST-260781 | SCE | 93230 | NEM | NEMA | SCE Engineer. Initial Review Complete | Solar PV | 781.056 | No | 0 | 4 | [12 empty] | 0
NST-260817 | SCE | 92335 | NEM | NEMA | Withdrawn | Solar PV | 166.035 | No | 0
NST-260835 | SCE | 93291 | NEM | NEM-ST | Application Review In Progress |  | 1313.517 | No | 0 | 9
NST-260835 | SCE | 93291 | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 1313.517 | No | 0
NST-260849 | SCE | 90606 | NEM | NEMA | SCE Engineer Assigned. Pending Technical Review | Solar PV | 132.097 | No | 0 | 1
NST-260849 | SCE | 90606 | NEM | NEM Aggregation | Application Review In Progress |  | 132.097 | No | 0
NST-261089 | SCE | 90241 | NEM | NEMA | NEMI - Sent to Engineering | Solar PV | 70.255 | No | 0 | 4
NST-261114 | SCE | 90266 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 36.611 | No | 0
NST-261177 | SCE | 92562 | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 36.296 | No | 0 | 3
NST-261229 | SCE | 92660 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 178.804 | No | 0 | #VALUE!
NST-261230 | SCE | 94558 | NEM | NEMA | SCE Engineer Assigned. Pending Technical Review | Solar PV | 648.163 | No | 0
NST-261231 | SCE | 94558 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 175.656 | No | 0 | 5
NST-261244 | SCE | 94558 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 626.012 | No | 0 | 2
NST-261246 | SCE | 94558 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 351.598 | No | 0 | 9
NST-261247 | SCE | 91765 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 289.627 | No | 0 | 10
NST-261389 | SCE | 92832 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 51.233 | No | 0 | [13 empty] | 42
NST-261400 | SCE | 92651 | NEM | NEMA | Withdrawn | Solar PV | 600 | No | 0 | 4
NST-261411 | SCE | 93109 | NEM | NEMA | Withdrawn | Solar PV | 232.819 | No | 0
NST-261449 | SCE | 93109 | NEM | NEMA | Withdrawn | Solar PV | 261.921 | No | 0 | 3
NST-261478 | SCE | 92688 | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 248.149 | No | 0 | 8
NST-261502 | SCE | 92210 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 278.313 | No | 0 | 52
NST-261605 | SCE | 92831 | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 442.891 | No | 0
NST-261606 | SCE | 92831 | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 224.767 | No | 0
NST-261784 | SCE | 93230 | NEM | NEM Aggregation | Supplemental Review In Progress |  | 998.341 | No | 0 | 4 | 15
NST-261784 | SCE | 93230 | NEM | NEMA | SCE Engineer. Supplemental Review In Progress | Solar PV | 998.341 | No | 0
NST-261814 | SCE | 92688 | NEM | NEM-ST | Fast Track Initial Review Complete |  | 1023.216 | No | 0 |  | 10
NST-261814 | SCE | 92688 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 1023.216 | No | 0 | 4
NST-261845 | SCE | 92374 | NEM | NEMA | Withdrawn | Solar PV | 1821.542 | No | 0 | 0
NST-261889 | SCE | 90712 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 515.802 | No | 0 | 4
NST-261903 | SCE | 92374 | NEM | NEM-ST | Application Review In Progress |  | 3491.473 | No | 0 | 4 | [12 empty] | 0
NST-261903 | SCE | 92374 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 3491.473 | No | 0 | 17 | [12 empty] | 0
NST-261906 | SCE | 92210 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 277.894 | No | 0 | 1
NST-262143 | SCE | 91764 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 36.804 | No | 0 | 8
NST-262144 | SCE | 91764 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 34.396 | No | 0 | #VALUE!
NST-262452 | SCE | 91790 | NEM | NEMA | NEMI - Application Returned 2nd Time. Pending Applicant Corrections | Solar PV | 909.388 | No | 0 | 7
NST-262485 | SCE | 92220 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 448.956 | No | 0 | 9
NST-262500 | SCE | 92220 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 151.423 | No | 0 | 0
NST-262618 | SCE | 92270 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 129.935 | No | 0 | 6
NST-262643 | SCE | 92626 | NEM | NEMA | Withdrawn | Solar PV | 39.25 | No | 0
NST-262644 | SCE | 92879 | NEM | NEMA | Withdrawn | Solar PV | 30.061 | No | 0
NST-262678 | SCE | 93501 | NEM | NEMA | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 69.319 | No | 0 | 7
NST-262679 | SCE | 93501 | NEM | NEMA | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 73.378 | No | 0 | 2
NST-262712 | SCE | 92210 | NEM | NEM-ST | Application Review In Progress |  | 668.958 | No | 0 | 3 | [12 empty] | 0
NST-262712 | SCE | 92210 | NEM | NEMA | Withdrawn | Solar PV | 668.958 | No | 0 | [13 empty] | 0
NST-262724 | SCE | 93012 | NEM | NEMA | NEMI - Application Re-Submitted | Solar PV | 80.471 | No | 0 | 18
NST-262733 | SCE | 93501 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 779.012 | No | 0 | 10
NST-262737 | SCE | 91730 | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 810.172 | No | 0 | 7
NST-262749 | SCE | 90670 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 470.067 | No | 0
NST-262824 | SCE | 92503 | NEM | NEMA | Withdrawn | Solar PV | 241.839 | No | 0
NST-262856 | SCE | 92637 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 33.29 | No | 0 | 0
NST-262882 | SCE | 92653 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 79.721 | No | 0
NST-262906 | SCE | 92821 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 155.668 | No | 0 | 4
NST-262926 | SCE | 91730 | NEM | NEMA | Withdrawn | Solar PV | 76.807 | No | 0 | 9
NST-262985 | SCE | 91302 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 77.725 | No | 0 | 2
NST-262994 | SCE | 92653 | NEM | NEMA | Withdrawn | Solar PV | 183.972 | No | 0
NST-263013 | SCE | 92653 | NEM | NEMA | NEMI - Application Returned. Pending Applicant Corrections | Solar PV | 797.214 | No | 0 | 3
NST-263018 | SCE | 92653 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 70.523 | No | 0 | 3
NST-263142 | SCE | 92234 | NEM | NEMA | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 61.2 | No | 0
NST-263323 | SCE | 90670 | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 417.847 | No | 0
NST-263334 | SCE | 93535 | NEM | NEMA | Withdrawn | Solar PV | 250.778 | No | 0
NST-263532 | SCE | 93065 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 189.979 | No | 0 | 4
NST-263533 | SCE | 93065 | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 626.048 | No | 0 | 11
NST-263618 | SCE | 92223 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 79.075 | No | 0
NST-263625 | SCE | 92562 | NEM | NEMA | NEMI - Application Returned 2nd Time. Pending Applicant Corrections | Solar PV | 177.016 | No | 0
NST-263626 | SCE | 92562 | NEM | NEMA | NEMI - Application Returned 2nd Time. Pending Applicant Corrections | Solar PV | 177.016 | No | 0
NST-263627 | SCE | 90505 | NEM | NEMA | NEMI - Application Returned 2nd Time. Pending Applicant Corrections | Solar PV | 177.016 | No | 0 | 5
NST-263628 | SCE | 90201 | NEM | NEMA | NEMI - Application Returned 2nd Time. Pending Applicant Corrections | Solar PV | 486.795 | No | 0 | 4
NST-263629 | SCE | 90201 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 177.016 | No | 0 | 8
NST-263630 | SCE | 91786 | NEM | NEMA | NEMI - Application Returned. Pending Applicant Corrections | Solar PV | 265.524 | No | 0 | 6
NST-263631 | SCE | 91786 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 132.538 | No | 0 | 6
NST-263632 | SCE | 92234 | NEM | NEMA | NEMI - Application Returned. Pending Applicant Corrections | Solar PV | 407.138 | No | 0
NST-263638 | SCE | 93010 | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 520.682 | No | 0
NST-263642 | SCE | 91331 | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 336.331 | No | 0 | 5
NST-263643 | SCE | 91331 | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 336.331 | No | 0
NST-263653 | SCE | 90732 | NEM | NEMA | Withdrawn | Solar PV | 238.972 | No | 0
NST-263654 | SCE | 90732 | NEM | NEMA | Withdrawn | Solar PV | 238.972 | No | 0
NST-263655 | SCE | 90732 | NEM | NEMA | Withdrawn | Solar PV | 159.315 | No | 0
NST-263656 | SCE | 92562 | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 88.508 | No | 0
NST-263657 | SCE | 92562 | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 88.508 | No | 0
NST-263658 | SCE | 92882 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 354.033 | No | 0 | 2
NST-263659 | SCE | 92882 | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 141.613 | No | 0
NST-263660 | SCE | 92882 | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 141.613 | No | 0
NST-263701 | SCE | 92595 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 66.933 | No | 0 | 0
NST-263775 | SCE | 91711 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 101.116 | No | 0 | 20
NST-263786 | SCE | 92264 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 35.2 | No | 0 | 6 | [12 empty] | 17
NST-263802 | SCE | 92230 | NEM | NEM-ST | Application Review In Progress |  | 1742.694 | No | 0 | [13 empty] | 0
NST-263802 | SCE | 92230 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 1742.694 | No | 0 | [13 empty] | 0
NST-263840 | SCE | 90660 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 537.126 | No | 0
NST-263871 | SCE | 92337 | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 76.41 | No | 0 | 9
NST-263872 | SCE | 92230 | NEM | NEM-ST | Application Review In Progress |  | 3509.296 | No | 0 | [13 empty] | 0
NST-263872 | SCE | 92230 | NEM | NEMA | NEMI - Equipment Change Submitted | Solar PV | 3509.296 | No | 0 | 24 | [12 empty] | 0
NST-263891 | SCE | 92337 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 331.528 | No | 0 | 3
NST-264116 | SCE | 90740 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 623.26 | No | 0
NST-264129 | SCE | 92320 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 234.234 | No | 0
NST-264168 | SCE | 92408 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 474.284 | No | 0
NST-264178 | SCE | 92606 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 50.584 | No | 0 | 4
NST-264182 | SCE | 92562 | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 481.258 | No | 0 | 7
NST-264188 | SCE | 92606 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 86.492 | No | 0 | 22
NST-264195 | SCE | 92503 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 131.106 | No | 0
NST-264199 | SCE | 92592 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 432.435 | No | 0 | 3
NST-264208 | SCE | 91755 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 481.258 | No | 0 | 0
NST-264210 | SCE | 90650 | NEM | NEMA | Withdrawn | Solar PV | 4688.326 | No | 0
NST-264219 | SCE | 92637 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 411.511 | No | 0
NST-264225 | SCE | 93065 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 327.814 | No | 0
NST-264235 | SCE | 90745 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 376.637 | No | 0 | 2
NST-264241 | SCE | 92223 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 411.511 | No | 0 | 10
NST-264249 | SCE | 93274 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 411.212 | No | 0 | 8
NST-264256 | SCE | 92530 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 526.158 | No | 0
NST-264267 | SCE | 92630 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 334.788 | No | 0
NST-264286 | SCE | 93257 | NEM | NEMA | Withdrawn | Solar PV | 45.081 | No | 0
NST-264288 | SCE | 92701 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 81.669 | No | 0 | 38
NST-264312 | SCE | 90621 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 168.676 | No | 0
NST-264313 | SCE | 92301 | NEM | NEMA | Withdrawn | Solar PV | 840.033 | No | 0 | 16
NST-264462 | SCE | 92832 | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 209.243 | No | 0 | 0
NST-264529 | SCE | 92868 | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 308.28 | No | 0
NST-264530 | SCE | 90802 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 98.65 | No | 0
NST-264532 | SCE | 90802 | NEM | NEMA | Applicant Response Received. Pending SCE Engineer Review | Solar PV | 147.975 | No | 0
NST-264534 | SCE | 90292 | NEM | NEMA | Applicant Response Received. Pending SCE Engineer Review | Solar PV | 110.981 | No | 0
NST-264536 | SCE | 90292 | NEM | NEMA | Withdrawn | Solar PV | 110.981 | No | 0
NST-264537 | SCE | 90292 | NEM | NEMA | Withdrawn | Solar PV | 135.643 | No | 0 | 4
NST-264538 | SCE | 90292 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 86.319 | No | 0 | 5
NST-264539 | SCE | 90292 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 73.987 | No | 0
NST-264540 | SCE | 90292 | NEM | NEMA | Withdrawn | Solar PV | 86.319 | No | 0
NST-264542 | SCE | 90292 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 147.975 | No | 0
NST-264620 | SCE | 93010 | NEM | NEMA | NEMI - Application Returned. Pending Applicant Corrections | Solar PV | 457.356 | No | 0 | 23
NST-264623 | SCE | 93010 | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 189.979 | No | 0
NST-264625 | SCE | 93010 | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 210.909 | No | 0 | 3
NST-264627 | SCE | 93117 | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 513.646 | No | 0 | 28
NST-264630 | SCE | 92630 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 265.524 | No | 0 | #VALUE!
NST-264634 | SCE | 92630 | NEM | NEMA | NEMI - Application Returned 2nd Time. Pending Applicant Corrections | Solar PV | 371.51 | No | 0
NST-264636 | SCE | 92630 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 203.569 | No | 0 | 7
NST-264642 | SCE | 92647 | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 531.049 | No | 0 | 4
NST-264903 | SCE | 92262 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 31.536 | No | 0 | [13 empty] | 21
NST-264919 | SCE | 93060 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 57.247 | No | 0 | 6
NST-264968 | SCE | 93109 | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 253.305 | No | 0 | 4
NST-264972 | SCE | 92562 | NEM | NEMA | NEMI - Application Returned. Pending Applicant Corrections | Solar PV | 309.779 | No | 0 | 11
NST-264973 | SCE | 92562 | NEM | NEMA | NEMI - Application Returned. Pending Applicant Corrections | Solar PV | 318.629 | No | 0 | 12
NST-264976 | SCE | 92562 | NEM | NEMA | NEMI - Application Returned. Pending Applicant Corrections | Solar PV | 327.48 | No | 0 | 4
NST-264980 | SCE | 92562 | NEM | NEMA | NEMI - Application Returned. Pending Applicant Corrections | Solar PV | 327.48 | No | 0 | 3
NST-264983 | SCE | 92562 | NEM | NEMA | NEMI - Application Returned. Pending Applicant Corrections | Solar PV | 327.48 | No | 0 | 5
NST-264987 | SCE | 91762 | NEM | NEMA | NEMI - Application Re-Submitted | Solar PV | 212.24 | No | 0 | 4
NST-264992 | SCE | 91762 | NEM | NEMA | NEMI - Application Re-Submitted | Solar PV | 212.24 | No | 0 | 13
NST-264994 | SCE | 91762 | NEM | NEMA | NEMI - Application Re-Submitted | Solar PV | 123.732 | No | 0 | 4
NST-264997 | SCE | 93536 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 256.674 | No | 0 | 7
NST-265002 | SCE | 93536 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 309.554 | No | 0 | 5
NST-265006 | SCE | 92831 | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 265.524 | No | 0
NST-265012 | SCE | 92831 | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 354.033 | No | 0 | 31
NST-265016 | SCE | 90242 | NEM | NEMA | NEMI - Application Returned 2nd Time. Pending Applicant Corrections | Solar PV | 189.979 | No | 0 | 4
NST-265021 | SCE | 90242 | NEM | NEMA | NEMI - Application Returned 2nd Time. Pending Applicant Corrections | Solar PV | 147.761 | No | 0
NST-265024 | SCE | 90242 | NEM | NEMA | NEMI - Application Returned 2nd Time. Pending Applicant Corrections | Solar PV | 386.994 | No | 0
NST-265027 | SCE | 90242 | NEM | NEMA | NEMI - Application Returned 2nd Time. Pending Applicant Corrections | Solar PV | 84.435 | No | 0 | 0
NST-265028 | SCE | 92408 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 87.566 | No | 0
NST-265029 | SCE | 90242 | NEM | NEMA | NEMI - Application Returned 2nd Time. Pending Applicant Corrections | Solar PV | 358.849 | No | 0 | 10
NST-265031 | SCE | 90242 | NEM | NEMA | NEMI - Application Returned 2nd Time. Pending Applicant Corrections | Solar PV | 147.761 | No | 0 | #VALUE!
NST-265035 | SCE | 90242 | NEM | NEMA | NEMI - Application Returned 2nd Time. Pending Applicant Corrections | Solar PV | 70.362 | No | 0
NST-265036 | SCE | 90242 | NEM | NEMA | NEMI - Application Returned 2nd Time. Pending Applicant Corrections | Solar PV | 140.725 | No | 0
NST-265041 | SCE | 90242 | NEM | NEMA | NEMI - Application Returned 2nd Time. Pending Applicant Corrections | Solar PV | 415.139 | No | 0
NST-265127 | SCE | 91748 | NEM | NEM-ST | Application Review Complete |  | 987.579 | No | 0 | 8
NST-265127 | SCE | 91748 | NEM | NEMA | SCE Engineer. Initial Review In Progress | Solar PV | 987.579 | No | 0 | 2
NST-265217 | SCE | 92571 | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 226.476 | No | 0
NST-265271 | SCE | 90755 | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 593.005 | No | 0
NST-265279 | SCE | 90755 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 177.016 | No | 0 | 18
NST-265297 | SCE | 92595 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 55.967 | No | 0 | 19
NST-265299 | SCE | 92595 | NEM | NEMA | NEMI - Application Re-Submitted | Solar PV | 194.718 | No | 0 | 3
NST-265304 | SCE | 91355 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 247.823 | No | 0 | 1
NST-265311 | SCE | 91355 | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 247.823 | No | 0 | 6
NST-265314 | SCE | 91355 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 247.823 | No | 0 | 4
NST-265323 | SCE | 91381 | NEM | NEMA | NEMI - Application Returned 2nd Time. Pending Applicant Corrections | Solar PV | 327.48 | No | 0 | 6
NST-265326 | SCE | 91381 | NEM | NEMA | NEMI - Application Returned 2nd Time. Pending Applicant Corrections | Solar PV | 256.674 | No | 0 | 1
NST-265330 | SCE | 91381 | NEM | NEMA | NEMI - Application Returned 2nd Time. Pending Applicant Corrections | Solar PV | 256.674 | No | 0 | 3
NST-265484 | SCE | 90242 | NEM | NEM-ST | Application Review In Progress |  | 1638.172 | No | 0
NST-265484 | SCE | 90242 | NEM | NEMA | Applicant Response Received. Pending SCE Engineer Review | Solar PV | 1638.172 | No | 0 | 68
NST-265622 | SCE | 92509 | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 312.5 | No | 0 | 4
NST-265644 | SCE | 92260 | NEM | NEMA | NEMI - Load Justification Reviewed | Solar PV | 32.109 | No | 0
NST-265677 | SCE | 93117 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 192.663 | No | 0 | 7
NST-265752 | SCE | 91762 | NEM | NEM-ST | Supplemental Review In Progress |  | 1103.674 | No | 0 | 5 | 6
NST-265752 | SCE | 91762 | NEM | NEMA | SCE Engineer. Initial Review Complete | Solar PV | 1103.674 | No | 0
NST-266056 | SCE | 92270 | NEM | NEMA | Withdrawn | Solar PV | 30.865 | No | 0
NST-266110 | SCE | 92260 | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 94.707 | No | 0 | 2
NST-266135 | SCE | 91730 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 86.998 | No | 0 | 2
NST-266160 | SCE | 92372 | NEM | NEMA | Applicant Response Received. Pending SCE Engineer Review | Solar PV | 46.527 | No | 0
NST-266189 | SCE | 90740 | NEM | NEMA | Applicant Response Received. Pending SCE Engineer Review | Solar PV | 198.604 | No | 0
NST-266199 | SCE | 93230 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 183.302 | No | 0
NST-266201 | SCE | 90720 | NEM | NEMA | NEMI - Sent to Engineering | Solar PV | 163.642 | No | 0
NST-266201 | SCE | 90720 | NEM | NEM-ST | Application Review In Progress |  | 163.642 | No | 0
NST-266254 | SCE | 92630 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 92.799 | No | 0 | #VALUE!
NST-266290 | SCE | 93230 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 159.393 | No | 0 | 3
NST-266300 | SCE | 90032 | NEM | NEMA | Withdrawn | Solar PV | 60.366 | No | 0
NST-266323 | SCE | 90304 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 37.759 | No | 0 | 12
NST-266330 | SCE | 91776 | NEM | NEMA | Withdrawn | Solar PV | 30.576 | No | 0
NST-266339 | SCE | 92841 | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 46.279 | No | 0 | 5
NST-266340 | SCE | 90403 | NEM | NEMA | Withdrawn | Solar PV | 60.011 | No | 0
NST-266355 | SCE | 93257 | NEM | NEMA | Withdrawn | Solar PV | 276.281 | No | 0
NST-266510 | SCE | 90250 | NEM | NEMA | Withdrawn | Solar PV | 85.303 | No | 0 | 7
NST-266632 | SCE | 92683 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 75.299 | No | 0 | 1
NST-266745 | SCE | 93001 | NEM | NEM-ST | Application Review In Progress |  | 6629.28 | No | 0
NST-266745 | SCE | 93001 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 6629.28 | No | 0 | 4
NST-266747 | SCE | 93227 | NEM | NEM Aggregation | Application Review In Progress |  | 4547.958 | No | 0
NST-266747 | SCE | 93227 | NEM | NEMA | SCE Engineer. Detail Study In Progress | Solar PV | 4547.958 | No | 0
NST-266754 | SCE | 91354 | NEM | NEMA | Withdrawn | Solar PV | 247.755 | No | 0
NST-266811 | SCE | 91302 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 53.279 | No | 0 | 0
NST-266813 | SCE | 90502 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 188.248 | No | 0 | 8
NST-266814 | SCE | 92860 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 71.953 | No | 0 | 5
NST-266815 | SCE | 93551 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 45.902 | No | 0
NST-266818 | SCE | 93536 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 54.918 | No | 0 | 0
NST-266971 | SCE | 91764 | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 85.511 | No | 0 | 8
NST-267007 | SCE | 92570 | NEM | NEMA | NEMI - Sent to Engineering | Solar PV | 34.954 | No | 0 | 2
NST-267038 | SCE | 91765 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 31.583 | No | 0 | 5 | [12 empty] | 28
NST-267276 | SCE | 93274 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 78.919 | No | 0 | 2
NST-267513 | SCE | 92345 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 67.644 | No | 0
NST-267593 | SCE | 92630 | NEM | NEMA | NEMI - Sent to Engineering | Solar PV | 43.443 | No | 0 | 8
NST-267666 | SCE | 92595 | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 49.072 | No | 0
NST-267668 | SCE | 92595 | NEM | NEMA | NEMI - Load Justification Reviewed | Solar PV | 49.072 | No | 0
NST-267676 | SCE | 92595 | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 49.072 | No | 0
NST-267677 | SCE | 92703 | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 274.196 | No | 0 | 3
NST-267680 | SCE | 92703 | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 194.538 | No | 0
NST-267681 | SCE | 92866 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 61.475 | No | 0
NST-267683 | SCE | 92703 | NEM | NEMA | NEMI - Application Re-Submitted | Solar PV | 256.674 | No | 0
NST-267686 | SCE | 90278 | NEM | NEMA | NEMI - Application Returned 2nd Time. Pending Applicant Corrections | Solar PV | 6446.997 | No | 0
NST-267686 | SCE | 90278 | NEM | NEM-ST | Application Review In Progress |  | 6446.997 | No | 0 | 25
NST-267822 | SCE | 91302 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 78.895 | No | 0 | #VALUE!
NST-268062 | SCE | 91340 | NEM | NEMA | Withdrawn | Solar PV | 54.782 | No | 0
NST-268092 | SCE | 93063 | NEM | NEMA | Withdrawn | Solar PV | 5000 | No | 0
NST-268292 | SCE | 93010 | NEM | NEMA | NEMI - 1.0 Expansion Ineligible | Solar PV | 186.096 | No | 0 | #VALUE!
NST-268293 | SCE | 93010 | NEM | NEMA | NEMI - 1.0 Expansion Ineligible | Solar PV | 219.11 | No | 0
NST-268294 | SCE | 93010 | NEM | NEMA | NEMI - 1.0 Expansion Ineligible | Solar PV | 163.825 | No | 0 | 14
NST-268298 | SCE | 93036 | NEM | NEMA | NEMI - 1.0 Expansion Ineligible | Solar PV | 391.957 | No | 0 | 4
NST-268299 | SCE | 93036 | NEM | NEMA | NEMI - 1.0 Expansion Ineligible | Solar PV | 606.768 | No | 0 | 3
NST-268300 | SCE | 93036 | NEM | NEMA | NEMI - 1.0 Expansion Ineligible | Solar PV | 410.201 | No | 0 | 6
NST-268304 | SCE | 91773 | NEM | NEMA | NEMI - 1.0 Expansion Ineligible | Solar PV | 547.234 | No | 0 | 15
NST-268308 | SCE | 92592 | NEM | NEMA | NEMI - 1.0 Expansion Ineligible | Solar PV | 126.273 | No | 0 | 4
NST-268309 | SCE | 92592 | NEM | NEMA | NEMI - 1.0 Expansion Ineligible | Solar PV | 203.724 | No | 0 | 4
NST-268310 | SCE | 92223 | NEM | NEMA | NEMI - Sent to Engineering | Solar PV | 378.284 | No | 0 | 4
NST-268319 | SCE | 90620 | NEM | NEMA | Applicant Response Received. Pending SCE Engineer Review | Solar PV | 39.064 | No | 0
NST-268369 | SCE | 92234 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 36.544 | No | 0 | 6 | [12 empty] | 36
NST-268514 | SCE | 91748 | NEM | NEMA | NEMI - 1.0 Expansion Ineligible | Solar PV | 268.966 | No | 0
NST-268515 | SCE | 91748 | NEM | NEMA | NEMI - 1.0 Expansion Ineligible | Solar PV | 569.366 | No | 0 | 5
NST-268516 | SCE | 91748 | NEM | NEMA | NEMI - 1.0 Expansion Ineligible | Solar PV | 253.254 | No | 0 | 4
NST-268517 | SCE | 91748 | NEM | NEMA | NEMI - 1.0 Expansion Ineligible | Solar PV | 226.908 | No | 0
NST-268556 | SCE | 90640 | NEM | NEMA | NEMI - Pending Final NEM Review | Solar PV | 255.821 | No | 0 | 7
NST-268657 | SCE | 92270 | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 153.692 | No | 0 | 4
NST-268662 | SCE | 92270 | NEM | NEMA | Applicant Response Received. Pending SCE Engineer Review | Solar PV | 502.597 | No | 0 | 67
NST-268664 | SCE | 92223 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 681.986 | No | 0 | 4
NST-268789 | SCE | 92223 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 456.123 | No | 0 | 6
NST-268930 | SCE | 90723 | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 397.561 | No | 0 | 31
NST-268948 | SCE | 91706 | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 446.385 | No | 0 | 4
NST-268958 | SCE | 91792 | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 648.653 | No | 0 | 5
NST-268972 | SCE | 90680 | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 495.208 | No | 0 | 4
NST-268975 | SCE | 90255 | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 404.536 | No | 0 | 1
NST-269014 | SCE | 90822 | NEM | NEMA | NEMI - Application Returned 2nd Time. Pending Applicant Corrections | Solar PV | 202.562 | No | 0
NST-269105 | SCE | 93277 | NEM | NEMA | NEMI - Application Re-Submitted | Solar PV | 56.213 | No | 0
NST-269116 | SCE | 93536 | NEM | NEMA | Withdrawn | Solar PV | 244.772 | No | 0 | 5
NST-269156 | SCE | 93277 | NEM | NEMA | NEMI - Application Re-Submitted | Solar PV | 265.266 | No | 0 | 5
NST-269172 | SCE | 92867 | NEM | NEMA | Withdrawn | Solar PV | 31.83 | No | 0
NST-269193 | SCE | 92518 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 1451.615 | No | 0 | 3
NST-269674 | SCE | 92252 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 306.535 | No | 0 | #VALUE!
NST-269713 | SCE | 92337 | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 220.24 | No | 0 | 2
NST-269714 | SCE | 92626 | NEM | NEMA | NEMI - Application Returned. Pending Applicant Corrections | Solar PV | 627.728 | No | 0 | 7
NST-269929 | SCE | 90723 | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 82.359 | No | 0 | 4
NST-269977 | SCE | 93021 | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 47.891 | No | 0
NST-270218 | SCE | 93215 | NEM | NEMA | NEMI - Application Re-Submitted | Solar PV | 2024.764 | No | 0 | 5
NST-270403 | SCE | 92260 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 35.284 | No | 0 | 0
NST-270431 | SCE | 91754 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 291.162 | No | 0 | 8
NST-270478 | SCE | 90806 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 67.562 | No | 0 | 1
NST-270682 | SCE | 93010 | NEM | NEMA | NEMI - Application Re-Submitted | Solar PV | 186.096 | No | 0 | 13
NST-270683 | SCE | 93010 | NEM | NEMA | NEMI - Application Re-Submitted | Solar PV | 219.11 | No | 0 | 20
NST-270684 | SCE | 93010 | NEM | NEMA | NEMI - Application Re-Submitted | Solar PV | 163.825 | No | 0 | 9
NST-270686 | SCE | 93036 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 391.957 | No | 0 | 5
NST-270687 | SCE | 93036 | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 606.768 | No | 0
NST-270688 | SCE | 93036 | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 410.201 | No | 0 | 4
NST-270690 | SCE | 91748 | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 268.966 | No | 0
NST-270691 | SCE | 91748 | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 569.366 | No | 0 | 39
NST-270692 | SCE | 91748 | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 253.254 | No | 0 | 25
NST-270693 | SCE | 91748 | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 226.908 | No | 0 | 25
NST-270694 | SCE | 91773 | NEM | NEMA | NEMI - Application Re-Submitted | Solar PV | 547.234 | No | 0 | 39
NST-270695 | SCE | 92592 | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 126.97 | No | 0 | 10
NST-270696 | SCE | 92592 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 203.724 | No | 0 | 12
NST-270699 | SCE | 91744 | NEM | NEMA | Applicant Response Received. Pending SCE Engineer Review | Solar PV | 79.882 | No | 0
NST-270702 | SCE | 93003 | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 98 | No | 0 | 3
NST-270796 | SCE | 92612 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 149.615 | No | 0
NST-270809 | SCE | 92612 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 156.739 | No | 0 | 7
NST-270841 | SCE | 92612 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 206.611 | No | 0 | 0
NST-270853 | SCE | 92612 | NEM | NEMA | NEMI - Application Re-Submitted | Solar PV | 427.471 | No | 0 | 10
NST-270936 | SCE | 92861 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 597.604 | No | 0 | 3
NST-270951 | SCE | 92868 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 78.772 | No | 0 | 2
NST-270958 | SCE | 92861 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 95.804 | No | 0 | 5
NST-270959 | SCE | 92335 | NEM | NEMA | Withdrawn | Solar PV | 77.303 | No | 0 | 1
NST-270961 | SCE | 92861 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 168.642 | No | 0 | 1
NST-270966 | SCE | 92618 | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 144.879 | No | 0 | 6
NST-271062 | SCE | 92626 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 488.233 | No | 0 | 6
NST-271069 | SCE | 92626 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 488.233 | No | 0
NST-271081 | SCE | 92612 | NEM | NEMA | Withdrawn | Solar PV | 3412.645 | No | 0 | 7
NST-271090 | SCE | 92612 | NEM | NEM-ST | Application Review In Progress |  | 2443.71 | No | 0 | 4
NST-271090 | SCE | 92612 | NEM | NEMA | NEMI - Application Returned. Pending Applicant Corrections | Solar PV | 2443.71 | No | 0
NST-271208 | SCE | 93230 | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 253.652 | No | 0 | 7
NST-271293 | SCE | 90745 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 31.235 | No | 0 | [13 empty] | 3
NST-271349 | SCE | 92705 | NEM | NEMA | Withdrawn | Solar PV | 134.936 | No | 0
NST-271351 | SCE | 93036 | NEM | NEMA | Withdrawn | Solar PV | 53.421 | No | 0
NST-271388 | SCE | 92518 | NEM | NEMA | NEMI - Equipment Change Submitted | Solar PV | 358.491 | No | 0
NST-271576 | SCE | 91789 | NEM | NEMA | NEMI - Returned from Engineering | Solar PV | 57.914 | No | 0
NST-271583 | SCE | 92879 | NEM | NEM-ST | Application Review In Progress |  | 1092.931 | No | 0
NST-271583 | SCE | 92879 | NEM | NEMA | SCE Engineer Assigned. Pending Technical Review | Solar PV | 1092.931 | No | 0
NST-271588 | SCE | 90265 | NEM | NEMA | NEMI - Application Re-Submitted | Solar PV | 50.062 | No | 0
NST-271719 | SCE | 93030 | NEM | NEMA | SCE Engineer Assigned. Pending Technical Review | Solar PV | 251.102 | No | 0
NST-271723 | SCE | 93030 | NEM | NEMA | NEMI - Application Returned. Pending Applicant Corrections | Solar PV | 589.638 | No | 0
NST-271725 | SCE | 93030 | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 888.432 | No | 0
NST-271729 | SCE | 93030 | NEM | NEMA | SCE Engineer Assigned. Pending Technical Review | Solar PV | 444.758 | No | 0 | 5
NST-271734 | SCE | 93030 | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 742.106 | No | 0
NST-271987 | SCE | 92618 | NEM | NEMA | NEMI - Returned from Engineering | Solar PV | 167.557 | No | 0 | 11
NST-271994 | SCE | 90806 | NEM | NEMA | NEMI - Application Re-Submitted | Solar PV | 52.487 | No | 0
NST-272010 | SCE | 93036 | NEM | NEMA | Withdrawn | Solar PV | 53.421 | No | 0 | 3
NST-272020 | SCE | 90670 | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 147.761 | No | 0 | 13
NST-272021 | SCE | 90670 | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 91.471 | No | 0 | 3
NST-272051 | SCE | 93001 | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 74.595 | No | 0
NST-272056 | SCE | 91762 | NEM | NEMA | Withdrawn | Solar PV | 1367.262 | No | 0
NST-272098 | SCE | 92408 | NEM | NEM-ST | Application Review In Progress |  | 2409.557 | No | 0
NST-272098 | SCE | 92408 | NEM | NEMA | SCE Engineer Assigned. Pending Technical Review | Solar PV | 2409.557 | No | 0
NST-272174 | SCE | 92869 | NEM | NEMA | Withdrawn | Solar PV | 33.27 | No | 0
NST-272209 | SCE | 93532 | NEM | NEMA | NEMI - Application Returned. Pending Applicant Corrections | Solar PV | 245.695 | No | 0
NST-272257 | SCE | 93001 | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 31.175 | No | 0 | 4
NST-272356 | SCE | 93215 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 400 | No | 0 | 7 | [12 empty] | 6
NST-272397 | SCE | 93291 | NEM | NEMA | NEMI - Sent to Engineering | Solar PV | 46.76 | No | 0 | 1
NST-272441 | SCE | 93277 | NEM | NEMA | NEMI - Sent to Engineering | Solar PV | 42.29 | No | 0 | 4
NST-272571 | SCE | 90806 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 37.094 | No | 0 | 5
NST-272602 | SCE | 91361 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 58.236 | No | 0 | 3
NST-272612 | SCE | 92316 | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 110.039 | No | 0
NST-272689 | SCE | 92311 | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 42.726 | No | 0
NST-272718 | SCE | 92335 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 187.118 | No | 0 | 8
NST-272866 | SCE | 91384 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 121.013 | No | 0
NST-272900 | SCE | 93654 | NEM | NEMA | NEMI - Application Returned. Pending Applicant Corrections | Solar PV | 723.631 | No | 0
NST-272937 | SCE | 90245 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 300.54 | No | 0 | 3
NST-273001 | SCE | 93110 | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 73.071 | No | 0 | 7
NST-273076 | SCE | 92563 | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 91.66 | No | 0 | 6
NST-273265 | SCE | 90274 | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 94.359 | No | 0 | 6
NST-273629 | SCE | 93256 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 536.515 | No | 0 | 4
NST-273659 | SCE | 93256 | NEM | NEMA | NEMI - Application Re-Submitted | Solar PV | 323.863 | No | 0
NST-273733 | SCE | 91355 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 60.366 | No | 0
NST-274219 | SCE | 99923 | NEM | NEMA | NEMI - Application Returned 2nd Time. Pending Applicant Corrections | Solar PV | 96.144 | No | 0 | 3
NST-274222 | SCE | 92376 | NEM | NEMA | Withdrawn | Solar PV | 238.43 | No | 0
NST-274240 | SCE | 92395 | NEM | NEMA | Withdrawn | Solar PV | 61.781 | No | 0
NST-274265 | SCE | 91711 | NEM | NEMA | NEMI - Sent to Engineering | Solar PV | 92.787 | No | 0 | 6
NST-274267 | SCE | 90723 | NEM | NEMA | SCE Engineer Assigned. Pending Technical Review | Solar PV | 130.7 | No | 0 | 27
NST-274529 | SCE | 92210 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 40.927 | No | 0 | [13 empty] | 13
NST-274533 | SCE | 92335 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 428.641 | No | 0 | 0
NST-274726 | SCE | 93230 | NEM | NEMA | Applicant Response Received. Pending SCE Engineer Review | Solar PV | 781.056 | No | 0
NST-274836 | SCE | 90670 | NEM | NEMA | NEMI - Application Returned. Pending Applicant Corrections | Solar PV | 76.272 | No | 0 | 6
NST-274837 | SCE | 92867 | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 65.278 | No | 0 | 3
NST-275116 | SCE | 93532 | NEM | NEMA | NEMI - Equipment Change Submitted | Solar PV | 71.062 | No | 0 | 1
NST-275337 | SCE | 92832 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 849.142 | No | 0 | 7
NST-275375 | SCE | 93292 | NEM | NEMA | NEMI - Application Re-Submitted | Solar PV | 52.603 | No | 0
NST-275378 | SCE | 92606 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 45.365 | No | 0 | 40 | [12 empty] | 10
NST-275427 | SCE | 92260 | NEM | NEMA | NEMI - PTO Issued | Solar PV | 171.638 | No | 0 | [13 empty] | 3
NST-275434 | SCE | 91765 | NEM | NEMA | NEMI - Application Re-Submitted | Solar PV | 86.776 | No | 0 | 3
NST-275439 | SCE | 92570 | NEM | NEMA | NEMI - Sent to Engineering | Solar PV | 163.21 | No | 0
NST-275472 | SCE | 90503 | NEM | NEMA | NEMI - Application Returned 2nd Time. Pending Applicant Corrections | Solar PV | 75.299 | No | 0 | 3
NST-275526 | SCE | 92704 | NEM | NEMA | NEMI - Application Returned. Pending Applicant Corrections | Solar PV | 72.439 | No | 0
NST-275530 | SCE | 93001 | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 56.754 | No | 0 | 23
NST-275576 | SCE | 93257 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 276.281 | No | 0 | 4
NST-275577 | SCE | 90810 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 79.721 | No | 0 | 0
NST-275706 | SCE | 92618 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 377.541 | No | 0
NST-275727 | SCE | 91724 | NEM | NEMA | Applicant Response Received. Pending SCE Engineer Review | Solar PV | 103.48 | No | 0 | 11
NST-275844 | SCE | 92627 | NEM | NEMA | NEMI - Application Returned. Pending Applicant Corrections | Solar PV | 36.034 | No | 0
NST-275867 | SCE | 93221 | NEM | NEM-ST | Fast Track Initial Review In Progress |  | 0.016037 | No | 0
NST-275939 | SCE | 92821 | NEM | NEMA | NEMI - Load Justification Reviewed | Solar PV | 88.774 | No | 0
NST-275951 | SCE | 93021 | NEM | NEMA | NEMI - Sent to Engineering | Solar PV | 136.905 | No | 0
NST-275967 | SCE | 90405 | NEM | NEMA | NEMI - Application Re-Submitted | Solar PV | 93.229 | No | 0 | 4
NST-275974 | SCE | 90638 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 40.481 | No | 0 | 4
NST-276088 | SCE | 93274 | NEM | NEMA | NEMI - Application Re-Submitted | Solar PV | 242.473 | No | 0 | 8
NST-276133 | SCE | 93257 | NEM | NEMA | NEMI - Application Re-Submitted | Solar PV | 77.562 | No | 0 | 1
NST-276220 | SCE | 91340 | NEM | NEMA | NEMI - Returned from Engineering | Solar PV | 54.782 | No | 0
NST-276300 | SCE | 93063 | NEM | NEM-ST | Application Review In Progress |  | 850.804 | No | 0 | 41
NST-276300 | SCE | 93063 | NEM | NEMA | SCE Engineer Assigned. Pending Technical Review | Solar PV | 850.804 | No | 0 | 3
NST-276577 | SCE | 93060 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 115.903 | No | 0
NST-276595 | SCE | 91730 | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 76.807 | No | 0 | 7
NST-276747 | SCE | 92867 | NEM | NEMA | NEMI - Application Returned. Pending Applicant Corrections | Solar PV | 36.567 | No | 0
NST-276954 | SCE | 93065 | NEM | NEM-ST | Application Review In Progress |  | 712.125 | No | 0
NST-276954 | SCE | 93065 | NEM | NEMA | SCE Engineer Assigned. Pending Technical Review | Solar PV | 712.125 | No | 0
NST-277053 | SCE | 93063 | NEM | NEMA | SCE Engineer Assigned. Pending Technical Review | Solar PV | 291.37 | No | 0 | 7
NST-277116 | SCE | 93257 | NEM | NEMA | NEMI - Application Re-Submitted | Solar PV | 46.468 | No | 0
NST-277193 | SCE | 92373 | NEM | NEMA | NEMI - Application Re-Submitted | Solar PV | 54.098 | No | 0
NST-277519 | SCE | 90746 | NEM | NEMA | NEMI - Application Re-Submitted | Solar PV | 58.045 | No | 0
NST-277609 | SCE | 93060 | NEM | NEMA | NEMI - Application Submitted | Solar PV | 429.032 | No | 0 | 7
NST-277764 | SCE | 92590 | NEM | NEMA | NEMI - Application Returned. Pending Applicant Corrections | Solar PV | 537.983 | No | 0 | 4
NST-277936 | SCE | 90706 | NEM | NEMA | NEMI - Application Submitted | Solar PV | 66.757 | No | 0 | 3
NST-277939 | SCE | 90210 | NEM | NEMA | NEMI - Application Submitted | Solar PV | 86.941 | No | 0 | 36
NST-277978 | SCE | 93065 | NEM | NEMA | NEMI - Equipment Change Submitted | Solar PV | 398.614 | No | 0 | 15
NST-277987 | SCE | 92240 | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 322.047 | No | 0
NST-278163 | SCE | 91354 | NEM | NEMA | NEMI - Application Returned. Pending Applicant Corrections | Solar PV | 247.755 | No | 0
NST-278598 | SCE | 90242 | NEM | NEMA | NEMI - Application Submitted | Solar PV | 260.54 | No | 0
NST-278862 | SCE | 90621 | NEM | NEMA | NEMI - Application Submitted | Solar PV | 198.727 | No | 0
NST-278913 | SCE | 93117 | NEM | NEMA | NEMI - Application Submitted | Solar PV | 232.819 | No | 0 | 14
NST-278915 | SCE | 92571 | NEM | NEMA | NEMI - Equipment Change Submitted | Solar PV | 997.192 | No | 0
NST-278918 | SCE | 93117 | NEM | NEMA | NEMI - Application Submitted | Solar PV | 261.921 | No | 0 | 6
NST-278952 | SCE | 92509 | NEM | NEMA | NEMI - Application Submitted | Solar PV | 312.5 | No | 0 | 27
NST-279091 | SCE | 92408 | NEM | NEMA | NEMI - Application Submitted | Solar PV | 643.754 | No | 0 | 12
NST-279200 | SCE | 91108 | NEM | NEMA | NEMI - Application Submitted | Solar PV | 51.297 | No | 0 | 15
NST-279215 | SCE | 92637 | NEM | NEMA | NEMI - Application Submitted | Solar PV | 69.652 | No | 0
NST-279228 | SCE | 93065 | NEM | NEMA | NEMI - Equipment Change Submitted | Solar PV | 247.761 | No | 0
NST-279229 | SCE | 90240 | NEM | NEMA | NEMI - Application Submitted | Solar PV | 218.956 | No | 0 | 29
NST-279248 | SCE | 92782 | NEM | NEMA | NEMI - Application Submitted | Solar PV | 249.848 | No | 0
NST-279327 | SCE | 91030 | NEM | NEMA | NEMI - Application Submitted | Solar PV | 30.099 | No | 0
NST-279372 | SCE | 93065 | NEM | NEMA | NEMI - Equipment Change Submitted | Solar PV | 215.914 | No | 0
NST-279376 | SCE | 92336 | NEM | NEMA | NEMI - Application Submitted | Solar PV | 38.307 | No | 0
NST-279383 | SCE | 93274 | NEM | NEMA | NEMI - Application Submitted | Solar PV | 741.2799 | No | 0 | 4
NST-279441 | SCE | 91362 | NEM | NEMA | NEMI - Application Submitted | Solar PV | 1365.731 | No | 0 | 9
NST-279454 | SCE | 90241 | NEM | NEMA | NEMI - Application Submitted | Solar PV | 114.539 | No | 0 | 14
NST-279457 | SCE | 90241 | NEM | NEMA | NEMI - Application Submitted | Solar PV | 432.51 | No | 0 | 15
NST-279458 | SCE | 90241 | NEM | NEMA | NEMI - Application Submitted | Solar PV | 464.521 | No | 0 | 22
NST-279461 | SCE | 90242 | NEM | NEMA | NEMI - Application Submitted | Solar PV | 199.383 | No | 0 | 7
NST-279664 | SCE | 92841 | NEM | NEMA | NEMI - Application Submitted | Solar PV | 850.641 | No | 0 | 1
NST-279726 | SCE | 92010 | NEM | NEMA | NEMI - Application Submitted | Solar PV | 150.96 | No | 0 | 3
NST-279808 | SCE | 90670 | NEM | NEMA | NEMI - Application Submitted | Solar PV | 122.353 | No | 0
NST-280019 | SCE | 90247 | NEM | NEMA | NEMI - Application Submitted | Solar PV | 46.541 | No | 0
NST-280130 | SCE | 90260 | NEM | NEMA | NEMI - Application Submitted | Solar PV | 992.607 | No | 0
NST-280153 | SCE | 92335 | NEM | NEMA | NEMI - Application Submitted | Solar PV | 77.635 | No | 0
NST-98090 | SCE | 90277 | NEM | NEM-ST | Transferred to NEM | Solar PV | 0.0388 | No | 0

## OP4 Processing Cost
This data set was compiled using the following data:
New Rule 21 non-export projects received from 4/1/2021 to 3/31/2021
Project size of 1MW or smaller
Using “midpoint” of pay ranges for the labor rate component (based on the employees included in the “stage of processing” buckets), with labor coming from both SCE employees and hired contractors (where applicable).
2022 Q1 Processing Cost Summary (≤ 1MW Rule 21 Non-Export)
Stage Name | Number Evaluated | Total Cost per Stage | Average Cost per Stage
Application Review | 216 | 25023.9231 | 115.8515
Technical Review and Engineering | 216 | 194528.8059 | 900.5963
Contract Negotiation and Execution | 151 | 20815.0529 | 137.848
Post Execution to PTO | 116 | 8776.25 | 75.6573
| Average Cost per Project |  | 1229.9532
Of the 216 projects received since the beginning of 2nd quarter 2021, 151 made it to the agreement stage, and 116 made it to post-agreement/Pre-PTO during that same time period.

## Cover page
Updated as of 03/31/2021
Southern California Edison Company
Rule 21 - Processing Timelines
This list of Interconnection Requests ("IR"s) reflects the processing time of requests for interconnection to SCE's Distribution System made pursuant to SCE's Rule 21 Tariff.
Types of Requests: Of the various types of Interconnection Requests that SCE administers, this report covers the following: - Rule 21 Non-Export - Rule 21 Export - Net Energy Metering (NEM) larger than 30 kW
Changes to Interconnection Requests Data: The information provided in this document is a snapshot of SCE's Interconnection Queue beginning with Interconnection Requests received on December 29, 2020 and ending as of the date indicated above (see 'Updated as of' date in top right corner). The specific information regarding each project may vary as projects may submit requests for modifications in accordance with the terms of the appropriate interconnection process of the Rule 21 Tariff.
Contact Information: For questions regarding these timelines or general questions regarding SCE's Interconnection Process please visit http://on.sce.com/gridinterconnections or email SCE at InterconnectionQA@sce.com.
Rule 21 Tariff Definition for "Business Day": Monday through Friday during business hours, excluding Federal and State Holidays.

## Processing Timelines
SCE's Rule 21 Processing Timelines - Q1-2022
12/29/2020 to 03/31/2021
Project Specifics | [7 empty] | Application Review: | [14 empty] | Fast Track Initial Review: |  |  | Initial Review Cost Report: |  | Fast Track Supplemental Review: |  |  | Supplemental Review Cost Report: |  | Electrical Independence Test (EIT): |  |  | Scoping Meeting and Study Agreement: |  |  |  |  | System Impact Study (SIS): |  |  | Facilities Study: | Draft Agreement: |  |  |  | Agreement Execution: |  | Material Modification: |  |  | Net Generating Output Meter (NGOM): |  |  |  |  | Minor* Distribution Upgrades Design: | [6 empty] | Minor Distribution Upgrades Construction: |  |  | Commissioning and In-Service:
[8 empty] | ● Informational purposes only for Business Days to Acknowledge Interconnection Request Submission | [14 empty] | 15 Business Days [F.2.a.] |  |  | 15 Business Days [F.2.a. & F.2.b.] |  | 20 Business Days [F.2.c.i.] |  |  | 15 Business Days [F.2.c.iii.] |  | 20 Business Days [F.3.a.] |  |  | ● 5 Business Days to Contact Applicant for Scheduling [F.3.b.i.] |  |  |  |  | 60 Business Days [F.3.b.ii.] |  |  | F.3.b.vii. | ● 15 Business Days for Fast Track [F.2.a., F.2.c.iii., F.2.e.] |  |  |  | Informational purposes only |  | 10 Business Days [F.3.b.v] (20 Business Days if Cost Envelope Option is selected [F.3.b.v]) (there is no limit as to the number of Material Modification requests) |  |  | ● 20 Business Days to Design* |  |  |  |  | 60 Business Days | [6 empty] | 60 Business Days |  |  | ● Commissioning Test Scheduling provided for informational purposes only
[8 empty] | ● 10 Business Days for initial application review [E.5.a.] (15 Business Days if Cost Envelope Option is selected [E.5.a.]) | [36 empty] | from Initial Review, Supplemental Review, or Agreement Requested Date, as applicable
[8 empty] | ● 10 Business Days for 1st deficiency response review [E.5.b.i.] | [45 empty] | *See Note #1 of 'Notes' tab | [14 empty] | ● 5 Business Days to Issue PTO from Commissioning Test Date (F.5.b.)
[8 empty] | ● 5 Business Days for 2nd deficiency response review [E.5.b.ii.] | [27 empty] | ● 15 Business Days to Issue Study Agreement [F.3.b.i.] | [8 empty] | ● 30 Calendar Days for Detailed Study [F.3.b.vii. & F.3.b.viii.] | [8 empty] | ● 20 Business Days to Install |  |  |  |  | Calculated as the sum of two sub-sections as show below (Business Days to Issue Preliminary Design + Business Days to Issue Final Design)
[8 empty] | ● 5 Business Days for withdrawal cure review [E.5.b.ii.; E.5.b.iv & F.6.] | [36 empty] | from Facilities Study Waiver, Facilities Study Report, or Facilities Study Results Meeting Date, as applicable | [13 empty] | *See Note #2 on 'Notes' tab | [6 empty] | *See Note #2 on 'Notes' tab |  |  | ● Overall time to issue PTO provided for informational purposes only
Project ID | Utlitity | NEM / Non-NEM | Project Type (Request Type) | Project Status (Current Phase) | Technology Type | Size (kW - Net Nameplate Rating) | Cost Envelope Requested? | Interconnection Request Received Date | Interconnection Request Submission Acknowledged Date | Business Days to Acknowledge Interconnection Request Submission | Interconnection Request Intake Acceptable (Stamp) Date | 1st Notice of Deficiency Sent to Customer Date | Business Days to send 1st Deficiency Notice | 1st Deficiency Response Date | 2nd Notice of Deficiency Sent to Customer Date | Business Days to send 2nd Deficiency Notice | 2nd Deficiency Response Date | Deficiency-Induced Withdrawal Date | Business Days to Withdraw Due to Outstanding Deficiency(ies) | Withdrawal Cure Date (if any) | Application Deemed Complete Date | Business Days to Deem Complete (From Stamp, 1st Def. Response, 2nd Def. Response, or Withdrawal Cure Date, as applicable) | Fast Track Initial Review Start Date | Fast Track Initial Review Results Issued to Customer Date | Business Days to Issue Fast Track Initial Review Results | Fast Track Initial Review Cost Report Issued to Customer Date | Business Days to Issue Cost Report | Fast Track Supplemental Review Start Date | Fast Track Supplemental Review Results Issued to Customer Date | Business Days to Issue Fast Track Supplemental Review Results | Fast Track Supplemental Review Cost Report Issued to Customer Date | Business Days to Issue Cost Report | EIT Start Date | EIT Results Issued to Customer Date | Business Days to Issue Eletrical Independence Test Results | Scoping Meeting Scheduled Date | Business Days to Contact Applicant to Schedule Scoping Meeting | Scoping Meeting Date | Study Agreement Issued Date | Business Days to Issue Study Agreement | Interconnection SIS Start Date | Interconnection SIS Report Issued to Customer Date | Business Days to Issue SIS Results | Facilities Study Waived Date (if waived) | Generator Interconnection Agreement Requested Date | Draft Generator Interconnection Agreement Sent to Customer Date | Business Days to Send Draft Agreement | Calendar Days to Send Draft Agreement | Generator Interconnection Agreement Execution Date | Calendar Days to Execute Agreement | Material Modification Request Received Date | Material Modification Results Date | Business Days to Issue Material Modifcation Review Results | NGOM Design Start Date | NGOM Service Request Issued Date | Business Days to Issue NGOM Service Request | NGOM Installed Date | Business Days to Issue PTO (From NGOM Service Request Date) | Preliminary Design Start Date | Preliminary Design Issued to Customer Date | Business Days to Issue Preliminary Design | Preliminary Design Approved by Customer Date | Final Design Issued Date | Business Days to Issue Final Design | Total Design Business Days (Preliminary plus Final) | SCE Construction Start Date | SCE Construction Complete Date | Business Days to Construct | Commissioning Test Scheduled Date | Commissioning Test Date | Business Days to Perform Commissioning Test (From Commissioning Test Scheduled Date) | Permission to Operate (PTO) Date (Conditional PTO or Unconditional PTO; whichever occurs first if both exist) | Business Days to Issue PTO (From Commissioning Test Date) | Overall Time from Calendar Days from Stamp Date to PTO Date
GFID100233 | SCE | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 10 | No | 2021-05-11 | 2021-05-11 | 0 | 2021-05-11 | 2021-05-20 | 7 | 2021-05-20 | [6 empty] | 2021-06-02 | 8 | 2021-06-02 | 2021-06-16 | 10 | [20 empty] | 2021-06-16 | 0 |  | 2021-07-27 | 41 | [21 empty] | 2021-08-06 |  | 87
GFID100286 | SCE | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 10 | No | 2021-03-31 | 2021-03-31 | 0 | 2021-03-31 | [9 empty] | 2021-04-13 | 8 | 2021-04-13 | 2021-04-14 | 1 | [20 empty] | 2021-04-14 | 0 |  | 2021-05-11 | 27 | [21 empty] | 2021-05-28 |  | 58
GFID100476 | SCE | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Other (Combustion Turbine) | 240 | No | 2021-03-11 | 2021-03-11 | 0 | 2021-03-11 | 2021-03-20 | 6 | 2021-03-30 | 2021-04-01 | 1 | 2021-04-07 |  |  |  | 2021-04-09 | 2 | 2021-04-09 | 2021-04-27 | 12 | 2021-05-19 | 16 | [18 empty] | 2022-03-08 | 0
GFID100477 | SCE | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 490 | No | 2021-02-09 | 2021-02-09 | 0 | 2021-02-09 | 2021-02-22 | 8 | 2021-03-04 | 2021-03-16 | 8 | 2021-03-17 | 2021-03-22 | 3 | 2021-04-27 | 2021-05-05 | 6 | 2021-05-25 | 2021-05-27 | 2 | [20 empty] | 2021-05-27 | 0 |  | 2021-07-22 | 56 | [21 empty] | 2021-09-13 |  | 216
GFID100487 | SCE | Non-NEM | Rule 21 Non-Export | Resolved-Withdrawn | Battery Storage | 10 | No | 2021-05-25 | 2021-05-25 | 0 | 2021-05-25 | 2021-06-07 | 11 | 2021-06-08 | 2021-06-17 | 7 | 2021-06-17
GFID100496 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Withdrawn | Other (Combustion Turbine) | 240 | No | 2021-03-09 | 2021-03-09 | 0 | 2021-03-09 | 2021-03-23 | 10 | 2021-03-29 | 2021-04-05 | 4 | 2021-04-07 | 2021-04-08 | 1 | 2021-04-16 | 2021-04-18 | 0 | 2021-04-18 | 2021-05-08 | 14 | 2021-05-28 | 14
GFID100497 | SCE | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Other (Combustion Turbine) | 240 | No | 2021-03-09 | 2021-03-09 | 0 | 2021-03-09 | 2021-03-23 | 10 | 2021-03-30 | 2021-04-14 | 10 | 2021-04-14 |  |  |  | 2021-04-20 | 4 | 2021-04-20 | 2021-05-08 | 13 | 2021-06-24 | 32
GFID100498 | SCE | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Solar PV + Other (Combustion Turbine) | 4164.7 | No | 2021-01-14 | 2021-01-14 | 0 | 2021-01-14 | 2021-01-28 | 9 | 2021-02-19 | 2021-03-03 | 8 | 2021-03-10 | 2021-03-16 | 4 | 2021-04-29 | 2021-04-30 | 1 | 2021-04-30 | 2021-05-19 | 13 | 2021-06-24 | 25
GFID100503 | SCE | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 15 | No | 2021-01-25 | 2021-01-25 | 0 | 2021-01-25 | 2021-02-04 | 8 | 2021-02-10 | [6 empty] | 2021-02-10 | 0 | 2021-02-10 | 2021-02-26 | 11 | [20 empty] | 2021-02-25 | 0 |  | 2021-04-19 | 53 | [21 empty] | 2021-10-14 |  | 262
GFID100504 | SCE | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 10 | No | 2021-01-25 | 2021-01-25 | 0 | 2021-01-25 | 2021-02-05 | 9 | 2021-02-10 | 2021-02-10 | 0 | 2021-03-02 |  |  |  | 2021-03-05 | 3 | 2021-03-06 | 2021-03-19 | 9 | [20 empty] | 2021-03-19 | 0 |  | 2021-04-06 | 18 | [21 empty] | 2021-04-12 |  | 77
GFID100505 | SCE | Non-NEM | Rule 21 Non-Export | Resolved-Withdrawn | Battery Storage | 10 | No | 2021-01-25 | 2021-01-25 | 0 | 2021-01-25 | 2021-02-04 | 8 | 2021-03-05 | [6 empty] | 2021-03-11 | 4 | 2021-03-11 | 2021-04-02 | 15 | [20 empty] | 2021-04-02 | 0
GFID100509 | SCE | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 10 | No | 2021-01-09 | 2021-01-09 | 0 | 2021-01-09 | 2021-01-20 | 6 | 2021-02-26 | 2021-03-10 | 8 | 2021-03-15 |  |  |  | 2021-03-19 | 4 | 2021-03-19 | 2021-04-09 | 14 | [20 empty] | 2021-04-09 | 0 |  | 2021-06-13 | 65 | [21 empty] | 2021-06-16 |  | 158
GFID100510 | SCE | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 30 | No | 2021-01-26 | 2021-01-26 | 0 | 2021-01-26 | 2021-02-03 | 6 | 2021-02-08 | 2021-02-23 | 10 | 2021-02-23 |  |  |  | 2021-02-24 | 1 | 2021-02-24 | 2021-03-04 | 6 | [20 empty] | 2021-03-04 | 0 |  | 2021-04-04 | 31 | [21 empty] | 2021-06-10 |  | 135
GFID100514 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 11.4 | No | 2021-02-10 | 2021-02-10 | 0 | 2021-02-10 | 2021-02-25 | 10 | 2021-04-13 | 2021-04-21 | 6 | 2021-04-28 |  |  |  | 2021-05-03 | 3 | 2021-05-03 | 2021-05-12 | 7 | [20 empty] | 2021-05-12 | 0 |  | 2021-06-23 | 42
GFID100518 | SCE | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 10 | No | 2021-03-19 | 2021-03-19 | 0 | 2021-03-19 | 2021-03-26 | 5 | 2021-03-26 | [6 empty] | 2021-03-29 | 1 | 2021-03-29 | 2021-04-02 | 3 | [20 empty] | 2021-04-02 | 0 |  | 2021-04-16 | 14 | [21 empty] | 2021-09-16 |  | 181
GFID100521 | SCE | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Solar PV + Battery Storage | 1746.5 | No | 2021-02-04 | 2021-02-04 | 0 | 2021-02-04 | 2021-02-24 | 13 | 2021-03-02 | 2021-03-16 | 10 | 2021-03-16 |  |  |  | 2021-03-23 | 5 | 2021-03-23 | 2021-04-20 | 19
GFID100524 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 572 | No | 2021-01-22 | 2021-01-22 | 0 | 2021-01-22 | 2021-02-04 | 9 | 2021-04-05 | 2021-04-15 | 8 | 2021-04-21 |  |  |  | 2021-04-27 | 4 | 2021-04-27 | 2021-05-11 | 10 | [20 empty] | 2021-03-30 | 0 |  | 2021-07-26 | 118
GFID100528 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 929.5 | No | 2021-01-28 | 2021-01-28 | 0 | 2021-01-28 | 2021-02-09 | 8 | 2021-02-18 | 2021-03-04 | 10 | 2021-03-24 |  |  |  | 2021-03-26 | 2 | 2021-03-26 | 2021-04-13 | 11 | [20 empty] | 2021-04-13 | 0 |  | 2021-06-21 | 69
GFID100530 | SCE | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 210 | No | 2021-02-09 | 2021-02-09 | 0 | 2021-02-09 | 2021-02-24 | 10 | 2021-02-25 | [6 empty] | 2021-03-11 | 10 | 2021-03-11 | 2021-04-08 | 19 | [20 empty] | 2021-04-13 | 3 |  | 2021-05-24 | 41 | [21 empty] | 2021-09-14 |  | 217
GFID100532 | SCE | Non-NEM | Rule 21 Non-Export | Pending-MomentaryParallel Review | Internal Combustion Engine | 3125 | No | 2021-02-09 | 2021-02-09 | 0 | 2021-02-09 | 2021-02-24 | 10 | 2021-03-03 | 2021-04-07 | 24 | 2021-04-08 |  |  |  | 2021-04-09 | 1
GFID100535 | SCE | Non-NEM | Rule 21 Non-Export | Pending-MomentaryParallel Review | Other (Combustion Turbine) | 1500 | No | 2021-04-05 | 2021-04-05 | 0 | 2021-04-05 | 2021-04-19 | 10 | 2021-04-29 | [6 empty] | 2021-05-12 | 9
GFID100539 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 10 | No | 2021-04-01 | 2021-04-01 | 0 | 2021-04-01 | 2021-04-15 | 10 | 2021-04-19 | [6 empty] | 2021-04-28 | 7 | 2021-04-28 | 2021-06-03 | 25 | [20 empty] | 2021-06-03 | 0 |  | 2021-07-04 | 31
GFID100540 | SCE | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 10 | No | 2021-03-03 | 2021-03-03 | 0 | 2021-03-03 | 2021-03-16 | 9 | 2021-04-15 | 2021-04-26 | 7 | 2021-04-28 |  |  |  | 2021-05-01 | 2 | 2021-05-01 | 2021-05-19 | 12 | [20 empty] | 2021-05-19 | 0 |  | 2021-06-18 | 30 | [21 empty] | 2021-08-25 |  | 175
GFID100544 | SCE | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 10 | No | 2021-03-03 | 2021-03-03 | 0 | 2021-03-03 | 2021-03-08 | 3 | 2021-03-09 | 2021-03-18 | 7 | 2021-03-18 |  |  |  | 2021-03-24 | 4 | 2021-03-24 | 2021-04-06 | 8 | [20 empty] | 2021-04-06 | 0 |  | 2021-06-03 | 58 | [21 empty] | 2021-06-04 |  | 93
GFID100547 | SCE | Non-NEM | Rule 21 Non-Export | Resolved-Withdrawn | Battery Storage | 210 | No | 2021-02-22 | 2021-02-22 | 0 | 2021-02-22 | 2021-03-08 | 10 | 2021-03-24 | 2021-04-07 | 9 | 2021-04-07
GFID100548 | SCE | Non-NEM | Rule 21 Non-Export | Resolved-Withdrawn | Battery Storage | 210 | No | 2021-02-22 | 2021-02-22 | 0 | 2021-02-22 | 2021-03-08 | 10 | 2021-04-15 | 2021-04-29 | 10 | 2021-05-04
GFID100549 | SCE | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 210 | No | 2021-02-18 | 2021-02-18 | 0 | 2021-02-18 | 2021-02-25 | 5 | 2021-03-14 | 2021-03-22 | 5 | 2021-03-25 |  |  |  | 2021-03-26 | 1 | 2021-03-26 | 2021-04-02 | 4 | [20 empty] | 2021-04-02 | 0 |  | 2021-04-29 | 27 | [21 empty] | 2021-09-21 |  | 215
GFID100550 | SCE | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 15 | No | 2021-02-22 | 2021-02-22 | 0 | 2021-02-22 | 2021-03-03 | 7 | 2021-03-16 | [6 empty] | 2021-03-22 | 4 | 2021-03-22 | 2021-03-30 | 6 | [20 empty] | 2021-03-30 | 0 |  | 2021-05-19 | 50 | [21 empty] | 2021-09-15 |  | 205
GFID100551 | SCE | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 20 | No | 2021-02-22 | 2021-02-22 | 0 | 2021-02-22 | 2021-02-26 | 4 | 2021-02-26 | [6 empty] | 2021-03-11 | 9 | 2021-03-11 | 2021-03-29 | 12 | [20 empty] | 2021-03-29 | 0 |  | 2021-05-19 | 51 | [21 empty] | 2021-09-15 |  | 205
GFID100552 | SCE | Non-NEM | Rule 21 Non-Export | Resolved-Withdrawn | Battery Storage | 30 | No | 2021-05-21 | 2021-05-21 | 0 | 2021-05-21 | 2021-06-04 | 9
GFID100556 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 210 | No | 2021-02-24 | 2021-02-24 | 0 | 2021-02-24 | 2021-03-04 | 6 | 2021-03-17 | 2021-03-23 | 4 | 2021-04-05 |  |  |  | 2021-04-05 | 0 | 2021-04-05 | 2021-04-07 | 2 | [20 empty] | 2021-04-07 | 0 |  | 2021-04-29 | 22
GFID100559 | SCE | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 350 | No | 2021-02-19 | 2021-02-19 | 0 | 2021-02-19 | 2021-03-05 | 10 | 2021-03-15 | 2021-03-26 | 9 | 2021-03-26 |  |  |  | 2021-04-01 | 3 | 2021-04-01 | 2021-04-19 | 12 | [20 empty] | 2021-04-19 | 0 |  | 2021-07-01 | 73 | [21 empty] | 2021-12-09 |  | 293
GFID100560 | SCE | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 210 | No | 2021-02-24 | 2021-02-24 | 0 | 2021-02-24 | 2021-03-09 | 9 | 2021-03-19 | 2021-03-30 | 7 | 2021-04-05 | 2021-04-08 | 3 | 2021-05-08 | 2021-05-08 | 0 | 2021-05-08 | 2021-05-27 | 13 | [20 empty] | 2021-05-28 | 1 |  | 2021-07-12 | 45 | [21 empty] | 2021-12-01 |  | 280
GFID100561 | SCE | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 20 | No | 2021-03-05 | 2021-03-05 | 0 | 2021-03-05 | 2021-03-16 | 7 | 2021-03-18 | [6 empty] | 2021-03-30 | 8 | 2021-03-30 | 2021-04-14 | 10 | [20 empty] | 2021-04-14 | 0 |  | 2021-05-11 | 27 | [21 empty] | 2021-06-23 |  | 110
GFID100565 | SCE | Non-NEM | Rule 21 Non-Export | Resolved-Completed | Internal Combustion Engine | 6800 | No | 2021-04-27 | 2021-04-27 | 0 | 2021-04-27 | [9 empty] | 2021-05-12 | 11 | [49 empty] | 2022-01-12 |  | 260
GFID100568 | SCE | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 350 | No | 2021-02-18 | 2021-02-18 | 0 | 2021-02-18 | [9 empty] | 2021-03-03 | 9 | 2021-03-03 | 2021-03-24 | 15 | [20 empty] | 2021-03-24 | 0 |  | 2021-12-30 | 281 | [21 empty] | 2022-03-25 |  | 400
GFID100569 | SCE | Non-NEM | Rule 21 Non-Export | Resolved-Withdrawn | Battery Storage | 20 | No | 2021-02-19 | 2021-02-19 | 0 | 2021-02-19 | 2021-03-03 | 8
GFID100570 | SCE | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 15 | No | 2021-02-23 | 2021-02-23 | 0 | 2021-02-23 | 2021-03-09 | 10 | 2021-03-09 | [6 empty] | 2021-03-10 | 1 | 2021-03-10 | 2021-03-25 | 11 | [20 empty] | 2021-03-25 | 0 |  | 2021-04-12 | 18 | [21 empty] | 2021-04-29 |  | 65
GFID100572 | SCE | Non-NEM | Rule 21 Non-Export | Resolved-Withdrawn | Solar PV + Battery Storage + Internal Combustion Engine | 1968 | No | 2021-04-16 | 2021-04-16 | 0 | 2021-04-16 | 2021-05-10 | 16 | 2021-05-24 | 2021-06-16 | 16 | 2021-06-21
GFID100573 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 572 | No | 2021-04-06 | 2021-04-06 | 0 | 2021-04-06 | 2021-04-15 | 7 | 2021-04-21 | 2021-05-05 | 10 | 2021-05-07 | 2021-05-10 | 1 | 2021-05-24 | 2021-05-29 | 4 | 2021-05-29 | 2021-06-11 | 8 | [20 empty] | 2021-06-15 | 2 |  | 2021-07-13 | 28
GFID100574 | SCE | Non-NEM | Rule 21 Non-Export | Pending Pre-Construction | Battery Storage | 1341 | No | 2021-04-08 | 2021-04-08 | 0 | 2021-04-08 | 2021-04-20 | 8 | 2021-04-26 | 2021-05-08 | 9 | 2021-05-10 |  |  |  | 2021-05-13 | 3 | 2021-05-13 | 2021-06-01 | 12 |  |  | 2021-07-09 | 2021-08-04 | 18 | 2021-08-25 | 15 | [13 empty] | 2021-09-27 | 14 |  | 2021-10-22 | 25
GFID100576 | SCE | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 5 | No | 2021-03-02 | 2021-03-02 | 0 | 2021-03-02 | 2021-03-11 | 7 | 2021-03-24 | 2021-03-25 | 1 | 2021-03-26 |  |  |  | 2021-04-02 | 4 | 2021-04-02 | 2021-04-12 | 6 | [20 empty] | 2021-04-12 | 0 |  | 2021-06-18 | 67 | [21 empty] | 2021-07-30 |  | 150
GFID100589 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 951.3 | No | 2021-03-30 | 2021-03-30 | 0 | 2021-03-30 | 2021-04-13 | 9 | 2021-06-28 | 2021-07-09 | 8 | 2021-07-16 |  |  |  | 2021-07-20 | 2 | 2021-07-20 | 2021-08-06 | 13 |  |  | 2021-08-24 | 2021-09-28 | 24 | [15 empty] | 2021-09-28 | 0 |  | 2021-11-18 | 51
GFID100591 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Construction | Solar PV + Battery Storage | 1611 | No | 2021-05-28 | 2021-05-28 | 0 | 2021-05-28 | 2021-06-11 | 9 | 2021-06-15 | [6 empty] | 2021-06-21 | 4 | 2021-06-21 | 2021-07-07 | 11 |  |  | 2021-08-17 | 2021-08-27 | 8 | [15 empty] | 2021-09-07 | 6 |  | 2021-12-23 | 107
GFID100593 | SCE | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 630 | No | 2021-03-08 | 2021-03-08 | 0 | 2021-03-08 | 2021-03-24 | 12 | 2021-04-15 | 2021-04-27 | 8 | 2021-04-30 | 2021-05-05 | 3 | 2021-05-28 | 2021-06-04 | 4 | 2021-06-04 | 2021-06-22 | 12 | [20 empty] | 2021-06-22 | 0 |  | 2021-08-24 | 63 | [21 empty] | 2022-03-30 |  | 387
GFID100596 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 10 | No | 2021-03-22 | 2021-03-22 | 0 | 2021-03-22 | [9 empty] | 2021-03-31 | 6 | 2021-03-31 | 2021-04-19 | 12 | [20 empty] | 2021-04-22 | 3 |  | 2021-05-11 | 19
GFID100601 | SCE | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 50 | No | 2021-03-14 | 2021-03-14 | 0 | 2021-03-14 | 2021-03-26 | 9 | 2021-04-13 | [6 empty] | 2021-04-24 | 8 | 2021-04-24 | 2021-05-11 | 11 | [20 empty] | 2021-05-10 | 0 |  | 2021-07-08 | 59 | [21 empty] | 2021-08-13 |  | 152
GFID100606 | SCE | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 10 | No | 2021-03-16 | 2021-03-16 | 0 | 2021-03-16 | 2021-03-22 | 4 | 2021-03-22 | 2021-03-22 | 0 | 2021-03-22 |  |  |  | 2021-03-22 | 0 | 2021-03-22 | 2021-03-29 | 5 | [20 empty] | 2021-03-29 | 0 |  | 2021-04-12 | 14 | [21 empty] | 2021-04-28 |  | 43
GFID100607 | SCE | Non-NEM | Rule 21 Non-Export | Resolved-Terminated | Battery Storage | 10 | No | 2021-04-01 | 2021-04-01 | 0 | 2021-04-01 | 2021-04-10 | 6 | 2021-05-19 | [6 empty] | 2021-05-25 | 4 | 2021-05-25 | 2021-05-27 | 2 | [20 empty] | 2021-05-27 | 0 |  | 2021-07-15 | 49 | [21 empty] | 2021-07-21 |  | 111
GFID100608 | SCE | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Battery Storage | 420 | No | 2021-03-19 | 2021-03-19 | 0 | 2021-03-19 | [9 empty] | 2021-04-05 | 10 | 2021-04-05 | 2021-04-20 | 11 |  |  | 2021-07-15 | 2021-08-12 | 20 | [15 empty] | 2021-08-12 | 0
GFID100612 | SCE | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 174 | No | 2021-03-24 | 2021-03-24 | 0 | 2021-03-24 | 2021-04-02 | 6 | 2021-04-06 | [6 empty] | 2021-04-09 | 3 | 2021-04-09 | 2021-04-15 | 4 | [20 empty] | 2021-04-15 | 0 |  | 2021-05-28 | 43 | [21 empty] | 2021-10-11 |  | 201
GFID100615 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 490 | No | 2021-05-18 | 2021-05-18 | 0 | 2021-05-18 | 2021-05-27 | 7 | 2021-06-15 | 2021-06-24 | 7 | 2021-07-14 | 2021-07-16 | 2 | 2021-08-03 | 2021-08-04 | 1 | 2021-08-04 | 2021-08-13 | 7 | [20 empty] | 2021-08-13 | 0 |  | 2021-09-17 | 35
GFID100616 | SCE | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 210 | No | 2021-04-20 | 2021-04-20 | 0 | 2021-04-20 | 2021-04-30 | 8 | 2021-05-03 | 2021-05-05 | 2 | 2021-05-07 |  |  |  | 2021-05-07 | 0 | 2021-05-07 | 2021-05-14 | 5 | [20 empty] | 2021-05-18 | 2 |  | 2021-06-03 | 16 | [21 empty] | 2021-09-28 |  | 161
GFID100617 | SCE | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 210 | No | 2021-04-20 | 2021-04-20 | 0 | 2021-04-20 | 2021-05-03 | 9 | 2021-05-06 | 2021-05-19 | 9 | 2021-05-28 |  |  |  | 2021-06-03 | 3 | 2021-06-03 | 2021-06-17 | 10 | [20 empty] | 2021-06-17 | 0 |  | 2021-08-31 | 75 | [21 empty] | 2021-12-15 |  | 239
GFID100630 | SCE | Non-NEM | Rule 21 Non-Export | Resolved-Withdrawn | Battery Storage | 1859 | No | 2021-03-31 | 2021-03-31 | 0 | 2021-03-31 | 2021-04-14 | 9
GFID100632 | SCE | Non-NEM | Rule 21 Non-Export | Resolved-Withdrawn | Other | 436 | No | 2021-07-19 | 2021-07-19 | 0 | 2021-07-19 | 2021-07-27 | 6 | 2021-11-01 | 2021-11-15 | 9 | 2021-12-21
GFID100635 | SCE | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 10 | No | 2021-04-15 | 2021-04-15 | 0 | 2021-04-15 | 2021-04-26 | 7 | 2021-04-28 | 2021-05-08 | 7 | 2021-05-24 |  |  |  | 2021-05-28 | 4 | 2021-05-28 | 2021-06-16 | 12 | [20 empty] | 2021-06-16 | 0 |  | 2021-08-05 | 50 | [21 empty] | 2021-12-14 |  | 243
GFID100637 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 572 | No | 2021-04-05 | 2021-04-05 | 0 | 2021-04-05 | 2021-04-13 | 6 | 2021-05-07 | 2021-05-12 | 3 | 2021-07-14 | 2021-07-20 | 4 | 2021-07-27 | 2021-07-27 | 0 | 2021-07-27 | 2021-08-10 | 10 |  |  | 2021-09-03 | 2021-09-27 | 15 | [15 empty] | 2021-10-18 | 14 |  | 2021-11-10 | 23
GFID100639 | SCE | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Battery Storage | 210 | No | 2021-04-20 | 2021-04-20 | 0 | 2021-04-20 | 2021-05-04 | 10 | 2021-05-06 | [6 empty] | 2021-05-20 | 10 | 2021-05-20 | 2021-06-14 | 16 | [20 empty] | 2021-06-14 | 0
GFID100642 | SCE | Non-NEM | Rule 21 Non-Export | Resolved-Withdrawn | Battery Storage | 10 | No | 2021-04-07 | 2021-04-07 | 0 | 2021-04-07 | 2021-04-09 | 2 | 2021-04-09 | [6 empty] | 2021-04-15 | 4 | 2021-04-15
GFID100647 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 10 | No | 2021-04-19 | 2021-04-19 | 0 | 2021-04-19 | 2021-04-29 | 8 | 2021-05-28 | [6 empty] | 2021-06-10 | 8 | 2021-06-10 | 2021-06-30 | 14 | [20 empty] | 2021-06-30 | 0 |  | 2021-07-26 | 26
GFID100648 | SCE | Non-NEM | Rule 21 Non-Export | Resolved-Withdrawn | Internal Combustion Engine | 308 | No | 2021-05-28 | 2021-05-28 | 0 | 2021-05-28 | 2021-06-14 | 10
GFID100649 | SCE | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 10 | No | 2021-04-19 | 2021-04-19 | 0 | 2021-04-19 | [9 empty] | 2021-04-29 | 8 | 2021-04-29 | 2021-05-07 | 6 | [20 empty] | 2021-05-14 | 5 |  | 2021-06-10 | 27 | [21 empty] | 2021-08-20 |  | 123
GFID100650 | SCE | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 10 | No | 2021-04-19 | 2021-04-19 | 0 | 2021-04-19 | [9 empty] | 2021-05-03 | 10 | 2021-05-03 | 2021-05-17 | 10 | [20 empty] | 2021-05-18 | 1 |  | 2021-06-10 | 23 | [21 empty] | 2021-08-03 |  | 106
GFID100652 | SCE | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 490 | No | 2021-04-14 | 2021-04-14 | 0 | 2021-04-14 | 2021-04-23 | 7 | 2021-05-17 | 2021-05-21 | 4 | 2021-05-24 |  |  |  | 2021-05-26 | 2 | 2021-05-26 | 2021-06-07 | 7 | [20 empty] | 2021-06-07 | 0 |  | 2021-08-06 | 60 | [19 empty] | 2021-10-15 |  | 2021-10-15 |  | 184
GFID100653 | SCE | Non-NEM | Rule 21 Non-Export | Resolved-Withdrawn | Battery Storage | 350 | No | 2021-04-14 | 2021-04-14 | 0 | 2021-04-14 | 2021-04-23 | 7 | 2021-05-24 | 2021-06-07 | 9 | 2021-06-17
GFID100657 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 10 | No | 2021-04-19 | 2021-04-19 | 0 | 2021-04-19 | [9 empty] | 2021-05-03 | 10 | 2021-05-03 | 2021-05-20 | 13 | [20 empty] | 2021-05-19 | 0 |  | 2021-06-03 | 15
GFID100667 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 174 | No | 2021-04-23 | 2021-04-23 | 0 | 2021-04-23 | 2021-05-05 | 8 | 2021-05-20 | [6 empty] | 2021-06-01 | 7 | 2021-06-01 | 2021-06-22 | 15 | [20 empty] | 2021-06-22 | 0 |  | 2021-09-16 | 86
GFID100668 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Construction | Solar PV + Battery Storage | 6405 | No | 2021-07-06 | 2021-07-06 | 0 | 2021-07-06 | 2021-07-16 | 8 | 2021-11-12 | 2021-12-06 | 14 | 2021-12-14 | 2021-12-20 | 4 | 2022-01-04 | 2022-01-11 | 5 | 2022-01-11 | 2022-01-27 | 11 | [20 empty] | 2022-01-27 | 0 |  | 2022-02-24 | 28
GFID100669 | SCE | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Battery Storage | 210 | No | 2021-04-23 | 2021-04-23 | 0 | 2021-04-23 | 2021-05-07 | 10 | 2021-05-17 | 2021-06-01 | 10 | 2021-06-15 | 2021-06-22 | 5 | 2022-02-04 | 2022-02-16 | 8 | 2022-02-16 | 2022-03-09 | 14 | [20 empty] | 2022-03-30 | 15
GFID100670 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 210 | No | 2021-05-05 | 2021-05-05 | 0 | 2021-05-05 | 2021-05-18 | 9 | 2021-06-03 | [6 empty] | 2021-06-15 | 8 | 2021-06-15 | 2021-07-02 | 13 | [20 empty] | 2021-07-02 | 0 |  | 2021-08-18 | 47
GFID100671 | SCE | Non-NEM | Rule 21 Non-Export | Pending Review | Battery Storage | 210 | No | 2021-04-23 | 2021-04-23 | 0 | 2021-04-23 | 2021-05-07 | 10 | 2021-05-18 | 2021-06-02 | 10 | 2021-08-05
GFID100673 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Resubmission | Solar PV + Battery Storage | 280 | No | 2021-04-26 | 2021-04-26 | 0 | 2021-04-26 | 2021-05-10 | 10 | 2021-06-14 | 2021-06-28 | 10 | 2021-09-08 | 2021-09-14 | 4
GFID100675 | SCE | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 280 | No | 2021-06-17 | 2021-06-17 | 0 | 2021-06-17 | 2021-06-29 | 8 | 2021-07-07 | 2021-07-19 | 8 | 2021-07-26 | 2021-07-29 | 3 | 2021-09-28 | 2021-09-28 | 0 | 2021-09-28 | 2021-10-22 | 17 |  |  | 2021-10-25 | 2021-11-10 | 12 | [15 empty] | 2021-11-09 | 0 |  | 2021-11-30 | 21 | [21 empty] | 2022-01-12 |  | 209
GFID100680 | SCE | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 490 | No | 2021-05-14 | 2021-05-14 | 0 | 2021-05-14 | 2021-05-26 | 8 | 2021-06-03 | [6 empty] | 2021-06-15 | 8 | 2021-06-15 | 2021-06-21 | 4 | [20 empty] | 2021-06-21 | 0 |  | 2021-07-15 | 24 | [21 empty] | 2021-12-17 |  | 217
GFID100682 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 490 | No | 2021-05-12 | 2021-05-12 | 0 | 2021-05-12 | 2021-05-24 | 8 | 2021-05-26 | [6 empty] | 2021-06-09 | 9 | 2021-06-09 | 2021-06-17 | 6 | [20 empty] | 2021-06-17 | 0 |  | 2021-08-05 | 49
GFID100684 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 10 | No | 2021-05-12 | 2021-05-12 | 0 | 2021-05-12 | [9 empty] | 2021-05-24 | 8 | 2021-05-24 | 2021-05-26 | 2 | [20 empty] | 2021-05-26 | 0 |  | 2021-07-09 | 44
GFID100685 | SCE | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 140 | No | 2021-05-12 | 2021-05-12 | 0 | 2021-05-12 | 2021-05-21 | 7 | 2021-05-28 | 2021-06-02 | 2 | 2021-06-03 |  |  |  | 2021-06-08 | 3 | 2021-06-18 | 2021-06-18 | 0 | [20 empty] | 2021-06-18 | 0 |  | 2021-08-16 | 59 | [19 empty] | 2021-11-16 |  | 2021-11-16 |  | 188
GFID100686 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 643.5 | No | 2021-05-13 | 2021-05-13 | 0 | 2021-05-13 | 2021-05-27 | 10 | 2021-05-28 | 2021-06-14 | 10 | 2021-07-17 | 2021-07-26 | 5 | 2021-08-23 | 2021-08-27 | 4 | 2021-08-27 | 2021-09-21 | 16 | [20 empty] | 2021-09-21 | 0 |  | 2022-02-01 | 133
GFID100687 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 210 | No | 2021-05-27 | 2021-05-27 | 0 | 2021-05-27 | 2021-06-08 | 7 | 2021-06-11 | 2021-06-17 | 4 | 2021-06-25 |  |  |  | 2021-06-25 | 0 | 2021-06-25 | 2021-06-30 | 3 | [20 empty] | 2021-06-30 | 0 |  | 2021-08-05 | 36
GFID100688 | SCE | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 210 | No | 2021-05-27 | 2021-05-27 | 0 | 2021-05-27 | 2021-06-08 | 7 | 2021-06-11 | 2021-06-22 | 7 | 2021-06-23 |  |  |  | 2021-06-25 | 2 | 2021-06-25 | 2021-06-30 | 3 | [20 empty] | 2021-06-30 | 0 |  | 2021-07-23 | 23 | [21 empty] | 2022-02-22 |  | 271
GFID100690 | SCE | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 5 | No | 2021-06-02 | 2021-06-02 | 0 | 2021-06-02 | 2021-06-14 | 8 | 2021-06-14 | [6 empty] | 2021-06-26 | 9 | 2021-06-26 | 2021-07-15 | 12 | [20 empty] | 2021-07-15 | 0 |  | 2021-08-24 | 40 | [21 empty] | 2021-09-13 |  | 103
GFID100692 | SCE | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 280 | No | 2021-05-20 | 2021-05-20 | 0 | 2021-05-20 | 2021-06-04 | 10 | 2021-06-16 | 2021-06-28 | 8 | 2021-07-01 | 2021-07-06 | 2 | 2021-07-24 | 2021-07-28 | 2 | 2021-07-28 | 2021-08-13 | 12 | [20 empty] | 2021-08-13 | 0 |  | 2021-09-30 | 48 | [21 empty] | 2021-10-25 |  | 158
GFID100694 | SCE | Non-NEM | Rule 21 Non-Export | Resolved-Withdrawn | Solar PV + Battery Storage + Fuel Cell | 1400 | No | 2021-05-20 | 2021-05-20 | 0 | 2021-05-20 | 2021-06-02 | 8 | 2021-06-15 | 2021-06-25 | 8 | 2021-07-27
GFID100702 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 140 | No | 2021-05-21 | 2021-05-21 | 0 | 2021-05-21 | 2021-06-02 | 7 | 2021-06-02 | 2021-06-11 | 7 | 2021-06-14 |  |  |  | 2021-06-15 | 1 | 2021-06-15 | 2021-06-30 | 11 | [20 empty] | 2021-06-30 | 0 |  | 2021-09-07 | 69
GFID100704 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 10 | No | 2021-05-25 | 2021-05-25 | 0 | 2021-05-25 | 2021-06-07 | 8 | 2021-06-07 | [6 empty] | 2021-06-09 | 2 | 2021-06-09 | 2021-06-24 | 11 | [20 empty] | 2021-06-24 | 0 |  | 2021-07-19 | 25
GFID100705 | SCE | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 10 | No | 2021-05-25 | 2021-05-25 | 0 | 2021-05-25 | [9 empty] | 2021-06-07 | 8 | 2021-06-07 | 2021-06-23 | 12 | [20 empty] | 2021-06-23 | 0 |  | 2021-07-28 | 35 | [21 empty] | 2021-09-30 |  | 128
GFID100706 | SCE | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 210 | No | 2021-05-27 | 2021-05-27 | 0 | 2021-05-27 | 2021-06-10 | 9 | 2021-06-16 | 2021-06-28 | 8 | 2021-06-29 |  |  |  | 2021-07-19 | 13 | 2021-07-19 | 2021-08-05 | 13 |  |  | 2021-08-16 | 2021-09-09 | 17 | [15 empty] | 2021-09-09 | 0 |  | 2021-11-10 | 62 | [21 empty] | 2021-12-06 |  | 193
GFID100707 | SCE | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 10 | No | 2021-05-26 | 2021-05-26 | 0 | 2021-05-26 | [9 empty] | 2021-06-08 | 8 | 2021-06-08 | 2021-06-27 | 13 | [20 empty] | 2021-06-26 | 0 |  | 2021-07-22 | 26 | [21 empty] | 2021-07-27 |  | 62
GFID100708 | SCE | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 280 | No | 2021-05-27 | 2021-05-27 | 0 | 2021-05-27 | 2021-06-11 | 10 | 2021-06-16 | 2021-06-29 | 9 | 2021-07-12 |  |  |  | 2021-07-15 | 3 | 2021-07-15 | 2021-08-06 | 16 | [20 empty] | 2021-08-06 | 0 |  | 2021-09-13 | 38 | [21 empty] | 2021-12-16 |  | 203
GFID100711 | SCE | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 140 | No | 2021-06-01 | 2021-06-01 | 0 | 2021-06-01 | 2021-06-14 | 9 | 2021-06-14 | [6 empty] | 2021-06-18 | 4 | 2021-06-18 | 2021-07-07 | 12 |  |  | 2021-07-22 | 2021-08-25 | 24 | [15 empty] | 2021-09-09 | 10 |  | 2021-10-06 | 27 | [21 empty] | 2021-12-06 |  | 188
GFID100713 | SCE | Non-NEM | Rule 21 Non-Export | Resolved-Withdrawn | Battery Storage | 10 | No | 2021-05-28 | 2021-05-28 | 0 | 2021-05-28 | 2021-06-08 | 6 | 2021-06-10 | 2021-06-17 | 5 | 2021-06-28
GFID100714 | SCE | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 210 | No | 2021-06-07 | 2021-06-07 | 0 | 2021-06-07 | 2021-06-16 | 7 | 2021-06-17 | [6 empty] | 2021-06-18 | 1 | 2021-06-18 | 2021-07-07 | 12 |  |  | 2021-07-22 | 2021-08-25 | 24 | [15 empty] | 2021-09-09 | 10 |  | 2021-10-05 | 26 | [19 empty] | 2021-12-22 |  | 2021-12-22 |  | 198
GFID100715 | SCE | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 10 | No | 2021-06-02 | 2021-06-02 | 0 | 2021-06-02 | [9 empty] | 2021-06-15 | 9 | 2021-06-15 | 2021-06-21 | 4 | [20 empty] | 2021-06-21 | 0 |  | 2021-07-14 | 23 | [21 empty] | 2021-12-15 |  | 196
GFID100719 | SCE | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 10 | No | 2021-06-02 | 2021-06-02 | 0 | 2021-06-02 | 2021-06-14 | 8 | 2021-06-16 | [6 empty] | 2021-06-19 | 2 | 2021-06-19 | 2021-07-07 | 11 | [20 empty] | 2021-07-07 | 0 |  | 2021-07-22 | 15 | [21 empty] | 2021-11-23 |  | 174
GFID100720 | SCE | Non-NEM | Rule 21 Non-Export | Resolved-Withdrawn | Battery Storage | 250 | No | 2021-06-23 | 2021-06-23 | 0 | 2021-06-23 | 2021-07-02 | 7 | 2021-08-31 | 2021-09-13 | 8
GFID100722 | SCE | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 210 | No | 2021-06-07 | 2021-06-07 | 0 | 2021-06-07 | 2021-06-16 | 7 | 2021-06-17 | [6 empty] | 2021-06-28 | 7 | 2021-06-28 | 2021-07-13 | 10 |  |  | 2021-07-22 | 2021-09-02 | 30 | [15 empty] | 2021-09-03 | 1 |  | 2021-11-10 | 68 | [21 empty] | 2021-12-23 |  | 199
GFID100724 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 15 | No | 2021-06-09 | 2021-06-09 | 0 | 2021-06-09 | [9 empty] | 2021-06-14 | 3 | 2021-06-14 | 2021-06-30 | 12 | [20 empty] | 2021-06-30 | 0 |  | 2021-08-12 | 43
GFID100725 | SCE | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 210 | No | 2021-06-08 | 2021-06-08 | 0 | 2021-06-08 | 2021-06-18 | 8 | 2021-06-22 | 2021-07-02 | 8 | 2021-07-05 |  |  |  | 2021-07-08 | 2 | 2021-07-08 | 2021-07-26 | 12 | [20 empty] | 2021-07-28 | 2 |  | 2021-08-11 | 14 | [21 empty] | 2022-03-25 |  | 290
GFID100727 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 10 | No | 2021-06-09 | 2021-06-09 | 0 | 2021-06-09 | [9 empty] | 2021-06-14 | 3 | 2021-06-14 | 2021-06-17 | 3 | [20 empty] | 2021-06-17 | 0 |  | 2021-08-09 | 53
GFID100733 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 5 | No | 2021-06-11 | 2021-06-11 | 0 | 2021-06-11 | 2021-06-16 | 3 | 2021-06-16 | 2021-06-25 | 7 | 2021-06-25 |  |  |  | 2021-06-28 | 1 | 2021-06-28 | 2021-07-02 | 4 | [20 empty] | 2021-07-02 | 0 |  | 2021-07-25 | 23
GFID100734 | SCE | Non-NEM | Rule 21 Non-Export | Resolved-Withdrawn | Solar PV | 100 | No | 2021-07-06 | 2021-07-06 | 0 | 2021-07-06 | 2021-07-19 | 9
GFID100739 | SCE | Non-NEM | Rule 21 Non-Export | Resolved-Withdrawn | Solar PV + Battery Storage | 1064.6 | No | 2021-06-16 | 2021-06-16 | 0 | 2021-06-16 | 2021-06-29 | 9 | 2021-07-29 | 2021-08-11 | 9 | 2021-08-30
GFID100740 | SCE | Non-NEM | Rule 21 Non-Export | Resolved-Withdrawn | Solar PV + Battery Storage | 1160 | No | 2021-06-16 | 2021-06-16 | 0 | 2021-06-16 | 2021-06-28 | 8 | 2021-07-29 | 2021-08-11 | 9 | 2021-08-30
GFID100742 | SCE | Non-NEM | Rule 21 Non-Export | Resolved-Withdrawn | Solar PV + Battery Storage | 382.16 | No | 2021-06-17 | 2021-06-17 | 0 | 2021-06-17 | 2021-07-01 | 10 | 2021-07-29 | 2021-08-10 | 8 | 2021-08-16 | 2021-08-19 | 3 | 2021-08-31 | 2021-08-31 | 0 | 2021-08-31 | 2021-10-08 | 27 | 2021-10-29 | 14 | [18 empty] | 2021-12-03 | 0
GFID100743 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 210 | No | 2021-06-17 | 2021-06-17 | 0 | 2021-06-17 | 2021-06-29 | 8 | 2021-08-03 | 2021-08-11 | 6 | 2021-08-16 |  |  |  | 2021-08-19 | 3 | 2021-08-19 | 2021-09-01 | 9 |  |  | 2021-09-02 | 2021-09-13 | 6 | [15 empty] | 2021-09-13 | 0 |  | 2021-10-18 | 35
GFID100746 | SCE | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 210 | No | 2021-06-18 | 2021-06-18 | 0 | 2021-06-18 | 2021-07-01 | 9 | 2021-07-01 | [6 empty] | 2021-07-14 | 8 | 2021-07-14 | 2021-07-28 | 10 | [20 empty] | 2021-08-13 | 12 |  | 2021-08-26 | 13 | [21 empty] | 2021-12-16 |  | 181
GFID100747 | SCE | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 10 | No | 2021-06-24 | 2021-06-24 | 0 | 2021-06-24 | [9 empty] | 2021-07-08 | 9 | 2021-07-08 | 2021-07-27 | 13 | [20 empty] | 2021-08-06 | 8 |  | 2021-08-20 | 14 | [21 empty] | 2021-09-08 |  | 76
GFID100750 | SCE | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 210 | No | 2021-06-21 | 2021-06-21 | 0 | 2021-06-21 | 2021-07-02 | 9 | 2021-07-29 | 2021-08-10 | 8 | 2021-08-16 |  |  |  | 2021-08-19 | 3 | 2021-08-19 | 2021-09-03 | 11 | [20 empty] | 2021-09-02 | 0 |  | 2021-10-20 | 48 | [21 empty] | 2021-12-01 |  | 163
GFID100755 | SCE | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 174 | No | 2021-07-05 | 2021-07-05 | 0 | 2021-07-05 | 2021-07-19 | 9 | 2021-08-20 | 2021-08-30 | 6 | 2021-09-09 |  |  |  | 2021-09-15 | 4 | 2021-09-15 | 2021-10-04 | 13 |  |  | 2021-10-04 | 2021-10-29 | 18 | [15 empty] | 2021-11-15 | 10 |  | 2021-12-30 | 45 | [21 empty] | 2022-03-14 |  | 252
GFID100760 | SCE | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 10 | No | 2021-07-13 | 2021-07-13 | 0 | 2021-07-13 | [9 empty] | 2021-07-23 | 8 | 2021-07-23 | 2021-08-12 | 14 | [20 empty] | 2021-08-12 | 0 |  | 2021-11-04 | 84 | [21 empty] | 2021-11-15 |  | 125
GFID100764 | SCE | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 10 | No | 2021-06-25 | 2021-06-25 | 0 | 2021-06-25 | 2021-07-07 | 7 | 2021-07-08 | [6 empty] | 2021-07-19 | 7 | 2021-07-19 | 2021-08-03 | 11 | [20 empty] | 2021-08-03 | 0 |  | 2021-08-11 | 8 | [21 empty] | 2021-08-24 |  | 60
GFID100768 | SCE | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 15 | No | 2021-07-09 | 2021-07-09 | 0 | 2021-07-09 | 2021-07-21 | 8 | 2021-07-21 | [6 empty] | 2021-08-03 | 9 | 2021-08-03 | 2021-08-26 | 17 | [20 empty] | 2021-08-26 | 0 |  | 2021-10-01 | 36 | [21 empty] | 2021-10-07 |  | 90
GFID100769 | SCE | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 10 | No | 2021-07-09 | 2021-07-09 | 0 | 2021-07-09 | 2021-07-21 | 8 | 2021-07-21 | 2021-08-03 | 9 | 2021-08-05 |  |  |  | 2021-08-05 | 0 | 2021-08-05 | 2021-08-24 | 13 | [20 empty] | 2021-08-24 | 0 |  | 2021-10-19 | 56 | [21 empty] | 2021-11-08 |  | 122
GFID100770 | SCE | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Battery Storage | 210 | No | 2021-06-30 | 2021-06-30 | 0 | 2021-06-30 | 2021-07-14 | 9 | 2021-07-29 | 2021-08-12 | 10 | 2021-09-01 | 2021-09-09 | 5 | 2021-10-16 | 2021-10-25 | 5 | 2021-10-25 | 2021-12-22 | 39 |  |  | 2021-12-30 | 2022-01-27 | 18 | [15 empty] | 2022-01-27 | 0
GFID100772 | SCE | Non-NEM | Rule 21 Non-Export | Resolved-Withdrawn | Battery Storage | 490 | No | 2021-07-01 | 2021-07-01 | 0 | 2021-07-01 | 2021-07-12 | 6 | 2021-07-27 | 2021-08-09 | 9
GFID100773 | SCE | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 140 | No | 2021-07-12 | 2021-07-12 | 0 | 2021-07-12 | [9 empty] | 2021-07-27 | 11 | 2021-07-27 | 2021-08-10 | 10 |  |  | 2021-08-25 | 2021-09-23 | 20 | [15 empty] | 2021-09-23 | 0 |  | 2022-01-05 | 104 | [21 empty] | 2022-01-19 |  | 191
GFID100774 | SCE | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 210 | No | 2021-07-13 | 2021-07-13 | 0 | 2021-07-13 | 2021-07-27 | 10 | 2021-08-11 | 2021-08-23 | 8 | 2021-08-24 |  |  |  | 2021-08-26 | 2 | 2021-08-26 | 2021-09-16 | 14 |  |  | 2021-09-21 | 2021-10-07 | 12 | [15 empty] | 2021-10-07 | 0 |  | 2021-12-17 | 71 | [21 empty] | 2022-01-19 |  | 190
GFID100775 | SCE | Non-NEM | Rule 21 Non-Export | Resolved-Withdrawn | Battery Storage | 588.9 | No | 2021-07-02 | 2021-07-02 | 0 | 2021-07-02 | 2021-07-12 | 5 | 2021-07-27 | 2021-08-04 | 6
GFID100776 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 491 | No | 2021-07-16 | 2021-07-16 | 0 | 2021-07-16 | 2021-07-28 | 8 | 2021-08-12 | 2021-08-23 | 7 | 2021-08-31 |  |  |  | 2021-09-03 | 3 | 2021-10-01 | 2021-10-12 | 6 | [20 empty] | 2021-10-12 | 0 |  | 2022-03-25 | 164
GFID100777 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 10 | No | 2021-07-08 | 2021-07-08 | 0 | 2021-07-08 | 2021-07-19 | 7 | 2021-07-20 | [6 empty] | 2021-07-27 | 5 | 2021-07-27 | 2021-08-09 | 9 | [20 empty] | 2021-08-09 | 0 |  | 2021-08-25 | 16
GFID100779 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 10 | No | 2021-07-15 | 2021-07-15 | 0 | 2021-07-15 | [9 empty] | 2021-07-22 | 5 | 2021-07-22 | 2021-08-02 | 7 | [20 empty] | 2021-08-02 | 0 |  | 2021-08-17 | 15
GFID100780 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 10 | No | 2021-07-15 | 2021-07-15 | 0 | 2021-07-15 | [9 empty] | 2021-07-27 | 8 | 2021-07-27 | 2021-08-06 | 8 | [20 empty] | 2021-08-06 | 0 |  | 2021-08-22 | 16
GFID100781 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 10 | No | 2021-09-30 | 2021-09-30 | 0 | 2021-09-30 | 2021-10-14 | 9 | 2021-11-01 | 2021-11-15 | 9 | 2021-11-23 |  |  |  | 2021-11-30 | 3 | 2021-11-30 | 2022-01-06 | 25 | [20 empty] | 2022-01-06 | 0 |  | 2022-02-03 | 28
GFID100782 | SCE | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 10 | No | 2021-07-15 | 2021-07-15 | 0 | 2021-07-15 | [9 empty] | 2021-07-20 | 3 | 2021-07-20 | 2021-08-04 | 11 | [20 empty] | 2021-08-04 | 0 |  | 2021-09-11 | 38 | [21 empty] | 2022-03-23 |  | 251
GFID100786 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 572 | No | 2021-09-01 | 2021-09-01 | 0 | 2021-09-01 | 2021-09-16 | 10 | 2021-10-04 | 2021-10-16 | 8 | 2021-10-18 |  |  |  | 2021-10-21 | 3 | 2021-10-21 | 2021-11-09 | 13 |  |  | 2021-12-03 | 2022-01-04 | 20 | [15 empty] | 2022-01-10 | 4 |  | 2022-02-28 | 49
GFID100794 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 464 | No | 2021-07-23 | 2021-07-23 | 0 | 2021-07-23 | 2021-08-03 | 7 | 2021-08-17 | 2021-08-26 | 7 | 2021-09-13 | 2021-09-17 | 4 | 2021-12-07 | 2021-12-13 | 4 | 2021-12-13 | 2022-01-12 | 20 | [20 empty] | 2022-01-12 | 0 |  | 2022-03-10 | 57
GFID100795 | SCE | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Battery Storage | 100 | No | 2021-08-04 | 2021-08-04 | 0 | 2021-08-04 | 2021-09-02 | 21 | 2021-09-14 | 2021-09-28 | 10 | 2021-10-01 |  |  |  | 2022-01-20 | 72 | 2022-01-20 | 2022-01-31 | 7
GFID100798 | SCE | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Battery Storage | 50 | No | 2021-08-04 | 2021-08-04 | 0 | 2021-08-04 | 2021-09-02 | 21 | 2021-09-15 | 2021-09-23 | 6 | 2021-09-30 | 2021-10-07 | 5 | 2022-01-06 | 2022-01-11 | 3 | 2022-01-11 | 2022-02-03 | 16
GFID100799 | SCE | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Battery Storage | 1000 | No | 2021-08-02 | 2021-08-02 | 0 | 2021-08-02 | 2021-08-19 | 13 | 2021-08-30 | 2021-09-09 | 7 | 2021-09-09 |  |  |  | 2021-09-15 | 4 | 2021-09-15 | 2021-09-30 | 11 | 2021-10-25 | 16
GFID100804 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 140 | No | 2021-08-10 | 2021-08-10 | 0 | 2021-08-10 | 2021-09-02 | 17 | 2021-09-03 | 2021-09-14 | 6 | 2021-09-15 |  |  |  | 2021-09-22 | 5 | 2021-09-22 | 2021-10-07 | 11 | [20 empty] | 2021-10-07 | 0 |  | 2022-03-02 | 146
GFID100807 | SCE | Non-NEM | Rule 21 Non-Export | Resolved-Withdrawn | Other | 60 | Yes | 2021-11-17 | 2021-11-17 | 0 | 2021-11-17 | 2021-12-10 | 15
GFID100809 | SCE | Non-NEM | Rule 21 Non-Export | Resolved-Withdrawn | Battery Storage | 24 | No | 2021-08-02 | 2021-08-02 | 0 | 2021-08-02 | 2021-08-13 | 9 | 2021-09-03 | 2021-09-08 | 2 | 2021-09-10
GFID100810 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 929.5 | No | 2021-10-11 | 2021-10-11 | 0 | 2021-10-11 | 2021-10-22 | 8 | 2021-10-22 | [6 empty] | 2021-10-27 | 3 | 2021-10-27 | 2021-11-11 | 10 |  |  | 2021-11-16 | 2021-12-15 | 19 | [15 empty] | 2021-12-15 | 0 |  | 2022-01-10 | 26
GFID100813 | SCE | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 10 | No | 2021-08-09 | 2021-08-09 | 0 | 2021-08-09 | 2021-08-23 | 10 | 2021-08-24 | [6 empty] | 2021-08-24 | 0 | 2021-08-24 | 2021-09-13 | 13 | [20 empty] | 2021-09-23 | 8 |  | 2021-09-24 | 1 | [21 empty] | 2021-11-01 |  | 84
GFID100814 | SCE | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 10 | No | 2021-08-09 | 2021-08-09 | 0 | 2021-08-09 | 2021-08-17 | 6 | 2021-08-17 | [6 empty] | 2021-08-27 | 8 | 2021-08-27 | 2021-09-11 | 9 | [20 empty] | 2021-09-23 | 8 |  | 2021-09-28 | 5 | [21 empty] | 2021-10-08 |  | 60
GFID100815 | SCE | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 10 | No | 2021-08-18 | 2021-08-18 | 0 | 2021-08-18 | [9 empty] | 2021-09-01 | 10 | 2021-09-01 | 2021-09-21 | 13 | [20 empty] | 2021-09-21 | 0 |  | 2021-12-27 | 97 | [21 empty] | 2022-01-31 |  | 166
GFID100819 | SCE | Non-NEM | Rule 21 Non-Export | Resolved-Withdrawn | Battery Storage | 210 | No | 2021-08-07 | 2021-08-07 | 0 | 2021-08-07 | 2021-08-20 | 9 | 2021-09-28 | 2021-10-11 | 9
GFID100824 | SCE | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 10 | No | 2021-08-13 | 2021-08-13 | 0 | 2021-08-13 | 2021-08-25 | 8 | 2021-08-31 | [6 empty] | 2021-09-13 | 8 | 2021-09-13 | 2021-09-30 | 13 | [20 empty] | 2021-09-30 | 0 |  | 2021-10-27 | 27 | [19 empty] | 2021-11-02 |  | 2021-11-04 |  | 83
GFID100826 | SCE | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 5 | No | 2021-08-18 | 2021-08-18 | 0 | 2021-08-18 | [9 empty] | 2021-09-01 | 10 | 2021-09-01 | 2021-09-20 | 12 | [20 empty] | 2021-09-21 | 1 |  | 2021-10-16 | 25 | [21 empty] | 2021-11-09 |  | 83
GFID100828 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 210 | No | 2021-08-27 | 2021-08-27 | 0 | 2021-08-27 | 2021-09-08 | 7 | 2021-09-14 | [6 empty] | 2021-09-22 | 6 | 2021-09-22 | 2021-10-07 | 11 |  |  | 2021-12-08 | 2021-12-27 | 12 | [15 empty] | 2021-12-27 | 0 |  | 2022-01-11 | 15
GFID100849 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 10 | No | 2021-08-27 | 2021-08-27 | 0 | 2021-08-27 | [9 empty] | 2021-09-10 | 9 | 2021-09-10 | 2021-09-29 | 13 | [20 empty] | 2021-09-30 | 1 |  | 2021-10-20 | 20
GFID100850 | SCE | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 10 | No | 2021-08-27 | 2021-08-27 | 0 | 2021-08-27 | 2021-09-10 | 9 | 2021-09-17 | [6 empty] | 2021-09-29 | 8 | 2021-09-29 | 2021-10-25 | 17 | [20 empty] | 2021-10-26 | 1 |  | 2021-11-08 | 13 | [21 empty] | 2022-01-19 |  | 145
GFID100851 | SCE | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 10 | No | 2021-08-26 | 2021-08-26 | 0 | 2021-08-26 | [9 empty] | 2021-09-09 | 9 | 2021-09-09 | 2021-10-04 | 17 | [20 empty] | 2021-10-04 | 0 |  | 2021-11-24 | 51 | [21 empty] | 2021-12-22 |  | 118
GFID100853 | SCE | Non-NEM | Rule 21 Non-Export | Pending-InitialReview | Battery Storage | 174 | No | 2021-08-27 | 2021-08-27 | 0 | 2021-08-27 | 2021-09-03 | 5 | 2021-09-28 | 2021-10-06 | 6 | 2021-10-27 | 2021-11-01 | 3 | 2022-01-24 | 2022-01-26 | 2 | 2022-01-26 | 2022-02-15 | 14 |  |  | 2022-03-15
GFID100855 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 929.5 | No | 2021-10-26 | 2021-10-26 | 0 | 2021-10-26 | 2021-11-01 | 4 | 2021-11-03 | 2021-11-17 | 9 | 2021-11-18 |  |  |  | 2021-11-23 | 3 | 2021-11-23 | 2021-12-31 | 24 |  |  | 2022-01-14 | 2022-02-11 | 19 | [15 empty] | 2022-03-01 | 11 |  | 2022-03-11 | 10
GFID100856 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 10 | No | 2021-09-03 | 2021-09-03 | 0 | 2021-09-03 | 2021-09-17 | 9 | 2021-09-22 | [6 empty] | 2021-10-05 | 9 | 2021-10-05 | 2021-10-26 | 14 | [20 empty] | 2021-11-16 | 14 |  | 2021-12-15 | 29
GFID100857 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 10 | No | 2021-09-03 | 2021-09-03 | 0 | 2021-09-03 | [9 empty] | 2021-09-20 | 10 | 2021-09-20 | 2021-10-11 | 15 | [20 empty] | 2021-10-11 | 0 |  | 2022-01-10 | 91
GFID100858 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 10 | No | 2021-09-03 | 2021-09-03 | 0 | 2021-09-03 | [9 empty] | 2021-09-17 | 9 | 2021-09-17 | 2021-10-05 | 12 | [20 empty] | 2021-10-05 | 0 |  | 2021-11-03 | 29
GFID100861 | SCE | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 10 | No | 2021-09-07 | 2021-09-07 | 0 | 2021-09-07 | 2021-09-09 | 2 | 2021-09-10 | [6 empty] | 2021-09-10 | 0 | 2021-09-10 | 2021-09-16 | 4 | [20 empty] | 2021-09-16 | 0 |  | 2021-10-30 | 44 | [21 empty] | 2022-03-08 |  | 182
GFID100863 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 10 | No | 2021-09-07 | 2021-09-07 | 0 | 2021-09-07 | 2021-09-16 | 7 | 2021-09-22 | [6 empty] | 2021-09-22 | 0 | 2021-09-22 | 2021-09-29 | 5 | [20 empty] | 2021-09-29 | 0 |  | 2021-10-18 | 19
GFID100866 | SCE | Non-NEM | Rule 21 Non-Export | Resolved-Withdrawn | Battery Storage | 996.4 | No | 2021-09-09 | 2021-09-09 | 0 | 2021-09-09 | 2021-09-23 | 10
GFID100867 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 10 | No | 2021-09-10 | 2021-09-10 | 0 | 2021-09-10 | 2021-09-22 | 8 | 2021-09-23 | [6 empty] | 2021-10-05 | 8 | 2021-10-05 | 2021-10-26 | 14 | [20 empty] | 2021-10-26 | 0 |  | 2021-12-21 | 56
GFID100868 | SCE | Non-NEM | Rule 21 Non-Export | On Hold | Battery Storage | 715 | No | 2021-10-19 | 2021-10-19 | 0 | 2021-10-19 | 2021-10-29 | 8 | 2021-11-06 | 2021-11-20 | 8 | 2022-03-24
GFID100870 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 210 | No | 2021-09-22 | 2021-09-22 | 0 | 2021-09-22 | 2021-10-05 | 9 | 2021-10-11 | [6 empty] | 2021-10-22 | 8 | 2021-10-22 | 2021-11-10 | 13 |  |  | 2021-11-15 | 2021-12-20 | 23 | [15 empty] | 2021-12-20 | 0 |  | 2022-02-03 | 45
GFID100873 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 140 | No | 2021-09-14 | 2021-09-14 | 0 | 2021-09-14 | 2021-09-28 | 10 | 2021-10-04 | 2021-10-15 | 8 | 2021-10-22 | 2021-10-27 | 3 | 2021-10-27 | 2021-11-01 | 3 | 2021-11-01 | 2021-11-20 | 13 |  |  | 2022-02-02 | 2022-03-01 | 18 | [15 empty] | 2022-03-04 | 3 |  | 2022-03-31 | 27
GFID100876 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 10 | No | 2021-09-20 | 2021-09-20 | 0 | 2021-09-20 | [9 empty] | 2021-09-29 | 7 | 2021-09-29 | 2021-10-06 | 5 | [20 empty] | 2021-10-06 | 0 |  | 2021-10-18 | 12
GFID100877 | SCE | Non-NEM | Rule 21 Non-Export | Pending-InitialReview | Other (Microturbine) | 130 | No | 2021-11-05 | 2021-11-05 | 0 | 2021-11-05 | 2021-11-19 | 9 | 2021-12-27 | 2022-01-11 | 10 | 2022-02-24 |  |  |  | 2022-04-01 | 25
GFID100879 | SCE | Non-NEM | Rule 21 Non-Export | Resolved-Withdrawn | Battery Storage | 1162.2 | No | 2021-11-01 | 2021-11-01 | 0 | 2021-11-01 | 2021-11-15 | 9
GFID100880 | SCE | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Battery Storage | 625.8 | No | 2021-10-22 | 2021-10-22 | 0 | 2021-10-22 | 2021-11-04 | 9 | 2021-11-24 | 2021-12-08 | 8 |  |  |  |  | 2021-12-09 | 9 | 2021-12-09 | 2022-01-10 | 20 | [20 empty] | 2022-01-10 | 0
GFID100882 | SCE | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 210 | No | 2021-09-24 | 2021-09-24 | 0 | 2021-09-24 | 2021-10-08 | 10 | 2021-10-18 | [6 empty] | 2021-11-01 | 10 | 2021-11-01 | 2021-12-22 | 34 | [20 empty] | 2021-12-22 | 0 |  | 2022-02-09 | 49
GFID100884 | SCE | Non-NEM | Rule 21 Non-Export | Resolved-Withdrawn | Battery Storage | 250 | No | 2021-12-03 | 2021-12-03 | 0 | 2021-12-03 | 2021-12-17 | 10 | 2021-12-17 | 2022-01-03 | 9 | 2022-01-06 | 2022-01-11 | 3 | 2022-01-13 | 2022-01-19 | 3 | 2022-01-20
GFID100885 | SCE | Non-NEM | Rule 21 Non-Export | Resolved-Withdrawn | Battery Storage | 250 | No | 2021-12-04 | 2021-12-04 | 0 | 2021-12-04 | 2021-12-17 | 9 | 2021-12-17 | 2022-01-03 | 9 | 2022-01-06 | 2022-01-11 | 3 | 2022-01-13 | 2022-01-21 | 5 | 2022-01-21
GFID100888 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 10 | No | 2021-09-29 | 2021-09-29 | 0 | 2021-09-29 | [9 empty] | 2021-10-14 | 10 | 2021-10-14 | 2021-11-04 | 15 | [20 empty] | 2021-11-04 | 0 |  | 2021-12-17 | 43
GFID100889 | SCE | Non-NEM | Rule 21 Non-Export | Pending-InitialReview | Solar PV + Battery Storage + Internal Combustion Engine | 1956.5 | No | 2021-10-06 | 2021-10-06 | 0 | 2021-10-06 | 2021-10-21 | 10 | 2021-12-14 | 2022-01-07 | 16 | 2022-01-12 | 2022-01-20 | 5 | 2022-01-21 | 2022-01-28 | 5 | 2022-01-28 | 2022-02-18 | 15 |  |  | 2022-03-04
GFID100891 | SCE | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 7.6 | No | 2021-09-29 | 2021-09-29 | 0 | 2021-09-29 | 2021-10-20 | 14 | 2021-10-22 | 2021-11-04 | 9 | 2021-11-04 | 2021-11-10 | 4 | 2021-11-15 | 2021-11-15 | 0 | 2021-11-15 | 2021-12-07 | 14 | [20 empty] | 2021-12-07 | 0 |  | 2022-01-11 | 35 | [21 empty] | 2022-01-14 |  | 107
GFID100892 | SCE | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Battery Storage | 7.68 | No | 2021-10-22 | 2021-10-22 | 0 | 2021-10-22 | 2021-11-04 | 9 | 2021-12-15 | 2021-12-17 | 2 | 2021-12-21 | 2021-12-22 | 1 | 2022-01-07 | 2022-01-08 | 0 | 2022-01-08 | 2022-01-27 | 12 | [20 empty] | 2022-01-31 | 2
GFID100895 | SCE | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Battery Storage | 572 | No | 2021-10-01 | 2021-10-01 | 0 | 2021-10-01 | 2021-10-18 | 10 | 2021-10-29 | [6 empty] | 2021-11-16 | 11 | 2021-11-16 | 2021-12-22 | 24 | [20 empty] | 2021-12-22 | 0
GFID100908 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 10 | No | 2021-10-12 | 2021-10-12 | 0 | 2021-10-12 | 2021-10-22 | 7 | 2021-10-25 | [6 empty] | 2021-11-03 | 7 | 2021-11-03 | 2021-11-15 | 7 | [20 empty] | 2021-11-15 | 0 |  | 2021-11-23 | 8
GFID100909 | SCE | Non-NEM | Rule 21 Non-Export | Resolved-Withdrawn | Battery Storage | 357.5 | No | 2021-11-15 | 2021-11-15 | 0 | 2021-11-15 | 2021-12-06 | 13
GFID100913 | SCE | Non-NEM | Rule 21 Non-Export | Resolved-Withdrawn | Battery Storage | 10 | No | 2021-10-18 | 2021-10-18 | 0 | 2021-10-18 | 2021-10-20 | 2 | 2021-10-20 | 2021-11-01 | 8 | 2021-11-30
GFID100917 | SCE | Non-NEM | Rule 21 Non-Export | Resolved-Withdrawn | Solar PV + Battery Storage + Internal Combustion Engine | 1968 | No | 2021-11-04 | 2021-11-04 | 0 | 2021-11-04 | 2021-11-18 | 9 | 2021-12-04 | 2021-12-28 | 15 | 2022-01-21
GFID100920 | SCE | Non-NEM | Rule 21 Non-Export | Resolved-Withdrawn | Solar PV | 360 | No | 2021-11-15 | 2021-11-15 | 0 | 2021-11-15 | 2021-12-01 | 10 | 2021-12-15 | 2021-12-21 | 4 | 2022-01-06
GFID100921 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Resubmission | Battery Storage | 804.6 | No | 2021-10-22 | 2021-10-22 | 0 | 2021-10-22 | 2021-11-01 | 6 | 2021-11-16 | 2021-11-24 | 6 | 2021-12-08
GFID100922 | SCE | Non-NEM | Rule 21 Non-Export | Pending-InitialReview | Battery Storage | 1287 | No | 2021-10-22 | 2021-10-22 | 0 | 2021-10-22 | 2021-11-03 | 8 | 2021-11-16 | 2021-12-01 | 9 | 2022-01-12 |  |  |  | 2022-01-18 | 3 | 2022-01-18 | 2022-02-12 | 18 | 2022-03-09 | 16
GFID100923 | SCE | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Battery Storage | 362.4 | No | 2021-11-17 | 2021-11-17 | 0 | 2021-11-17 | 2021-12-03 | 10 | 2022-02-04 | 2022-02-09 | 3 | 2022-02-20 | 2022-03-01 | 5 | 2022-03-01 | 2022-03-08 | 5 | 2022-03-08 | 2022-03-24 | 12
GFID100924 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Resubmission | Battery Storage | 983.4 | No | 2021-11-22 | 2021-11-22 | 0 | 2021-11-22 | 2021-12-08 | 10 | 2022-03-14 | 2022-03-23 | 7 | 2022-03-24
GFID100927 | SCE | Non-NEM | Rule 21 Non-Export | Resolved-Withdrawn | Battery Storage | 10 | No | 2021-11-08 | 2021-11-08 | 0 | 2021-11-08 | 2021-11-24 | 11 | 2021-11-30 | 2021-12-14 | 10 | 2022-01-06 |  |  |  | 2022-01-13 | 5 | 2022-01-13 | 2022-01-28 | 10 | [20 empty] | 2022-01-28 | 0
GFID100928 | SCE | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 7.6 | No | 2021-10-21 | 2021-10-21 | 0 | 2021-10-21 | 2021-11-04 | 10 | 2021-11-12 | 2021-11-29 | 9 | 2021-11-29 | 2021-12-06 | 5 | 2022-01-18 | 2022-01-18 | 0 | 2022-01-18 | 2022-02-08 | 15 | [20 empty] | 2022-02-09 | 1 |  | 2022-03-08 | 27 | [21 empty] | 2022-03-17 |  | 147
GFID100934 | SCE | Non-NEM | Rule 21 Non-Export | Resolved-Withdrawn | Internal Combustion Engine | 160 | No | 2022-01-13 | 2022-01-13 | 0 | 2022-01-13 | 2022-01-27 | 9 | 2022-01-27 | 2022-02-08 | 8 | 2022-02-14
GFID100936 | SCE | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Solar PV + Battery Storage + Fuel Cell | 1377.4 | No | 2021-12-08 | 2021-12-08 | 0 | 2021-12-08 | [9 empty] | 2021-12-16 | 6 | 2021-12-16 | 2022-01-05 | 12 | [20 empty] | 2022-01-05 | 0
GFID100940 | SCE | Non-NEM | Rule 21 Non-Export | Resolved-Withdrawn | Solar PV + Battery Storage | 1285.5 | No | 2021-10-27 | 2021-10-27 | 0 | 2021-10-27 | 2021-11-09 | 9 | 2021-11-12 | 2021-11-29 | 9 | 2021-12-07
GFID100942 | SCE | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 10 | No | 2021-11-09 | 2021-11-09 | 0 | 2021-11-09 | [9 empty] | 2021-11-15 | 3 | 2021-11-15 | 2021-11-23 | 6 | [20 empty] | 2021-12-17 | 15 |  | 2022-01-14 | 28 | [21 empty] | 2022-02-01 |  | 84
GFID100943 | SCE | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 20 | No | 2021-11-26 | 2021-11-26 | 0 | 2021-11-26 | [9 empty] | 2021-12-06 | 5 | 2021-12-06 | 2021-12-27 | 14 | [20 empty] | 2021-12-27 | 0 |  | 2022-01-21 | 25 | [21 empty] | 2022-02-01 |  | 67
GFID100944 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Construction | Other (Microturbine) | 130 | No | 2021-10-27 | 2021-10-27 | 0 | 2021-10-27 | 2021-11-01 | 3 | 2021-11-22 | 2021-12-13 | 13 | 2021-12-13 |  |  |  | 2021-12-16 | 3 | 2021-12-16 | 2021-12-30 | 9 | [20 empty] | 2021-12-30 | 0 |  | 2022-02-07 | 39
GFID100945 | SCE | Non-NEM | Rule 21 Non-Export | Pending-InitialReview | Other (Microturbine) | 1180 | No | 2021-11-24 | 2021-11-24 | 0 | 2021-11-24 | 2021-12-10 | 10 | 2022-01-03 | 2022-01-18 | 10 | 2022-01-25 | 2022-02-01 | 5 | 2022-02-18 | 2022-02-23 | 2 | 2022-02-23 | 2022-03-17 | 16 | 2022-03-17 | 0
GFID100946 | SCE | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Battery Storage | 7.68 | No | 2021-11-04 | 2021-11-04 | 0 | 2021-11-04 | 2021-11-19 | 10 | 2021-12-15 | [6 empty] | 2021-12-27 | 7 | 2021-12-27 | 2022-01-13 | 12 | [20 empty] | 2022-01-12 | 0
GFID100949 | SCE | Non-NEM | Rule 21 Non-Export | Pending-InitialReview | Solar PV + Battery Storage + Internal Combustion Engine | 2322 | No | 2021-11-19 | 2021-11-19 | 0 | 2021-11-19 | 2021-12-16 | 17 | 2021-12-21 | [6 empty] | 2021-12-30 | 6 | 2021-12-30 | 2022-01-18 | 11 | 2022-02-09 | 16
GFID100950 | SCE | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 10 | No | 2021-11-10 | 2021-11-10 | 0 | 2021-11-10 | 2021-11-16 | 3 | 2021-11-16 | [6 empty] | 2021-11-16 | 0 | 2021-11-16 | 2021-12-14 | 18 | [20 empty] | 2021-12-14 | 0 |  | 2021-12-21 | 7 | [21 empty] | 2022-01-31 |  | 82
GFID100951 | SCE | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Battery Storage | 8.96 | No | 2021-11-09 | 2021-11-09 | 0 | 2021-11-09 | 2021-11-24 | 10 | 2021-12-14 |  |  | 2021-12-21 |  |  |  | 2021-12-21 | 0 | 2021-12-21 | 2022-01-12 | 14 | [20 empty] | 2022-01-18 | 3
GFID100952 | SCE | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Battery Storage | 9 | No | 2021-11-15 | 2021-11-15 | 0 | 2021-11-15 | 2021-11-29 | 8 | 2021-12-21 | 2022-01-05 | 9 | 2022-01-05 | 2022-01-10 | 3 | 2022-03-10 | 2022-03-10 | 0 | 2022-03-11 | 2022-03-30 | 13
GFID100953 | SCE | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Battery Storage | 6.4 | No | 2021-11-15 | 2021-11-15 | 0 | 2021-11-15 | 2021-11-30 | 9 | 2021-12-14 | [6 empty] | 2021-12-22 | 6 | 2021-12-22 | 2022-01-12 | 13 | [20 empty] | 2022-01-12 | 0
GFID100954 | SCE | Non-NEM | Rule 21 Non-Export | Resolved-Withdrawn | Battery Storage | 8.96 | No | 2021-11-15 | 2021-11-15 | 0 | 2021-11-15 | 2021-11-18 | 3 | 2021-12-20 | 2021-12-24 | 3 | 2021-12-27 |  |  |  | 2021-12-28 | 1 | 2021-12-28 | 2022-01-12 | 10 | [20 empty] | 2022-01-18 | 3
GFID100955 | SCE | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Battery Storage | 6.4 | No | 2021-11-15 | 2021-11-15 | 0 | 2021-11-15 | 2021-12-01 | 10 | 2021-12-21 | [6 empty] | 2022-01-04 | 8 | 2022-01-04 | 2022-01-22 | 12 | [20 empty] | 2022-01-21 | 0
GFID100959 | SCE | Non-NEM | Rule 21 Non-Export | Resolved-Withdrawn | Battery Storage | 6.4 | No | 2021-11-15 | 2021-11-15 | 0 | 2021-11-15 | 2021-11-25 | 7 | 2021-12-14 | 2021-12-22 | 6
GFID100960 | SCE | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Battery Storage | 7.68 | No | 2021-11-15 | 2021-11-15 | 0 | 2021-11-15 | 2021-11-18 | 3 | 2021-12-14 | 2021-12-15 | 1 | 2021-12-22 |  |  |  | 2021-12-27 | 2 | 2021-12-27 | 2022-01-13 | 12 | [20 empty] | 2022-01-13 | 0
GFID100961 | SCE | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Battery Storage | 10.24 | No | 2021-11-15 | 2021-11-15 | 0 | 2021-11-15 | 2021-12-08 | 15 | 2021-12-16 | [6 empty] | 2021-12-29 | 8 | 2021-12-29 | 2022-01-18 | 12 | [20 empty] | 2022-01-18 | 0
GFID100962 | SCE | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Battery Storage | 10.24 | No | 2021-11-15 | 2021-11-15 | 0 | 2021-11-15 | 2021-11-27 | 7 | 2021-12-08 | 2021-12-20 | 8 | 2021-12-20 |  |  |  | 2021-12-27 | 4 | 2021-12-27 | 2022-01-14 | 13 | [20 empty] | 2022-01-14 | 0
GFID100963 | SCE | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Battery Storage | 18 | No | 2021-11-15 | 2021-11-15 | 0 | 2021-11-15 | 2021-11-24 | 7 | 2021-12-08 | 2021-12-21 | 9 | 2021-12-22 |  |  |  | 2021-12-30 | 5 | 2021-12-30 | 2022-01-19 | 12 | [20 empty] | 2022-01-19 | 0
GFID100964 | SCE | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Battery Storage | 18 | No | 2021-11-15 | 2021-11-15 | 0 | 2021-11-15 | 2021-11-24 | 7 | 2021-12-08 | 2021-12-17 | 7 | 2021-12-21 |  |  |  | 2021-12-22 | 1 | 2021-12-22 | 2022-01-10 | 11 | [20 empty] | 2022-01-10 | 0
GFID100966 | SCE | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Battery Storage | 18 | No | 2021-11-15 | 2021-11-15 | 0 | 2021-11-15 | 2021-12-08 | 15 | 2021-12-20 | 2022-01-04 | 9 | 2022-01-05 | 2022-01-06 | 1 | 2022-03-16 | 2022-03-16 | 0 | 2022-03-16
GFID100972 | SCE | Non-NEM | Rule 21 Non-Export | Pending Review | Solar PV + Battery Storage | 1796 | No | 2021-12-06 | 2021-12-06 | 0 | 2021-12-06 | 2021-12-17 | 9 | 2022-01-21 | 2022-02-04 | 10 | 2022-02-14
GFID100973 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 210 | No | 2021-11-24 | 2021-11-24 | 0 | 2021-11-24 | 2021-12-10 | 10 | 2021-12-15 | 2021-12-21 | 4 | 2021-12-23 |  |  |  | 2022-01-04 | 6 | 2022-01-04 | 2022-01-24 | 13 | [20 empty] | 2022-01-24 | 0 |  | 2022-02-23 | 30
GFID100974 | SCE | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Solar PV + Battery Storage | 1250 | No | 2021-12-06 | 2021-12-06 | 0 | 2021-12-06 | 2021-12-16 | 8 | 2021-12-21 | [6 empty] | 2021-12-28 | 4 | 2021-12-28 | 2022-01-18 | 13 | 2022-02-08 | 15 | [18 empty] | 2022-03-28 | 0
GFID100975 | SCE | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Solar PV + Battery Storage | 1250 | No | 2021-12-06 | 2021-12-06 | 0 | 2021-12-06 | 2021-12-13 | 5 | 2021-12-21 | [6 empty] | 2021-12-23 | 2 | 2022-01-13 | 2022-01-14 | 1 | 2022-01-18 | 1 | [18 empty] | 2022-01-25 | 0
GFID100976 | SCE | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Solar PV + Battery Storage | 1250 | No | 2021-12-06 | 2021-12-06 | 0 | 2021-12-06 | 2021-12-16 | 8 | 2021-12-21 | [6 empty] | 2021-12-28 | 4 | 2021-12-28 | 2022-01-18 | 13 | 2022-02-08 | 15
GFID100977 | SCE | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Solar PV + Battery Storage | 839 | No | 2021-12-06 | 2021-12-06 | 0 | 2021-12-06 | 2021-12-13 | 5 | 2021-12-21 | [6 empty] | 2021-12-23 | 2 | 2022-01-13 | 2022-01-14 | 1 | 2022-01-18 | 1 | [18 empty] | 2022-01-25 | 0
GFID100978 | SCE | Non-NEM | Rule 21 Non-Export | Resolved-Withdrawn | Battery Storage | 280 | No | 2021-11-17 | 2021-11-17 | 0 | 2021-11-17 | 2021-12-01 | 8 | 2021-12-18 | 2021-12-30 | 7 | 2022-01-29 | 2022-02-04 | 4
GFID100979 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 10 | No | 2021-11-16 | 2021-11-16 | 0 | 2021-11-16 | [9 empty] | 2021-12-02 | 10 | 2021-12-02 | 2021-12-22 | 14 | [20 empty] | 2021-12-22 | 0 |  | 2022-03-25 | 93
GFID100981 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 10 | No | 2021-12-09 | 2021-12-09 | 0 | 2021-12-09 | [9 empty] | 2021-12-22 | 9 | 2021-12-22 | 2022-01-12 | 13 | [20 empty] | 2022-01-12 | 0 |  | 2022-02-20 | 39
GFID100982 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 10 | No | 2021-11-17 | 2021-11-17 | 0 | 2021-11-17 | [9 empty] | 2021-12-03 | 10 | 2021-12-03 | 2021-12-22 | 13 | [20 empty] | 2021-12-22 | 0 |  | 2022-03-23 | 91
GFID100988 | SCE | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Battery Storage | 116 | No | 2021-11-22 | 2021-11-22 | 0 | 2021-11-22 | 2021-12-07 | 9 | 2022-02-04 | 2022-02-17 | 9 | 2022-02-28 |  |  |  | 2022-03-04 | 4 | 2022-03-04 | 2022-03-25 | 15
GFID100989 | SCE | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Battery Storage | 174 | No | 2021-11-22 | 2021-11-22 | 0 | 2021-11-22 | 2021-12-07 | 9 | 2022-02-04 | 2022-02-16 | 8 | 2022-02-28 | 2022-03-04 | 4 | 2022-03-04 | 2022-03-11 | 5 | 2022-03-11 | 2022-03-30 | 13
GFID100990 | SCE | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Battery Storage | 116 | No | 2021-11-22 | 2021-11-22 | 0 | 2021-11-22 | 2021-12-01 | 5 | 2022-02-04 | [6 empty] | 2022-02-10 | 4 | 2022-02-10 | 2022-03-10 | 19
GFID100991 | SCE | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Battery Storage | 174 | No | 2021-11-22 | 2021-11-22 | 0 | 2021-11-22 | 2021-12-03 | 7 | 2022-02-04 | [6 empty] | 2022-02-16 | 8 | 2022-02-16 | 2022-03-10 | 15
GFID100992 | SCE | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 10 | No | 2021-11-22 | 2021-11-22 | 0 | 2021-11-22 | 2021-12-08 | 10 | 2021-12-08 | [6 empty] | 2021-12-15 | 5 | 2021-12-15 | 2022-01-08 | 15 | [20 empty] | 2022-01-07 | 0 |  | 2022-02-10 | 34 | [21 empty] | 2022-02-17 |  | 87
GFID100993 | SCE | Non-NEM | Rule 21 Non-Export | Resolved-Withdrawn | Battery Storage | 375.5 | No | 2021-11-22 | 2021-11-22 | 0 | 2021-11-22 | 2021-12-08 | 10
GFID100994 | SCE | Non-NEM | Rule 21 Non-Export | Pending-InitialReview | Battery Storage | 357.5 | No | 2022-02-11 | 2022-02-11 | 0 | 2022-02-11 | 2022-02-24 | 8 | 2022-03-04 | [6 empty] | 2022-03-11 | 5 | 2022-03-31
GFID100995 | SCE | Non-NEM | Rule 21 Non-Export | Pending-InitialReview | Battery Storage | 210 | No | 2021-11-22 | 2021-11-22 | 0 | 2021-11-22 | 2021-12-08 | 10 | 2021-12-21 | 2022-01-06 | 10 | 2022-01-28 |  |  |  | 2022-03-22 | 36 | 2022-03-22
GFID101000 | SCE | Non-NEM | Rule 21 Non-Export | Pending-InitialReview | Battery Storage | 10 | No | 2022-03-11 | 2022-03-11 | 0 | 2022-03-11 | 2022-03-23 | 8 | 2022-03-24 | [6 empty] | 2022-03-25 | 1 | 2022-03-25
GFID101005 | SCE | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Battery Storage | 10 | No | 2021-12-01 | 2021-12-01 | 0 | 2021-12-01 | 2021-12-15 | 10 | 2022-01-17 | 2022-01-26 | 6 | 2022-01-27 | 2022-02-01 | 3 | 2022-02-11 | 2022-02-22 | 6 | 2022-02-22 | 2022-03-08 | 10 | [20 empty] | 2022-03-09 | 1
GFID101009 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 10 | No | 2021-12-06 | 2021-12-06 | 0 | 2021-12-06 | 2021-12-17 | 9 | 2021-12-17 | 2021-12-29 | 7 |  |  |  |  | 2021-12-30 | 8 | 2021-12-30 | 2022-01-18 | 11 | [20 empty] | 2022-01-18 | 0 |  | 2022-03-09 | 50
GFID101013 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 10 | No | 2021-12-04 | 2021-12-04 | 0 | 2021-12-04 | 2021-12-15 | 7 | 2021-12-16 | [6 empty] | 2021-12-22 | 4 | 2021-12-22 | 2022-01-25 | 21 | [20 empty] | 2022-01-25 | 0 |  | 2022-02-11 | 17
GFID101014 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 10 | No | 2021-12-04 | 2021-12-04 | 0 | 2021-12-04 | [9 empty] | 2021-12-16 | 8 | 2021-12-16 | 2022-01-07 | 14 | [20 empty] | 2022-01-06 | 0 |  | 2022-03-18 | 71
GFID101015 | SCE | Non-NEM | Rule 21 Non-Export | Pending-CommissioningTest | Battery Storage | 5 | No | 2022-01-27 | 2022-01-27 | 0 | 2022-01-27 | 2022-02-01 | 3 | 2022-02-04 | [6 empty] | 2022-02-09 | 3 | 2022-02-09 | 2022-02-25 | 11 | [20 empty] | 2022-02-25 | 0 |  | 2022-03-23 | [24 empty] | 0
GFID101016 | SCE | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 10 | No | 2021-12-06 | 2021-12-06 | 0 | 2021-12-06 | [9 empty] | 2021-12-16 | 8 | 2021-12-16 | 2022-01-06 | 13 | [20 empty] | 2022-01-06 | 0 |  | 2022-02-11 | 36 | [21 empty] | 2022-02-17 |  | 73
GFID101017 | SCE | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Battery Storage | 10 | No | 2021-12-06 | 2021-12-06 | 0 | 2021-12-06 | 2021-12-17 | 9 | 2021-12-17 | 2021-12-30 | 8 | 2022-03-03 |  |  |  | 2022-03-07 | 2 | 2022-03-07 | 2022-03-23 | 12 | [20 empty] | 2022-03-23 | 0
GFID101018 | SCE | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 10 | No | 2021-12-06 | 2021-12-06 | 0 | 2021-12-06 | 2021-12-10 | 4 | 2021-12-10 | [6 empty] | 2021-12-23 | 9 | 2021-12-23 | 2022-01-12 | 12 | [20 empty] | 2022-01-12 | 0 |  | 2022-03-01 | 48 | [21 empty] | 2022-03-11 |  | 95
GFID101019 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 15 | No | 2021-12-06 | 2021-12-06 | 0 | 2021-12-06 | 2021-12-17 | 9 | 2022-01-07 | 2022-01-18 | 6 | 2022-01-19 | 2022-01-26 | 5 | 2022-02-22 | 2022-02-22 | 0 | 2022-02-28 | 2022-03-15 | 11 | [20 empty] | 2022-03-24 | 7 |  | 2022-03-28 | 4
GFID101020 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 10 | No | 2021-12-06 | 2021-12-06 | 0 | 2021-12-06 | 2021-12-17 | 9 | 2021-12-17 | 2021-12-29 | 7 | 2021-12-30 |  |  |  | 2022-01-04 | 2 | 2022-01-04 | 2022-01-22 | 12 | [20 empty] | 2022-01-21 | 0 |  | 2022-03-04 | 42
GFID101021 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 10 | No | 2021-12-06 | 2021-12-06 | 0 | 2021-12-06 | 2021-12-16 | 8 | 2021-12-17 | 2021-12-29 | 7 | 2021-12-29 | 2022-01-05 | 4 | 2022-01-13 | 2022-01-18 | 2 | 2022-01-18 | 2022-01-28 | 8 | [20 empty] | 2022-01-28 | 0 |  | 2022-03-17 | 48
GFID101022 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 10 | No | 2021-12-06 | 2021-12-06 | 0 | 2021-12-06 | 2021-12-08 | 2 | 2022-01-17 | 2022-01-26 | 6 | 2022-01-27 |  |  |  | 2022-01-31 | 2 | 2022-01-31 | 2022-02-16 | 12 | [20 empty] | 2022-02-17 | 1 |  | 2022-02-28 | 11
GFID101024 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 10 | No | 2021-12-06 | 2021-12-06 | 0 | 2021-12-06 | 2021-12-09 | 3 | 2021-12-10 | [6 empty] | 2021-12-20 | 6 | 2021-12-20 | 2022-01-11 | 14 | [20 empty] | 2022-01-10 | 0 |  | 2022-02-28 | 49
GFID101025 | SCE | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Battery Storage | 10 | No | 2021-12-08 | 2021-12-08 | 0 | 2021-12-08 | 2021-12-17 | 7 | 2022-01-06 | 2022-01-06 | 0 |  |  |  |  | 2022-01-20 | 9 | 2022-01-20 | 2022-02-08 | 13 | [20 empty] | 2022-02-08 | 0
GFID101027 | SCE | Non-NEM | Rule 21 Non-Export | Resolved-Withdrawn | Solar PV | 24.9165 | No | 2021-12-29 | 2021-12-29 | 0 | 2021-12-29
GFID101028 | SCE | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Battery Storage | 10 | No | 2021-12-08 | 2021-12-08 | 0 | 2021-12-08 | 2021-12-20 | 8 | 2021-12-21 | 2022-01-06 | 10 | 2022-01-06 |  |  |  | 2022-01-13 | 5 | 2022-01-13 | 2022-01-28 | 10 | [20 empty] | 2022-01-28 | 0
GFID101031 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Resubmission | Battery Storage | 7.6 | No | 2022-03-08 | 2022-03-08 | 0 | 2022-03-08 | 2022-03-18 | 8
GFID101037 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 15 | No | 2021-12-30 | 2021-12-30 | 0 | 2021-12-30 | 2022-01-14 | 10 | 2022-01-14 | [6 empty] | 2022-01-25 | 6 | 2022-01-25 | 2022-02-12 | 13 | [20 empty] | 2022-02-17 | 3 |  | 2022-03-15 | 26
GFID101039 | SCE | Non-NEM | Rule 21 Non-Export | LongTerm-Management | Battery Storage | 10 | No | 2021-12-30 | 2021-12-30 | 0 | 2021-12-30 | 2022-01-10 | 6 | 2022-01-10 | [6 empty] | 2022-01-26 | 11 | 2022-01-26 | 2022-02-11 | 12 | [20 empty] | 2022-02-11 | 0 |  | 2022-03-17 | 34 | [21 empty] | 2022-03-23 |  | 83
GFID101042 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 7.6 | No | 2021-12-17 | 2021-12-17 | 0 | 2021-12-17 | 2021-12-21 | 2 | 2021-12-23 | 2022-01-04 | 6 | 2022-01-11 |  |  |  | 2022-02-09 | 20 | 2022-02-09 | 2022-03-01 | 13 | [20 empty] | 2022-03-05 | 3 |  | 2022-03-31 | 26
GFID101043 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 10 | No | 2021-12-20 | 2021-12-20 | 0 | 2021-12-20 | [9 empty] | 2022-01-05 | 10 | 2022-01-05 | 2022-01-25 | 13 | [20 empty] | 2022-01-25 | 0 |  | 2022-03-02 | 36
GFID101044 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 10 | No | 2021-12-20 | 2021-12-20 | 0 | 2021-12-20 | [9 empty] | 2021-12-30 | 7 | 2021-12-30 | 2022-01-14 | 10 | [20 empty] | 2022-01-13 | 0 |  | 2022-02-08 | 26
GFID101052 | SCE | Non-NEM | Rule 21 Non-Export | Resolved-Withdrawn | Solar PV | 16 | No | 2022-01-13 | 2022-01-13 | 0 | 2022-01-13 | 2022-01-28 | 10 | 2022-01-28 | 2022-02-10 | 9 | 2022-02-14
GFID101054 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Withdrawn | Battery Storage | 18 | No | 2022-01-12 | 2022-01-12 | 0 | 2022-01-12 | 2022-01-26 | 9 | 2022-02-17 | 2022-03-01 | 7 | 2022-03-07
GFID101055 | SCE | Non-NEM | Rule 21 Non-Export | Resolved-Withdrawn | Battery Storage | 18 | No | 2022-01-03 | 2022-01-03 | 0 | 2022-01-03 | 2022-01-03 | 0 | 2022-01-18 | 2022-01-31 | 9
GFID101059 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 10 | No | 2021-12-30 | 2021-12-30 | 0 | 2021-12-30 | 2022-01-12 | 8 | 2022-01-12 | [6 empty] | 2022-01-12 | 0 | 2022-01-12 | 2022-01-27 | 10 | [20 empty] | 2022-01-27 | 0 |  | 2022-02-28 | 32
GFID101062 | SCE | Non-NEM | Rule 21 Non-Export | Pending-MomentaryParallel Review | Internal Combustion Engine | 2750 | No | 2022-01-14 | 2022-01-14 | 0 | 2022-01-14 | 2022-01-28 | 9 | 2022-01-31 | [6 empty] | 2022-02-10 | 8
GFID101064 | SCE | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Battery Storage | 10 | No | 2022-02-04 | 2022-02-04 | 0 | 2022-02-04 | 2022-02-12 | 5 | 2022-02-24 | 2022-03-08 | 8 |  |  |  |  | 2022-03-09 | 9 | 2022-03-09 | 2022-03-25 | 12 | [20 empty] | 2022-03-28 | 1 | [26 empty] | 0
GFID101070 | SCE | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Battery Storage | 210 | No | 2022-02-08 | 2022-02-08 | 0 | 2022-02-08 | 2022-02-24 | 11 | 2022-03-11 | [6 empty] | 2022-03-15 | 2 | 2022-03-15 | 2022-03-31 | 11
GFID101075 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Resubmission | Solar PV + Battery Storage | 382.16 | No | 2022-01-12 | 2022-01-12 | 0 | 2022-01-12 | 2022-01-26 | 9 | 2022-03-24 | 2022-03-31 | 4
GFID101077 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 10 | No | 2022-01-13 | 2022-01-13 | 0 | 2022-01-13 | 2022-01-27 | 9 | 2022-01-28 | [6 empty] | 2022-02-09 | 8 | 2022-02-09 | 2022-03-01 | 13 | [20 empty] | 2022-03-01 | 0 |  | 2022-03-23 | 22
GFID101079 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 10 | No | 2022-01-18 | 2022-01-18 | 0 | 2022-01-18 | [9 empty] | 2022-01-26 | 6 | 2022-01-26 | 2022-02-11 | 12 | [20 empty] | 2022-02-15 | 2 |  | 2022-03-02 | 15
GFID101082 | SCE | Non-NEM | Rule 21 Non-Export | Pending-CommissioningTest | Solar PV + Battery Storage + Internal Combustion Engine | 31152.44 | No | 2022-01-22 | 2022-01-22 | 0 | 2022-01-22 | 2022-02-03 | 8 | 2022-02-11 | [59 empty] | 0
GFID101084 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 10 | No | 2022-01-28 | 2022-01-28 | 0 | 2022-01-28 | [9 empty] | 2022-02-03 | 4 | 2022-02-03 | 2022-02-26 | 15 | [20 empty] | 2022-03-03 | 3 | [26 empty] | 0
GFID101085 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Withdrawn | Battery Storage | 1072.5 | No | 2022-01-19 | 2022-01-19 | 0 | 2022-01-19 | 2022-02-05 | 12 | 2022-02-11 | 2022-02-25 | 9 | 2022-03-02 | [56 empty] | 0
GFID101089 | SCE | Non-NEM | Rule 21 Non-Export | Pending-InitialReview | Battery Storage | 10 | No | 2022-03-25 | 2022-03-25 | 0 | 2022-03-25 | 2022-03-29 | 2 | 2022-03-30 | [6 empty] | 2022-03-30 | 0 | 2022-03-30
GFID101090 | SCE | Non-NEM | Rule 21 Non-Export | Pending Review | Battery Storage | 10 | No | 2022-03-24 | 2022-03-24 | 0 | 2022-03-24
GFID101091 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Resubmission | Battery Storage | 429 | No | 2022-03-18 | 2022-03-18 | 0 | 2022-03-18 | 2022-03-29 | 7
GFID101092 | SCE | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Battery Storage | 15 | No | 2022-01-27 | 2022-01-27 | 0 | 2022-01-27 | [9 empty] | 2022-02-08 | 8 | 2022-02-08 | 2022-02-28 | 13 | [20 empty] | 2022-02-28 | 0 | [26 empty] | 0
GFID101094 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Construction | Battery Storage | 10 | No | 2022-01-26 | 2022-01-26 | 0 | 2022-01-26 | [9 empty] | 2022-02-08 | 9 | 2022-02-08 | 2022-02-24 | 11 | [20 empty] | 2022-02-24 | 0 |  | 2022-03-06 | [24 empty] | 0
GFID101098 | SCE | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Battery Storage | 210 | No | 2022-02-02 | 2022-02-02 | 0 | 2022-02-02 | 2022-02-15 | 9 | 2022-02-23 | 2022-03-07 | 8 | 2022-03-10 |  |  |  | 2022-03-10 | 0 | 2022-03-10 | 2022-03-28 | 12 | [20 empty] | 2022-03-29 | 1 | [26 empty] | 0
GFID101100 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Resubmission | Battery Storage | 500 | No | 2022-03-17 | 2022-03-17 | 0 | 2022-03-17 | 2022-03-29 | 8
GFID101102 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Resubmission | Battery Storage | 250 | No | 2022-03-17 | 2022-03-17 | 0 | 2022-03-17 | 2022-03-30 | 9
GFID101105 | SCE | Non-NEM | Rule 21 Non-Export | Pending Review | Battery Storage | 180 | No | 2022-03-11 | 2022-03-11 | 0 | 2022-03-11 | 2022-03-24 | 9 | 2022-03-29 | 2022-03-30 | 1
GFID101113 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Withdrawn | Solar PV + Battery Storage | 750 | No | 2022-03-02 | 2022-03-02 | 0 | 2022-03-02 | 2022-03-15 | 9
GFID101116 | SCE | Non-NEM | Rule 21 Non-Export | Pending-InitialReview | Battery Storage | 15 | No | 2022-02-16 | 2022-02-16 | 0 | 2022-02-16 | 2022-03-01 | 8 | 2022-03-10 | [6 empty] | 2022-03-24 | 10 | 2022-03-24
GFID101118 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Resubmission | Battery Storage | 572 | No | 2022-02-17 | 2022-02-17 | 0 | 2022-02-17 | 2022-03-01 | 7
GFID101125 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Withdrawn | Battery Storage | 572 | No | 2022-02-23 | 2022-02-23 | 0 | 2022-02-23 | 2022-03-08 | 9
GFID101140 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Resubmission | Solar PV + Battery Storage | 448.2 | No | 2022-03-05 | 2022-03-05 | 0 | 2022-03-05 | 2022-03-15 | 6
GFID101141 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Resubmission | Solar PV + Battery Storage | 1160 | No | 2022-03-05 | 2022-03-05 | 0 | 2022-03-05 | 2022-03-18 | 9
GFID101142 | SCE | Non-NEM | Rule 21 Non-Export | Pending-InitialReview | Battery Storage | 7.6 | No | 2022-03-07 | 2022-03-07 | 0 | 2022-03-07 | 2022-03-18 | 9 | 2022-03-22 | [6 empty] | 2022-04-06 | 10
GFID101143 | SCE | Non-NEM | Rule 21 Non-Export | Pending-InitialReview | Battery Storage | 10 | No | 2022-03-08 | 2022-03-08 | 0 | 2022-03-08 | [9 empty] | 2022-03-21 | 9 | 2022-03-21
GFID101145 | SCE | Non-NEM | Rule 21 Non-Export | Pending-ContractDevelopment | Battery Storage | 357.5 | No | 2022-03-09 | 2022-03-09 | 0 | 2022-03-09 | [9 empty] | 2022-03-21 | 8 | 2022-03-21
GFID101147 | SCE | Non-NEM | Rule 21 Non-Export | Pending Review | Battery Storage | 286 | No | 2022-03-16 | 2022-03-16 | 0 | 2022-03-16 | 2022-03-28 | 8
GFID101156 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Resubmission | Battery Storage | 643 | No | 2022-03-15 | 2022-03-15 | 0 | 2022-03-15 | 2022-03-28 | 9
GFID101157 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Withdrawn | Solar PV | 50 | No | 2022-03-16 | 2022-03-16 | 0 | 2022-03-16
GFID101158 | SCE | Non-NEM | Rule 21 Non-Export | Pending-InitialReview | Battery Storage | 490 | No | 2022-03-16 | 2022-03-16 | 0 | 2022-03-16 | [9 empty] | 2022-03-30 | 10 | 2022-03-30
GFID101160 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Resubmission | Battery Storage | 429 | No | 2022-03-16 | 2022-03-16 | 0 | 2022-03-16 | 2022-03-29 | 9
GFID101162 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Resubmission | Battery Storage | 214.5 | No | 2022-03-17 | 2022-03-17 | 0 | 2022-03-17
GFID101170 | SCE | Non-NEM | Rule 21 Non-Export | Pending Review | Battery Storage | 10 | No | 2022-03-21 | 2022-03-21 | 0 | 2022-03-21 | 2022-03-29 | 6 | 2022-03-29
GFID101178 | SCE | Non-NEM | Rule 21 Non-Export | Pending-Resubmission | Battery Storage | 20 | No | 2022-03-24 | 2022-03-24 | 0 | 2022-03-24 | 2022-03-31 | 4
GFID101181 | SCE | Non-NEM | Rule 21 Non-Export | Pending Review | Battery Storage | 429 | No | 2022-03-25 | 2022-03-25 | 0 | 2022-03-25
GFID8745 | SCE | Non-NEM | Rule 21 Non-Export | Application Review In Progress | Internal Combustion Engine | 4 | No | 2021-01-28 | 2021-01-28 | 0 | 2021-02-04 | 2021-02-18 | 9 | 2021-02-25
GFID8748 | SCE | Non-NEM | Rule 21 Non-Export | IA Negotiation | Battery Storage | 0 | No | 2021-02-18 | 2021-02-18 | 0 | 2021-03-23 | 2021-04-06 | 9 | 2021-05-17 | 2021-05-25 | 6 | 2021-06-01 |  |  |  | 2021-06-08 | 5 | 2021-06-08 | 2021-07-07 | 20 | [20 empty] | 2021-07-27 | 14
GFID8754 | SCE | Non-NEM | Rule 21 Export | IA Negotiation |  | 2.25 | No | 2021-04-09 | 2021-04-13 | 2 | 2021-04-14 | 2021-05-04 | 14 | 2021-05-04 | 2021-05-24 | 14 | 2021-05-25 |  |  |  | 2021-06-18 | 17 | 2021-06-18 | 2021-07-13 | 16 |  |  | 2021-08-06 | 2021-09-03 | 20 | 2021-09-24 | 14
GFID8755 | SCE | Non-NEM | Rule 21 Non-Export | IA Negotiation | Battery Storage | 0.3 | No | 2021-05-11 | 2021-05-14 | 3 | 2021-05-25 | 2021-06-09 | 10 | 2021-06-22 | [6 empty] | 2021-07-07 | 10 | 2021-07-07 | 2021-07-28 | 15 | [20 empty] | 2021-08-18 | 15
GFID8758 | SCE | Non-NEM | QF Conversion | In-Service | Other (Hydroelectric) | 0.13 | No | 2021-05-24 | 2021-05-24 | 0 | 2021-05-24 | 2021-06-15 | 15 | 2021-06-19 | [6 empty] | 2021-06-22 | 1 | [23 empty] | 2021-07-09 | 12 |  | 2021-07-21 | 12 | [21 empty] | 2021-07-29 |  | 66
GFID8763 | SCE | Non-NEM | Rule 21 Export | IA Negotiation |  | 0 | No | 2021-08-10 | 2021-08-10 | 0 | 2021-09-01 | 2021-09-16 | 10 | 2021-09-20 | [6 empty] | 2021-10-05 | 11 | 2021-10-05 | 2021-10-25 | 13 | [20 empty] | 2021-11-15 | 14
GFID8766 | SCE | Non-NEM | Rule 21 Non-Export | Cancelled-Intake |  | 0 | No |  |  |  | 2021-09-13
GFID8767 | SCE | Non-NEM | Rule 21 Non-Export | Application Review In Progress |  | 0 | No |  |  |  | 2021-09-13
GFID8768 | SCE | Non-NEM | Rule 21 Non-Export | Application Review In Progress |  | 0 | No |  |  |  | 2021-09-13
GFID8769 | SCE | Non-NEM | Rule 21 Export | Supplemental Review Complete |  | 0.4815 | No | 2021-07-20 | 2021-07-20 | 0 | 2021-09-28 | 2021-10-11 | 9 | 2021-10-18 | 2021-10-25 | 5 | 2021-10-28 |  |  |  | 2021-11-03 | 4 | 2021-11-03 | 2021-11-24 | 14 |  |  | 2022-01-19 | 2022-02-17 | 21 | 2022-03-11 | 15
GFID8770 | SCE | Non-NEM | Rule 21 Export | Withdrawn |  | 0 | No | 2021-07-20 | 2021-07-20 | 0 | 2021-09-28 | 2021-10-04 | 4 | 2021-10-13 | 2021-12-07 | 36 | 2021-12-09 |  |  |  | 2021-12-09 | 0 | 2021-12-14 | 2022-01-05 | 14 |  |  | 2022-01-20 | 2022-02-14 | 17
GFID8771 | SCE | Non-NEM | Rule 21 Export | Withdrawn |  | 0 | No | 2021-09-01 | 2021-09-02 | 1 | 2021-09-28 | 2021-10-04 | 4 | 2021-10-13 | 2021-12-07 | 36 | 2021-12-09 |  |  |  | 2021-12-10 | 1 | 2021-12-14 | 2022-01-05 | 14 |  |  | 2022-01-20 | 2022-02-14 | 17
GFID8775 | SCE | Non-NEM | Rule 21 Export | System Impact Study In Progress |  | 3.49 | No | 2021-11-16 | 2021-11-19 | 3 | 2021-11-24 | 2021-12-10 | 10 | 2021-12-22 | [6 empty] | 2021-12-29 | 4 | [15 empty] | 2022-02-09 | 2022-03-17
GFID8776 | SCE | Non-NEM | Rule 21 Export | Application Review In Progress |  | 0 | No |  |  |  | 2022-01-13
GFID8777 | SCE | Non-NEM | Rule 21 Export | Application Review In Progress |  | 0 | No |  |  |  | 2022-01-14
GFID8778 | SCE | Non-NEM | Rule 21 Export | Application Review In Progress |  | 0 | No |  |  |  | 2022-01-20 | [62 empty] | 0
GFID8779 | SCE | Non-NEM | Rule 21 Export | Supplemental Review Complete |  | 0 | No | 2022-01-31 | 2022-02-02 | 2 | 2022-02-02 | 2022-02-17 | 11 | 2022-02-18 | [6 empty] | 2022-03-11 | 14 | 2022-03-11 | 2022-03-15 | 2 |  |  | 2022-03-18 | 2022-03-22 | 2
GFID8781 | SCE | Non-NEM | Rule 21 Export | Fast Track Initial Review Complete |  | 0 | No | 2022-02-04 | 2022-02-07 | 1 | 2022-02-08 | 2022-02-17 | 7 | 2022-02-18 | [6 empty] | 2022-03-11 | 14 | 2022-03-11
NST-137551 | SCE | NEM | NEM | Engineering Study In Progress | Solar PV + Battery Storage | 0.603 | No | 2021-02-09 | 2021-02-09 | 0 | 2021-02-09 | [9 empty] | 2020-04-22 | 17 | [23 empty] | 2021-04-15 | 28 |  | 2021-05-28 | 43
NST-147897 | SCE | NEM | NEMA | SCE Engineer Review. Pending SCE System Upgrades | Solar PV | 128.752 | No | 2021-07-08 | 2021-07-08 | 0 | 2021-07-08 | 2021-07-22 | 10 | 2021-08-08 | 2021-08-09 | 0 |  |  |  |  | 2021-09-14 | 25
NST-147897 | SCE | NEM | NEM Aggregation | Construction |  | 128.752 | No |  |  |  | 2021-09-14
NST-149934 | SCE | NEM | NEM-ST | Application Review In Progress | Solar PV | 0 | No |  |  |  | 2021-02-01
NST-155960 | SCE | NEM | NEM Aggregation | IA Negotiation | Solar PV | 0 | No | 2021-01-13 | 2021-01-13 | 0 | 2021-01-13 | 2021-01-14 | 1 | 2021-07-14 | 2021-07-23 | 7 | 2021-08-04 |  |  |  | 2021-08-17 | 9 | 2021-08-17 | 2021-08-17 | 0 |  |  | 2021-08-17 | 2021-09-15 | 20 | 2021-10-06 | 15
NST-164580 | SCE | NEM | VNEM | Withdrawn | Solar PV | 503.303 | No | 2021-01-14 | 2021-01-14 | 0 | 2021-01-14 | 2021-01-21 | 4 |  |  |  |  | 2021-02-05 | 11
NST-165244 | SCE | NEM | NEM | Pending PTO | Solar PV | 0.15 | No | 2021-01-11 | 2021-01-11 | 0 | 2021-01-11 | [9 empty] | 2021-01-11 | 0 | 2021-02-05 | 2021-02-16 | 6 | 2021-02-16 | 0 | [17 empty] | 2021-02-19 | 2021-02-23 | 2 |  | 2021-03-17 | 22
NST-167710 | SCE | NEM | NEM Aggregation | Pending PTO | Solar PV | 2.5 | No | 2021-01-28 | 2021-01-28 | 0 | 2021-01-28 | 2021-02-12 | 11 | 2021-02-24 | [6 empty] | 2021-03-15 | 13 | 2021-03-15 | 2021-04-05 | 14 |  |  | 2021-04-19 | 2021-05-17 | 20 |  |  | 2021-05-27 | 2021-06-23 | 18 | 2021-07-06 |  | 2021-07-06 | [6 empty] | 2021-11-01 | 2021-11-05 | 4 |  | 2021-12-21 | 46
NST-167713 | SCE | NEM | NEM Aggregation | In-Service | Solar PV | 2.6 | No | 2021-01-15 | 2021-01-15 | 0 | 2021-01-15 | 2021-01-28 | 8 | 2021-02-11 | 2021-02-18 | 4 | 2021-03-12 |  |  |  | 2021-03-12 | 0 | 2021-03-12 | 2021-04-05 | 15 | 2021-04-22 | 13 | [18 empty] | 2021-07-02 | 4 |  | 2021-08-23 | 52
NST-167897 | SCE | NEM | NEM-ST | Construction |  | 2.5 | No | 2021-01-15 | 2021-01-15 | 0 | 2021-01-15 | 2021-01-27 | 7 | 2021-02-02 | [6 empty] | 2021-02-10 | 6 | 2021-04-01 | 2021-04-20 | 13 | [7 empty] | 2021-05-27 | 2021-06-23 | 18 | 2021-06-25 | 2 | 2021-06-30 | 2021-08-02 | 22 | 2021-08-18 | 2021-10-28 | 49 |  |  | 2021-11-30 |  | 33 | 2022-03-22 | 44642
NST-167898 | SCE | NEM | NEM Aggregation | Construction | Solar PV | 2.5 | No | 2021-01-26 | 2021-01-26 | 0 | 2021-01-26 | 2021-02-10 | 11 | 2021-02-24 | [6 empty] | 2021-03-01 | 3 | 2021-03-01 | 2021-04-20 | 35 | [7 empty] | 2021-05-27 | 2021-06-23 | 18 | 2021-06-25 | 2 | 2021-06-30 | 2021-08-02 | 22 | 2021-08-18 | 2021-10-28 | 49 |  |  | 2021-11-30 |  | 33 | 2022-03-22 | 44642
NST-173645 | SCE | NEM | NEM Aggregation | Application Review Complete | Solar PV | 1.8 | No | 2021-01-12 | 2021-01-12 | 0 | 2021-01-12 | 2021-01-22 | 7 | 2021-01-26 | [6 empty] | 2021-02-04 | 7 | 2021-02-04 | 2021-02-26 | 15 | [7 empty] | 2021-04-19 | 2021-04-26 | 5 |  |  |  | 2021-07-06 |  | 2021-07-20 | 2021-10-19 | 63
NST-173746 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 34.066 | No | 2021-01-26 | 2021-01-26 | 0 | 2021-01-26 | [9 empty] | 2021-01-27 | 1 | [49 empty] | 2021-01-28 |  | 2
NST-174421 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Construction | Solar PV | 265.971 | No | 2021-02-26 | 2021-02-26 | 0 | 2021-02-26 | 2021-03-02 | 2 | 2021-03-25 | 2021-03-30 | 3 | 2021-03-30 |  |  |  | 2021-03-31 | 0
NST-177459 | SCE | NEM | NEM Aggregation | Pending PTO | Solar PV | 0.59665 | No | 2021-04-05 | 2021-04-05 | 0 | 2021-04-05 | 2021-04-08 | 3 | 2021-04-30 | 2021-04-30 | 0 | 2021-04-30 |  |  |  | 2021-04-30 | 0 | 2021-04-30 | 2021-04-30 | 0 | 2021-04-30 | 0 | [17 empty] | 2021-05-18 | 2021-05-19 | 1 |  | 2021-07-07 | 49
NST-177527 | SCE | NEM | NEM | In-Service | Solar PV | 0.03 | No | 2021-01-21 | 2021-01-21 | 0 | 2021-01-21 | [9 empty] | 2021-01-21 | 0 | 2021-01-21 | 2021-01-26 | 3 | 2021-02-12 | 13 | [17 empty] | 2021-03-08 | 2021-03-19 | 9 |  | 2021-04-20 | 32
NST-177735 | SCE | NEM | NEM Aggregation | Construction | Solar PV | 3.75 | No | 2020-12-23 | 2020-12-23 | 0 | 2020-12-30 | 2021-01-25 | 16 | 2021-02-01 | [6 empty] | 2021-02-02 | 1 | 2021-02-02 | 2021-02-23 | 14 |  |  | 2021-03-04 | 2021-03-30 | 18 | 2021-04-20 | 14 | [12 empty] | 2021-05-14 | 2021-06-03 | 13 |  | 2021-07-16 | 43
NST-178155 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 32.591 | No | 2020-12-29 | 2020-12-29 | 0 | 2020-12-29 | [9 empty] | 2021-01-12 | 9 | [49 empty] | 2021-01-22 |  | 24
NST-178193 | SCE | NEM | NEMA | Withdrawn | Solar PV | 41.336 | No | 2020-12-29 | 2020-12-29 | 0 | 2020-12-29 | 2021-01-07 | 6 |  |  |  |  | 2021-01-25 | 11
NST-178235 | SCE | NEM | NEMA | Withdrawn | Solar PV | 291.975 | No | 2020-12-29 | 2020-12-29 | 0 | 2020-12-29 | 2020-12-31 | 2 | 2021-01-05 | 2021-02-02 | 19 | 2021-02-08 | 2021-02-12 | 4
NST-178278 | SCE | NEM | NEM Aggregation | Construction | Solar PV | 0 | No | 2021-05-25 | 2021-05-25 | 0 | 2021-05-25 | 2021-06-15 | 14 | 2021-06-29 | [6 empty] | 2021-07-02 | 3 | 2021-07-03 | 2021-07-27 | 15 | 2021-08-16 | 14 | [17 empty] | 2021-08-26 | 2021-09-20 | 16 |  | 2021-10-12 | 22
NST-178295 | SCE | NEM | NEMA | SCE System Upgrades. Pending Local Planner Process | Solar PV | 114.05 | No | 2020-12-29 | 2020-12-29 | 0 | 2020-12-29 | 2021-01-04 | 3 | 2021-01-05 | [6 empty] | 2021-01-28 | 16
NST-178295 | SCE | NEM | NEM Aggregation | Construction | Solar PV | 114.05 | No | 2021-03-12 | 2021-03-12 | 0 | 2021-03-12 | 2021-04-05 | 15 | 2021-04-20 | 2021-04-28 | 6 | 2021-05-10 |  |  |  | 2021-05-14 | 4 | 2021-05-14
NST-178439 | SCE | NEM | NEM Aggregation | Transferred to NEM | Solar PV | 0 | No | 2020-12-30 | 2020-12-30 | 0 | 2020-12-30 | 2021-01-14 | 10 | 2021-01-22 | 2021-01-29 | 5
NST-178602 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 30 | No | 2021-01-04 | 2021-01-04 | 0 | 2021-01-04 | 2021-01-06 | 2 | 2021-01-26 | 2021-04-12 | 52 | 2021-04-12 |  |  |  | 2021-04-20 | 6 | [49 empty] | 2021-05-06 |  | 122
NST-178637 | SCE | NEM | NEMA | Withdrawn | Solar PV | 46.639 | No | 2021-01-02 | 2021-01-02 | 0 | 2021-01-02 | 2021-01-05 | 1 | 2021-01-27 |  |  |  | 2021-01-21 | 11
NST-178787 | SCE | NEM | NEMA | Withdrawn | Solar PV | 55.2 | No | 2021-01-04 | 2021-01-04 | 0 | 2021-01-04 | 2021-01-06 | 2 | 2021-01-07 | 2021-01-12 | 3 | 2021-01-28 | 2021-02-01 | 2
NST-178962 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 41.611 | No | 2021-01-05 | 2021-01-05 | 0 | 2021-01-05 | 2021-01-06 | 1 | 2021-01-06 | 2021-01-11 | 3 | 2021-01-11 |  |  |  | 2021-01-14 | 3 | [49 empty] | 2021-04-05 |  | 90
NST-178986 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 286.806 | No | 2021-01-08 | 2021-01-08 | 0 | 2021-01-08 | 2021-01-11 | 1 | 2021-02-08 | 2021-02-18 | 7 | 2021-02-23 |  |  |  | 2021-02-27 | 3 | [49 empty] | 2021-06-18 |  | 161
NST-179136 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 167.982 | No | 2021-01-05 | 2021-01-05 | 0 | 2021-01-05 | 2021-01-06 | 1 | 2021-01-20 | [6 empty] | 2021-01-26 | 4 | [49 empty] | 2022-03-01 |  | 420
NST-179182 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 158.155 | No | 2021-01-06 | 2021-01-06 | 0 | 2021-01-06 | 2021-01-07 | 1 | 2021-01-08 | [6 empty] | 2021-01-13 | 3 | [49 empty] | 2021-03-29 |  | 82
NST-179344 | SCE | NEM | VNEM | NGOM Installation. Pending ESR Violation Corrections | Solar PV | 82.879 | No | 2021-01-06 | 2021-01-06 | 0 | 2021-01-06 | [9 empty] | 2021-01-13 | 5 | [31 empty] | 2021-04-12 | 2021-04-19 | 5
NST-179352 | SCE | NEM | VNEM | NGOM Installation. Pending ESR Violation Corrections | Solar PV | 70.467 | No | 2021-01-06 | 2021-01-06 | 0 | 2021-01-06 | [9 empty] | 2021-01-13 | 5 | [31 empty] | 2021-04-12 | 2021-04-19 | 5
NST-179530 | SCE | NEM | NEMA | Withdrawn | Solar PV + Battery Storage | 55.696 | No | 2021-01-07 | 2021-01-07 | 0 | 2021-01-07 | 2021-01-21 | 9 | 2021-01-21 | [6 empty] | 2021-01-22 | 1
NST-179663 | SCE | NEM | Other-MT | NEMI - PTO Issued | Solar PV | 165.396 | No | 2021-01-07 | 2021-01-07 | 0 | 2021-01-07 | 2021-01-25 | 11 | 2021-02-16 | [6 empty] | 2021-02-23 | 5 | [49 empty] | 2021-08-25 |  | 230
NST-179671 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 680.828 | No | 2021-01-07 | 2021-01-07 | 0 | 2021-01-07 | 2021-01-13 | 4 | 2021-01-13 | [6 empty] | 2021-01-21 | 5 | [49 empty] | 2021-09-08 |  | 244
NST-179730 | SCE | NEM | NEMA | Withdrawn | Solar PV | 182.069 | No | 2021-01-08 | 2021-01-08 | 0 | 2021-01-08 | 2021-01-11 | 1 |  |  |  |  | 2021-01-27 | 11
NST-179880 | SCE | NEM | NEMA | Withdrawn | Solar PV | 2867.296 | No | 2021-01-08 | 2021-01-08 | 0 | 2021-01-08 | 2021-01-14 | 4 | 2021-01-27 |  |  |  | 2021-05-09 | 70 |  | 2021-02-11 | 11
NST-179880 | SCE | NEM | NEM-ST | Withdrawn | Solar PV | 2867.296 | No | 2021-01-27 | 2021-01-27 | 0 | 2021-01-27 | 2021-02-08 | 8 | 2021-02-10 | [6 empty] | 2021-02-11 | 1 | 2021-02-11 | 2021-03-04 | 14 |  |  | 2021-03-08 | 2021-04-07 | 21 | 2021-04-27 | 14
NST-180019 | SCE | NEM | VNEM | NEMI - PTO Issued | Solar PV | 205.067 | No | 2021-01-11 | 2021-01-11 | 0 | 2021-01-11 | 2021-01-20 | 6 | 2021-01-20 | 2021-03-08 | 32 | 2021-03-10 |  |  |  | 2021-03-10 | 0 | [31 empty] | 2021-05-07 | 2021-06-30 | 37 | 2021-06-30 | 0 | [13 empty] | 2021-09-03 |  | 235
NST-180252 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 33.561 | No | 2021-01-12 | 2021-01-12 | 0 | 2021-01-12 | 2021-01-13 | 1 | 2021-02-02 | [6 empty] | 2021-02-11 | 7 | 2021-02-19 | 2021-02-24 | 3 | [46 empty] | 2021-03-02 |  | 49
NST-180317 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 220.502 | No | 2021-01-12 | 2021-01-12 | 0 | 2021-01-12 | 2021-01-13 | 1 | 2021-01-19 | [6 empty] | 2021-01-26 | 5 | [49 empty] | 2021-05-13 |  | 121
NST-180450 | SCE | NEM | NEM-FC | NEMI - PTO Issued | Fuel Cell - Renewable | 787.5 | No | 2021-01-12 | 2021-01-12 | 0 | 2021-01-12 | [9 empty] | 2021-02-08 | 18 | [49 empty] | 2021-05-05 |  | 113
NST-180450 | SCE | NEM | NEM | Transferred to NEM | Fuel Cell | 787.5 | No | 2021-01-12 | 2021-01-14 | 2 | 2021-01-25 | [9 empty] | 2021-02-08 | 10 | [49 empty] | 2021-05-05 |  | 100
NST-180659 | SCE | NEM | NEM | Construction | Solar PV | 214.249 | No | 2021-01-22 | 2021-01-22 | 0 | 2021-01-22 | [9 empty] | 2021-01-22 | 0 | 2021-01-22 | 2021-02-12 | 15 |  |  | 2021-02-12 | 2021-03-16 | 21 | 2021-03-16 | 0 | [12 empty] | 2021-04-27 | 2021-05-17 | 14 |  | 2021-07-25 | 69
NST-180659 | SCE | NEM | NEMA | SCE Engineer Review. Pending SCE System Upgrades | Solar PV | 214.249 | No | 2021-01-13 | 2021-01-13 | 0 | 2021-01-13 | 2021-01-15 | 2 | 2021-01-20 | [6 empty] | 2021-01-22 | 0
NST-180728 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 32.616 | No | 2021-02-09 | 2021-02-09 | 0 | 2021-02-09 | 2021-02-16 | 4 | 2021-02-16 | 2021-03-02 | 10 | 2021-03-02 |  |  |  | 2021-03-02 | 0 | [49 empty] | 2021-04-01 |  | 51
NST-181017 | SCE | NEM | NEMA | Cancelled By Applicant | Solar PV + Battery Storage | 243.4 | No | 2021-01-15 | 2021-01-15 | 0 | 2021-01-15 | 2021-01-20 | 2 | 2021-01-21 | [5 empty] | 2021-09-16 | 2021-01-26 | 3 | 2021-02-09 | 2021-02-17 | 5
NST-181189 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV + Battery Storage | 34.42 | No | 2021-01-15 | 2021-01-15 | 0 | 2021-01-15 | 2021-01-22 | 4 | 2021-01-22 | [6 empty] | 2021-01-28 | 4 | [49 empty] | 2021-02-03 |  | 19
NST-181290 | SCE | NEM | NEMA | Withdrawn | Solar PV | 235.488 | No | 2021-01-16 | 2021-01-16 | 0 | 2021-01-16 | 2021-01-21 | 2 | 2021-01-29 | 2021-03-11 | 28 |  | 2021-03-19 | 6
NST-181433 | SCE | NEM | NEMA | Withdrawn | Solar PV | 64.212 | No | 2021-01-18 | 2021-01-18 | 0 | 2021-01-18 | 2021-01-21 | 2 |  |  |  |  | 2021-02-05 | 11
NST-181442 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 59.285 | No | 2021-01-18 | 2021-01-18 | 0 | 2021-01-18 | 2021-01-20 | 1 | 2021-01-20 | [6 empty] | 2021-01-25 | 3 | [49 empty] | 2021-09-07 |  | 232
NST-181602 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 30.965 | No | 2021-01-19 | 2021-01-19 | 0 | 2021-01-19 | [9 empty] | 2021-01-20 | 1 | [49 empty] | 2021-03-31 |  | 71
NST-181721 | SCE | NEM | VNEM | NGOM Installation. Pending AHJ Panel Permit | Solar PV | 62.484 | No | 2021-01-19 | 2021-01-19 | 0 | 2021-01-19 | [9 empty] | 2021-02-02 | 10 | [31 empty] | 2021-02-26 | 2021-09-16 | 140
NST-181726 | SCE | NEM | VNEM | NGOM Installation. Pending AHJ Panel Permit | Solar PV | 111.746 | No | 2021-01-19 | 2021-01-19 | 0 | 2021-01-19 | [9 empty] | 2021-02-02 | 10 | [31 empty] | 2021-02-25 | 2021-09-16 | 141
NST-181731 | SCE | NEM | VNEM | NGOM Installation. Pending AHJ Panel Permit | Solar PV | 113.586 | No | 2021-01-19 | 2021-01-19 | 0 | 2021-01-19 | [9 empty] | 2021-02-02 | 10 | [31 empty] | 2021-02-25 | 2021-07-27 | 105
NST-181893 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 65.126 | No | 2021-01-20 | 2021-01-20 | 0 | 2021-01-20 | 2021-01-23 | 2 | 2021-02-17 | 2021-03-17 | 20 | 2021-03-17 |  |  |  | 2021-03-18 | 1 | [49 empty] | 2021-07-26 |  | 187
NST-182021 | SCE | NEM | NEMA | Withdrawn | Solar PV | 31.853 | No | 2021-01-21 | 2021-01-21 | 0 | 2021-01-21 | 2021-01-26 | 3 | 2021-01-27 | 2021-02-05 | 7 |  | 2021-02-16 | 6
NST-182036 | SCE | NEM | NEMA | SCE Engineer Review. Pending SCE System Upgrades | Solar PV | 2867.296 | No | 2021-01-21 | 2021-01-21 | 0 | 2021-01-21 | 2021-01-28 | 5 | 2021-02-03 | 2021-02-05 | 2 | 2021-02-05 |  |  |  | 2021-03-03 | 17
NST-182036 | SCE | NEM | NEM-ST | In-Service | Solar PV | 2867.296 | No | 2021-02-05 | 2021-02-05 | 0 | 2021-02-05 | 2021-02-17 | 7 | 2021-02-19 | [6 empty] | 2021-03-03 | 8 | 2021-03-03 | 2021-03-23 | 14 |  |  | 2021-04-07 | 2021-05-05 | 20 | 2021-05-26 | 15 | [13 empty] | 2021-06-17 | 14 |  | 2021-07-23 | 36
NST-182245 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 35.591 | No | 2021-01-22 | 2021-01-22 | 0 | 2021-01-22 | [9 empty] | 2021-01-22 | 0 | [49 empty] | 2021-01-27 |  | 5
NST-182426 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 66.6 | No | 2021-01-22 | 2021-01-22 | 0 | 2021-01-22 | 2021-01-28 | 4 | 2021-01-29 | [6 empty] | 2021-02-08 | 6 | [49 empty] | 2021-02-16 |  | 25
NST-182430 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 66.6 | No | 2021-01-22 | 2021-01-22 | 0 | 2021-01-22 | 2021-01-28 | 4 | 2021-01-29 | [6 empty] | 2021-02-02 | 2 | [49 empty] | 2021-02-26 |  | 35
NST-182576 | SCE | NEM | NEMA | Withdrawn | Solar PV | 133.349 | No | 2021-01-25 | 2021-01-25 | 0 | 2021-01-25 | [9 empty] | 2021-02-05 | 9 | [49 empty] | 2021-02-11 |  | 17
NST-182712 | SCE | NEM | NEMA | Withdrawn | Solar PV | 407.95 | No | 2021-01-26 | 2021-01-26 | 0 | 2021-01-26 | 2021-01-27 | 1 |  |  |  |  | 2021-02-11 | 11
NST-183066 | SCE | NEM | NEMA | Withdrawn | Solar PV | 30.665 | No | 2021-01-27 | 2021-01-27 | 0 | 2021-01-27 | 2021-02-01 | 3 | 2021-02-05 | 2021-02-10 | 3 |  | 2021-02-19 | 6
NST-183344 | SCE | NEM | VNEM | NGOM Requirements Met. Pending Local Planner SO Release | Solar PV | 98.412 | No | 2021-01-28 | 2021-01-28 | 0 | 2021-01-28 | 2021-02-05 | 6 | 2021-02-25 | 2021-05-25 | 62 | 2021-05-26 |  |  |  | 2021-05-26 | 0
NST-183381 | SCE | NEM | VNEM | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 48.435 | No | 2021-01-29 | 2021-01-29 | 0 | 2021-01-29 | 2021-02-05 | 5 | 2021-02-15 | 2021-03-16 | 20 | 2021-03-16 |  |  |  | 2021-03-16 | 0
NST-183386 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 40.028 | No | 2021-01-28 | 2021-01-28 | 0 | 2021-01-28 | 2021-02-02 | 3 | 2021-02-05 | 2021-04-21 | 51 | 2021-04-22 |  |  |  | 2021-04-22 | 0 | [49 empty] | 2021-04-29 |  | 91
NST-183547 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 35.502 | No | 2021-01-29 | 2021-01-29 | 0 | 2021-01-29 | 2021-02-03 | 3 | 2021-03-08 | 2021-03-10 | 2 | 2021-04-08 |  |  |  | 2021-04-21 | 9 | [49 empty] | 2021-06-18 |  | 140
NST-183549 | SCE | NEM | VNEM | Withdrawn | Solar PV | 46.598 | No | 2021-01-29 | 2021-01-29 | 0 | 2021-01-29 | 2021-02-08 | 6 |  |  |  |  | 2021-02-24 | 11
NST-183551 | SCE | NEM | VNEM | Withdrawn | Solar PV | 47.317 | No | 2021-01-29 | 2021-01-29 | 0 | 2021-01-29 | 2021-02-08 | 6 | 2021-02-15 | 2021-03-12 | 18 | 2021-03-12 |  |  | 2021-12-14 | 2021-03-16 | 2
NST-183554 | SCE | NEM | VNEM-SOMAH | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 75.123 | No | 2021-01-29 | 2021-01-29 | 0 | 2021-01-29 | 2021-02-08 | 6 | 2021-02-22 | 2021-02-23 | 1 |  |  |  |  | 2021-03-16 | 15
NST-183613 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 763 | No | 2021-01-29 | 2021-01-29 | 0 | 2021-01-29 | 2021-02-03 | 3 | 2021-02-09 | [6 empty] | 2021-02-26 | 12 | [49 empty] | 2021-06-28 |  | 122
NST-183613 | SCE | NEM | NEM-ST | In-Service | Solar PV | 763 | No | 2021-02-26 | 2021-02-26 | 0 | 2021-02-26 | 2021-03-11 | 9 | 2021-03-23 | 2021-04-05 | 8 | 2021-04-06 |  |  |  | 2021-04-13 | 5 | 2021-04-13 | 2021-04-13 | 0 | [20 empty] | 2021-04-13 | 0 |  | 2021-05-26 | 43 | [21 empty] | 2021-06-28 |  | 122
NST-183676 | SCE | NEM | VNEM | Meter Request Released. Pending NGOM installation | Solar PV | 81.365 | No | 2021-01-29 | 2021-01-29 | 0 | 2021-01-29 | 2021-02-09 | 7 | 2021-02-15 | 2021-02-19 | 3 | 2021-02-19 |  |  |  | 2021-02-24 | 3
NST-183680 | SCE | NEM | VNEM | NGOM Installation. Pending New Service Request and AHJ Panel Permit | Solar PV | 87.588 | No | 2021-01-29 | 2021-01-29 | 0 | 2021-01-29 | 2021-02-09 | 7 | 2021-02-15 | 2021-02-19 | 3 | 2021-02-19 |  |  |  | 2021-02-24 | 3
NST-184015 | SCE | NEM | NEMA | Withdrawn | Solar PV | 50.061 | No | 2021-02-02 | 2021-02-02 | 0 | 2021-02-02 | 2021-02-05 | 3 | 2021-02-10 | 2021-02-19 | 6 | 2021-02-23 | 2021-03-09 | 10
NST-184127 | SCE | NEM | VNEM | NGOM Installation. Pending AHJ Panel Permit | Solar PV | 114.919 | No | 2021-02-02 | 2021-02-02 | 0 | 2021-02-02 | [9 empty] | 2021-02-17 | 10 | [32 empty] | 2021-02-26
NST-184151 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 33.545 | No | 2021-02-02 | 2021-02-02 | 0 | 2021-02-02 | 2021-02-22 | 13 | 2021-02-22 | 2021-02-27 | 4 | 2021-03-01 |  |  |  | 2021-03-01 | 0 | [49 empty] | 2021-03-08 |  | 34
NST-184165 | SCE | NEM | VNEM | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 37.2 | No | 2021-02-03 | 2021-02-03 | 0 | 2021-02-03 | 2021-02-11 | 6 | 2021-02-24 | 2021-04-06 | 28 | 2021-04-06 |  |  |  | 2021-04-09 | 3
NST-184172 | SCE | NEM | VNEM | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 96 | No | 2021-02-03 | 2021-02-03 | 0 | 2021-02-03 | 2021-02-11 | 6 | 2021-02-24 | 2021-03-04 | 6 | 2021-04-02 |  |  |  | 2021-04-08 | 4
NST-184175 | SCE | NEM | VNEM | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 31.6 | No | 2021-02-03 | 2021-02-03 | 0 | 2021-02-03 | 2021-02-11 | 6 | 2021-02-24 | 2021-03-04 | 6 | 2021-04-02 |  |  |  | 2021-04-08 | 4
NST-184177 | SCE | NEM | VNEM | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 54 | No | 2021-02-03 | 2021-02-03 | 0 | 2021-02-03 | 2021-02-11 | 6 | 2021-02-24 | 2021-03-04 | 6 | 2021-04-02 |  |  |  | 2021-04-06 | 2
NST-184435 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 269.851 | No | 2021-02-03 | 2021-02-03 | 0 | 2021-02-03 | 2021-02-12 | 7 | 2021-02-16 | [6 empty] | 2021-02-23 | 5 | [49 empty] | 2022-01-21 |  | 352
NST-184642 | SCE | NEM | NEMA | NEMI - Returned from Engineering | Solar PV | 68.816 | No | 2021-02-04 | 2021-02-04 | 0 | 2021-02-04 | 2021-02-10 | 4 | 2021-02-12 | 2021-03-15 | 20 | 2021-03-17 |  |  |  | 2021-03-24 | 5
NST-184733 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 64.36 | No | 2021-02-04 | 2021-02-04 | 0 | 2021-02-04 | 2021-02-10 | 4 | 2021-02-10 | [6 empty] | 2021-02-16 | 3 | [49 empty] | 2021-04-29 |  | 84
NST-184818 | SCE | NEM | NEMA | Withdrawn | Solar PV | 69.017 | No | 2021-02-05 | 2021-02-05 | 0 | 2021-02-05 | 2021-02-10 | 3 |  |  |  |  | 2021-02-26 | 11
NST-185013 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 31.002 | No | 2021-02-08 | 2021-02-08 | 0 | 2021-02-08 | 2021-02-09 | 1 | 2021-02-09 | [6 empty] | 2021-02-16 | 4 | 2021-02-09 | 2021-02-16 | 4 | [46 empty] | 2021-07-21 |  | 163
NST-185057 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 333.058 | No | 2021-02-08 | 2021-02-08 | 0 | 2021-02-08 | 2021-02-18 | 7 | 2021-02-19 | [6 empty] | 2021-02-25 | 4 | [49 empty] | 2022-01-13 |  | 339
NST-185072 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 995.253 | No | 2021-02-08 | 2021-02-08 | 0 | 2021-02-08 | [9 empty] | 2021-02-12 | 4 | [49 empty] | 2021-07-14 |  | 156
NST-185130 | SCE | NEM | VNEM | NGOM Installation. Pending AHJ Panel Permit | Solar PV | 75.864 | No | 2021-02-08 | 2021-02-08 | 0 | 2021-02-08 | [9 empty] | 2021-02-16 | 5 | [31 empty] | 2021-03-10 | 2021-09-16 | 132
NST-185356 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 170.071 | No | 2021-02-09 | 2021-02-09 | 0 | 2021-02-09 | [9 empty] | 2021-02-16 | 4 | 2021-02-09 | 2021-02-16 | 4 | [46 empty] | 2021-04-27 |  | 77
NST-185361 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 37.333 | No | 2021-02-09 | 2021-02-09 | 0 | 2021-02-09 | [9 empty] | 2021-02-19 | 7 | [49 empty] | 2021-02-24 |  | 15
NST-185620 | SCE | NEM | NEMA | SCE Engineer. Supplemental Review In Progress | Solar PV | 2226.453 | No | 2021-02-10 | 2021-02-10 | 0 | 2021-02-10 | 2021-02-16 | 3 | 2021-02-24 | 2021-02-28 | 2 | 2021-03-03 |  |  |  | 2021-06-21 | 76
NST-185620 | SCE | NEM | NEM-ST | Withdrawn | Solar PV | 2226.453 | No | 2021-03-03 | 2021-03-03 | 0 | 2021-03-03 | 2021-03-17 | 10 | 2021-04-15 | [6 empty] | 2021-04-28 | 9
NST-185673 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 266.048 | No | 2021-02-10 | 2021-02-10 | 0 | 2021-02-10 | 2021-02-17 | 4 | 2021-02-18 | [6 empty] | 2021-02-23 | 3 | [49 empty] | 2021-09-15 |  | 217
NST-185905 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 32.09 | No | 2021-02-11 | 2021-02-11 | 0 | 2021-02-11 | [9 empty] | 2021-02-22 | 6 | [49 empty] | 2021-02-25 |  | 14
NST-185916 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 79.408 | No | 2021-02-11 | 2021-02-11 | 0 | 2021-02-11 | 2021-02-18 | 4 | 2021-02-18 | 2021-02-23 | 3 | 2021-02-23 |  |  |  | 2021-03-02 | 5 | [49 empty] | 2021-03-04 |  | 21
NST-186160 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 165.319 | No | 2021-02-12 | 2021-02-12 | 0 | 2021-02-12 | 2021-04-23 | 48 | 2021-05-03 | [6 empty] | 2021-05-11 | 6 | [49 empty] | 2022-02-14 |  | 367
NST-186173 | SCE | NEM | NEM-ST | Transferred to NEM | Solar PV | 0 | No | 2021-05-05 | 2021-05-05 | 0 | 2021-05-05 | 2021-05-13 | 6 | 2021-05-24
NST-186189 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 41.336 | No | 2021-02-12 | 2021-02-12 | 0 | 2021-02-12 | 2021-02-18 | 3 | 2021-02-26 | 2021-03-02 | 2 | 2021-03-05 |  |  |  | 2021-03-05 | 0 | [49 empty] | 2021-03-10 |  | 26
NST-186196 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV + Battery Storage | 341.25 | No | 2021-02-13 | 2021-02-13 | 0 | 2021-02-13 | 2021-02-18 | 2 | 2021-02-24 | 2021-03-02 | 4 | 2021-03-08 |  |  |  | 2021-03-12 | 4
NST-186216 | SCE | NEM | VNEM | NEMI - PTO Issued | Solar PV | 45.172 | No | 2021-02-14 | 2021-02-14 | 0 | 2021-02-14 | 2021-02-22 | 4 | 2021-02-23 | 2021-04-05 | 28 | 2021-04-05 |  |  |  | 2021-04-07 | 2 | [31 empty] | 2021-05-07 | 2021-09-21 | 94 | [15 empty] | 2022-02-03 |  | 354
NST-186287 | SCE | NEM | NEMA | Withdrawn | Solar PV | 43.991 | No | 2021-02-15 | 2021-02-15 | 0 | 2021-02-15 | 2021-02-16 | 0 |  |  |  |  | 2021-03-03 | 11
NST-186495 | SCE | NEM | VNEM | SCE System Upgrades. Pending Local Planner Process | Solar PV | 410.612 | No | 2021-02-16 | 2021-02-16 | 0 | 2021-02-16 | 2021-03-04 | 12 | 2021-03-04 | 2021-04-19 | 31 | 2021-04-19 |  |  |  | 2021-04-27 | 6
NST-186495 | SCE | NEM | NEM-ST | Construction | Solar PV | 410.612 | No | 2021-04-27 | 2021-04-27 | 0 | 2021-04-27 | [9 empty] | 2021-04-27 | 0 | 2021-04-27 | 2021-05-24 | 19 | 2021-05-25 | 1 | [18 empty] | 2021-05-28 | 3 |  | 2021-06-18 | 21
NST-186511 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 137.035 | No | 2021-02-16 | 2021-02-16 | 0 | 2021-02-16 | [9 empty] | 2021-02-20 | 3
NST-186828 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 77.371 | No | 2021-02-17 | 2021-02-17 | 0 | 2021-02-17 | 2021-02-23 | 4 | 2021-03-15 | [6 empty] | 2021-03-19 | 4 | [49 empty] | 2021-09-29 |  | 224
NST-186860 | SCE | NEM | NEMA | Withdrawn | Solar PV + Battery Storage | 725.873 | No | 2021-02-17 | 2021-02-17 | 0 | 2021-02-17 | 2021-02-23 | 4 |  |  |  |  | 2021-03-10 | 11
NST-186949 | SCE | NEM | VNEM | NEMI - PTO Issued | Solar PV | 30.832 | No | 2021-02-18 | 2021-02-18 | 0 | 2021-02-18 | 2021-02-24 | 4 | 2021-02-24 | 2021-03-04 | 6 | 2021-03-04 |  |  |  | 2021-03-10 | 4 | [49 empty] | 2022-03-25 |  | 400
NST-186951 | SCE | NEM | VNEM | NEMI - PTO Issued | Solar PV | 46.248 | No | 2021-02-18 | 2021-02-18 | 0 | 2021-02-18 | 2021-03-04 | 10 | 2021-03-04 | [6 empty] | 2021-03-12 | 6 | [49 empty] | 2022-03-01 |  | 376
NST-186961 | SCE | NEM | VNEM | NEMI - PTO Issued | Solar PV | 30.832 | No | 2021-02-18 | 2021-02-18 | 0 | 2021-02-18 | 2021-02-26 | 6 | 2021-02-26 | [6 empty] | 2021-03-09 | 7 | [49 empty] | 2022-02-22 |  | 369
NST-186964 | SCE | NEM | VNEM | NEMI - PTO Issued | Solar PV | 30.832 | No | 2021-02-18 | 2021-02-18 | 0 | 2021-02-18 | 2021-03-09 | 13 | 2021-03-09 | [6 empty] | 2021-03-18 | 7 | [49 empty] | 2022-03-01 |  | 376
NST-186968 | SCE | NEM | VNEM | NEMI - PTO Issued | Solar PV | 30.832 | No | 2021-02-18 | 2021-02-18 | 0 | 2021-02-18 | 2021-03-09 | 13 | 2021-03-09 | [6 empty] | 2021-03-12 | 3 | [49 empty] | 2022-02-25 |  | 372
NST-186970 | SCE | NEM | VNEM | NEMI - PTO Issued | Solar PV | 30.832 | No | 2021-02-18 | 2021-02-18 | 0 | 2021-02-18 | 2021-02-24 | 4 | 2021-02-24 | 2021-03-04 | 6 | 2021-03-04 |  |  |  | 2021-03-10 | 4 | [49 empty] | 2022-03-08 |  | 383
NST-186974 | SCE | NEM | VNEM | NEMI - PTO Issued | Solar PV | 30.832 | No | 2021-02-18 | 2021-02-18 | 0 | 2021-02-18 | 2021-02-25 | 5 | 2021-02-25 | 2021-03-08 | 7 | 2021-03-08 |  |  |  | 2021-03-16 | 6 | [49 empty] | 2022-02-23 |  | 370
NST-187024 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 248.003 | No | 2021-02-18 | 2021-02-18 | 0 | 2021-02-18 | 2021-07-07 | 96 | 2021-07-07 | [6 empty] | 2021-07-07 | 0 | [49 empty] | 2021-07-12 |  | 144
NST-187270 | SCE | NEM | VNEM | NGOM Installation. Pending AHJ Panel Permit | Solar PV | 106.734 | No | 2021-02-19 | 2021-02-19 | 0 | 2021-02-19 | [9 empty] | 2021-03-02 | 7 | [31 empty] | 2021-03-10
NST-187386 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 64.212 | No | 2021-02-19 | 2021-02-19 | 0 | 2021-02-19 | 2021-02-25 | 4 | 2021-03-01 | [6 empty] | 2021-03-05 | 4 | [49 empty] | 2021-04-12 |  | 52
NST-187426 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 380.485 | No | 2021-02-19 | 2021-02-19 | 0 | 2021-02-19 | [9 empty] | 2021-02-25 | 4 | [49 empty] | 2021-09-27 |  | 220
NST-187430 | SCE | NEM | VNEM | Withdrawn | Solar PV | 239.953 | No | 2021-02-19 | 2021-02-19 | 0 | 2021-02-19 | 2021-03-08 | 11 |  |  |  |  | 2021-03-23 | 11
NST-187547 | SCE | NEM | VNEM | Withdrawn | Solar PV | 81.045 | No | 2021-02-22 | 2021-02-22 | 0 | 2021-02-22 | 2021-03-01 | 5 |  |  |  |  | 2021-04-12 | 29
NST-187553 | SCE | NEM | VNEM | Withdrawn | Solar PV | 94.667 | No | 2021-02-22 | 2021-02-22 | 0 | 2021-02-22 | 2021-03-04 | 8 |  |  |  |  | 2021-04-12 | 26
NST-187580 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Construction | Solar PV | 333.927 | No | 2021-02-22 | 2021-02-22 | 0 | 2021-02-22 | 2021-02-26 | 4 | 2021-03-11 | 2021-03-23 | 8 | 2021-03-23 |  |  |  | 2021-04-01 | 6
NST-187582 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Construction | Solar PV | 459.15 | No | 2021-02-22 | 2021-02-22 | 0 | 2021-02-22 | 2021-02-26 | 4 | 2021-03-11 | 2021-03-15 | 2 | 2021-03-16 |  |  |  | 2021-03-17 | 1
NST-187587 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Construction | Solar PV | 822.296 | No | 2021-02-22 | 2021-02-22 | 0 | 2021-02-22 | 2021-03-01 | 5 | 2021-03-11 | [6 empty] | 2021-03-13 | 1
NST-187589 | SCE | NEM | NEMA | Withdrawn | Solar PV | 2489.614 | No | 2021-02-22 | 2021-02-22 | 0 | 2021-02-22 | 2021-02-26 | 4 |  |  |  |  | 2021-03-15 | 11
NST-187641 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 93.203 | No | 2021-02-22 | 2021-02-22 | 0 | 2021-02-22 | 2021-03-01 | 5 | 2021-03-01 | 2021-03-06 | 4 | 2021-03-15 |  |  |  | 2021-03-18 | 3 | [49 empty] | 2021-08-10 |  | 169
NST-187650 | SCE | NEM | NEMA | Withdrawn | Solar PV | 33.42 | No | 2021-02-22 | 2021-02-22 | 0 | 2021-02-22 | 2021-02-25 | 3 |  |  |  |  | 2021-03-12 | 11
NST-187661 | SCE | NEM | NEMA | Withdrawn | Solar PV | 79.862 | No | 2021-02-22 | 2021-02-22 | 0 | 2021-02-22 | 2021-02-25 | 3 |  |  |  |  | 2021-03-12 | 11
NST-187732 | SCE | NEM | VNEM | Meter Request Released. Pending NGOM installation | Solar PV | 47.397 | No | 2021-02-23 | 2021-02-23 | 0 | 2021-02-23 | 2021-03-05 | 8 | 2021-03-08 | [6 empty] | 2021-03-12 | 4
NST-187750 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 154.225 | No | 2021-02-23 | 2021-02-23 | 0 | 2021-02-23 | [9 empty] | 2021-03-03 | 6 | [49 empty] | 2021-03-05 |  | 10
NST-187773 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 33.349 | No | 2021-02-23 | 2021-02-23 | 0 | 2021-02-23 | 2021-03-01 | 4 | 2021-03-01 | 2021-03-03 | 2 | 2021-03-09 |  |  |  | 2021-03-09 | 0 | [49 empty] | 2021-03-16 |  | 21
NST-188311 | SCE | NEM | NEM Aggregation | Construction | Solar PV | 981.745 | No | 2021-03-02 | 2021-03-02 | 0 | 2021-03-02 | 2021-03-10 | 6 | 2021-03-18 | [6 empty] | 2021-03-22 | 2 | 2021-03-22 | 2021-04-12 | 14 |  |  | 2021-04-12 | 2021-04-26 | 10 | 2021-05-14 | 14 | [12 empty] | 2021-05-25 | 2021-06-11 | 12 |  | 2021-07-21 | 40
NST-188311 | SCE | NEM | NEMA | SCE Engineer Review. Pending SCE System Upgrades | Solar PV | 981.745 | No | 2021-02-25 | 2021-02-25 | 0 | 2021-02-25 | 2021-03-02 | 3 | 2021-03-03 | 2021-06-11 | 70 | 2021-06-14 |  |  |  | 2021-06-14 | 0
NST-188321 | SCE | NEM | VNEM | NGOM Installation. Pending AHJ Panel Permit | Solar PV | 94.208 | No | 2021-02-25 | 2021-02-25 | 0 | 2021-02-25 | 2021-03-09 | 8 | 2021-03-09 | [6 empty] | 2021-03-22 | 9 | [31 empty] | 2021-04-21 | 2021-09-17 | 104
NST-188322 | SCE | NEM | VNEM | NGOM Installation. Pending AHJ Panel Permit | Solar PV | 93.484 | No | 2021-02-25 | 2021-02-25 | 0 | 2021-02-25 | 2021-03-10 | 9 | 2021-03-10 | [6 empty] | 2021-03-19 | 7 | [31 empty] | 2021-04-21 | 2021-09-17 | 104
NST-188324 | SCE | NEM | VNEM | NGOM Installation. Pending AHJ Panel Permit | Solar PV | 88.411 | No | 2021-02-25 | 2021-02-25 | 0 | 2021-02-25 | 2021-03-10 | 9 | 2021-03-10 | [6 empty] | 2021-03-23 | 9 | [31 empty] | 2021-04-21 | 2021-09-17 | 104
NST-188375 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 57.825 | No | 2021-02-25 | 2021-02-25 | 0 | 2021-02-25 | 2021-03-01 | 2 | 2021-03-23 | [6 empty] | 2021-03-26 | 3 | [49 empty] | 2021-07-28 |  | 153
NST-188376 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 61.441 | No | 2021-02-25 | 2021-02-25 | 0 | 2021-02-25 | 2021-03-02 | 3 | 2021-04-07 | [6 empty] | 2021-04-15 | 6 | [49 empty] | 2021-06-15 |  | 110
NST-188456 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 34.855 | No | 2021-02-26 | 2021-02-26 | 0 | 2021-02-26 | [9 empty] | 2021-03-01 | 1 | [49 empty] | 2021-04-05 |  | 38
NST-188481 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 643.61 | No | 2021-02-26 | 2021-02-26 | 0 | 2021-02-26 | 2021-03-04 | 4 | 2021-03-10 | [6 empty] | 2021-03-12 | 2 | [49 empty] | 2022-01-19 |  | 327
NST-188491 | SCE | NEM | NEMA | SCE System Upgrades. Pending Local Planner Process | Solar PV | 291.975 | No | 2021-02-26 | 2021-02-26 | 0 | 2021-02-26 | 2021-02-28 | 0 | 2021-03-03 | 2021-03-08 | 3 | 2021-03-09 |  |  |  | 2021-05-26 | 55
NST-188491 | SCE | NEM | NEM-ST | Construction | Solar PV | 291.975 | No | 2021-05-26 | 2021-05-26 | 0 | 2021-05-26 | [9 empty] | 2021-05-26 | 0 | 2021-07-01 | 2021-07-20 | 12 |  |  | 2021-07-20 | 2021-07-30 | 8 | 2021-08-17 | 12 | [12 empty] | 2021-09-22 |  |  |  | 2022-02-10 | 44602
NST-188493 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 108.246 | No | 2021-02-26 | 2021-02-26 | 0 | 2021-02-26 | [9 empty] | 2021-03-01 | 1 | [49 empty] | 2022-01-26 |  | 334
NST-188565 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Construction | Solar PV | 869.602 | No | 2021-02-26 | 2021-02-26 | 0 | 2021-02-26 | 2021-03-24 | 18 | 2021-03-25 | 2021-04-01 | 4 | 2021-04-01 |  |  |  | 2021-04-07 | 4
NST-188568 | SCE | NEM | NEMA | NEMI - Conditional PTO | Solar PV | 445.236 | No | 2021-02-26 | 2021-02-26 | 0 | 2021-02-26 | 2021-03-02 | 2 | 2021-03-11 | 2022-03-21 | 255 | 2022-03-25 |  |  |  | 2022-03-30 | 3 | [49 empty] | 2022-03-30 |  | 397
NST-188579 | SCE | NEM | NEMA | SCE Engineer Assigned. Pending Technical Review | Solar PV | 666.116 | No | 2021-02-26 | 2021-02-26 | 0 | 2021-02-26 | 2021-03-03 | 3 | 2021-03-05 | 2021-03-10 | 3 | 2021-03-12 |  |  |  | 2021-05-21 | 49
NST-188579 | SCE | NEM | NEM Aggregation | Supplemental Review Complete | Solar PV | 666.116 | No | 2021-03-12 | 2021-03-12 | 0 | 2021-03-12 | [9 empty] | 2021-03-26 | 10 | 2021-05-20 | 2021-06-04 | 10 |  |  | 2021-06-04
NST-188585 | SCE | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 797.56 | No | 2021-03-01 | 2021-03-01 | 0 | 2021-03-01 | [9 empty] | 2021-03-04 | 3
NST-188590 | SCE | NEM | NEMA | Withdrawn | Solar PV | 38.757 | No | 2021-02-26 | 2021-02-26 | 0 | 2021-02-26 | [6 empty] | 2021-04-28 | 42 |  | 2021-03-01 | 1
NST-188646 | SCE | NEM | NEMA | NGOM Installation. Pending AHJ Panel Permit | Solar PV | 50.454 | No | 2021-03-02 | 2021-03-02 | 0 | 2021-03-02 | 2021-03-05 | 3 | 2021-04-14 |  |  |  | 2021-03-22 | 11 |  | 2021-04-15 | 1 | [31 empty] | 2021-05-20 | 2021-09-15 | 81
NST-188795 | SCE | NEM | NEMA | NGOM Installation. Pending Local Planner Process | Solar PV + Battery Storage | 807.788 | No | 2021-03-01 | 2021-03-01 | 0 | 2021-03-01 | [9 empty] | 2021-03-05 | 4 | [31 empty] | 2021-06-09 | 2021-06-25 | 12
NST-188839 | SCE | NEM | NEMA | Applicant Response Received. Pending SCE Engineer Review | Solar PV + Battery Storage | 185.223 | No | 2021-03-01 | 2021-03-01 | 0 | 2021-03-01 | 2021-03-05 | 4 | 2021-04-14 | [6 empty] | 2021-04-21 | 5
NST-188840 | SCE | NEM | NEMA | Cancelled By Applicant | Solar PV + Battery Storage | 207.968 | No | 2021-03-01 | 2021-03-01 | 0 | 2021-03-01 | 2021-03-05 | 4 | 2021-04-14 | [5 empty] | 2021-04-26 | 2021-04-22 | 6
NST-188957 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 299.466 | No | 2021-03-02 | 2021-03-02 | 0 | 2021-03-02 | 2021-03-05 | 3 | 2021-03-16 | [6 empty] | 2021-03-24 | 6 | [49 empty] | 2021-05-13 |  | 72
NST-189093 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 162.777 | No | 2021-03-03 | 2021-03-03 | 0 | 2021-03-03 | 2021-03-08 | 3 | 2021-03-16 | [6 empty] | 2021-03-19 | 3 | [49 empty] | 2021-05-11 |  | 69
NST-189148 | SCE | NEM | NEM-ST | Construction | Solar PV | 511.33 | No | 2021-04-15 | 2021-04-15 | 0 | 2021-04-15 | [9 empty] | 2021-04-15 | 0 | 2021-04-15 | 2021-05-05 | 14 | [20 empty] | 2021-05-19 | 10 |  | 2021-06-10 | 22
NST-189148 | SCE | NEM | VNEM | SCE Engineer Review. Pending Applicant Construction | Solar PV | 511.33 | No | 2021-03-02 | 2021-03-02 | 0 | 2021-03-02 | 2021-03-12 | 8 | 2021-04-08 | 2021-06-10 | 44 | 2021-06-10 |  |  |  | 2021-06-10 | 0
NST-189219 | SCE | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 77.49 | No | 2021-03-03 | 2021-03-03 | 0 | 2021-03-03 | 2021-03-08 | 3 | [7 empty] | 2021-03-19 | 9
NST-189439 | SCE | NEM | NEMA | Withdrawn | Solar PV | 238.591 | No | 2021-03-04 | 2021-03-04 | 0 | 2021-03-04 | 2021-03-09 | 3 | 2021-05-17 |  |  |  | 2021-06-02 | 11
NST-189532 | SCE | NEM | NEMA | Withdrawn | Solar PV | 31.461 | No | 2021-03-04 | 2021-03-04 | 0 | 2021-03-04 | 2021-03-10 | 4 |  |  |  |  | 2021-03-25 | 11
NST-189535 | SCE | NEM | NEMA | Withdrawn | Solar PV | 43.79 | No | 2021-03-04 | 2021-03-04 | 0 | 2021-03-04 | 2021-03-10 | 4 |  |  |  |  | 2021-03-25 | 11
NST-189675 | SCE | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 942.055 | No | 2021-03-05 | 2021-03-05 | 0 | 2021-03-05 | 2021-03-11 | 4 | 2021-04-12 | [6 empty] | 2021-04-21 | 7
NST-189710 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 456.53 | No | 2021-03-05 | 2021-03-05 | 0 | 2021-03-05 | 2021-03-09 | 2 | 2021-03-09 | 2021-03-11 | 2 | 2021-03-15 |  |  |  | 2021-03-16 | 1 | [49 empty] | 2022-01-28 |  | 329
NST-189770 | SCE | NEM | VNEM | Withdrawn | Solar PV | 30.28 | No | 2021-03-05 | 2021-03-05 | 0 | 2021-03-05 | 2021-03-12 | 5 |  |  |  |  | 2021-03-29 | 11
NST-189800 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 43.991 | No | 2021-03-05 | 2021-03-05 | 0 | 2021-03-05 | 2021-03-09 | 2 | 2021-03-12 | 2021-03-29 | 11 | 2021-03-30 |  |  |  | 2021-04-13 | 9 | [49 empty] | 2021-05-17 |  | 73
NST-189869 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 78.295 | No | 2021-03-18 | 2021-03-18 | 0 | 2021-03-18 | 2021-03-23 | 3 | 2021-03-23 | [6 empty] | 2021-03-25 | 2 | [49 empty] | 2021-09-28 |  | 194
NST-189999 | SCE | NEM | Other-MT | SCE Engineer Review. Pending Applicant Response | Solar PV + Battery Storage | 340.269 | No | 2021-03-08 | 2021-03-08 | 0 | 2021-03-08 | [9 empty] | 2021-03-12 | 4
NST-190031 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 697.32 | No | 2021-03-11 | 2021-03-11 | 0 | 2021-03-11
NST-190261 | SCE | NEM | NEMA | Withdrawn | Solar PV | 54.737 | No | 2021-03-09 | 2021-03-09 | 0 | 2021-03-09 | 2021-03-11 | 2 |  |  |  |  | 2021-03-26 | 11
NST-190296 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 480.021 | No | 2021-03-09 | 2021-03-09 | 0 | 2021-03-09 | 2021-03-11 | 2 | 2021-03-16 | [6 empty] | 2021-03-24 | 6
NST-190308 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Construction | Solar PV | 403.496 | No | 2021-03-09 | 2021-03-09 | 0 | 2021-03-09 | 2021-03-11 | 2 | 2021-03-16 | [6 empty] | 2021-03-24 | 6
NST-190313 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Construction | Solar PV | 271.316 | No | 2021-03-09 | 2021-03-09 | 0 | 2021-03-09 | 2021-03-11 | 2 | 2021-03-16 | 2021-04-15 | 21 | 2021-04-15 |  |  |  | 2021-04-22 | 5
NST-190316 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Construction | Solar PV | 396.539 | No | 2021-03-09 | 2021-03-09 | 0 | 2021-03-09 | 2021-03-11 | 2 | 2021-03-15 | [6 empty] | 2021-03-19 | 4
NST-190334 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 68.448 | No | 2021-03-09 | 2021-03-09 | 0 | 2021-03-09 | 2021-03-11 | 2 | 2021-03-12 | [6 empty] | 2021-03-15 | 1 | [49 empty] | 2021-07-29 |  | 142
NST-190581 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 40.36 | No | 2021-03-10 | 2021-03-10 | 0 | 2021-03-10 | 2021-03-11 | 1 | 2021-03-12 | [6 empty] | 2021-03-16 | 2 | [49 empty] | 2021-05-06 |  | 57
NST-190590 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 110.822 | No | 2021-03-10 | 2021-03-10 | 0 | 2021-03-10 | 2021-03-12 | 2 | 2021-03-22 | [6 empty] | 2021-03-25 | 3 | [49 empty] | 2021-09-28 |  | 202
NST-190683 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 443.42 | No | 2021-03-10 | 2021-03-10 | 0 | 2021-03-10 | 2021-03-12 | 2 | 2021-03-17 | [6 empty] | 2021-03-24 | 5 | [49 empty] | 2021-08-19 |  | 162
NST-190820 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 158.647 | No | 2021-03-11 | 2021-03-11 | 0 | 2021-03-11 | 2021-03-13 | 1 | 2021-03-13 | [6 empty] | 2021-03-15 | 0 | [49 empty] | 2021-04-22 |  | 42
NST-190880 | SCE | NEM | NEMA | Withdrawn | Solar PV | 59.525 | No | 2021-03-11 | 2021-03-11 | 0 | 2021-03-11 | 2021-03-12 | 1 | 2021-03-22 | [5 empty] | 2022-02-18 | 2021-03-24 | 2 | [49 empty] | 2021-05-21 |  | 71
NST-190914 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 154.481 | No | 2021-03-11 | 2021-03-11 | 0 | 2021-03-11 | [9 empty] | 2021-03-23 | 8 | [49 empty] | 2021-03-31 |  | 20
NST-191034 | SCE | NEM | NEMA | Withdrawn | Solar PV | 33.849 | No | 2021-03-12 | 2021-03-12 | 0 | 2021-03-12 | 2021-03-18 | 4 |  |  |  |  | 2021-04-02 | 10
NST-191044 | SCE | NEM | NEMA | NEMI - Transferred to GICD | Solar PV | 130.759 | No | 2021-03-25 | 2021-03-25 | 0 | 2021-03-25 | [9 empty] | 2021-03-30 | 3
NST-191044 | SCE | NEM | NEM-ST | Pending PTO |  | 130.759 | No |  |  |  | 2021-04-13
NST-191106 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 50.061 | No | 2021-03-12 | 2021-03-12 | 0 | 2021-03-12 | [9 empty] | 2021-03-15 | 1 | [49 empty] | 2021-03-16 |  | 4
NST-191170 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 32.051 | No | 2021-03-12 | 2021-03-12 | 0 | 2021-03-12 | 2021-03-15 | 1 | 2021-03-15 | 2021-03-16 | 1 | 2021-03-16 |  |  |  | 2021-03-18 | 2 | [49 empty] | 2021-04-01 |  | 20
NST-191185 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 158.647 | No | 2021-03-12 | 2021-03-12 | 0 | 2021-03-12 | 2021-03-15 | 1 | 2021-03-18 | 2021-03-25 | 5 | 2021-04-22 |  |  |  | 2021-05-06 | 10 | [49 empty] | 2022-02-02 |  | 327
NST-191186 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 122.704 | No | 2021-03-12 | 2021-03-12 | 0 | 2021-03-12 | [9 empty] | 2021-03-15 | 1 | [49 empty] | 2022-02-25 |  | 350
NST-191188 | SCE | NEM | NEMA | Withdrawn | Solar PV | 332.023 | No | 2021-03-12 | 2021-03-12 | 0 | 2021-03-12 | 2021-03-15 | 1 | 2021-03-18 | 2021-04-27 | 27 |  | 2021-06-03 | 26
NST-191189 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Construction | Solar PV | 180.447 | No | 2021-03-12 | 2021-03-12 | 0 | 2021-03-12 | 2021-03-15 | 1 | 2021-03-29 | [6 empty] | 2021-04-13 | 10
NST-191193 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Construction | Solar PV | 137.14 | No | 2021-03-13 | 2021-03-13 | 0 | 2021-03-13 | 2021-03-15 | 0 | 2021-03-29 | [6 empty] | 2021-04-13 | 10
NST-191194 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Construction | Solar PV | 492.162 | No | 2021-03-13 | 2021-03-13 | 0 | 2021-03-13 | 2021-03-15 | 0 | 2021-04-13 | 2021-04-23 | 8 | 2021-06-01 |  |  |  | 2021-06-14 | 9
NST-191196 | SCE | NEM | NEMA | Pending Agreement Approval/Execution | Solar PV + Battery Storage | 750.66 | No | 2021-03-18 | 2021-03-18 | 0 | 2021-03-18 | 2021-03-24 | 4 | 2021-03-29 | 2021-06-08 | 49 | 2021-06-08 |  |  |  | 2021-06-11 | 3
NST-191197 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Construction | Solar PV | 151.576 | No | 2021-03-13 | 2021-03-13 | 0 | 2021-03-13 | 2021-03-15 | 0 | 2021-04-19 | [6 empty] | 2021-05-04 | 11
NST-191201 | SCE | NEM | NEMA | Withdrawn | Solar PV | 40.611 | No | 2021-03-13 | 2021-03-13 | 0 | 2021-03-13 | 2021-03-17 | 2 | 2021-03-19 | 2021-04-07 | 12 |  | 2021-04-15 | 6
NST-191203 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 150.26 | No | 2021-03-13 | 2021-03-13 | 0 | 2021-03-13 | 2021-03-15 | 0 | 2021-03-19 | [6 empty] | 2021-03-23 | 2 | [49 empty] | 2021-06-29 |  | 108
NST-191227 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 75.679 | No | 2021-05-20 | 2021-05-20 | 0 | 2021-05-20 | [9 empty] | 2021-05-24 | 2 | [49 empty] | 2021-07-15 |  | 56
NST-191278 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 31.853 | No | 2021-03-15 | 2021-03-15 | 0 | 2021-03-15 | 2021-03-16 | 1 | 2021-03-29 | [6 empty] | 2021-04-19 | 14 | [49 empty] | 2021-06-18 |  | 95
NST-191314 | SCE | NEM | NEMA | Withdrawn | Solar PV | 318.515 | No | 2021-03-15 | 2021-03-15 | 0 | 2021-03-15 | 2021-03-16 | 1 | 2021-03-16 | [5 empty] | 2021-05-13 | 2021-03-24 | 6 | [49 empty] | 2021-05-13 |  | 59
NST-191346 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 52.299 | No | 2021-03-15 | 2021-03-15 | 0 | 2021-03-15 | 2021-03-24 | 7 | 2021-03-31 | 2021-04-06 | 3 | 2021-04-07 |  |  |  | 2021-04-19 | 8 | [31 empty] | 2021-06-07 | 2021-06-25 | 14 | [15 empty] | 2021-09-10 |  | 179
NST-191397 | SCE | NEM | NEMA | SCE Engineer Assigned. Pending Technical Review | Solar PV | 1783.78 | No | 2021-05-13 | 2021-05-13 | 0 | 2021-05-13 | 2021-05-18 | 3 | 2021-06-02 | 2021-06-16 | 10 | 2021-07-14 |  |  |  | 2021-08-13 | 22
NST-191397 | SCE | NEM | NEM Aggregation | Construction | Solar PV | 1783.78 | No | 2021-07-14 | 2021-07-14 | 0 | 2021-07-14 | 2021-07-28 | 10 | 2021-08-09 | [6 empty] | 2021-08-13 | 4 | 2021-08-13 | 2021-09-01 | 13 |  |  | 2021-09-13 | 2021-10-11 | 20 | 2021-11-04 | 17 | [16 empty] | 2022-03-23 | 44643
NST-191399 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV + Battery Storage | 138.314 | No | 2021-03-15 | 2021-03-15 | 0 | 2021-03-15 | 2021-03-16 | 1 | 2021-03-17 | 2021-03-19 | 2 | 2021-03-22 |  |  |  | 2021-03-30 | 6 | [31 empty] | 2021-09-14 | [17 empty] | 2021-09-14 |  | 183
NST-191584 | SCE | NEM | NEMA | Withdrawn | Solar PV | 6062.846 | No | 2021-03-16 | 2021-03-16 | 0 | 2021-03-16 | 2021-03-17 | 1 |  |  |  |  | 2021-04-01 | 10
NST-191628 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 30.493 | No | 2021-03-16 | 2021-03-16 | 0 | 2021-03-16 | 2021-03-17 | 1 | 2021-03-17 | [6 empty] | 2021-03-24 | 5 | [49 empty] | 2022-02-02 |  | 323
NST-191683 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 119.663 | No | 2021-03-16 | 2021-03-16 | 0 | 2021-03-16 | 2021-03-17 | 1 | 2021-03-17 | [6 empty] | 2021-03-23 | 4 | [49 empty] | 2021-03-25 |  | 9
NST-191752 | SCE | NEM | NEMA | NEMI - Transferred to GICD | Solar PV | 1821.492 | No | 2021-03-17 | 2021-03-17 | 0 | 2021-03-17 | 2021-03-22 | 3 | 2021-03-23 | 2021-04-27 | 24 | 2021-05-04 |  |  |  | 2021-05-14 | 8
NST-191752 | SCE | NEM | NEM Aggregation | System Impact Study Complete | Solar PV | 1821.492 | No | 2021-03-30 | 2021-03-30 | 0 | 2021-03-30 | 2021-04-21 | 15 | 2021-04-21 | 2021-04-27 | 4 | 2021-05-04 |  |  |  | 2021-05-14 | 8 | 2021-05-14 | [9 empty] | 2021-10-01 | 2021-10-22 | 14 |  |  | 2021-10-26 |  |  | 2021-12-14 | 2022-03-02
NST-191790 | SCE | NEM | NEMA | Withdrawn | Solar PV | 229.615 | No | 2021-03-17 | 2021-03-17 | 0 | 2021-03-17 | 2021-03-24 | 5 |  |  |  |  | 2021-05-03 | 27
NST-191821 | SCE | NEM | NEMA | Withdrawn | Solar PV | 94.577 | No | 2021-03-17 | 2021-03-17 | 0 | 2021-03-17 | 2021-03-22 | 3 | 2021-04-27 | 2021-05-12 | 11 | 2021-05-17 | 2021-06-02 | 11
NST-191903 | SCE | NEM | NEMA | NEMI - Equipment Change Submitted | Solar PV | 727.784 | No | 2021-03-18 | 2021-03-18 | 0 | 2021-03-18 | [9 empty] | 2021-03-23 | 3
NST-191954 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 337.3 | No | 2021-03-17 | 2021-03-17 | 0 | 2021-03-17 | [9 empty] | 2021-03-19 | 2 | [49 empty] | 2021-09-08 |  | 175
NST-191969 | SCE | NEM | NEMA | Withdrawn | Solar PV | 72.02 | No | 2021-03-18 | 2021-03-18 | 0 | 2021-03-18 | 2021-03-23 | 3 |  |  |  |  | 2021-04-07 | 10
NST-192012 | SCE | NEM | NEMA | NEMI - Load Justification Reviewed | Solar PV | 54.551 | No | 2021-03-24 | 2021-03-24 | 0 | 2021-03-24 | [9 empty] | 2021-03-30 | 4
NST-192113 | SCE | NEM | NEM-ST | IA Negotiation | Solar PV | 1282.236 | No | 2021-03-18 | 2021-03-18 | 0 | 2021-03-18 | 2021-04-02 | 10 | 2021-04-16 | [6 empty] | 2021-04-29 | 9 | 2021-04-29 | 2021-05-20 | 15
NST-192113 | SCE | NEM | NEMA | SCE Engineer Assigned. Pending Technical Review | Solar PV | 1282.236 | No | 2021-03-18 | 2021-03-18 | 0 | 2021-03-18 | [9 empty] | 2021-03-24 | 4
NST-192226 | SCE | NEM | VNEM | Withdrawn | Solar PV | 619.865 | No | 2021-03-19 | 2021-03-19 | 0 | 2021-03-19 | 2021-03-30 | 7 | 2021-05-02 | 2021-06-14 | 29 | 2021-06-30 | 2021-07-07 | 4
NST-192300 | SCE | NEM | NEMA | Withdrawn | Solar PV | 48.541 | No | 2021-03-19 | 2021-03-19 | 0 | 2021-03-19 | 2021-03-24 | 3 | 2021-04-07 | 2021-04-15 | 6 |  | 2021-04-23 | 6
NST-192359 | SCE | NEM | NEMA | SCE Engineer. Initial Review Complete | Solar PV | 189.541 | No | 2021-03-19 | 2021-03-19 | 0 | 2021-03-19 | [9 empty] | 2021-03-23 | 2
NST-192359 | SCE | NEM | NEM-ST | Pending PTO | Solar PV | 189.541 | No | 2021-03-19 | 2021-03-19 | 0 | 2021-03-23 | 2021-04-26 | 23 | 2021-05-10 | [8 empty] | 2021-07-27 | 2021-08-04 | 6 | [20 empty] | 2021-08-25 | 15
NST-192504 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 57.927 | No | 2021-03-22 | 2021-03-22 | 0 | 2021-03-22 | 2021-03-24 | 2 | 2021-03-24 | 2021-03-29 | 3 | 2021-03-30 |  |  |  | 2021-04-06 | 4 | [49 empty] | 2021-05-07 |  | 46
NST-192510 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 46.141 | No | 2021-03-22 | 2021-03-22 | 0 | 2021-03-22 | 2021-03-23 | 1 | 2021-03-23 | [6 empty] | 2021-03-25 | 2 | [49 empty] | 2021-05-06 |  | 45
NST-192701 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV + Battery Storage | 128.082 | No | 2021-03-23 | 2021-03-23 | 0 | 2021-03-23 | 2021-03-29 | 4 | 2021-04-06 | [6 empty] | 2021-04-12 | 4 | [49 empty] | 2021-07-15 |  | 114
NST-192885 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 36.653 | No | 2021-03-23 | 2021-03-23 | 0 | 2021-03-23 | [9 empty] | 2021-03-23 | 0 | [49 empty] | 2021-03-24 |  | 1
NST-193092 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 66.517 | No | 2021-03-24 | 2021-03-24 | 0 | 2021-03-24 | [9 empty] | 2021-03-29 | 3 | [49 empty] | 2021-06-22 |  | 90
NST-193123 | SCE | NEM | NEMA | Withdrawn | Solar PV | 62.568 | No | 2021-03-24 | 2021-03-24 | 0 | 2021-03-24 | 2021-03-29 | 3 | 2021-04-06 | 2021-04-16 | 8 | 2021-04-21 | 2021-04-22 | 1
NST-193178 | SCE | NEM | NEMA | Withdrawn | Solar PV | 331.58 | No | 2021-03-24 | 2021-03-24 | 0 | 2021-03-24 | 2021-03-29 | 3 |  |  |  |  | 2021-04-13 | 10
NST-193331 | SCE | NEM | NEM-ST | Withdrawn | Solar PV | 0 | No | 2021-04-08 | 2021-04-08 | 0 | 2021-04-08 | 2021-04-20 | 8 | 2021-04-22 | 2021-05-06 | 10
NST-193452 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV + Battery Storage | 40.002 | No | 2021-03-25 | 2021-03-25 | 0 | 2021-03-25 | 2021-03-31 | 3 | 2021-03-31 | [6 empty] | 2021-04-09 | 6 | [49 empty] | 2021-04-23 |  | 29
NST-193645 | SCE | NEM | NEMA | Cancelled By Applicant | Solar PV | 340.11 | No | 2021-03-26 | 2021-03-26 | 0 | 2021-03-26 | 2021-03-30 | 2 | 2021-03-30 | [5 empty] | 2021-04-08 | 2021-04-01 | 1
NST-193648 | SCE | NEM | NEMA | Withdrawn | Solar PV | 41.266 | No | 2021-03-26 | 2021-03-26 | 0 | 2021-03-26 | 2021-03-31 | 2 | 2021-04-06 | 2021-04-29 | 17 | 2021-06-01 | 2021-07-12 | 28
NST-193674 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 46.639 | No | 2021-03-27 | 2021-03-27 | 0 | 2021-03-27 | 2021-03-29 | 0 | 2021-03-29 | 2021-04-12 | 9 | 2021-04-12 |  |  |  | 2021-04-20 | 6 | [49 empty] | 2021-04-20 |  | 24
NST-193743 | SCE | NEM | VNEM | NEMI - PTO Issued | Solar PV | 48.064 | No | 2021-03-29 | 2021-03-29 | 0 | 2021-03-29 | 2021-04-02 | 3 | 2021-04-22 | [6 empty] | 2021-05-05 | 9 | [31 empty] | 2021-08-18 | 2021-09-16 | 20 | [15 empty] | 2022-01-25 |  | 302
NST-193744 | SCE | NEM | VNEM | NEMI - PTO Issued | Solar PV | 57.676 | No | 2021-03-29 | 2021-03-29 | 0 | 2021-03-29 | 2021-04-05 | 4 | 2021-04-28 | [6 empty] | 2021-05-11 | 9 | [31 empty] | 2021-08-18 | 2021-09-16 | 20 | [15 empty] | 2022-01-24 |  | 301
NST-193796 | SCE | NEM | NEMA | Withdrawn | Solar PV | 69.017 | No | 2021-03-30 | 2021-03-30 | 0 | 2021-03-30 | 2021-04-19 | 13 | 2021-04-29 | 2021-05-17 | 12 | 2021-05-18 | 2021-04-16 | 12
NST-193836 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 77.063 | No | 2021-03-29 | 2021-03-29 | 0 | 2021-03-29 | 2021-04-01 | 2 | 2021-04-06 | 2021-05-24 | 34 | 2021-05-27 |  |  |  | 2021-06-02 | 3 | [49 empty] | 2021-07-06 |  | 99
NST-193956 | SCE | NEM | NEMA | SCE Engineer Assigned. Pending Technical Review | Solar PV | 34319.856 | No | 2021-03-31 | 2021-03-31 | 0 | 2021-03-31 | 2021-04-05 | 2 | 2021-04-06 | 2021-04-29 | 17 | 2021-04-29 |  |  |  | 2021-05-01 | 1
NST-193956 | SCE | NEM | NEM Aggregation | IA Negotiation | Solar PV | 34319.856 | No | 2021-04-06 | 2021-04-06 | 0 | 2021-04-06 | [9 empty] | 2021-05-01 | 17 | [13 empty] | 2021-06-14 |  | 2021-06-14
NST-194237 | SCE | NEM | NEMA | Withdrawn | Solar PV | 235.488 | No | 2021-03-30 | 2021-03-30 | 0 | 2021-03-30 | 2021-04-19 | 13 | 2021-05-24 |  |  |  | 2021-06-09 | 11
NST-194276 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 143.503 | No | 2021-03-31 | 2021-03-31 | 0 | 2021-03-31 | 2021-04-05 | 2 | 2021-05-05 | [6 empty] | 2021-05-17 | 8 | [49 empty] | 2021-09-10 |  | 163
NST-194404 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 30.665 | No | 2021-03-31 | 2021-03-31 | 0 | 2021-03-31 | [9 empty] | 2021-04-01 | 0 | [49 empty] | 2022-01-04 |  | 279
NST-194428 | SCE | NEM | NEMA | Withdrawn | Solar PV | 457.644 | No | 2021-03-31 | 2021-03-31 | 0 | 2021-03-31 | 2021-04-08 | 5 | 2021-04-16 | 2021-04-23 | 5 |  | 2021-05-03 | 6
NST-194496 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 333.058 | No | 2021-03-31 | 2021-03-31 | 0 | 2021-03-31 | 2021-04-19 | 12 | 2021-04-20 | 2021-05-10 | 14 | 2021-05-13 |  |  |  | 2021-05-21 | 6 | [49 empty] | 2021-09-28 |  | 181
NST-194583 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 43.214 | No | 2021-04-01 | 2021-04-01 | 0 | 2021-04-01 | 2021-04-02 | 1 | 2021-04-09 | [6 empty] | 2021-04-15 | 4 | [49 empty] | 2021-05-05 |  | 34
NST-194634 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 54.615 | No | 2021-04-01 | 2021-04-01 | 0 | 2021-04-01 | [9 empty] | 2021-04-07 | 4 | [49 empty] | 2021-04-27 |  | 26
NST-194659 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 36.832 | No | 2021-04-05 | 2021-04-05 | 0 | 2021-04-05 | [9 empty] | 2021-04-15 | 8 | [49 empty] | 2021-04-21 |  | 16
NST-194756 | SCE | NEM | NEMA | SCE Engineer Assigned. Pending Technical Review | Solar PV + Battery Storage | 632.432 | No | 2021-04-01 | 2021-04-01 | 0 | 2021-04-01 | 2021-04-16 | 11 | 2021-05-19 | 2021-06-03 | 10 | 2021-06-03 | 2021-06-02 | 9 |  | 2021-06-07 | 2
NST-194756 | SCE | NEM | NEM-ST | On Hold |  | 632.432 | No |  |  |  | 2021-06-03
NST-194764 | SCE | NEM | NEM Aggregation | Withdrawn | Solar PV | 0 | No |  |  |  | 2021-05-18
NST-194977 | SCE | NEM | Other-NEM-V | NEMI - PTO Issued | Solar PV | 46.155 | No | 2021-04-02 | 2021-04-02 | 0 | 2021-04-02 | 2021-04-22 | 14 | 2021-04-26 | 2021-05-21 | 19 | 2021-05-23 |  |  |  | 2021-06-01 | 5 | [49 empty] | 2021-06-18 |  | 77
NST-195095 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 303.348 | No | 2021-04-05 | 2021-04-05 | 0 | 2021-04-05 | 2021-04-12 | 5 | 2021-04-22 | [6 empty] | 2021-04-30 | 6
NST-195132 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 132.698 | No | 2021-04-05 | 2021-04-05 | 0 | 2021-04-05 | 2021-04-05 | 0 | 2021-04-12 | 2021-05-06 | 18 | 2021-05-10 |  |  |  | 2021-05-12 | 2 | [49 empty] | 2021-09-02 |  | 150
NST-195313 | SCE | NEM | NEMA | SCE Engineer. Supplemental Review Complete | Solar PV | 2888.109 | No | 2021-04-06 | 2021-04-06 | 0 | 2021-04-06 | 2021-04-09 | 3 | 2021-05-17 | [6 empty] | 2021-08-17 | 64
NST-195313 | SCE | NEM | NEM-ST | Application Review In Progress | Solar PV | 2888.109 | No |  |  |  | 2021-05-17
NST-195484 | SCE | NEM | NEMA | Withdrawn | Solar PV | 6062.846 | No | 2021-04-06 | 2021-04-06 | 0 | 2021-04-06 | 2021-04-09 | 3 | 2021-04-09 | 2021-04-13 | 2 |  | 2021-04-21 | 6
NST-195562 | SCE | NEM | NEMA | Meter Request Released. Pending NGOM installation | Solar PV | 322.637 | No | 2021-04-07 | 2021-04-07 | 0 | 2021-04-07 | 2021-04-16 | 7 | 2021-04-16 | [6 empty] | 2021-04-26 | 6 | [31 empty] | 2021-09-14
NST-195562 | SCE | NEM | NEM-ST | Construction | Solar PV | 322.637 | No | 2021-04-27 | 2021-04-27 | 0 | 2021-04-27 | 2021-05-20 | 17 | 2021-06-10 | [6 empty] | 2021-06-24 | 10 | [22 empty] | 2021-09-21 | 2021-09-23 | 2
NST-195661 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 35.483 | No | 2021-04-07 | 2021-04-07 | 0 | 2021-04-07 | 2021-05-13 | 26 | 2021-05-17 | [6 empty] | 2021-05-17 | 0 | [49 empty] | 2021-06-02 |  | 56
NST-195808 | SCE | NEM | NEMA | NEMI - Pending Permanent Service | Solar PV + Battery Storage | 34.142 | No | 2021-04-08 | 2021-04-08 | 0 | 2021-04-08 | [9 empty] | 2021-04-19 | 7
NST-195934 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 54.666 | No | 2021-04-08 | 2021-04-08 | 0 | 2021-04-08 | 2021-04-15 | 5 | 2021-04-27 | [6 empty] | 2021-05-07 | 8 | [49 empty] | 2021-09-30 |  | 175
NST-196012 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 233.246 | No | 2021-04-09 | 2021-04-09 | 0 | 2021-04-09 | 2021-04-21 | 8 | 2021-04-22 | [6 empty] | 2021-05-05 | 9 | [49 empty] | 2021-09-16 |  | 160
NST-196126 | SCE | NEM | NEMA | Withdrawn | Solar PV | 275.571 | No | 2021-04-09 | 2021-04-09 | 0 | 2021-04-09 | 2021-04-16 | 5 |  |  |  |  | 2021-05-03 | 11
NST-196192 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 31.461 | No | 2021-04-10 | 2021-04-10 | 0 | 2021-04-10 | [9 empty] | 2021-04-19 | 5 | [49 empty] | 2021-05-05 |  | 25
NST-196195 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 54.737 | No | 2021-04-10 | 2021-04-10 | 0 | 2021-04-10 | [9 empty] | 2021-05-04 | 16 | [49 empty] | 2021-05-13 |  | 33
NST-196218 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV + Battery Storage | 342.455 | No | 2021-04-11 | 2021-04-11 | 0 | 2021-04-11 | [9 empty] | 2021-04-21 | 7 | [49 empty] | 2022-02-23 |  | 318
NST-196299 | SCE | NEM | NEMA | Withdrawn | Solar PV | 33.849 | No | 2021-04-12 | 2021-04-12 | 0 | 2021-04-12 | 2021-04-13 | 1 | 2021-04-26 | 2021-05-19 | 17 | 2021-05-26 | 2021-06-09 | 9
NST-196306 | SCE | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 34.396 | No | 2021-04-12 | 2021-04-12 | 0 | 2021-04-12 | 2021-04-19 | 5 | 2021-04-19 | [6 empty] | 2021-04-23 | 4
NST-196317 | SCE | NEM | NEMA | NEMI - Equipment Change Submitted | Solar PV | 140.143 | No | 2021-04-12 | 2021-04-12 | 0 | 2021-04-12 | [9 empty] | 2021-04-19 | 5
NST-196394 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 878.495 | No | 2021-04-12 | 2021-04-12 | 0 | 2021-04-12 | 2021-04-20 | 6 | 2021-04-21 | 2021-06-02 | 29 | 2021-06-02 |  |  |  | 2021-06-08 | 4 | [49 empty] | 2021-09-30 |  | 171
NST-196494 | SCE | NEM | VNEM | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 53.755 | No | 2021-04-19 | 2021-04-19 | 0 | 2021-04-19 | 2021-04-27 | 6 | 2021-05-06 | [6 empty] | 2021-05-07 | 1
NST-196563 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 860.628 | No | 2021-04-13 | 2021-04-13 | 0 | 2021-04-13 | 2021-04-23 | 8 | 2021-04-26 | [6 empty] | 2021-05-10 | 10 | [49 empty] | 2022-02-04 |  | 297
NST-196626 | SCE | NEM | VNEM | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 74.891 | No | 2021-04-13 | 2021-04-13 | 0 | 2021-04-13 | 2021-04-22 | 7 | 2021-04-22 | [6 empty] | 2021-04-27 | 3 | [31 empty] | 2021-06-04 | 2021-09-15 | 71
NST-196646 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 332.4 | No | 2021-04-13 | 2021-04-13 | 0 | 2021-04-13 | 2021-04-14 | 1 | 2021-04-14 | [6 empty] | 2021-04-21 | 5
NST-196660 | SCE | NEM | VNEM | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 55.248 | No | 2021-04-13 | 2021-04-13 | 0 | 2021-04-13 | 2021-04-22 | 7 | 2021-04-22 | [6 empty] | 2021-04-28 | 4 | [31 empty] | 2021-06-04 | 2021-09-15 | 71
NST-196662 | SCE | NEM | VNEM | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 60.159 | No | 2021-04-13 | 2021-04-13 | 0 | 2021-04-13 | 2021-04-21 | 6 | 2021-04-21 | [6 empty] | 2021-04-28 | 5 | [31 empty] | 2021-06-02 | 2021-09-15 | 73
NST-196668 | SCE | NEM | VNEM | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 77.347 | No | 2021-04-13 | 2021-04-13 | 0 | 2021-04-13 | 2021-04-21 | 6 | 2021-04-21 | [6 empty] | 2021-04-27 | 4 | [31 empty] | 2021-06-04 | 2021-09-15 | 71
NST-196790 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 187.176 | No | 2021-04-14 | 2021-04-14 | 0 | 2021-04-14 | 2021-04-21 | 5 | 2021-04-21 | [6 empty] | 2021-04-30 | 7 | [49 empty] | 2022-02-04 |  | 296
NST-196800 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 187.176 | No | 2021-04-14 | 2021-04-14 | 0 | 2021-04-14 | 2021-04-21 | 5 | 2021-04-21 | [6 empty] | 2021-05-06 | 11 | [49 empty] | 2022-02-23 |  | 315
NST-196887 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Construction | Solar PV | 624.316 | No | 2021-04-14 | 2021-04-14 | 0 | 2021-04-14 | [9 empty] | 2021-04-21 | 5
NST-197118 | SCE | NEM | VNEM | Cancelled By Applicant | Solar PV | 331.66 | No | 2021-04-15 | 2021-04-15 | 0 | 2021-04-15 | 2021-04-26 | 7 | 2021-05-06 | [5 empty] | 2021-05-17
NST-197147 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 38.757 | No | 2021-04-15 | 2021-04-15 | 0 | 2021-04-15 | 2021-04-22 | 5 | 2021-04-22 | [6 empty] | 2021-04-28 | 4
NST-197171 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 94.49 | No | 2021-04-15 | 2021-04-15 | 0 | 2021-04-15 | [9 empty] | 2021-04-22 | 5
NST-197197 | SCE | NEM | VNEM | NGOM Installation. Pending New Service Request and AHJ Panel Permit | Solar PV | 40.268 | No | 2021-04-15 | 2021-04-15 | 0 | 2021-04-15 | 2021-04-26 | 7 | 2021-05-05 | [6 empty] | 2021-05-17 | 8 | [31 empty] | 2021-05-25 | 2021-09-15 | 78
NST-197227 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Construction | Solar PV | 313.057 | No | 2021-04-15 | 2021-04-15 | 0 | 2021-04-15 | 2021-04-22 | 5 | 2021-04-26 | [6 empty] | 2021-04-27 | 1
NST-197230 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Construction | Solar PV | 187.834 | No | 2021-04-15 | 2021-04-15 | 0 | 2021-04-15 | 2021-04-26 | 7 | 2021-04-27 | [6 empty] | 2021-05-05 | 6
NST-197236 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Construction | Solar PV | 211.024 | No | 2021-04-15 | 2021-04-15 | 0 | 2021-04-15 | 2021-04-26 | 7 | 2021-05-10 | [6 empty] | 2021-05-20 | 8
NST-197341 | SCE | NEM | NEMA | NEMI - Sent to Engineering | Solar PV | 800.715 | No | 2021-04-15 | 2021-04-15 | 0 | 2021-04-15 | 2021-05-05 | 14 | 2021-05-20 | 2021-05-27 | 5 | 2021-05-27 |  |  |  | 2021-06-03 | 4
NST-197341 | SCE | NEM | NEM Aggregation | Construction | Solar PV | 800.715 | No | 2021-06-03 | 2021-06-03 | 0 | 2021-06-03 | 2021-06-11 | 6 | 2021-06-25 | [6 empty] | 2021-06-30 | 3 | 2021-06-30 | 2021-07-14 | 9 |  |  | 2021-07-14 | 2021-08-13 | 22 | 2021-08-26 | 9 | [12 empty] | 2021-09-21 | 2021-09-28 | 5 |  | 2021-10-20 | 22
NST-197515 | SCE | NEM | NEMA | Withdrawn | Solar PV | 31.536 | No | 2021-04-16 | 2021-04-16 | 0 | 2021-04-16 | [9 empty] | 2021-04-16 | 0 | [49 empty] | 2021-04-19 |  | 3
NST-197545 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 31.827 | No | 2021-04-16 | 2021-04-16 | 0 | 2021-04-16 | [9 empty] | 2021-04-19 | 1
NST-197557 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 132.549 | No | 2021-04-16 | 2021-04-16 | 0 | 2021-04-16 | 2021-05-04 | 12 | 2021-05-12 | 2021-05-28 | 12 | 2021-05-28 |  |  |  | 2021-06-04 | 4
NST-197794 | SCE | NEM | NEM-ST | Construction | Solar PV | 80.632 | No | 2021-06-04 | 2021-06-04 | 0 | 2021-06-04 | [33 empty] | 2021-07-19 | 2021-07-23 | 4 |  | 2021-09-13 | 52
NST-197794 | SCE | NEM | VNEM | SCE Engineer Review. Pending SCE System Upgrades | Solar PV | 80.632 | No | 2021-04-19 | 2021-04-19 | 0 | 2021-04-19 | 2021-04-27 | 6 | 2021-05-06 | 2021-05-11 | 3 | 2021-05-11 |  |  |  | 2021-05-18 | 5
NST-197857 | SCE | NEM | VNEM | SCE Engineer Review. Pending SCE System Upgrades | Solar PV | 106.669 | No | 2021-04-19 | 2021-04-19 | 0 | 2021-04-19 | 2021-04-27 | 6 | 2021-05-06 | 2021-05-10 | 2 | 2021-05-11 |  |  |  | 2021-05-13 | 2
NST-197886 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 337.896 | No | 2021-04-19 | 2021-04-19 | 0 | 2021-04-19 | 2021-04-26 | 5 | 2021-05-05 | [6 empty] | 2021-05-17 | 8 | [49 empty] | 2022-02-17 |  | 304
NST-197957 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 148.762 | No | 2021-04-20 | 2021-04-20 | 0 | 2021-04-20 | 2021-04-26 | 4 | 2021-05-10 | [6 empty] | 2021-05-11 | 1 | [49 empty] | 2021-09-29 |  | 162
NST-198052 | SCE | NEM | NEMA | Applicant Response Received. Pending SCE Engineer Review | Solar PV | 866.874 | No | 2021-04-20 | 2021-04-20 | 0 | 2021-04-20 | 2021-04-26 | 4 | 2021-05-05 | 2021-05-13 | 6 | 2021-05-20 |  |  |  | 2021-05-28 | 6
NST-198058 | SCE | NEM | NEMA | Applicant Response Received. Pending SCE Engineer Review | Solar PV | 121.362 | No | 2021-04-20 | 2021-04-20 | 0 | 2021-04-20 | 2021-04-30 | 8 | 2021-05-05 | 2021-05-12 | 5 | 2021-05-13 |  |  |  | 2021-05-19 | 4
NST-198066 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 316.1 | No | 2021-04-20 | 2021-04-20 | 0 | 2021-04-20 | 2021-04-29 | 7 | 2021-05-06 | [6 empty] | 2021-05-06 | 0 | [49 empty] | 2021-09-09 |  | 142
NST-198231 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 41.363 | No | 2021-04-21 | 2021-04-21 | 0 | 2021-04-21 | 2021-04-28 | 5 | 2021-05-05 | 2021-06-08 | 23 | 2021-06-08 |  |  |  | 2021-06-10 | 2 | [49 empty] | 2021-06-17 |  | 57
NST-198252 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 301.746 | No | 2021-05-06 | 2021-05-06 | 0 | 2021-05-06 | [9 empty] | 2021-05-20 | 10
NST-198270 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 50 | No | 2021-04-21 | 2021-04-21 | 0 | 2021-04-21 | 2021-04-27 | 4 | 2021-05-05 | [6 empty] | 2021-05-12 | 5 | [49 empty] | 2021-07-07 |  | 77
NST-198436 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 62.568 | No | 2021-04-22 | 2021-04-22 | 0 | 2021-04-22 | 2021-04-28 | 4 | 2021-05-10 | [6 empty] | 2021-05-20 | 8 | [49 empty] | 2021-05-25 |  | 33
NST-198538 | SCE | NEM | NEMA | SCE Engineer Assigned. Pending Technical Review | Solar PV | 3740.773 | No | 2021-04-22 | 2021-04-22 | 0 | 2021-04-22 | [9 empty] | 2021-06-18 | 40
NST-198538 | SCE | NEM | NEM-ST | IA Negotiation | Solar PV | 3740.773 | No | 2021-04-28 | 2021-04-28 | 0 | 2021-04-28 | 2021-05-13 | 11 | 2021-06-18 | [6 empty] | 2021-06-29 | 7 | [10 empty] | 2021-07-09 | 2021-08-10 | 22 | 2021-08-10 | 0 | 2021-08-16 | 2021-08-25 | 7 | 2021-10-04 | 2022-01-06 | 62 |  |  | 2022-01-21 |  | 15
NST-198742 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 50 | No | 2021-04-23 | 2021-04-23 | 0 | 2021-04-23 | 2021-04-29 | 4 | 2021-05-05 | 2021-05-27 | 16 | 2021-05-31 |  |  |  | 2021-06-03 | 2 | [49 empty] | 2021-07-27 |  | 95
NST-198752 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 137.073 | No | 2021-04-23 | 2021-04-23 | 0 | 2021-04-23 | 2021-04-29 | 4 | 2021-04-29 | [6 empty] | 2021-05-12 | 9 | [49 empty] | 2021-05-20 |  | 27
NST-198827 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 1641.354 | No | 2021-04-23 | 2021-04-23 | 0 | 2021-04-23 | 2021-04-28 | 3 | 2021-05-05 | [6 empty] | 2021-06-23 | 34
NST-198827 | SCE | NEM | NEM-ST | IA Negotiation | Solar PV | 1641.354 | No | 2021-05-05 | 2021-05-05 | 0 | 2021-05-05 | 2021-05-19 | 10 | 2021-06-09 | [6 empty] | 2021-06-23 | 10 | 2021-06-23 | 2021-07-16 | 16 |  |  | 2021-08-23 | 2021-09-21 | 20 | 2021-10-13 | 15
NST-198832 | SCE | NEM | Other-NEM-V | NEMI - Conditional PTO | Solar PV | 85.937 | No | 2021-04-23 | 2021-04-23 | 0 | 2021-04-23 | 2021-05-05 | 8 | 2021-05-11 | [6 empty] | 2021-05-21 | 8 | [49 empty] | 2022-02-07 |  | 290
NST-199009 | SCE | NEM | NEM-ST | Construction | Solar PV | 575.484 | No | 2021-05-24 | 2021-05-24 | 0 | 2021-05-24 | [33 empty] | 2021-08-25 | 2021-09-16 | 15 |  | 2021-10-14 | 28
NST-199009 | SCE | NEM | NEMA | NEMI - Returned from Engineering | Solar PV | 575.484 | No | 2021-04-26 | 2021-04-26 | 0 | 2021-04-26 | 2021-05-03 | 5 | 2021-05-17 | [6 empty] | 2021-05-24 | 5
NST-199024 | SCE | NEM | NEM-ST | IA Negotiation | Solar PV | 725.873 | No | 2021-06-08 | 2021-06-08 | 0 | 2021-06-08 | 2021-06-11 | 3 | 2021-06-28 | 2021-07-06 | 5 | 2021-07-26 |  |  |  | 2021-08-04 | 7 | 2021-08-04 | 2021-08-04 | 0 |  |  | 2021-08-04 | 2021-08-31 | 19 | 2021-09-22 | 15 | [12 empty] | 2022-03-09
NST-199024 | SCE | NEM | NEMA | SCE Engineer. Supplemental Review Complete | Solar PV + Battery Storage | 725.873 | No | 2021-04-26 | 2021-04-26 | 0 | 2021-04-26 | 2021-05-21 | 19 | 2021-06-04 | [6 empty] | 2021-06-08 | 2
NST-199260 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 690.54 | No | 2021-04-27 | 2021-04-27 | 0 | 2021-04-27 | 2021-05-04 | 5 | 2021-05-07 | 2021-05-13 | 4 | 2021-05-24 |  |  |  | 2021-05-26 | 2 | [49 empty] | 2021-08-20 |  | 115
NST-199299 | SCE | NEM | VNEM | Meter Request Released. Pending NGOM installation | Solar PV | 42.03 | No | 2021-05-03 | 2021-05-03 | 0 | 2021-05-03 | 2021-05-11 | 6 | 2021-05-24 | 2021-06-17 | 17 | 2021-06-18 |  |  |  | 2021-06-22 | 2 | [31 empty] | 2021-08-23 | 2021-09-21 | 20
NST-199306 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV + Battery Storage | 57.512 | No | 2021-04-27 | 2021-04-27 | 0 | 2021-04-27 | [9 empty] | 2021-05-04 | 5
NST-199341 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 57.533 | No | 2021-04-27 | 2021-04-27 | 0 | 2021-04-27 | 2021-05-04 | 5 | 2021-05-13 | 2021-05-19 | 4 | 2021-05-26 |  |  |  | 2021-06-08 | 8
NST-199389 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 276.258 | No | 2021-04-27 | 2021-04-27 | 0 | 2021-04-27 | [9 empty] | 2021-05-04 | 5 | [49 empty] | 2022-03-16 |  | 323
NST-199579 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 119.693 | No | 2021-04-28 | 2021-04-28 | 0 | 2021-04-28 | 2021-05-10 | 8 | 2021-05-12 | 2021-05-19 | 5 | 2021-05-28 |  |  |  | 2021-06-03 | 3 | [49 empty] | 2021-09-28 |  | 153
NST-199608 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 163.882 | No | 2021-04-28 | 2021-04-28 | 0 | 2021-04-28 | 2021-05-06 | 6 | 2021-06-09 | 2021-06-11 | 2 | 2021-06-15 |  |  |  | 2021-06-21 | 4 | [49 empty] | 2022-03-16 |  | 322
NST-199613 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 525.855 | No | 2021-04-29 | 2021-04-29 | 0 | 2021-04-29 | 2021-05-11 | 8 | 2021-05-11 | [6 empty] | 2021-05-18 | 5 | [49 empty] | 2021-08-06 |  | 99
NST-199653 | SCE | NEM | NEMA | Withdrawn | Solar PV | 39.379 | No | 2021-04-28 | 2021-04-28 | 0 | 2021-04-28 | 2021-05-06 | 6 |  |  |  |  | 2021-05-21 | 11
NST-199706 | SCE | NEM | NEMA | SCE Engineer. Initial Review Complete | Solar PV | 6062.846 | No | 2021-04-28 | 2021-04-28 | 0 | 2021-04-28 | [9 empty] | 2021-08-03 | 67
NST-199706 | SCE | NEM | NEM-ST | Phase I Complete | Solar PV | 6062.846 | No | 2021-04-28 | 2021-04-28 | 0 | 2021-04-28 | 2021-05-13 | 11 | 2021-06-25 | 2021-07-13 | 11 | 2021-07-27 |  |  |  | 2021-08-02 | 4 | [10 empty] | 2021-08-02 | 2021-08-30 | 20 |  |  | 2021-09-09 | 2021-10-01 | 16 | 2021-12-08 | 2022-03-11 | 63
NST-199716 | SCE | NEM | NEMA | Pending Agreement Approval/Execution | Solar PV | 2378.373 | No | 2021-05-11 | 2021-05-11 | 0 | 2021-05-11 | 2021-05-14 | 3 | 2021-06-02 | 2021-06-16 | 10 | 2021-07-14 |  |  |  | 2021-08-13 | 22
NST-199716 | SCE | NEM | NEM-ST | Construction | Solar PV | 2378.373 | No | 2021-07-14 | 2021-07-14 | 0 | 2021-07-14 | 2021-07-28 | 10 | 2021-08-09 | [6 empty] | 2021-08-13 | 4 | 2021-08-13 | 2021-09-01 | 13 |  |  | 2021-09-13 | 2021-10-11 | 20 | 2021-11-04 | 17 | [16 empty] | 2022-03-23 | 44643
NST-199736 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 48.399 | No | 2021-04-29 | 2021-04-29 | 0 | 2021-04-29 | [9 empty] | 2021-05-11 | 8 | [49 empty] | 2021-06-11 |  | 43
NST-200073 | SCE | NEM | NEM-ST | Transferred to NEM | Solar PV | 0 | No |  |  |  | 2021-04-30
NST-200175 | SCE | NEM | NEMA | SCE Engineer Review. Pending SCE System Upgrades | Solar PV | 2907.78 | No | 2021-04-30 | 2021-04-30 | 0 | 2021-04-30 | 2021-05-05 | 3 | 2021-05-13 | 2021-05-17 | 2 | 2021-05-24 |  |  |  | 2021-07-06 | 29
NST-200175 | SCE | NEM | NEM Aggregation | Construction | Solar PV | 2907.78 | No | 2021-05-24 | 2021-05-24 | 0 | 2021-05-24 | 2021-06-24 | 22 | 2021-06-28 | [6 empty] | 2021-07-06 | 5 | 2021-07-06 | 2021-07-27 | 15 |  |  | 2021-07-30 | 2021-08-27 | 20 | 2021-09-17 | 14 | [13 empty] | 2021-10-04 | 10 |  | 2022-01-11 | 99
NST-200251 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 98 | No | 2021-05-03 | 2021-05-03 | 0 | 2021-05-03 | 2021-05-11 | 6 | 2021-05-25 | [6 empty] | 2021-06-02 | 5 | [49 empty] | 2021-07-20 |  | 78
NST-200259 | SCE | NEM | VNEM | NGOM Requirements Met. Pending Local Planner SO Release | Solar PV | 51.37 | No | 2021-05-03 | 2021-05-03 | 0 | 2021-05-03 | 2021-05-13 | 8 | 2021-05-24 | 2021-05-25 | 1 | 2021-05-26 |  |  |  | 2021-06-02 | 4 | [31 empty] | 2021-08-23 | 2021-09-21 | 20
NST-200293 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 41.101 | No | 2021-05-03 | 2021-05-03 | 0 | 2021-05-03 | 2021-05-04 | 1 | 2021-05-18 | [6 empty] | 2021-05-24 | 4 | [49 empty] | 2021-09-28 |  | 148
NST-200315 | SCE | NEM | NEMA | Withdrawn | Solar PV + Battery Storage | 81 | No | 2021-05-03 | 2021-05-03 | 0 | 2021-05-03 | 2021-05-10 | 5 | 2021-05-10 | 2021-06-16 | 26 |  | 2021-07-28 | 29
NST-200329 | SCE | NEM | NEMA | Withdrawn | Solar PV | 317.739 | No | 2021-05-03 | 2021-05-03 | 0 | 2021-05-03 | 2021-05-11 | 6 | 2021-05-23 | 2021-05-24 | 0 |  | 2021-06-02 | 6
NST-200341 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV + Battery Storage | 529.334 | No | 2021-05-03 | 2021-05-03 | 0 | 2021-05-03 | 2021-05-11 | 6 | 2021-05-14 | [6 empty] | 2021-05-19 | 3
NST-200347 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 257.41 | No | 2021-05-03 | 2021-05-03 | 0 | 2021-05-03 | 2021-05-11 | 6 | 2021-05-18 | 2021-05-25 | 5 | 2021-06-04 |  |  |  | 2021-06-14 | 6 | [49 empty] | 2022-02-11 |  | 284
NST-200411 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 174.211 | No | 2021-05-03 | 2021-05-03 | 0 | 2021-05-03 | 2021-05-10 | 5 | 2021-05-14 | [6 empty] | 2021-05-25 | 7 | [49 empty] | 2022-02-09 |  | 282
NST-200414 | SCE | NEM | NEMA | NEMI - Returned from Engineering | Solar PV | 152.733 | No | 2021-05-03 | 2021-05-03 | 0 | 2021-05-03 | 2021-05-10 | 5 | 2021-05-14 | 2021-05-25 | 7 | 2021-06-04 |  |  |  | 2021-06-14 | 6
NST-200454 | SCE | NEM | NEM-ST | Withdrawn | Solar PV | 1583.53 | No | 2021-05-25 | 2021-05-25 | 0 | 2021-05-25 | 2021-06-10 | 11 | 2021-07-06 | 2021-07-20 | 10 | 2021-07-30
NST-200454 | SCE | NEM | NEMA | Withdrawn | Solar PV + Battery Storage | 1583.53 | No | 2021-05-03 | 2021-05-03 | 0 | 2021-05-03 | 2021-05-06 | 3 | 2021-05-17 | 2021-05-19 | 2 | 2021-05-25 | 2021-09-20 | 81 |  | 2021-06-25 | 22
NST-200473 | SCE | NEM | NEMA | Pending Agreement Approval/Execution | Solar PV | 1124.734 | No | 2021-05-03 | 2021-05-03 | 0 | 2021-05-03 | [9 empty] | 2021-05-20 | 13
NST-200473 | SCE | NEM | NEM-ST | Pending PTO | Solar PV | 1124.734 | No | 2021-05-03 | 2021-05-03 | 0 | 2021-05-03 | 2021-05-17 | 10 | 2021-05-20 | [6 empty] | 2021-05-21 | 1 | 2021-05-21 | 2021-06-14 | 15 |  |  | 2021-06-29 | 2021-07-28 | 20 | 2021-08-17 | 14 | [13 empty] | 2021-09-07 | 3 |  | 2021-10-06 | 29
NST-200525 | SCE | NEM | NEMA | Applicant Response Received. Pending SCE Engineer Review | Solar PV | 275.571 | No | 2021-05-04 | 2021-05-04 | 0 | 2021-05-04 | [9 empty] | 2021-05-19 | 11
NST-200574 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 51.297 | No | 2021-05-04 | 2021-05-04 | 0 | 2021-05-04 | 2021-05-11 | 5 | 2021-05-13 | 2021-09-23 | 92 | 2021-09-30
NST-200654 | SCE | NEM | NEMA | Withdrawn | Solar PV | 31.34 | No | 2021-05-04 | 2021-05-04 | 0 | 2021-05-04 | [9 empty] | 2021-06-24 | 36
NST-200678 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 63.644 | No | 2021-05-04 | 2021-05-04 | 0 | 2021-05-04 | [9 empty] | 2021-05-11 | 5 | [49 empty] | 2021-08-20 |  | 108
NST-200860 | SCE | NEM | NEMA | Withdrawn | Solar PV | 70.996 | No | 2021-05-05 | 2021-05-05 | 0 | 2021-05-05 | 2021-05-12 | 5 | [6 empty] | 2021-05-27
NST-200907 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Construction | Solar PV | 144.307 | No | 2021-05-05 | 2021-05-05 | 0 | 2021-05-05 | [9 empty] | 2021-05-12 | 5
NST-200986 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 59.4 | No | 2021-05-05 | 2021-05-05 | 0 | 2021-05-05 | [9 empty] | 2021-05-12 | 5 | [49 empty] | 2021-06-22 |  | 48
NST-201002 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 37.948 | No | 2021-05-05 | 2021-05-05 | 0 | 2021-05-05 | 2021-05-14 | 7 | 2021-05-14 | 2021-05-19 | 3 | 2021-05-19 |  |  |  | 2021-06-01 | 8 | [49 empty] | 2021-06-09 |  | 35
NST-201083 | SCE | NEM | NEMA | Withdrawn | Solar PV | 407.95 | No | 2021-05-06 | 2021-05-06 | 0 | 2021-05-06 | 2021-05-13 | 5 | 2021-05-13 | [5 empty] | 2021-06-04
NST-201222 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 33.576 | No | 2021-05-06 | 2021-05-06 | 0 | 2021-05-06 | 2021-05-17 | 7 | 2021-05-23 | 2021-05-26 | 2 | 2021-06-13 |  |  |  | 2021-06-16 | 2 | [49 empty] | 2021-06-21 |  | 46
NST-201244 | SCE | NEM | NEMA | Withdrawn | Solar PV | 89.208 | No | 2021-05-06 | 2021-05-06 | 0 | 2021-05-06 | 2021-05-13 | 5 | 2021-05-20 | 2021-05-21 | 1 |  | 2021-06-04 | 9
NST-201770 | SCE | NEM | NEMA | Applicant Response Received. Pending SCE Engineer Review | Solar PV | 999.174 | No | 2021-05-10 | 2021-05-10 | 0 | 2021-05-10 | 2021-05-13 | 3 | 2021-05-21 | 2021-05-27 | 4 | 2021-06-01 |  |  |  | 2021-07-07 | 25
NST-201770 | SCE | NEM | NEM Aggregation | Construction | Solar PV | 999.174 | No | 2021-06-08 | 2021-06-08 | 0 | 2021-06-08 | 2021-06-22 | 10 | 2021-06-28 | [6 empty] | 2021-07-07 | 6 | 2021-07-07 | 2021-07-26 | 13 |  |  | 2021-07-28 | 2021-08-23 | 18 | 2021-09-10 | 13 | [12 empty] | 2021-10-13 |  |  |  | 2022-02-10 | 44602
NST-201854 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 52.021 | No | 2021-05-10 | 2021-05-10 | 0 | 2021-05-10 | [9 empty] | 2021-05-14 | 4 | [49 empty] | 2021-09-22 |  | 135
NST-201925 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 34.809 | No | 2021-06-08 | 2021-06-08 | 0 | 2021-06-08 | 2021-06-09 | 1 | 2021-06-11 | [6 empty] | 2021-06-16 | 3 | [49 empty] | 2021-07-15 |  | 37
NST-201927 | SCE | NEM | NEMA | Withdrawn | Solar PV | 30.716 | No | 2021-07-02 | 2021-07-02 | 0 | 2021-07-02 | 2021-07-12 | 5 |  |  |  |  | 2021-08-13 | 24
NST-201936 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 34.33 | No | 2021-05-11 | 2021-05-11 | 0 | 2021-05-11 | [9 empty] | 2021-05-18 | 5 | [49 empty] | 2021-05-20 |  | 9
NST-201942 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 54.899 | No | 2021-05-11 | 2021-05-11 | 0 | 2021-05-11 | 2021-05-17 | 4 | 2021-05-26 | [6 empty] | 2021-07-02 | 26 | [49 empty] | 2021-07-02 |  | 52
NST-201978 | SCE | NEM | NEMA | Applicant Response Received. Pending SCE Engineer Review | Solar PV | 905.878 | No | 2021-05-11 | 2021-05-11 | 0 | 2021-05-11 | 2021-05-19 | 6 | 2021-05-20 | 2021-05-26 | 4 | 2021-05-26 |  |  |  | 2021-05-27 | 1
NST-201978 | SCE | NEM | NEM Aggregation | Construction | Solar PV | 905.878 | No | 2021-05-27 | 2021-05-27 | 0 | 2021-05-27 | [9 empty] | 2021-05-27 | 13 | 2021-06-16 | 2021-07-08 | 15 |  |  | 2021-07-08 | 2021-08-05 | 20 | [14 empty] | 2021-08-09 | 2021-09-03 | 19 |  | 2021-10-26 | 53
NST-202268 | SCE | NEM | NEMA | Pending Agreement Approval/Execution | Solar PV | 333.058 | No | 2021-05-12 | 2021-05-12 | 0 | 2021-05-12 | [9 empty] | 2021-05-19 | 5
NST-202268 | SCE | NEM | NEM Aggregation | Pending PTO | Solar PV | 333.058 | No | 2021-05-12 | 2021-05-12 | 0 | 2021-05-12 | [9 empty] | 2021-05-19 | 5 | 2021-06-15 | 2021-07-06 | 14 | 2021-07-06 | 0 | [17 empty] | 2021-07-26 | 2021-08-02 | 5 |  | 2021-09-21 | 50
NST-202288 | SCE | NEM | NEMA | Withdrawn | Solar PV | 136.614 | No | 2021-05-12 | 2021-05-12 | 0 | 2021-05-12 | 2021-05-12 | 0 | [6 empty] | 2021-05-27
NST-202352 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 38.668 | No | 2021-05-12 | 2021-05-12 | 0 | 2021-05-12 | 2021-05-18 | 4 | 2021-05-18 | [6 empty] | 2021-05-21 | 3 | [49 empty] | 2021-07-01 |  | 50
NST-202386 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 344.163 | No | 2021-05-12 | 2021-05-12 | 0 | 2021-05-12 | [9 empty] | 2021-05-18 | 4 | [49 empty] | 2021-05-25 |  | 13
NST-202800 | SCE | NEM | NEM Aggregation | Transferred to NEM | Solar PV | 0.024951 | No |  |  |  | 2021-07-26
NST-202821 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 95.01 | No | 2021-05-14 | 2021-05-14 | 0 | 2021-05-14 | 2021-05-19 | 3 | 2021-05-28 | [6 empty] | 2021-06-02 | 2 | [49 empty] | 2021-09-28 |  | 137
NST-202824 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 122.263 | No | 2021-05-14 | 2021-05-14 | 0 | 2021-05-14 | [9 empty] | 2021-05-21 | 5 | [49 empty] | 2022-02-03 |  | 265
NST-202829 | SCE | NEM | NEMA | Withdrawn | Solar PV | 156.052 | No | 2021-05-14 | 2021-05-14 | 0 | 2021-05-14 | 2021-05-20 | 4 |  |  |  |  | 2021-06-07 | 11
NST-202901 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 235.488 | No | 2021-05-15 | 2021-05-15 | 0 | 2021-05-15 | 2021-05-24 | 5 | 2021-06-01 | [6 empty] | 2021-06-03 | 2 | [49 empty] | 2021-08-09 |  | 86
NST-202908 | SCE | NEM | Other-NEM-V | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 139.168 | No | 2021-05-16 | 2021-05-16 | 0 | 2021-05-16 | 2021-05-26 | 7 | 2021-06-27 | 2021-07-09 | 8 |  |  |  |  | 2021-09-22 | 52
NST-202910 | SCE | NEM | Other-NEM-V | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 125.966 | No | 2021-05-16 | 2021-05-16 | 0 | 2021-05-16 | 2021-05-27 | 8 | 2021-06-27 | 2021-08-23 | 39 |  |  |  |  | 2021-09-20 | 19
NST-202911 | SCE | NEM | Other-NEM-V | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 88.867 | No | 2021-05-16 | 2021-05-16 | 0 | 2021-05-16 | 2021-05-26 | 7 | 2021-06-27 | 2021-07-19 | 14 |  |  |  |  | 2021-09-14 | 40
NST-202912 | SCE | NEM | Other-NEM-V | Withdrawn | Solar PV | 167.998 | No | 2021-05-16 | 2021-05-16 | 0 | 2021-05-16 | 2021-05-27 | 8 | 2021-06-27 | 2021-06-30 | 2 | 2021-07-15 | 2021-07-23 | 6
NST-202961 | SCE | NEM | NEMA | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 66.227 | No | 2021-05-17 | 2021-05-17 | 0 | 2021-05-17 | 2021-05-27 | 8 | 2021-07-11 | 2021-09-23 | 52 | 2021-09-28 |  |  |  | 2021-11-18 | 35
NST-202964 | SCE | NEM | NEMA | Withdrawn | Solar PV | 64.256 | No | 2021-05-17 | 2021-05-17 | 0 | 2021-05-17 | 2021-05-27 | 8 | 2021-07-11 | 2021-08-23 | 30 |  | 2021-08-31 | 6
NST-202966 | SCE | NEM | NEMA | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 61.496 | No | 2021-05-17 | 2021-05-17 | 0 | 2021-05-17 | 2021-05-27 | 8 | 2021-07-11 | 2021-09-28 | 55 |  |  |  |  | 2021-11-23 | 38
NST-202968 | SCE | NEM | NEMA | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 62.285 | No | 2021-05-17 | 2021-05-17 | 0 | 2021-05-17 | 2021-05-26 | 7 | 2021-07-11 | 2021-09-30 | 57 |  |  |  |  | 2021-11-09 | 27
NST-202986 | SCE | NEM | NEMA | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 63.467 | No | 2021-05-17 | 2021-05-17 | 0 | 2021-05-17 | 2021-05-26 | 7 | 2021-07-11 | 2021-09-23 | 52 | 2021-09-28 |  |  |  | 2021-10-29 | 22
NST-202989 | SCE | NEM | NEMA | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 62.679 | No | 2021-05-17 | 2021-05-17 | 0 | 2021-05-17 | 2021-05-26 | 7 | 2021-07-11 | 2021-09-24 | 53 |  |  |  |  | 2021-10-28 | 23
NST-203056 | SCE | NEM | Other-NEM-V | SCE Engineer Review. Pending SCE System Upgrades | Solar PV | 93.513 | No | 2021-05-17 | 2021-05-17 | 0 | 2021-05-17 | 2021-05-27 | 8 | 2021-06-27 | 2021-07-07 | 6 |  |  |  |  | 2021-09-22 | 54
NST-203061 | SCE | NEM | Other-NEM-V | NGOM Installation. Pending AHJ Panel Permit | Solar PV | 88.758 | No | 2021-05-17 | 2021-05-17 | 0 | 2021-05-17 | 2021-05-27 | 8 | 2021-06-27 | 2021-07-28 | 21 |  |  |  |  | 2021-09-23 | 40
NST-203063 | SCE | NEM | Other-NEM-V | NGOM Installation. Pending AHJ Panel Permit | Solar PV | 80.833 | No | 2021-05-17 | 2021-05-17 | 0 | 2021-05-17 | 2021-05-26 | 7 | 2021-06-27 | 2021-09-28 | 64 | 2021-09-30 |  |  |  | 2021-10-05 | 3
NST-203068 | SCE | NEM | Other-NEM-V | NGOM Installation. Pending AHJ Panel Permit | Solar PV | 53.096 | No | 2021-05-17 | 2021-05-17 | 0 | 2021-05-17 | 2021-05-26 | 7 | 2021-06-27 | 2021-07-28 | 21 | 2021-08-20 |  |  |  | 2021-09-14 | 16
NST-203070 | SCE | NEM | Other-NEM-V | NGOM Installation. Pending AHJ Panel Permit | Solar PV | 66.568 | No | 2021-05-17 | 2021-05-17 | 0 | 2021-05-17 | 2021-05-26 | 7 | 2021-06-27 | 2021-07-27 | 20 |  |  |  |  | 2021-09-24 | 42
NST-203355 | SCE | NEM | NEMA | Withdrawn | Solar PV | 430.855 | No | 2021-05-21 | 2021-05-21 | 0 | 2021-05-21 | 2021-05-28 | 5 |  |  |  |  | 2021-07-06 | 25
NST-203422 | SCE | NEM | NEM Aggregation | Construction | Solar PV | 52.613 | No | 2021-05-19 | 2021-05-19 | 0 | 2021-05-19 | 2021-06-04 | 11 | 2021-06-23 | 2021-07-07 | 9 | 2021-07-30 |  |  |  | 2021-08-03 | 2 | 2021-08-03 | 2021-08-24 | 15 | [19 empty] | 2021-09-20 | 2021-09-21 | 1 |  | 2021-09-30 | 9
NST-203422 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 52.613 | No | 2021-05-19 | 2021-05-19 | 0 | 2021-05-19 | 2021-06-04 | 11 | 2021-06-23 | 2021-07-30 | 26 | 2021-07-30 |  |  |  | 2021-08-03 | 2
NST-203530 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 48.941 | No | 2021-05-19 | 2021-05-19 | 0 | 2021-05-19 | [9 empty] | 2021-05-20 | 1 | [49 empty] | 2021-06-22 |  | 34
NST-203829 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 73.34 | No | 2021-05-24 | 2021-05-24 | 0 | 2021-05-24 | 2021-05-26 | 2 | 2021-06-08 | [6 empty] | 2021-06-15 | 5 | [49 empty] | 2021-07-13 |  | 50
NST-203847 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 77.639 | No | 2021-05-26 | 2021-05-26 | 0 | 2021-05-26 | 2021-06-01 | 3 | 2021-06-01 | 2021-06-09 | 6 | 2021-06-14 |  |  |  | 2021-06-18 | 4 | [49 empty] | 2021-08-27 |  | 93
NST-203851 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 139.365 | No | 2021-05-20 | 2021-05-20 | 0 | 2021-05-20 | 2021-05-25 | 3 | 2021-06-07 | [6 empty] | 2021-06-11 | 4
NST-203980 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV + Battery Storage | 795.781 | No | 2021-05-21 | 2021-05-21 | 0 | 2021-05-21 | [9 empty] | 2021-05-27 | 4 | [31 empty] | 2021-08-04 | 2021-08-04 | 0 | 2021-08-25 | 15 | [13 empty] | 2021-09-08 |  | 110
NST-204012 | SCE | NEM | NEMA | Withdrawn | Solar PV | 160.234 | No | 2021-05-21 | 2021-05-21 | 0 | 2021-05-21 | 2021-05-26 | 3 |  |  |  |  | 2021-06-11 | 11
NST-204045 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 57.787 | No | 2021-05-21 | 2021-05-21 | 0 | 2021-05-21 | 2021-06-29 | 26 | 2021-07-09 | [6 empty] | 2021-07-09 | 0 | [49 empty] | 2021-07-26 |  | 66
NST-204050 | SCE | NEM | NEM Aggregation | Withdrawn | Solar PV | 346.581 | No | 2021-07-01 | 2021-07-01 | 0 | 2021-07-01 | 2021-07-26 | 16 | 2021-08-06
NST-204050 | SCE | NEM | NEMA | Withdrawn | Solar PV | 346.581 | No | 2021-05-21 | 2021-05-21 | 0 | 2021-05-21 | 2021-05-28 | 5 | 2021-06-02 | 2021-08-19 | 55 |  | 2021-08-27 | 6
NST-204149 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 390.647 | No | 2021-05-21 | 2021-05-21 | 0 | 2021-05-21 | 2021-05-26 | 3 | 2021-05-26 | 2021-05-28 | 2 | 2021-06-07 |  |  |  | 2021-06-10 | 3
NST-204228 | SCE | NEM | NEMA | Withdrawn | Solar PV | 911 | No | 2021-05-24 | 2021-05-24 | 0 | 2021-05-24 | [6 empty] | 2021-06-14 | 14
NST-204510 | SCE | NEM | NEMA | Withdrawn | Solar PV | 233.842 | No | 2021-05-25 | 2021-05-25 | 0 | 2021-05-25 | 2021-06-02 | 5 |  |  |  |  | 2021-06-17 | 11
NST-204597 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 103.184 | No | 2021-05-25 | 2021-05-25 | 0 | 2021-05-25 | 2021-05-28 | 3 | 2021-05-28 | [6 empty] | 2021-06-02 | 2
NST-204659 | SCE | NEM | NEMA | Withdrawn | Solar PV | 259.057 | No | 2021-05-25 | 2021-05-25 | 0 | 2021-05-25 | 2021-05-28 | 3 |  |  |  |  | 2021-06-15 | 11
NST-204787 | SCE | NEM | NEMA | NEMI - Pending Final Documents | Solar PV + Battery Storage | 1935.784 | No | 2021-06-14 | 2021-06-14 | 0 | 2021-06-14 | 2021-06-28 | 10 | 2021-07-02 | [6 empty] | 2021-07-15 | 8
NST-205131 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 52.279 | No | 2021-05-27 | 2021-05-27 | 0 | 2021-05-27 | [9 empty] | 2021-06-01 | 2 | [49 empty] | 2021-09-28 |  | 124
NST-205265 | SCE | NEM | NEMA | Withdrawn | Solar PV + Battery Storage | 395.416 | No | 2021-05-28 | 2021-05-28 | 0 | 2021-05-28 | 2021-06-03 | 3 |  |  |  |  | 2021-07-19 | 31
NST-205352 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 69.017 | No | 2021-05-28 | 2021-05-28 | 0 | 2021-05-28 | [9 empty] | 2021-06-08 | 6 | [49 empty] | 2021-09-14 |  | 109
NST-205416 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 779.056 | No | 2021-05-28 | 2021-05-28 | 0 | 2021-05-28 | 2021-06-03 | 3 | 2021-06-03 | [6 empty] | 2021-06-07 | 2
NST-205421 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 483.015 | No | 2021-05-28 | 2021-05-28 | 0 | 2021-05-28 | 2021-06-04 | 4 | 2021-06-04 | 2021-06-10 | 4 | 2021-06-11 |  |  |  | 2021-06-16 | 3
NST-205650 | SCE | NEM | NEMA | Pending Agreement Approval/Execution | Solar PV | 582.338 | No | 2021-06-01 | 2021-06-01 | 0 | 2021-06-01 | 2021-06-03 | 2 | 2021-06-03 | 2021-06-07 | 2 | 2021-07-09 |  |  |  | 2021-07-15 | 4
NST-205650 | SCE | NEM | NEM Aggregation | IA Negotiation | Solar PV | 582.338 | No | 2021-07-09 | 2021-07-09 | 0 | 2021-07-09 | 2021-07-21 | 8 | 2021-08-10 | [6 empty] | 2021-08-10 | 0 | 2021-08-10 | 2021-08-31 | 15 | 2021-10-21 | 35 | 2021-09-01 | 2021-09-30 | 20
NST-205900 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 89.002 | No | 2021-06-02 | 2021-06-02 | 0 | 2021-06-02 | 2021-06-04 | 2 | 2021-06-07 | 2021-06-09 | 2 | 2021-06-29 |  |  |  | 2021-06-29 | 0
NST-206051 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 226.371 | No | 2021-06-02 | 2021-06-02 | 0 | 2021-06-02 | 2021-06-04 | 2 | 2021-06-07 | 2021-06-09 | 2 | 2021-06-29 |  |  |  | 2021-06-29 | 0
NST-206127 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 187.881 | No | 2021-06-03 | 2021-06-03 | 0 | 2021-06-03 | [9 empty] | 2021-06-11 | 6
NST-206142 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 109.756 | No | 2021-06-03 | 2021-06-03 | 0 | 2021-06-03 | 2021-06-07 | 2 | 2021-06-07 | [6 empty] | 2021-06-09 | 2
NST-206224 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 464.71 | No | 2021-06-03 | 2021-06-03 | 0 | 2021-06-03 | 2021-06-07 | 2 | 2021-06-07 | [6 empty] | 2021-06-09 | 2
NST-206395 | SCE | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 31.884 | No | 2021-06-04 | 2021-06-04 | 0 | 2021-06-04 | [9 empty] | 2021-06-08 | 2
NST-206412 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 35.638 | No | 2021-06-04 | 2021-06-04 | 0 | 2021-06-04 | 2021-06-08 | 2 | 2021-06-08 | [6 empty] | 2021-06-18 | 8 | [49 empty] | 2021-06-28 |  | 24
NST-206453 | SCE | NEM | NEMA | NGOM Requirements Met. Pending Local Planner SO Release | Solar PV | 309.987 | No | 2021-06-04 | 2021-06-04 | 0 | 2021-06-04 | 2021-06-08 | 2 | 2021-07-26 | 2021-07-27 | 1 | 2021-07-28 |  |  |  | 2021-07-28 | 0
NST-206469 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 65.136 | No | 2021-06-04 | 2021-06-04 | 0 | 2021-06-04 | 2021-06-09 | 3 | 2021-06-29 | 2021-06-30 | 1 | 2021-07-12 |  |  |  | 2021-07-13 | 1 | [49 empty] | 2021-08-04 |  | 61
NST-206601 | SCE | NEM | VNEM-SOMAH | NGOM Installation. Pending AHJ Panel Permit | Solar PV | 41.525 | No | 2021-06-07 | 2021-06-07 | 0 | 2021-06-07 | [9 empty] | 2021-06-15 | 6 | [31 empty] | 2021-07-07
NST-206603 | SCE | NEM | VNEM-SOMAH | NGOM Installation. Pending AHJ Panel Permit | Solar PV | 38.757 | No | 2021-06-07 | 2021-06-07 | 0 | 2021-06-07 | [9 empty] | 2021-06-15 | 6 | [31 empty] | 2021-07-07
NST-206608 | SCE | NEM | VNEM-SOMAH | NGOM Installation. Pending AHJ Panel Permit | Solar PV | 42.448 | No | 2021-06-07 | 2021-06-07 | 0 | 2021-06-07 | [9 empty] | 2021-06-17 | 8 | [31 empty] | 2021-07-07
NST-206610 | SCE | NEM | VNEM-SOMAH | NGOM Installation. Pending AHJ Panel Permit | Solar PV | 41.525 | No | 2021-06-07 | 2021-06-07 | 0 | 2021-06-07 | [9 empty] | 2021-06-16 | 7 | [31 empty] | 2021-07-07
NST-206611 | SCE | NEM | VNEM-SOMAH | NGOM Installation. Pending AHJ Panel Permit | Solar PV | 32.912 | No | 2021-06-07 | 2021-06-07 | 0 | 2021-06-07 | [9 empty] | 2021-06-15 | 6 | [31 empty] | 2021-07-07
NST-206616 | SCE | NEM | VNEM-SOMAH | NGOM Installation. Pending AHJ Panel Permit | Solar PV | 35.066 | No | 2021-06-07 | 2021-06-07 | 0 | 2021-06-07 | [9 empty] | 2021-06-16 | 7 | [31 empty] | 2021-07-07
NST-206659 | SCE | NEM | NEM-ST | Withdrawn |  | 178.5 | No | 2021-07-02 | 2021-07-02 | 0 | 2021-07-02 | 2021-10-11 | 69 | 2021-10-19 | 2021-11-02 | 10 | 2022-01-18 |  |  |  | 2021-07-02 | 15 | 2022-02-08 | 2022-03-22 | 29
NST-206659 | SCE | NEM | Other-MT-ST | NEMI - Application Returned. Pending Applicant Corrections | Solar PV | 178.5 | No | 2021-06-07 | 2021-06-07 | 0 | 2021-06-07 | 2021-06-09 | 2 | 2021-06-11 | 2021-06-21 | 6 | 2021-06-22 |  |  |  | 2021-06-25 | 3
NST-206698 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 89.208 | No | 2021-06-07 | 2021-06-07 | 0 | 2021-06-07 | [9 empty] | 2021-06-16 | 7 | [49 empty] | 2021-06-18 |  | 11
NST-206760 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 642.3 | No | 2021-06-07 | 2021-06-07 | 0 | 2021-06-07 | [9 empty] | 2021-06-09 | 2 | [49 empty] | 2021-06-17 |  | 10
NST-206822 | SCE | NEM | NEM-Military (SB-83) | Pending PTO |  | 0.235 | No | 2021-11-23 | 2021-11-23 | 0 | 2021-11-23 | 2021-12-09 | 10 | 2021-12-13 | [6 empty] | 2021-12-30 | 12 | 2021-12-30 | 2022-01-19 | 12 | [20 empty] | 2022-02-08 | 14 |  | 2022-03-15 | 35
NST-206863 | SCE | NEM | VNEM-SOMAH | NEMI - PTO Issued | Solar PV | 90.953 | No | 2021-07-13 | 2021-07-13 | 0 | 2021-07-13 | [9 empty] | 2021-07-13 | 0 | [49 empty] | 2021-07-13 |  | 0
NST-207061 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV + Battery Storage | 183.506 | No | 2021-06-11 | 2021-06-11 | 0 | 2021-06-11 | 2021-06-15 | 2 | 2021-06-27 | 2021-06-28 | 0 | 2021-07-15 |  |  |  | 2021-09-22 | 48
NST-207064 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV + Battery Storage | 232.492 | No | 2021-06-11 | 2021-06-11 | 0 | 2021-06-11 | 2021-06-16 | 3 | 2021-08-19 | 2021-08-20 | 1 | 2021-08-20 |  |  |  | 2021-08-28 | 5
NST-207068 | SCE | NEM | NEMA | Applicant Response Received. Pending SCE Engineer Review | Solar PV + Battery Storage | 183.538 | No | 2021-06-11 | 2021-06-11 | 0 | 2021-06-11 | 2021-06-15 | 2 | 2021-07-21 | 2021-07-22 | 1 | 2021-07-22 |  |  |  | 2021-07-29 | 5
NST-207070 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV + Battery Storage | 91.611 | No | 2021-06-11 | 2021-06-11 | 0 | 2021-06-11 | 2021-06-15 | 2 | 2021-07-07 | 2021-07-08 | 1 | 2021-07-12 |  |  |  | 2021-07-15 | 3
NST-207071 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV + Battery Storage | 244.707 | No | 2021-06-11 | 2021-06-11 | 0 | 2021-06-11 | [9 empty] | 2021-06-15 | 2
NST-207073 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV + Battery Storage | 507.704 | No | 2021-06-11 | 2021-06-11 | 0 | 2021-06-11 | 2021-06-15 | 2 | 2021-08-22 | 2021-08-23 | 0 | 2021-09-02 |  |  |  | 2021-09-14 | 7
NST-207078 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV + Battery Storage | 350.523 | No | 2021-06-11 | 2021-06-11 | 0 | 2021-06-11 | 2021-06-15 | 2 | 2021-07-26 | 2021-07-27 | 1 | 2021-08-11 |  |  |  | 2021-09-08 | 19
NST-207080 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV + Battery Storage | 246.297 | No | 2021-06-11 | 2021-06-11 | 0 | 2021-06-11 | 2021-06-16 | 3 | 2021-07-15 | 2021-07-16 | 1 | 2021-08-06 |  |  |  | 2021-08-07 | 0
NST-207081 | SCE | NEM | NEMA | Applicant Response Received. Pending SCE Engineer Review | Solar PV + Battery Storage | 370.445 | No | 2021-06-11 | 2021-06-11 | 0 | 2021-06-11 | 2021-06-15 | 2 | 2021-07-02 | 2021-08-23 | 35 | 2021-09-07 |  |  |  | 2021-09-21 | 10
NST-207127 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 156.052 | No | 2021-06-09 | 2021-06-09 | 0 | 2021-06-09 | [9 empty] | 2021-06-17 | 6 | [49 empty] | 2022-03-11 |  | 275
NST-207154 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV + Battery Storage | 246.951 | No | 2021-06-09 | 2021-06-09 | 0 | 2021-06-09 | 2021-06-16 | 5 | 2021-06-28 | 2021-06-29 | 1 | 2021-07-08 |  |  |  | 2021-07-13 | 3
NST-207163 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 135.121 | No | 2021-06-27 | 2021-06-27 | 0 | 2021-06-27 | 2021-06-30 | 2 | 2021-08-02 | [6 empty] | 2021-08-10 | 6
NST-207170 | SCE | NEM | VNEM-SOMAH | NGOM Installation. Pending AHJ Panel Permit | Solar PV | 47.462 | No | 2021-06-10 | 2021-06-10 | 0 | 2021-06-10 | 2021-06-17 | 5 | 2021-06-21 | 2021-06-23 | 2 | 2021-06-24 |  |  |  | 2021-06-28 | 2 | [31 empty] | 2021-07-15 | 2021-08-19 | 25
NST-207206 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 96.524 | No | 2021-06-09 | 2021-06-09 | 0 | 2021-06-09 | 2021-06-11 | 2 | 2021-07-08 | [6 empty] | 2021-07-23 | 11
NST-207227 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 127.774 | No | 2021-06-09 | 2021-06-09 | 0 | 2021-06-09 | 2021-06-14 | 3 | 2021-06-17 | 2021-06-21 | 2 | 2021-06-22 |  |  |  | 2021-06-23 | 1
NST-207269 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 41.367 | No | 2021-06-09 | 2021-06-09 | 0 | 2021-06-09 | 2021-06-17 | 6 | 2021-07-06 | 2021-07-12 | 4 | 2021-07-27 |  |  |  | 2021-07-27 | 0
NST-207292 | SCE | NEM | NEMA | Withdrawn | Solar PV | 624.255 | No | 2021-06-09 | 2021-06-09 | 0 | 2021-06-09 | 2021-06-11 | 2 | 2021-06-14 | 2021-06-21 | 5 |  | 2021-07-06 | 10
NST-207400 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 407.95 | No | 2021-06-10 | 2021-06-10 | 0 | 2021-06-10 | 2021-06-14 | 2 | 2021-06-14 | 2021-06-21 | 5 | 2021-06-27 |  |  |  | 2021-07-14 | 11 | [49 empty] | 2021-07-21 |  | 41
NST-207414 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 263.982 | No | 2021-06-10 | 2021-06-10 | 0 | 2021-06-10 | [9 empty] | 2021-06-14 | 2 | [49 empty] | 2022-01-21 |  | 225
NST-207456 | SCE | NEM | NEMA | Withdrawn | Solar PV | 457.644 | No | 2021-06-10 | 2021-06-10 | 0 | 2021-06-10 | 2021-06-14 | 2 | 2021-06-17 | 2021-06-18 | 1 |  | 2021-06-28 | 6
NST-207551 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV + Battery Storage | 54.006 | No | 2021-06-10 | 2021-06-10 | 0 | 2021-06-10 | 2021-06-15 | 3 | 2021-07-01 | 2021-07-02 | 1 |  |  |  |  | 2021-07-09 | 4 | [49 empty] | 2021-09-28 |  | 110
NST-207763 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Construction | Solar PV | 211.232 | No | 2021-06-11 | 2021-06-11 | 0 | 2021-06-11 | 2021-06-15 | 2 | 2021-06-29 | [6 empty] | 2021-07-08 | 6
NST-207772 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Construction | Solar PV | 354.798 | No | 2021-06-11 | 2021-06-11 | 0 | 2021-06-11 | 2021-06-15 | 2 | 2021-07-02 | 2021-07-12 | 5 | 2021-07-21 |  |  |  | 2021-08-06 | 12
NST-207778 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Construction | Solar PV | 229.575 | No | 2021-06-11 | 2021-06-11 | 0 | 2021-06-11 | 2021-06-15 | 2 | 2021-07-16 | 2021-07-28 | 8 | 2021-07-31 |  |  |  | 2021-08-10 | 6
NST-207787 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Construction | Solar PV | 229.575 | No | 2021-06-11 | 2021-06-11 | 0 | 2021-06-11 | 2021-06-15 | 2 | 2021-06-28 | 2021-06-29 | 1 | 2021-07-07 |  |  |  | 2021-07-16 | 7
NST-207874 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV + Battery Storage | 123.475 | No | 2021-06-11 | 2021-06-11 | 0 | 2021-06-11 | 2021-06-21 | 6 | 2021-06-30 | 2021-07-02 | 2 | 2021-07-20 |  |  |  | 2021-07-20 | 0
NST-207892 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 198.932 | No | 2021-06-12 | 2021-06-12 | 0 | 2021-06-12 | 2021-06-15 | 1 | 2021-06-29 | 2021-06-30 | 1 | 2021-06-30 |  |  |  | 2021-07-02 | 2
NST-207929 | SCE | NEM | NEMA | Withdrawn | Solar PV + Battery Storage | 3160.29 | No | 2021-06-15 | 2021-06-15 | 0 | 2021-06-15 | 2021-06-17 | 2 |  |  |  |  | 2021-07-02 | 11
NST-207999 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 253.422 | No | 2021-06-14 | 2021-06-14 | 0 | 2021-06-14 | 2021-06-16 | 2 | 2021-06-22 | [6 empty] | 2021-06-23 | 1
NST-208000 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 75.9 | No | 2021-06-14 | 2021-06-14 | 0 | 2021-06-14 | 2021-06-16 | 2 | 2021-06-23 | [6 empty] | 2021-06-25 | 2 | [49 empty] | 2021-07-27 |  | 43
NST-208001 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 92.221 | No | 2021-06-14 | 2021-06-14 | 0 | 2021-06-14 | [9 empty] | 2021-06-16 | 2
NST-208079 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 276.965 | No | 2021-06-14 | 2021-06-14 | 0 | 2021-06-14 | [9 empty] | 2021-06-18 | 4
NST-208665 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 184.321 | No | 2021-06-21 | 2021-06-21 | 0 | 2021-06-21 | 2021-06-23 | 2 | 2021-06-24 | [6 empty] | 2021-06-28 | 2
NST-208666 | SCE | NEM | NEMA | Withdrawn | Solar PV | 92.236 | No | 2021-06-21 | 2021-06-21 | 0 | 2021-06-21 | 2021-06-23 | 2 |  |  |  |  | 2021-07-08 | 10
NST-208906 | SCE | NEM | Other-MT-ST | NEMI - Equipment Change Submitted | Solar PV + Battery Storage | 2482.964 | No | 2021-06-17 | 2021-06-17 | 0 | 2021-06-17 | 2021-06-22 | 3 | 2021-07-07 | [6 empty] | 2021-07-14 | 5
NST-208913 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 99.235 | No | 2021-06-17 | 2021-06-17 | 0 | 2021-06-17 | 2021-06-22 | 3 | 2021-06-23 | 2021-06-25 | 2 | 2021-06-30 |  |  |  | 2021-07-19 | 12 | [49 empty] | 2021-08-09 |  | 53
NST-208965 | SCE | NEM | NEM-ST | Application Review In Progress | Solar PV | 2222.448 | No | 2021-07-07 | 2021-07-07 | 0 | 2021-07-07 | 2021-08-09 | 23 | 2021-09-20 | 2021-09-29 | 7
NST-208965 | SCE | NEM | Other-MT-ST | SCE Engineer Review. Pending Applicant Response | Solar PV + Battery Storage | 2222.448 | No | 2021-06-17 | 2021-06-17 | 0 | 2021-06-17 | 2021-06-23 | 4 | 2021-07-07 | [6 empty] | 2021-07-14 | 5
NST-209334 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 70.996 | No | 2021-06-18 | 2021-06-18 | 0 | 2021-06-18 | 2021-06-28 | 6 | 2021-06-30 | 2021-07-02 | 2 |  |  |  |  | 2021-07-20 | 11 | [49 empty] | 2021-07-30 |  | 42
NST-209489 | SCE | NEM | NEMA | Withdrawn | Solar PV | 469.342 | No | 2021-06-21 | 2021-06-21 | 0 | 2021-06-21 | 2021-06-22 | 1 |  |  |  |  | 2021-07-07 | 10
NST-209643 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 51.527 | No | 2021-06-21 | 2021-06-21 | 0 | 2021-06-21 | 2021-06-23 | 2 | 2021-06-23 | 2021-07-13 | 13 |  |  |  |  | 2021-07-23 | 8 | [49 empty] | 2021-08-03 |  | 43
NST-209765 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 45.921 | No | 2021-06-22 | 2021-06-22 | 0 | 2021-06-22 | [9 empty] | 2021-06-23 | 1 | [49 empty] | 2021-09-17 |  | 87
NST-210226 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 160.23 | No | 2021-06-23 | 2021-06-23 | 0 | 2021-06-23 | 2021-06-28 | 3 | 2021-07-20 | 2021-07-30 | 8 | 2021-08-03 |  |  |  | 2021-08-18 | 11 | [49 empty] | 2022-03-14 |  | 264
NST-210290 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 790.146 | No | 2021-06-23 | 2021-06-23 | 0 | 2021-06-23 | [9 empty] | 2021-06-28 | 3
NST-210399 | SCE | NEM | NEMA | Withdrawn | Solar PV | 460.734 | No | 2021-06-23 | 2021-06-23 | 0 | 2021-06-23 | 2021-06-28 | 3 |  |  |  |  | 2021-07-13 | 10
NST-210501 | SCE | NEM | NEMA | Withdrawn | Solar PV | 31.695 | No | 2021-06-24 | 2021-06-24 | 0 | 2021-06-24 | 2021-06-28 | 2 |  |  |  |  | 2021-07-13 | 10
NST-210608 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 335.937 | No | 2021-06-25 | 2021-06-25 | 0 | 2021-06-25 | 2021-06-29 | 2 | 2021-06-30 | [6 empty] | 2021-06-30 | 0 | [49 empty] | 2022-03-11 |  | 259
NST-211268 | SCE | NEM | NEMA | Withdrawn | Solar PV | 233.842 | No | 2021-06-28 | 2021-06-28 | 0 | 2021-06-28 | 2021-07-01 | 3 |  |  |  |  | 2021-07-16 | 10
NST-211302 | SCE | NEM | NEMA | NEMI - Pending Permanent Service | Solar PV | 161.585 | No | 2021-06-28 | 2021-06-28 | 0 | 2021-06-28 | 2021-07-02 | 4 | 2021-08-02 | 2021-08-03 | 1 |  |  |  |  | 2021-08-31 | 20
NST-211422 | SCE | NEM | NEMA | Withdrawn | Solar PV + Battery Storage | 45.441 | No | 2021-06-29 | 2021-06-29 | 0 | 2021-06-29 | 2021-06-30 | 1 |  |  |  |  | 2021-07-15 | 10
NST-211777 | SCE | NEM | VNEM-SOMAH | Withdrawn | Solar PV | 65.769 | No | 2021-07-01 | 2021-07-01 | 0 | 2021-07-01 | 2021-07-07 | 3 | 2021-07-13 | 2021-07-14 | 1 |  | 2021-07-22 | 6
NST-211902 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 259.211 | No | 2021-06-30 | 2021-06-30 | 0 | 2021-06-30 | 2021-07-06 | 3 | 2021-07-08 | [6 empty] | 2021-07-13 | 3 | [49 empty] | 2021-08-13 |  | 44
NST-212562 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV + Battery Storage | 36.69 | No | 2021-07-05 | 2021-07-05 | 0 | 2021-07-05 | 2021-07-09 | 3 | 2021-07-15 | [6 empty] | 2021-07-21 | 4 | [49 empty] | 2021-10-05 |  | 92
NST-213005 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 80.312 | No | 2021-07-07 | 2021-07-07 | 0 | 2021-07-07 | 2021-07-12 | 3 | 2021-07-19 | [6 empty] | 2021-07-20 | 1 | [49 empty] | 2021-08-17 |  | 41
NST-213190 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 35.202 | No | 2021-07-07 | 2021-07-07 | 0 | 2021-07-07 | [9 empty] | 2021-07-08 | 1 | [49 empty] | 2021-09-24 |  | 79
NST-213277 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 238.591 | No | 2021-07-07 | 2021-07-07 | 0 | 2021-07-07 | [9 empty] | 2021-07-14 | 5 | [49 empty] | 2022-01-13 |  | 190
NST-213463 | SCE | NEM | NEM-ST | Supplemental Review Complete |  | 2845.108 | No | 2021-09-15 | 2021-09-15 | 0 | 2021-09-15 | 2021-09-24 | 7 | 2021-10-06 | 2021-10-29 | 16 | 2021-11-04 |  |  |  | 2021-11-10 | 4 | 2021-11-10 | 2021-12-02 | 13 |  |  | 2021-12-17 | 2022-01-19 | 20 | 2022-02-22 | 23
NST-213463 | SCE | NEM | NEMA | SCE Engineer. Supplemental Review Complete | Solar PV + Battery Storage | 2845.108 | No | 2021-07-08 | 2021-07-08 | 0 | 2021-07-08 | 2021-07-14 | 4 | 2021-09-03 | 2021-09-10 | 4 | 2021-09-15 |  |  |  | 2021-09-16 | 1
NST-213573 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 162.639 | No | 2021-07-08 | 2021-07-08 | 0 | 2021-07-08 | [9 empty] | 2021-07-19 | 7 | [49 empty] | 2021-07-26 |  | 18
NST-213818 | SCE | NEM | NEMA | Withdrawn | Solar PV + Battery Storage | 145.686 | No | 2021-07-09 | 2021-07-09 | 0 | 2021-07-09 | 2021-07-14 | 3 |  |  |  |  | 2021-07-29 | 11
NST-213822 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 225.868 | No | 2021-07-09 | 2021-07-09 | 0 | 2021-07-09 | 2021-07-14 | 3 | 2021-08-04 | [6 empty] | 2021-08-13 | 7 | [49 empty] | 2021-09-09 |  | 62
NST-213847 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 288.672 | No | 2021-07-09 | 2021-07-09 | 0 | 2021-07-09 | 2021-07-14 | 3 | 2021-08-04 | [6 empty] | 2021-12-13 | 88 | [49 empty] | 2021-08-23 |  | 45
NST-213890 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 39.518 | No | 2021-07-09 | 2021-07-09 | 0 | 2021-07-09 | 2021-07-22 | 9 | 2021-08-11 | 2021-08-12 | 1 |  |  |  |  | 2021-09-22 | 28 | [49 empty] | 2021-09-23 |  | 76
NST-214173 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 157.156 | No | 2021-07-12 | 2021-07-12 | 0 | 2021-07-12 | [9 empty] | 2021-07-15 | 3 | [49 empty] | 2022-01-06 |  | 178
NST-214208 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Construction | Solar PV | 133.78 | No | 2021-07-12 | 2021-07-12 | 0 | 2021-07-12 | [9 empty] | 2021-07-19 | 5
NST-214235 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Construction | Solar PV | 239.396 | No | 2021-07-12 | 2021-07-12 | 0 | 2021-07-12 | [9 empty] | 2021-07-20 | 6
NST-214244 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Construction | Solar PV | 267.56 | No | 2021-07-12 | 2021-07-12 | 0 | 2021-07-12 | [9 empty] | 2021-07-19 | 5
NST-214250 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV + Battery Storage | 49.498 | No | 2021-07-14 | 2021-07-14 | 0 | 2021-07-14 | 2021-07-22 | 6 | 2021-08-04 | [6 empty] | 2021-08-24 | 14
NST-214809 | SCE | NEM | NEMA | Withdrawn | Solar PV | 111.034 | No | 2021-07-21 | 2021-07-21 | 0 | 2021-07-21 | 2021-07-27 | 4 |  |  |  |  | 2021-08-11 | 11
NST-214836 | SCE | NEM | NEMA | Withdrawn | Solar PV | 94.577 | No | 2021-07-14 | 2021-07-14 | 0 | 2021-07-14 | 2021-07-21 | 5 | 2021-07-21 | 2021-08-05 | 11 |  | 2021-08-13 | 6
NST-214921 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 110.87 | No | 2021-07-14 | 2021-07-14 | 0 | 2021-07-14 | 2021-07-20 | 4 | 2021-07-29 | [6 empty] | 2021-08-12 | 10
NST-215027 | SCE | NEM | NEMA | SCE Engineer. Supplemental Review In Progress | Solar PV + Battery Storage | 999.235 | No | 2021-07-15 | 2021-07-15 | 0 | 2021-07-15 | 2021-07-28 | 9 | 2021-09-14 | [6 empty] | 2021-09-14 | 0
NST-215031 | SCE | NEM | NEMA | Withdrawn | Solar PV | 43.194 | No | 2021-07-15 | 2021-07-15 | 0 | 2021-07-15 | 2021-07-23 | 6 |  |  |  |  | 2021-08-09 | 11
NST-215307 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 126.748 | No | 2021-07-16 | 2021-07-16 | 0 | 2021-07-16 | 2021-07-22 | 4 | 2021-07-26 | 2021-08-17 | 16 | 2021-08-17 |  |  |  | 2021-08-26 | 7 | [49 empty] | 2021-08-27 |  | 42
NST-215473 | SCE | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 521.34 | No | 2021-07-16 | 2021-07-16 | 0 | 2021-07-16 | 2021-07-22 | 4 | 2021-07-30 | 2021-08-09 | 6 | 2021-08-09 |  |  |  | 2021-08-18 | 7
NST-215591 | SCE | NEM | NEMA | Withdrawn | Solar PV + Battery Storage | 45.441 | No | 2021-07-19 | 2021-07-19 | 0 | 2021-07-19 | 2021-07-22 | 3 |  |  |  |  | 2021-08-06 | 11
NST-215645 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 282.95 | No | 2021-07-19 | 2021-07-19 | 0 | 2021-07-19 | 2021-07-27 | 6 | 2021-07-28 | [6 empty] | 2021-08-05 | 6
NST-215657 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 333.058 | No | 2021-07-19 | 2021-07-19 | 0 | 2021-07-19 | 2021-07-26 | 5 | 2021-08-04 | 2021-09-21 | 33 | 2021-09-23 |  |  |  | 2021-09-27 | 2
NST-215685 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 126.626 | No | 2021-07-19 | 2021-07-19 | 0 | 2021-07-19 | [9 empty] | 2021-07-26 | 5 | [49 empty] | 2021-07-27 |  | 8
NST-215783 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 327.78 | No | 2021-07-21 | 2021-07-21 | 0 | 2021-07-21 | 2021-08-05 | 11 | 2021-08-16
NST-215801 | SCE | NEM | VNEM-SOMAH | Withdrawn | Solar PV | 186.707 | No | 2021-07-26 | 2021-07-26 | 0 | 2021-07-26 | 2021-08-09 | 10 | 2021-08-13 | 2021-08-26 | 9 |  | 2021-09-13 | 11
NST-215837 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 78.253 | No | 2021-07-19 | 2021-07-19 | 0 | 2021-07-19 | [9 empty] | 2021-07-23 | 4 | [49 empty] | 2021-08-09 |  | 21
NST-216134 | SCE | NEM | NEM-ST | Application Review In Progress |  | 561.872 | No | 2021-12-06 | 2021-12-06 | 0 | 2021-12-06 | 2021-12-16 | 8 | 2021-12-30 | 2022-01-03 | 1 | 2022-03-17 |  |  |  | 2022-03-23 | 4 | 2022-03-23
NST-216134 | SCE | NEM | NEMA | NEMI - Transferred to GICD | Solar PV + Battery Storage | 561.872 | No | 2021-07-20 | 2021-07-20 | 0 | 2021-07-20 |  |  | 2021-07-26 |  |  |  | 2021-08-10 | 11 |  | 2022-03-23 | 4
NST-216275 | SCE | NEM | NEMA | Withdrawn | Solar PV | 42.29 | No | 2021-07-21 | 2021-07-21 | 0 | 2021-07-21 | 2021-07-26 | 3 | 2021-07-27 | 2021-08-09 | 9 |  | 2021-08-17 | 6
NST-216299 | SCE | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 142.661 | No | 2021-07-21 | 2021-07-21 | 0 | 2021-07-21 | 2021-07-27 | 4 | 2021-08-11 | [6 empty] | 2021-08-18 | 5
NST-216352 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 118.17 | No | 2021-07-21 | 2021-07-21 | 0 | 2021-07-21 | [9 empty] | 2021-07-27 | 4
NST-216585 | SCE | NEM | NEMA | Withdrawn | Solar PV | 46.76 | No | 2021-07-22 | 2021-07-22 | 0 | 2021-07-22 | 2021-08-06 | 11 | 2021-08-06 | 2021-08-24 | 12 | 2021-09-24 | 2021-09-11 | 12
NST-216624 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 948.028 | No | 2021-07-22 | 2021-07-22 | 0 | 2021-07-22 | 2021-07-28 | 4 | 2021-08-04
NST-216837 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 33.184 | No | 2021-07-23 | 2021-07-23 | 0 | 2021-07-23 | 2021-07-26 | 1 | 2021-07-27 | 2021-08-11 | 11 | 2021-09-03 |  |  |  | 2021-09-15 | 7 | [49 empty] | 2021-09-22 |  | 61
NST-216914 | SCE | NEM | NEM-ST | Application Review In Progress | Solar PV | 5430.038 | No | 2021-07-23 | 2021-07-23 | 0 | 2021-07-23 | 2021-08-06 | 10 | 2021-09-19 | 2021-10-05 | 11
NST-216914 | SCE | NEM | Other-MT-ST | Applicant Response Received. Pending SCE Engineer Review | Solar PV + Battery Storage | 5430.038 | No | 2021-07-23 | 2021-07-23 | 0 | 2021-07-23 | 2021-08-06 | 10 | 2021-09-19 | [6 empty] | 2021-09-21 | 1
NST-216933 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 44.255 | No | 2021-07-23 | 2021-07-23 | 0 | 2021-07-23 | [9 empty] | 2021-07-23 | 0 | [49 empty] | 2021-07-29 |  | 6
NST-216981 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV + Battery Storage | 33.111 | No | 2021-07-23 | 2021-07-23 | 0 | 2021-07-23 | [9 empty] | 2021-07-23 | 0 | [49 empty] | 2021-08-11 |  | 19
NST-217100 | SCE | NEM | NEM-ST | Application Review In Progress |  | 0.011337 | No | 2022-01-28 | 2022-01-28 | 0 | 2022-01-28 | [9 empty] | 2022-02-09 | 8 | [22 empty] | 2022-02-09 | 2022-02-11 | 2 |  | 2022-02-11 | 0
NST-217154 | SCE | NEM | NEMA | NEMI - Pending Final NEM Review | Solar PV | 460.734 | No | 2021-07-25 | 2021-07-25 | 0 | 2021-07-25 | 2021-07-30 | 4 | 2021-08-02 | 2021-08-09 | 5 | 2021-08-09 |  |  |  | 2021-08-16 | 5
NST-217243 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 909.719 | No | 2021-07-26 | 2021-07-26 | 0 | 2021-07-26 | 2021-08-11 | 12 | 2021-08-18 | 2021-08-27 | 7 | 2021-08-30 |  |  |  | 2021-09-14 | 10
NST-217243 | SCE | NEM | NEM Aggregation | Application Review In Progress |  | 909.719 | No | 2021-09-14 | 2021-09-14 | 0 | 2021-09-14 | 2021-09-24 | 8
NST-217294 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 674.324 | No | 2021-07-26 | 2021-07-26 | 0 | 2021-07-26 | [9 empty] | 2021-07-30 | 4
NST-217310 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 515.257 | No | 2021-07-26 | 2021-07-26 | 0 | 2021-07-26 | 2021-08-02 | 5 | 2021-08-02 | [6 empty] | 2021-08-10 | 6
NST-218066 | SCE | NEM | NEMA | Withdrawn | Solar PV | 91.095 | No | 2021-07-28 | 2021-07-28 | 0 | 2021-07-28 | 2021-08-17 | 14 | 2021-10-21 | 2021-10-21 | 0 |  | 2021-10-29 | 6
NST-218257 | SCE | NEM | NEMA | SCE Engineer. Initial Review Complete | Solar PV + Battery Storage | 1932.248 | No | 2021-07-29 | 2021-07-29 | 0 | 2021-07-29 | 2021-08-02 | 2 | 2021-08-12 | 2021-08-19 | 5 | 2021-08-31 | 2021-09-09 | 6
NST-218783 | SCE | NEM | NEM-FC | SCE Engineer Review. Pending Applicant Response | Fuel Cell - Renewable | 400 | No | 2021-07-30 | 2021-07-30 | 0 | 2021-07-30 | 2021-08-16 | 11 | 2021-08-24 | 2021-08-25 | 1
NST-218793 | SCE | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 71.528 | No | 2021-07-30 | 2021-07-30 | 0 | 2021-07-30 | 2021-08-10 | 7 | 2021-08-13 | [6 empty] | 2021-08-23 | 6
NST-218970 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV + Battery Storage | 168.97 | No | 2021-08-02 | 2021-08-02 | 0 | 2021-08-02 | 2021-08-05 | 3 | 2021-08-06
NST-218971 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 128.493 | No | 2021-08-02 | 2021-08-02 | 0 | 2021-08-02 | 2021-08-10 | 6 | 2021-08-11 | [6 empty] | 2021-08-18 | 5
NST-218974 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 229.615 | No | 2021-08-02 | 2021-08-02 | 0 | 2021-08-02 | 2021-08-30 | 20 | 2021-08-31 | [6 empty] | 2021-09-16 | 11
NST-218975 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 103.08 | No | 2021-08-02 | 2021-08-02 | 0 | 2021-08-02 | 2021-08-10 | 6 | 2021-08-11 | [6 empty] | 2021-08-20 | 7
NST-218978 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 160.086 | No | 2021-08-02 | 2021-08-02 | 0 | 2021-08-02 | 2021-08-10 | 6 | 2021-08-23 | [6 empty] | 2021-09-02 | 8
NST-218981 | SCE | NEM | NEMA | Withdrawn | Solar PV | 95.661 | No | 2021-08-02 | 2021-08-02 | 0 | 2021-08-02 | 2021-08-12 | 8 | 2021-08-24 | 2021-09-13 | 13 |  | 2021-09-21 | 6
NST-218984 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 177.429 | No | 2021-08-02 | 2021-08-02 | 0 | 2021-08-02 | 2021-08-10 | 6 | 2021-08-24 | [6 empty] | 2021-09-09 | 11
NST-218989 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 172.244 | No | 2021-08-02 | 2021-08-02 | 0 | 2021-08-02 | [9 empty] | 2021-08-11 | 7
NST-218994 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 154.441 | No | 2021-08-02 | 2021-08-02 | 0 | 2021-08-02 | 2021-08-11 | 7 | 2021-08-17 | [6 empty] | 2021-08-26 | 7
NST-219028 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 100.855 | No | 2021-08-02 | 2021-08-02 | 0 | 2021-08-02 | [9 empty] | 2021-08-10 | 6
NST-219138 | SCE | NEM | NEM-ST | In-Service (Conditional PTO) |  | 1124.354 | No | 2021-08-26 | 2021-08-26 | 0 | 2021-08-26 | [9 empty] | 2021-09-01 | 4 | 2021-09-01 | 2021-09-13 | 7 |  |  | 2021-09-17 | 2021-10-15 | 19 | [14 empty] | 2021-10-15 | 2021-10-26 | 7 |  | 2022-02-08 | 105
NST-219138 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 1124.354 | No | 2021-08-03 | 2021-08-03 | 0 | 2021-08-03 | 2021-08-04 | 1 | 2021-08-26 | [6 empty] | 2021-09-01 | 4
NST-219258 | SCE | NEM | NEM-ST | Transferred to NEM |  | 153.159 | No |  |  |  | 2022-01-21
NST-219258 | SCE | NEM | Other-NEM-V | SCE Engineer Review. Pending Applicant Response | Solar PV | 153.159 | No | 2021-08-03 | 2021-08-03 | 0 | 2021-08-03 | 2021-08-11 | 6 | 2021-09-02 | 2021-10-15 | 29
NST-219556 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 33.849 | No | 2021-08-04 | 2021-08-04 | 0 | 2021-08-04 | 2021-08-13 | 7 | 2021-08-25 | 2021-09-02 | 6 | 2021-09-03 |  |  |  | 2021-09-15 | 7 | [49 empty] | 2021-09-24 |  | 51
NST-219644 | SCE | NEM | NEMA | NGOM Installation. Pending AHJ Panel Permit | Solar PV + Battery Storage | 317.739 | No | 2021-08-04 | 2021-08-04 | 0 | 2021-08-04 | 2021-08-12 | 6 | 2021-08-25 | 2021-09-27 | 22 | 2021-10-07 |  |  |  | 2021-10-13 | 3
NST-219944 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 152.099 | No | 2021-08-05 | 2021-08-05 | 0 | 2021-08-05 | 2021-08-12 | 5 | 2021-08-17 | [6 empty] | 2021-08-26 | 7
NST-219965 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 491.582 | No | 2021-08-05 | 2021-08-05 | 0 | 2021-08-05 | [9 empty] | 2021-08-12 | 5
NST-219973 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 469.342 | No | 2021-08-05 | 2021-08-05 | 0 | 2021-08-05 | 2021-08-12 | 5 | 2021-08-16 | [6 empty] | 2021-08-31 | 11 | [49 empty] | 2021-09-27 |  | 53
NST-220174 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV + Battery Storage | 37.95 | No | 2021-08-05 | 2021-08-05 | 0 | 2021-08-05 | 2021-09-01 | 19 | 2021-09-02
NST-220427 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 53.907 | No | 2021-08-06 | 2021-08-06 | 0 | 2021-08-06 | [9 empty] | 2021-08-13 | 5 | [49 empty] | 2021-09-20 |  | 45
NST-220470 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 184.398 | No | 2021-08-18 | 2021-08-18 | 0 | 2021-08-18 | 2021-08-26 | 6 | 2021-09-14 | 2021-09-23 | 7 |  |  |  |  | 2021-10-07 | 10 | [49 empty] | 2022-02-23 |  | 189
NST-220495 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 496.475 | No | 2021-08-08 | 2021-08-08 | 0 | 2021-08-08 | 2021-08-20 | 9 | 2021-09-12 | [6 empty] | 2021-09-21 | 6 | [49 empty] | 2021-09-21 |  | 44
NST-220503 | SCE | NEM | NEMA | Withdrawn | Solar PV | 37.089 | No | 2021-08-08 | 2021-08-08 | 0 | 2021-08-08 | 2021-09-10 | 23 | 2021-09-13 | 2021-09-14 | 1 |  | 2021-09-22 | 6
NST-220653 | SCE | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 37.923 | No | 2021-08-09 | 2021-08-09 | 0 | 2021-08-09 | 2021-08-11 | 2 | 2021-08-12 | [6 empty] | 2021-08-19 | 5
NST-220790 | SCE | NEM | NEMA | Withdrawn | Solar PV | 37.207 | No | 2021-08-09 | 2021-08-09 | 0 | 2021-08-09 | 2021-08-10 | 1 |  |  |  |  | 2021-08-25 | 11
NST-220885 | SCE | NEM | NEMA | Withdrawn | Solar PV | 3227.722 | No | 2021-08-10 | 2021-08-10 | 0 | 2021-08-10 | [8 empty] | 2021-09-09 | 2021-08-17 | 5
NST-221339 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Construction | Solar PV | 494.247 | No | 2021-08-11 | 2021-08-11 | 0 | 2021-08-11 | [9 empty] | 2021-08-17 | 4
NST-221368 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 76.417 | No | 2021-08-11 | 2021-08-11 | 0 | 2021-08-11 | 2021-08-27 | 12 | 2021-09-02 | 2021-09-28 | 17 | 2021-09-30
NST-221381 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 91.207 | No | 2021-08-11 | 2021-08-11 | 0 | 2021-08-11 | 2021-08-27 | 12 | 2021-09-02 | 2021-09-21 | 12 | 2021-09-23 |  |  |  | 2021-09-28 | 3
NST-221402 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 394.41 | No | 2021-08-11 | 2021-08-11 | 0 | 2021-08-11 | 2021-08-27 | 12 | 2021-09-02 | 2021-09-22 | 13 | 2021-09-23 | 2021-09-27 | 2
NST-221425 | SCE | NEM | NEMA | Withdrawn | Solar PV + Battery Storage | 80.471 | No | 2021-08-11 | 2021-08-11 | 0 | 2021-08-11 | 2021-08-19 | 6 | 2021-08-30 | 2021-09-20 | 14 | 2021-09-21 | 2021-09-20 | 0
NST-221476 | SCE | NEM | NEMA | NGOM Installation. Pending Invoice Payment and AHJ Panel Permit | Solar PV | 129.62 | No | 2021-08-12 | 2021-08-12 | 0 | 2021-08-12 | [9 empty] | 2021-08-18 | 4
NST-221480 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 122.902 | No | 2021-08-12 | 2021-08-12 | 0 | 2021-08-12 | [9 empty] | 2021-08-18 | 4
NST-221483 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 233.157 | No | 2021-08-12 | 2021-08-12 | 0 | 2021-08-12 | [9 empty] | 2021-08-18 | 4
NST-221567 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 30.712 | No | 2021-08-12 | 2021-08-12 | 0 | 2021-08-12 | [9 empty] | 2021-08-13 | 1 | [49 empty] | 2021-09-15 |  | 34
NST-221650 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV + Battery Storage | 32.616 | No | 2021-08-12 | 2021-08-12 | 0 | 2021-08-12 | 2021-08-19 | 5 | 2021-08-27 | [6 empty] | 2021-09-15 | 12
NST-221966 | SCE | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 44.085 | No | 2021-08-13 | 2021-08-13 | 0 | 2021-08-13 | 2021-08-27 | 10 | 2021-09-29
NST-222023 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 45.676 | No | 2021-08-13 | 2021-08-13 | 0 | 2021-08-13 | 2021-08-20 | 5 | 2021-08-24 | 2021-08-31 | 5 | 2021-09-01 |  |  |  | 2021-09-01 | 0 | [49 empty] | 2021-09-13 |  | 31
NST-222059 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV + Battery Storage | 231.64 | No | 2021-09-09 | 2021-09-09 | 0 | 2021-09-09 | 2021-09-17 | 6 | 2021-10-06 | 2021-10-07 | 1
NST-222199 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 118.417 | No | 2021-08-20 | 2021-08-20 | 0 | 2021-08-20 | 2021-08-27 | 5 | 2021-09-01 | [6 empty] | 2021-09-13 | 7
NST-222224 | SCE | NEM | NEMA | Withdrawn | Solar PV | 177.111 | No | 2021-08-16 | 2021-08-16 | 0 | 2021-08-16 | 2021-08-25 | 7 |  |  |  |  | 2021-10-05 | 28
NST-222295 | SCE | NEM | NEM-ST | IA Negotiation |  | 3160.29 | No | 2021-10-05 | 2021-10-05 | 0 | 2021-10-05 | 2021-10-19 | 9 | 2021-11-02 | [6 empty] | 2021-11-08 | 4 | 2021-11-08 | 2021-11-19 | 8 |  |  | 2021-12-27 | 2022-01-19 | 15 | 2022-02-08 | 14 | [12 empty] | 2022-02-15
NST-222295 | SCE | NEM | NEMA | SCE Engineer. Supplemental Review Complete | Solar PV + Battery Storage | 3160.29 | No | 2021-08-19 | 2021-08-19 | 0 | 2021-08-19 | 2021-08-20 | 1 | 2021-08-29 | 2021-09-06 | 4 |  | 2021-09-15 | 6 |  | 2021-11-08 | 4
NST-222464 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV + Battery Storage | 418.132 | No | 2021-08-16 | 2021-08-16 | 0 | 2021-08-16 | 2021-08-30 | 10 | 2021-09-20 | 2021-09-21 | 1
NST-222541 | SCE | NEM | NEM-ST | Supplemental Review Complete |  | 616.224 | No | 2021-11-03 | 2021-11-03 | 0 | 2021-11-03 | [9 empty] | 2021-11-03 | 31 | 2021-12-22 | 2022-01-14 | 15 |  |  | 2022-01-25 | 2022-03-02 | 25
NST-222541 | SCE | NEM | VNEM-SOMAH | NEMI - Transferred to GICD | Solar PV | 616.224 | No | 2021-08-17 | 2021-08-17 | 0 | 2021-08-17 | 2021-08-20 | 3 | 2021-08-31 | 2021-09-08 | 5 |  |  |  |  | 2021-12-21 | 31
NST-222571 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 57.509 | No | 2021-08-17 | 2021-08-17 | 0 | 2021-08-17 | [9 empty] | 2021-08-24 | 5
NST-222572 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 58.185 | No | 2021-08-17 | 2021-08-17 | 0 | 2021-08-17 | [9 empty] | 2021-08-23 | 4
NST-222653 | SCE | NEM | VNEM-SOMAH | Withdrawn | Solar PV | 48.499 | No | 2021-08-26 | 2021-08-26 | 0 | 2021-08-26 | 2021-08-31 | 3 | 2021-09-15 | 2021-09-20 | 3 | 2021-09-28 | 2021-10-06 | 6
NST-222654 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 164.634 | No | 2021-08-17 | 2021-08-17 | 0 | 2021-08-17 | 2021-08-25 | 6 | 2021-09-16 | [6 empty] | 2021-09-21 | 3
NST-222693 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 992.334 | No | 2021-08-17 | 2021-08-17 | 0 | 2021-08-17 | 2021-08-23 | 4 | 2021-08-23 | [6 empty] | 2021-08-30 | 5
NST-222697 | SCE | NEM | VNEM-SOMAH | Withdrawn | Solar PV | 48.843 | No | 2021-08-26 | 2021-08-26 | 0 | 2021-08-26 | 2021-09-03 | 6 | 2021-09-15 | 2021-09-23 | 6 | 2021-09-28 |  |  | 2021-09-28
NST-223043 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 42.398 | No | 2021-08-18 | 2021-08-18 | 0 | 2021-08-18 | [9 empty] | 2021-08-24 | 4 | [49 empty] | 2021-09-07 |  | 20
NST-223259 | SCE | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 71.217 | No | 2021-08-18 | 2021-08-18 | 0 | 2021-08-18 | [9 empty] | 2021-08-26 | 6
NST-223309 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 50.073 | No | 2021-08-19 | 2021-08-19 | 0 | 2021-08-19 | 2021-08-25 | 4 | 2021-09-02 | [6 empty] | 2021-09-13 | 6
NST-223453 | SCE | NEM | NEM-ST | Application Review In Progress |  | 1271.853 | No | 2021-08-27 | 2021-08-27 | 0 | 2021-08-27 | 2021-09-16 | 13 | 2021-10-01 | 2021-10-20 | 12
NST-223453 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV + Battery Storage | 1271.853 | No | 2021-08-19 | 2021-08-19 | 0 | 2021-08-19 | 2021-08-20 | 1 | 2021-08-27 | [6 empty] | 2021-09-02 | 4
NST-223606 | SCE | NEM | NEMA | Withdrawn | Solar PV | 52.17 | No | 2021-08-19 | 2021-08-19 | 0 | 2021-08-19 | 2021-08-26 | 5 |  |  |  |  | 2021-10-07 | 29
NST-223693 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 73.271 | No | 2021-08-20 | 2021-08-20 | 0 | 2021-08-20 | [9 empty] | 2021-08-27 | 5 | [49 empty] | 2022-02-10 |  | 174
NST-223694 | SCE | NEM | Other-NEM-V | NGOM Installation. Pending AHJ Panel Permit | Solar PV | 173.702 | No | 2021-08-20 | 2021-08-20 | 0 | 2021-08-20 | [9 empty] | 2021-09-14 | 16
NST-223828 | SCE | NEM | NEMA | Withdrawn | Solar PV | 30.716 | No | 2021-08-20 | 2021-08-20 | 0 | 2021-08-20 | 2021-08-31 | 7 |  |  |  |  | 2021-10-08 | 27
NST-223930 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 938.859 | No | 2021-08-20 | 2021-08-20 | 0 | 2021-08-20 | [9 empty] | 2021-08-31 | 7
NST-224237 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 207.925 | No | 2021-08-23 | 2021-08-23 | 0 | 2021-08-23 | 2021-08-31 | 6 | 2021-09-01 | [6 empty] | 2021-09-11 | 6 | [49 empty] | 2021-09-13 |  | 21
NST-224243 | SCE | NEM | NEM-ST | Application Review In Progress |  | 2017.36 | No |  |  |  | 2021-09-13
NST-224243 | SCE | NEM | NEMA | Applicant Response Received. Pending SCE Engineer Review | Solar PV + Battery Storage | 2017.36 | No | 2021-08-24 | 2021-08-24 | 0 | 2021-08-24
NST-224291 | SCE | NEM | NEM | Application Review In Progress |  | 666.05 | No |  |  |  | 2021-09-03
NST-224291 | SCE | NEM | NEMA | Applicant Response Received. Pending SCE Engineer Review | Solar PV | 666.05 | No | 2021-08-24 | 2021-08-24 | 0 | 2021-08-24
NST-224292 | SCE | NEM | NEM-ST | Application Review In Progress |  | 762.47 | No |  |  |  | 2021-09-09
NST-224292 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 762.47 | No | 2021-08-24 | 2021-08-24 | 0 | 2021-08-24
NST-224342 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 67.252 | No | 2021-08-24 | 2021-08-24 | 0 | 2021-08-24 | 2021-08-31 | 5 | 2021-09-09 | [6 empty] | 2021-09-18 | 6 | [49 empty] | 2022-01-24 |  | 153
NST-224404 | SCE | NEM | NEMA | Withdrawn | Solar PV | 306.623 | No | 2021-08-24 | 2021-08-24 | 0 | 2021-08-24 | 2021-09-01 | 6 |  |  |  |  | 2021-09-17 | 11
NST-224453 | SCE | NEM | NEMA | SCE Engineer. Initial Review In Progress | Solar PV | 609.029 | No | 2021-08-24 | 2021-08-24 | 0 | 2021-08-24 | 2021-08-26 | 2 | 2021-09-02 | [6 empty] | 2021-09-07 | 2
NST-224453 | SCE | NEM | NEM-Military (SB-83) | Application Review In Progress |  | 609.029 | No |  |  |  | 2021-09-02
NST-224456 | SCE | NEM | NEMA | Withdrawn | Solar PV + Battery Storage | 77.176 | No | 2021-08-24 | 2021-08-24 | 0 | 2021-08-24 | 2021-09-02 | 7 |  |  |  |  | 2021-09-20 | 11
NST-224734 | SCE | NEM | NEMA | Applicant Response Received. Pending SCE Engineer Review | Solar PV | 591.515 | No | 2021-08-25 | 2021-08-25 | 0 | 2021-08-25 | 2021-09-01 | 5 | 2021-09-02 | [6 empty] | 2021-09-14 | 7
NST-224785 | SCE | NEM | NEMA | Withdrawn | Solar PV | 299.298 | No | 2021-08-25 | 2021-08-25 | 0 | 2021-08-25 | 2021-09-01 | 5 |  |  |  |  | 2021-09-17 | 11
NST-224796 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 172.073 | No | 2021-08-25 | 2021-08-25 | 0 | 2021-08-25 | 2021-09-01 | 5 | 2021-09-03 | [6 empty] | 2021-09-21 | 11
NST-224954 | SCE | NEM | NEMA | NGOM Installation. Pending Invoice Payment and AHJ Panel Permit | Solar PV + Battery Storage | 45.622 | No | 2021-08-26 | 2021-08-26 | 0 | 2021-08-26 | [9 empty] | 2021-08-27 | 1
NST-225062 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 119.479 | No | 2021-08-26 | 2021-08-26 | 0 | 2021-08-26 | [9 empty] | 2021-09-08 | 8
NST-225068 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 236.615 | No | 2021-08-26 | 2021-08-26 | 0 | 2021-08-26 | [9 empty] | 2021-09-13 | 11
NST-225078 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 98.394 | No | 2021-08-26 | 2021-08-26 | 0 | 2021-08-26 | [9 empty] | 2021-09-08 | 8
NST-225090 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 145.071 | No | 2021-08-26 | 2021-08-26 | 0 | 2021-08-26 | [9 empty] | 2021-09-08 | 8
NST-225094 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 145.071 | No | 2021-08-26 | 2021-08-26 | 0 | 2021-08-26 | 2021-09-03 | 6 | 2021-09-08 | 2021-09-16 | 6
NST-225111 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 142.502 | No | 2021-08-26 | 2021-08-26 | 0 | 2021-08-26 | [9 empty] | 2021-09-03 | 6
NST-225124 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 133.757 | No | 2021-08-26 | 2021-08-26 | 0 | 2021-08-26 | [9 empty] | 2021-09-07 | 7
NST-225366 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 37.055 | No | 2021-08-27 | 2021-08-27 | 0 | 2021-08-27 | [9 empty] | 2021-08-27 | 0 | [49 empty] | 2021-09-08 |  | 12
NST-225471 | SCE | NEM | NEMA | Withdrawn | Solar PV | 40.88 | No | 2021-08-27 | 2021-08-27 | 0 | 2021-08-27 | 2021-09-08 | 7 | 2021-09-08 | 2021-09-20 | 8 |  | 2021-09-28 | 6
NST-225637 | SCE | NEM | NEMA | Withdrawn | Solar PV | 296.582 | No | 2021-08-30 | 2021-08-30 | 0 | 2021-08-30 | 2021-09-07 | 5 | 2021-09-15 | 2021-09-21 | 4 |  | 2021-09-29 | 6
NST-225695 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 997.192 | No | 2021-08-30 | 2021-08-30 | 0 | 2021-08-30 | [9 empty] | 2021-09-09 | 7
NST-225702 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 483.015 | No | 2021-08-30 | 2021-08-30 | 0 | 2021-08-30 | 2021-09-07 | 5 | 2021-09-09 | [6 empty] | 2021-09-15 | 4
NST-225748 | SCE | NEM | NEMA | Withdrawn | Solar PV | 997.192 | No | 2021-08-30 | 2021-08-30 | 0 | 2021-08-30 | [9 empty] | 2021-09-08 | 6
NST-225752 | SCE | NEM | NEMA | SCE Engineer. Initial Review Complete | Solar PV | 997.192 | No | 2021-08-30 | 2021-08-30 | 0 | 2021-08-30 | [9 empty] | 2021-09-08 | 6
NST-226207 | SCE | NEM | NEMA | Withdrawn | Solar PV | 551.919 | No | 2021-08-31 | 2021-08-31 | 0 | 2021-08-31 | 2021-09-15 | 10 |  |  |  |  | 2021-09-30 | 11
NST-226404 | SCE | NEM | NEMA | Withdrawn | Solar PV | 6005.196 | No | 2021-09-01 | 2021-09-01 | 0 | 2021-09-01 | [6 empty] | 2021-09-27 | 17
NST-226614 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 68.245 | No | 2021-09-01 | 2021-09-01 | 0 | 2021-09-01 | 2021-11-24 | 57 | 2021-11-25 | [6 empty] | 2021-11-25 | 0 | [49 empty] | 2021-09-28 |  | 27
NST-226637 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 37.093 | No | 2021-09-01 | 2021-09-01 | 0 | 2021-09-01 | 2021-09-02 | 1 | 2021-09-07 | [6 empty] | 2021-09-16 | 7 | [49 empty] | 2021-09-27 |  | 26
NST-226900 | SCE | NEM | NEMA | NEMI - 1.0 Expansion Ineligible | Solar PV | 31.394 | No | 2021-09-02 | 2021-09-02 | 0 | 2021-09-02
NST-226928 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 301.627 | No | 2021-09-02 | 2021-09-02 | 0 | 2021-09-02 | 2021-09-11 | 5 | 2021-09-14 | [6 empty] | 2021-09-14 | 0 | [49 empty] | 2022-01-07 |  | 127
NST-227017 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 271.625 | No | 2021-09-03 | 2021-09-03 | 0 | 2021-09-03 | 2021-09-14 | 6 | 2021-11-02 | 2021-11-09 | 5 | 2021-11-09 |  |  |  | 2021-11-16 | 4 | [49 empty] | 2022-03-23 |  | 201
NST-227190 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 51.486 | No | 2021-09-14 | 2021-09-14 | 0 | 2021-09-14 | 2021-09-20 | 4 | [7 empty] | 2021-10-11 | 15 | [49 empty] | 2021-09-20 |  | 6
NST-227289 | SCE | NEM | Other-NEM-V | Withdrawn | Solar PV | 57.534 | No | 2021-09-03 | 2021-09-03 | 0 | 2021-09-03 | 2021-09-15 | 7 | 2021-09-21 | 2021-09-29 | 6 |  | 2021-09-29 | 0
NST-227416 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 224.606 | No | 2021-09-06 | 2021-09-06 | 0 | 2021-09-06 | [9 empty] | 2021-09-13 | 4 | [49 empty] | 2022-03-30 |  | 205
NST-227529 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 31.695 | No | 2021-09-07 | 2021-09-07 | 0 | 2021-09-07 | [9 empty] | 2021-09-17 | 8
NST-227638 | SCE | NEM | NEMA | Applicant Response Received. Pending SCE Engineer Review | Solar PV | 204.951 | No | 2021-09-07 | 2021-09-07 | 0 | 2021-09-07 | 2021-09-17 | 8 | 2021-09-22 | 2021-09-23 | 1 | 2021-09-24 |  |  |  | 2021-09-28 | 2
NST-227638 | SCE | NEM | NEM-ST | Application Review In Progress |  | 204.951 | No | 2021-09-28 | 2021-09-28 | 0 | 2021-09-28 | 2021-10-19 | 14
NST-227998 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 165.052 | No | 2021-09-08 | 2021-09-08 | 0 | 2021-09-08 | [9 empty] | 2021-09-14 | 4
NST-228797 | SCE | NEM | NEMA | Withdrawn | Solar PV | 129.672 | No | 2021-09-12 | 2021-09-12 | 0 | 2021-09-12 | 2021-09-17 | 4 |  |  |  |  | 2021-10-04 | 11
NST-228865 | SCE | NEM | NEMA | Withdrawn | Solar PV | 42.29 | No | 2021-09-13 | 2021-09-13 | 0 | 2021-09-13 | 2021-09-18 | 4 | 2021-09-20 | 2021-09-21 | 1 |  | 2021-09-29 | 6
NST-228992 | SCE | NEM | NEMA | NEMI - 1.0 Expansion Ineligible | Solar PV | 30 | No | 2021-09-13 | 2021-09-13 | 0 | 2021-09-13
NST-229047 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 31.663 | No | 2021-09-13 | 2021-09-13 | 0 | 2021-09-13 | 2021-09-17 | 4 | 2021-09-24 | [6 empty] | 2021-09-30 | 4 | [49 empty] | 2021-10-04 |  | 21
NST-229209 | SCE | NEM | NEM Aggregation | Transferred to NEM |  | 354.405 | No |  |  |  | 2021-10-05
NST-229209 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 354.405 | No | 2021-09-14 | 2021-09-14 | 0 | 2021-09-14 | 2021-09-20 | 4 | 2021-09-21 | 2021-09-22 | 1 | 2021-09-24
NST-229327 | SCE | NEM | NEMA | Withdrawn | Solar PV | 4547.958 | No | 2021-09-14 | 2021-09-14 | 0 | 2021-09-14 | [9 empty] | 2021-09-27 | 9
NST-229327 | SCE | NEM | NEM Aggregation | Withdrawn |  | 4547.958 | No | 2021-09-14 | 2021-09-14 | 0 | 2021-09-14 | 2021-09-27 | 9 | 2021-09-27 | [6 empty] | 2021-09-27 | 0
NST-229578 | SCE | NEM | Other-NEM-V | NEMI - 1.0 Expansion Ineligible | Solar PV | 241.532 | No | 2021-09-15 | 2021-09-15 | 0 | 2021-09-15
NST-229582 | SCE | NEM | NEMA | NEMI - Equipment Change Submitted | Solar PV | 209.759 | No | 2021-09-15 | 2021-09-15 | 0 | 2021-09-15 | 2021-09-22 | 5 | 2021-10-18 | [6 empty] | 2021-10-21 | 3
NST-229630 | SCE | NEM | NEM-ST | Application Review In Progress |  | 2423.25 | No | 2021-09-30 | 2021-09-30 | 0 | 2021-09-30 | 2021-10-19 | 12
NST-229630 | SCE | NEM | NEMA | Applicant Response Received. Pending SCE Engineer Review | Solar PV | 2423.25 | No | 2021-09-15 | 2021-09-15 | 0 | 2021-09-15 | 2021-09-16 | 1 | 2021-09-24 | 2021-09-29 | 3 | 2021-09-30
NST-229728 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 125.643 | No | 2021-09-15 | 2021-09-15 | 0 | 2021-09-15 | 2021-09-21 | 4 | 2021-09-21 | [6 empty] | 2021-09-27 | 4
NST-229858 | SCE | NEM | VNEM-SOMAH | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 45.215 | No | 2021-09-16 | 2021-09-16 | 0 | 2021-09-16 | 2021-09-21 | 3 | 2021-10-14 | 2021-10-15 | 1 |  |  |  |  | 2021-11-08 | 16
NST-229861 | SCE | NEM | VNEM-SOMAH | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 50.111 | No | 2021-09-16 | 2021-09-16 | 0 | 2021-09-16 | 2021-09-21 | 3 | 2021-10-05 | 2021-10-06 | 1
NST-229865 | SCE | NEM | VNEM-SOMAH | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 46.079 | No | 2021-09-16 | 2021-09-16 | 0 | 2021-09-16 | 2021-09-21 | 3 | 2021-10-05 | 2021-10-06 | 1 |  |  |  |  | 2021-11-04 | 20
NST-229908 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 131.4 | No | 2021-09-16 | 2021-09-16 | 0 | 2021-09-16 | 2021-09-21 | 3 | 2021-09-21 | [6 empty] | 2021-09-27 | 4 | [49 empty] | 2021-09-27 |  | 11
NST-229916 | SCE | NEM | VNEM-SOMAH | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 44.639 | No | 2021-09-16 | 2021-09-16 | 0 | 2021-09-16 | 2021-09-21 | 3 | 2021-10-05 | 2021-10-06 | 1 |  |  |  |  | 2021-11-04 | 20
NST-230091 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 66.734 | No | 2021-09-16 | 2021-09-16 | 0 | 2021-09-16 | 2021-09-22 | 4 | 2021-09-22 | 2021-09-28 | 4 | 2021-09-28 |  |  |  | 2021-10-01 | 3 | [49 empty] | 2022-02-25 |  | 162
NST-230377 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 276.258 | No | 2021-09-17 | 2021-09-17 | 0 | 2021-09-17 | 2021-09-21 | 2 | 2021-09-22 | [6 empty] | 2021-09-24 | 2
NST-230385 | SCE | NEM | NEM-ST | Application Review In Progress |  | 1199.13 | No |  |  |  | 2021-09-23
NST-230385 | SCE | NEM | NEMA | Applicant Response Received. Pending SCE Engineer Review | Solar PV + Battery Storage | 1199.13 | No | 2021-09-17 | 2021-09-17 | 0 | 2021-09-17
NST-230387 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 102.549 | No | 2021-09-17 | 2021-09-17 | 0 | 2021-09-17 | 2021-09-21 | 2 | 2021-09-21 | 2021-09-24 | 3 | 2021-09-24 |  |  |  | 2021-09-29 | 3
NST-230435 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 715.752 | No | 2021-09-17 | 2021-09-17 | 0 | 2021-09-17 | [9 empty] | 2021-10-01 | 10 | [49 empty] | 2021-09-24 |  | 7
NST-230628 | SCE | NEM | Other-NEM-V | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 66.78 | No | 2021-09-20 | 2021-09-20 | 0 | 2021-09-20 | 2021-09-24 | 4 | 2021-09-27 | 2021-09-28 | 1 |  |  |  |  | 2021-10-29 | 22
NST-230810 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 30.571 | No | 2021-09-20 | 2021-09-20 | 0 | 2021-09-20 | 2021-09-21 | 1 | 2021-09-22 | [6 empty] | 2021-10-01 | 7 | [49 empty] | 2021-09-27 |  | 7
NST-230846 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 34.224 | No | 2021-09-21 | 2021-09-21 | 0 | 2021-09-21 | 2021-09-22 | 1 | 2021-09-22 | 2021-09-27 | 3 | 2021-09-27 |  |  |  | 2021-09-27 | 0 | [49 empty] | 2021-09-30 |  | 9
NST-231067 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 32.17 | No | 2021-09-21 | 2021-09-21 | 0 | 2021-09-21 | [9 empty] | 2021-09-21 | 0 | [49 empty] | 2021-11-12 |  | 52
NST-231287 | SCE | NEM | NEM-ST | Application Review In Progress |  | 646.721 | No |  |  |  | 2021-11-15
NST-231287 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV + Battery Storage | 646.721 | No | 2021-09-22 | 2021-09-22 | 0 | 2021-09-22 | 2021-09-29 | 5
NST-231715 | SCE | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 81.22 | No | 2021-09-23 | 2021-09-23 | 0 | 2021-09-23 | 2021-09-27 | 2 | 2021-11-11
NST-231810 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 84.45 | No | 2021-09-23 | 2021-09-23 | 0 | 2021-09-23 | [9 empty] | 2021-09-28 | 3 | [49 empty] | 2022-02-09 |  | 139
NST-231824 | SCE | NEM | NEMA | Withdrawn | Solar PV | 127.476 | No | 2021-09-23 | 2021-09-23 | 0 | 2021-09-23 | 2021-09-28 | 3 | 2021-10-19 | 2021-10-20 | 1 |  |  |  | 2021-11-29
NST-231836 | SCE | NEM | NEMA | Withdrawn | Solar PV | 167.156 | No | 2021-09-23 | 2021-09-23 | 0 | 2021-09-23 | 2021-09-28 | 3 | 2021-10-13 | 2021-10-14 | 1 |  |  |  | 2021-10-22
NST-231856 | SCE | NEM | NEMA | Withdrawn | Solar PV | 83.578 | No | 2021-09-23 | 2021-09-23 | 0 | 2021-09-23 | 2021-09-28 | 3 | 2021-10-07 | [5 empty] | 2021-11-29
NST-231870 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 541.46 | No | 2021-09-23 | 2021-09-23 | 0 | 2021-09-23 | 2021-09-27 | 2 | 2021-10-07
NST-231895 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 427.458 | No | 2021-09-23 | 2021-09-23 | 0 | 2021-09-23 | 2021-09-24 | 1 | 2021-10-07
NST-231909 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 36.715 | No | 2021-09-23 | 2021-09-23 | 0 | 2021-09-23 | [9 empty] | 2021-09-23 | 0 | [49 empty] | 2021-09-24 |  | 1
NST-231986 | SCE | NEM | NEMA | Withdrawn | Solar PV | 44.06 | No | 2021-09-23 | 2021-09-23 | 0 | 2021-09-23 | 2021-09-24 | 1 | 2021-10-10 | 2021-10-11 | 0 |  |  |  | 2021-10-19
NST-232042 | SCE | NEM | NEMA | Withdrawn | Solar PV | 30.777 | No | 2021-09-24 | 2021-09-24 | 0 | 2021-09-24 | 2021-09-29 | 3 |  |  |  |  | 2021-10-14 | 10
NST-232069 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 93.745 | No | 2021-09-24 | 2021-09-24 | 0 | 2021-09-24 | 2021-09-30 | 4 | 2021-09-30
NST-232122 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 44.306 | No | 2021-09-24 | 2021-09-24 | 0 | 2021-09-24 | 2021-09-24 | 0 | 2022-01-10 | [6 empty] | 2022-01-10 | 0 | [49 empty] | 2022-01-20 |  | 118
NST-232124 | SCE | NEM | NEMA | NGOM Installation. Pending AHJ Panel Permit | Solar PV | 78.246 | No | 2021-09-24 | 2021-09-24 | 0 | 2021-09-24 | 2021-09-30 | 4 | 2021-10-01 | [6 empty] | 2021-10-06 | 3
NST-232139 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 306.623 | No | 2021-09-24 | 2021-09-24 | 0 | 2021-09-24
NST-232143 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 81.905 | No | 2021-09-24 | 2021-09-24 | 0 | 2021-09-24 | [9 empty] | 2021-09-29 | 3
NST-232232 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 124.347 | No | 2021-09-24 | 2021-09-24 | 0 | 2021-09-24 | [9 empty] | 2021-09-29 | 3
NST-232348 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 60.945 | No | 2021-09-25 | 2021-09-25 | 0 | 2021-09-25 | 2021-09-28 | 1 | 2021-09-29 | 2021-10-04 | 3 |  |  |  |  | 2021-11-04 | 22 | [49 empty] | 2021-09-29 |  | 4
NST-232379 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 75.28 | No | 2021-09-25 | 2021-09-25 | 0 | 2021-09-25 | 2021-10-01 | 4 | 2021-10-12
NST-232380 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 53.974 | No | 2021-09-25 | 2021-09-25 | 0 | 2021-09-25 | 2021-09-29 | 2 | 2021-09-30
NST-232543 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 59.656 | No | 2021-09-27 | 2021-09-27 | 0 | 2021-09-27 | 2021-09-30 | 3 | 2021-09-30 | [6 empty] | 2021-10-07 | 5 | [49 empty] | 2022-02-15 |  | 141
NST-232550 | SCE | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 59.656 | No | 2021-09-27 | 2021-09-27 | 0 | 2021-09-27 | 2021-09-29 | 2 | 2021-09-30 | 2021-10-07 | 5
NST-232563 | SCE | NEM | NEM-ST | Application Review In Progress |  | 220.216 | No |  |  |  | 2022-02-01
NST-232563 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 220.216 | No | 2021-09-27 | 2021-09-27 | 0 | 2021-09-27 | 2021-10-05 | 6 | 2021-10-05
NST-232584 | SCE | NEM | NEMA | NEMI - Sent to Engineering | Solar PV | 161.305 | No | 2021-09-27 | 2021-09-27 | 0 | 2021-09-27 | 2021-10-04 | 5 | 2021-10-05 | [6 empty] | 2021-10-11 | 4
NST-232584 | SCE | NEM | NEM-ST | Application Review In Progress |  | 161.305 | No |  |  |  | 2022-02-01
NST-232590 | SCE | NEM | NEMA | NEMI - Sent to Engineering | Solar PV | 145.074 | No | 2021-09-27 | 2021-09-27 | 0 | 2021-09-27 | 2021-10-05 | 6 | 2021-10-05 | [6 empty] | 2021-10-11 | 4
NST-232590 | SCE | NEM | NEM-ST | Application Review In Progress |  | 145.074 | No |  |  |  | 2021-10-11
NST-232595 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 54.475 | No | 2021-09-27 | 2021-09-27 | 0 | 2021-09-27 | 2021-09-30 | 3 | 2021-09-30
NST-232601 | SCE | NEM | NEMA | NEMI - Sent to Engineering | Solar PV | 173.009 | No | 2021-09-27 | 2021-09-27 | 0 | 2021-09-27 | 2021-10-05 | 6 | 2021-10-05 | [6 empty] | 2021-10-08 | 3
NST-232601 | SCE | NEM | NEM-ST | Application Review In Progress |  | 173.009 | No |  |  |  | 2021-10-08
NST-232607 | SCE | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 71.019 | No | 2021-09-27 | 2021-09-27 | 0 | 2021-09-27 | 2021-09-30 | 3 | 2021-09-30
NST-232609 | SCE | NEM | NEM-ST | Supplemental Review In Progress |  | 1007.193 | No | 2021-09-27 | 2021-09-27 | 0 | 2021-09-27 | 2021-10-12 | 10 | 2021-10-26 | 2021-11-08 | 9 | 2021-12-13 |  |  |  | 2021-12-29 | 11 | 2021-12-29 | 2022-01-20 | 14
NST-232609 | SCE | NEM | NEMA | SCE Engineer Assigned. Pending Technical Review | Solar PV + Battery Storage | 1007.193 | No | 2021-09-27 | 2021-09-27 | 0 | 2021-09-27 | [9 empty] | 2021-12-29 | 11
NST-232626 | SCE | NEM | NEMA | NEMI - Sent to Engineering | Solar PV | 316.089 | No | 2021-09-27 | 2021-09-27 | 0 | 2021-09-27 | 2021-10-04 | 5 | 2021-10-05 | [6 empty] | 2021-10-08 | 3
NST-232626 | SCE | NEM | NEM-ST | Application Review In Progress |  | 316.089 | No |  |  |  | 2021-10-08
NST-232635 | SCE | NEM | NEMA | Withdrawn | Solar PV | 198.604 | No | 2021-09-27 | 2021-09-27 | 0 | 2021-09-27 | 2021-10-04 | 5 | 2021-10-05 |  |  |  | 2021-12-27 | 54
NST-232641 | SCE | NEM | NEMA | Withdrawn | Solar PV | 290.145 | No | 2021-09-27 | 2021-09-27 | 0 | 2021-09-27 | 2021-10-01 | 4 | 2021-10-10 | 2021-10-11 | 0 |  | 2021-10-19 | 5
NST-232650 | SCE | NEM | NEMA | NEMI - Sent to Engineering | Solar PV | 145.074 | No | 2021-09-27 | 2021-09-27 | 0 | 2021-09-27 | 2021-10-04 | 5 | 2021-10-05 | [6 empty] | 2021-10-11 | 4
NST-232650 | SCE | NEM | NEM-ST | Intake |  | 145.074 | No |  |  |  | 2021-10-11
NST-232660 | SCE | NEM | NEMA | Withdrawn | Solar PV | 163.642 | No | 2021-09-27 | 2021-09-27 | 0 | 2021-09-27 | 2021-10-04 | 5 | 2021-10-05 |  |  |  | 2021-12-27 | 54
NST-232696 | SCE | NEM | NEMA | Withdrawn | Solar PV | 37.089 | No | 2021-09-27 | 2021-09-27 | 0 | 2021-09-27 | 2021-10-05 | 6 | [6 empty] | 2021-10-20
NST-232697 | SCE | NEM | NEMA | Withdrawn | Solar PV | 32.331 | No | 2021-09-27 | 2021-09-27 | 0 | 2021-09-27 | 2021-10-05 | 6 |  |  |  |  | 2021-10-20 | 10
NST-232699 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV + Battery Storage | 675.834 | No | 2021-09-27 | 2021-09-27 | 0 | 2021-09-27 | 2021-10-05 | 6 | 2021-11-02 | 2021-11-03 | 1 |  |  |  |  | 2021-11-09 | 4
NST-232708 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV + Battery Storage | 499.758 | No | 2021-09-27 | 2021-09-27 | 0 | 2021-09-27 | 2021-10-01 | 4 | 2021-11-02 | 2021-11-03 | 1 |  |  |  |  | 2021-11-17 | 9
NST-232735 | SCE | NEM | NEMA | Withdrawn | Solar PV | 113.32 | No | 2021-10-04 | 2021-10-04 | 0 | 2021-10-04 | 2021-10-07 | 3 | 2021-11-15 |  |  |  | 2021-12-08 | 15
NST-232792 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 265.196 | No | 2021-09-28 | 2021-09-28 | 0 | 2021-09-28 | [9 empty] | 2021-09-28 | 0 | [49 empty] | 2021-09-30 |  | 2
NST-232996 | SCE | NEM | NEMA | Applicant Response Received. Pending SCE Engineer Review | Solar PV + Battery Storage | 426.064 | No | 2021-10-01 | 2021-10-01 | 0 | 2021-10-01 | 2021-10-08 | 5 | 2021-10-27 | [6 empty] | 2021-12-07 | 26
NST-233019 | SCE | NEM | NEMA | SCE Engineer. Initial Review Complete | Solar PV + Battery Storage | 749.966 | No | 2021-10-01 | 2021-10-01 | 0 | 2021-10-01 | [9 empty] | 2021-12-03 | 41
NST-233019 | SCE | NEM | NEM-ST | IA Negotiation |  | 749.966 | No | 2021-11-04 | 2021-11-04 | 0 | 2021-11-04 | 2021-12-20 | 29 | 2021-12-29 | [6 empty] | 2022-01-03 | 2 | 2022-01-05 | 2022-01-25 | 13 | 2022-01-25 | 0
NST-233223 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 158.582 | No | 2021-09-29 | 2021-09-29 | 0 | 2021-09-29 | 2021-10-05 | 4 | 2021-10-11 | 2021-10-12 | 0
NST-233264 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 296.582 | No | 2021-09-29 | 2021-09-29 | 0 | 2021-09-29
NST-233290 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 41.501 | No | 2021-09-29 | 2021-09-29 | 0 | 2021-09-29 | [9 empty] | 2021-09-30 | 1 | [49 empty] | 2021-09-30 |  | 1
NST-233382 | SCE | NEM | NEMA | SCE Engineer. Detail Study In Progress | Solar PV | 1492.488 | No | 2021-09-29 | 2021-09-29 | 0 | 2021-09-29 | 2021-11-18 | 34 | 2021-12-03 | 2021-12-10 | 5 | 2022-01-10 |  |  |  | 2022-01-11 | 1
NST-233382 | SCE | NEM | NEM-ST | System Impact Study In Progress |  | 1492.488 | No | 2021-11-02 | 2021-11-02 | 0 | 2021-11-02 | 2021-11-18 | 11 | 2021-12-03 | 2021-12-10 | 5 | 2022-01-10 |  |  |  | 2022-01-11 | 1 | 2022-01-11 | 2022-01-31 | 13 | [7 empty] | 2022-03-04 | 2022-03-17 | 9 | 2022-03-17 |  | 2022-03-24
NST-233467 | SCE | NEM | NEM-ST | Construction |  | 0.0142 | No | 2021-10-07 | 2021-10-07 | 0 | 2021-10-07 | [9 empty] | 2021-10-07 | 0 | 2021-11-23 | 2021-12-01 | 4 | [20 empty] | 2021-12-28 | 18 |  | 2022-01-26 | 29
NST-233633 | SCE | NEM | NEM-ST | In-Service |  | 162.607 | No | 2021-10-20 | 2021-10-20 | 0 | 2021-10-20 | 2021-11-03 | 10 | 2021-11-23 | [6 empty] | 2021-11-30 | 3 | 2021-11-30 | 2021-12-21 | 15 | 2022-01-28 | 25 | [21 empty] | 2022-03-18 | 44638
NST-233633 | SCE | NEM | NEMA | SCE Engineer Assigned. Pending Technical Review | Solar PV | 162.607 | No | 2021-09-30 | 2021-09-30 | 0 | 2021-09-30 | [9 empty] | 2021-11-30 | 3
NST-233878 | SCE | NEM | VNEM-SOMAH | NGOM Installation. Pending AHJ Panel Permit | Solar PV | 46.387 | No | 2021-10-01 | 2021-10-01 | 0 | 2021-10-01 | 2021-10-12 | 6
NST-233880 | SCE | NEM | VNEM-SOMAH | NGOM Installation. Pending AHJ Panel Permit | Solar PV | 72.514 | No | 2021-10-01 | 2021-10-01 | 0 | 2021-10-01 | 2021-10-14 | 8 | [7 empty] | 2021-10-14 | 0
NST-234059 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 31.394 | No | 2021-10-01 | 2021-10-01 | 0 | 2021-10-01 | 2021-10-07 | 4 | 2021-10-13 | 2021-10-14 | 1
NST-234148 | SCE | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 40.127 | No | 2021-10-04 | 2021-10-04 | 0 | 2021-10-04
NST-234149 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 74.308 | No | 2021-10-04 | 2021-10-04 | 0 | 2021-10-04
NST-234157 | SCE | NEM | NEMA | Withdrawn | Solar PV | 66.757 | No | 2021-10-04 | 2021-10-04 | 0 | 2021-10-04 | 2021-10-08 | 4 | 2021-11-10 |  |  |  | 2021-12-09 | 18
NST-234158 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 31.21 | No | 2021-10-04 | 2021-10-04 | 0 | 2021-10-04
NST-234159 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 87.312 | No | 2021-10-04 | 2021-10-04 | 0 | 2021-10-04 | [9 empty] | 2021-10-08 | 4
NST-234160 | SCE | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 42.727 | No | 2021-10-04 | 2021-10-04 | 0 | 2021-10-04
NST-234161 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 51.91 | No | 2021-10-04 | 2021-10-04 | 0 | 2021-10-04 | 2021-10-08 | 4 | 2021-11-15
NST-234162 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 51.91 | No | 2021-10-04 | 2021-10-04 | 0 | 2021-10-04 | [9 empty] | 2021-10-11 | 5
NST-234163 | SCE | NEM | NEMA | Withdrawn | Solar PV | 76.538 | No | 2021-10-04 | 2021-10-04 | 0 | 2021-10-04 | 2021-10-13 | 6 | 2021-11-22 |  |  |  | 2021-12-14 | 14
NST-234164 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 54.511 | No | 2021-10-04 | 2021-10-04 | 0 | 2021-10-04 | 2021-10-08 | 4 | 2021-11-18 | 2021-11-19 | 1
NST-234165 | SCE | NEM | NEMA | Withdrawn | Solar PV | 86.941 | No | 2021-10-04 | 2021-10-04 | 0 | 2021-10-04 | 2021-10-08 | 4 | 2021-11-10 |  |  |  | 2021-12-09 | 18
NST-234166 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 47.316 | No | 2021-10-04 | 2021-10-04 | 0 | 2021-10-04 | [9 empty] | 2021-10-08 | 4
NST-234167 | SCE | NEM | NEMA | Withdrawn | Solar PV | 48.191 | No | 2021-10-04 | 2021-10-04 | 0 | 2021-10-04 | 2021-10-08 | 4 | 2021-11-15 |  |  |  | 2021-12-08 | 15
NST-234291 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 95.661 | No | 2021-10-04 | 2021-10-04 | 0 | 2021-10-04
NST-234467 | SCE | NEM | VNEM-SOMAH | SCE Engineer Review. Pending Applicant Response | Solar PV | 32.806 | No | 2021-10-04 | 2021-10-04 | 0 | 2021-10-04 | 2021-10-13 | 6 | 2021-10-19
NST-234508 | SCE | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 253.667 | No | 2021-10-04 | 2021-10-04 | 0 | 2021-10-04
NST-234681 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 346.581 | No | 2021-10-05 | 2021-10-05 | 0 | 2021-10-05 | 2021-10-14 | 6 | 2021-10-27 | 2021-10-28 | 1 |  |  |  |  | 2021-11-16 | 12
NST-234735 | SCE | NEM | VNEM-SOMAH | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 34.588 | No | 2021-10-05 | 2021-10-05 | 0 | 2021-10-05 | [9 empty] | 2021-10-12 | 4
NST-234744 | SCE | NEM | VNEM-SOMAH | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 47.609 | No | 2021-10-05 | 2021-10-05 | 0 | 2021-10-05 | [9 empty] | 2021-10-15 | 7
NST-234776 | SCE | NEM | NEMA | Withdrawn | Solar PV + Battery Storage | 230 | No | 2021-10-05 | 2021-10-05 | 0 | 2021-10-05 | 2021-10-11 | 4 |  |  |  |  | 2021-10-26 | 10
NST-234819 | SCE | NEM | NEMA | Withdrawn | Solar PV + Battery Storage | 230 | No | 2021-10-05 | 2021-10-05 | 0 | 2021-10-05 | 2021-10-11 | 4 |  |  |  |  | 2021-10-26 | 10
NST-235155 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 177.095 | No | 2021-10-06 | 2021-10-06 | 0 | 2021-10-06 | 2021-10-13 | 4 | 2021-10-14 | [6 empty] | 2021-10-28 | 10
NST-235155 | SCE | NEM | NEM Aggregation | Transferred to NEM |  | 177.095 | No |  |  |  | 2021-10-28
NST-235240 | SCE | NEM | NEMA | SCE Engineer Review. Pending SCE System Upgrades | Solar PV | 400.546 | No | 2021-10-07 | 2021-10-07 | 0 | 2021-10-07 | 2021-10-12 | 2 | 2021-11-04 | 2021-11-05 | 1 |  |  |  |  | 2021-11-30 | 14
NST-235240 | SCE | NEM | NEM-ST | Transferred to NEM |  | 400.546 | No | 2021-11-30 | 2021-11-30 | 0 | 2021-11-30
NST-235259 | SCE | NEM | NEMA | Withdrawn | Solar PV | 51.402 | No | 2021-10-07 | 2021-10-07 | 0 | 2021-10-07 | 2021-10-13 | 3 |  |  |  |  | 2021-10-28 | 11
NST-235366 | SCE | NEM | VNEM-SOMAH | NGOM Installation. Pending New Service Request and AHJ Panel Permit | Solar PV | 123.995 | No | 2021-10-07 | 2021-10-07 | 0 | 2021-10-07 | 2021-10-20 | 8 | 2021-10-25 | [6 empty] | 2021-11-05 | 9
NST-235385 | SCE | NEM | VNEM-SOMAH | Withdrawn | Solar PV | 99.785 | No | 2021-10-07 | 2021-10-07 | 0 | 2021-10-07 | 2021-10-12 | 2 |  |  |  |  | 2021-10-27 | 10
NST-235478 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 33.788 | No | 2021-10-07 | 2021-10-07 | 0 | 2021-10-07 | 2021-10-11 | 2 | 2021-10-14 | 2021-10-15 | 1 |  |  |  |  | 2021-10-28 | 9 | [49 empty] | 2021-11-10 |  | 34
NST-235512 | SCE | NEM | NEM-FC | NEMI - Conditional PTO | Fuel Cell - Renewable | 1100 | No | 2021-10-07 | 2021-10-07 | 0 | 2021-10-07 | 2021-10-14 | 4 | 2021-10-15 | [6 empty] | 2021-10-20 | 3 | [49 empty] | 2022-03-04 |  | 148
NST-235512 | SCE | NEM | NEM-ST | IA Negotiation |  | 1100 | No |  |  |  | 2021-10-15 | [60 empty] | 2022-03-04 |  | 140
NST-235698 | SCE | NEM | NEMA | Withdrawn | Solar PV | 290.845 | No | 2021-10-08 | 2021-10-08 | 0 | 2021-10-08 | 2021-10-11 | 1 |  |  |  |  | 2021-10-26 | 10
NST-236173 | SCE | NEM | NEM-ST | Application Review In Progress |  | 1305 | No |  |  |  | 2021-10-19
NST-236173 | SCE | NEM | Other-MT-ST | SCE Engineer Assigned. Pending Technical Review | Other | 1305 | No | 2021-10-11 | 2021-10-11 | 0 | 2021-10-11
NST-236463 | SCE | NEM | NEM Aggregation | Application Review In Progress |  | 147.915 | No |  |  |  | 2021-11-29
NST-236463 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 147.915 | No | 2021-10-12 | 2021-10-12 | 0 | 2021-10-12 | 2021-10-22 | 7 | 2021-11-02 | 2021-11-03 | 1
NST-236933 | SCE | NEM | NEMA | Withdrawn | Solar PV | 63.547 | No | 2021-10-13 | 2021-10-13 | 0 | 2021-10-13 | 2021-10-19 | 4 | 2021-11-22 | 2021-11-23 | 1 |  | 2021-12-08 | 9
NST-236987 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 32.324 | No | 2021-10-22 | 2021-10-22 | 0 | 2021-10-22 | 2021-10-26 | 2 | 2021-10-28 | [6 empty] | 2021-11-03 | 4
NST-237191 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 38.311 | No | 2021-10-14 | 2021-10-14 | 0 | 2021-10-14 | [9 empty] | 2021-10-20 | 4
NST-237236 | SCE | NEM | NEMA | NEMI - Sent to Engineering | Solar PV + Battery Storage | 1462.698 | No | 2021-10-14 | 2021-10-14 | 0 | 2021-10-14 | [9 empty] | 2022-03-03 | 93
NST-237236 | SCE | NEM | NEM-ST | Withdrawn |  | 1462.698 | No |  |  |  | 2021-10-28
NST-237346 | SCE | NEM | NEMA | Withdrawn | Solar PV | 428.831 | No | 2021-10-14 | 2021-10-14 | 0 | 2021-10-14 | 2021-10-26 | 8 |  |  |  |  | 2021-11-10 | 11
NST-237456 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 31.064 | No | 2021-10-15 | 2021-10-15 | 0 | 2021-10-15 | [9 empty] | 2021-10-18 | 1 | [49 empty] | 2022-03-16 |  | 152
NST-237462 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 46.079 | No | 2021-10-15 | 2021-10-15 | 0 | 2021-10-15 | [9 empty] | 2021-10-25 | 6 | [49 empty] | 2022-03-16 |  | 152
NST-237530 | SCE | NEM | NEMA | Withdrawn | Solar PV | 123.891 | No | 2021-10-15 | 2021-10-15 | 0 | 2021-10-15 | 2021-10-20 | 3 | 2021-11-29 | 2021-11-30 | 1 |  | 2021-12-08 | 6
NST-237681 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV + Battery Storage | 76.852 | No | 2021-10-15 | 2021-10-15 | 0 | 2021-10-15 | 2021-10-25 | 6 | 2021-10-25 | [6 empty] | 2021-11-02 | 6 | [49 empty] | 2022-02-14 |  | 122
NST-237751 | SCE | NEM | NEMA | Withdrawn | Solar PV | 68.086 | No | 2021-10-17 | 2021-10-17 | 0 | 2021-10-17 | 2021-10-18 | 0 | 2021-10-24 | 2021-10-25 | 0 |  | 2021-11-02 | 6
NST-237802 | SCE | NEM | Other-NEM-V | SCE Engineer Review. Pending Applicant Response | Solar PV | 710.48 | No | 2021-10-20 | 2021-10-20 | 0 | 2021-10-20 | 2021-10-26 | 4 | 2021-11-02
NST-237830 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 30.236 | No | 2021-10-18 | 2021-10-18 | 0 | 2021-10-18 | [9 empty] | 2021-10-26 | 6 | [49 empty] | 2021-11-04 |  | 17
NST-237887 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 52.17 | No | 2021-10-18 | 2021-10-18 | 0 | 2021-10-18 | 2021-10-25 | 5 | 2021-11-24 | [6 empty] | 2021-12-03 | 5 | [49 empty] | 2022-01-24 |  | 98
NST-238138 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 146.577 | No | 2021-10-19 | 2021-10-19 | 0 | 2021-10-19 | 2021-10-22 | 3 | 2021-11-01 | [6 empty] | 2021-11-12 | 8 | [49 empty] | 2021-12-02 |  | 44
NST-238201 | SCE | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 159.041 | No | 2021-10-19 | 2021-10-19 | 0 | 2021-10-19 | 2021-10-22 | 3 | 2021-11-05 | [6 empty] | 2021-11-10 | 3
NST-238228 | SCE | NEM | NEMA | SCE Engineer. Initial Review Complete | Solar PV | 998.341 | No | 2021-10-19 | 2021-10-19 | 0 | 2021-10-19
NST-238337 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 31.319 | No | 2021-10-19 | 2021-10-19 | 0 | 2021-10-19 | 2021-10-22 | 3 | 2021-10-31 | 2021-11-01 | 0 |  |  |  |  | 2021-11-08 | 5 | [49 empty] | 2022-01-22 |  | 95
NST-238443 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 125.954 | No | 2021-10-19 | 2021-10-19 | 0 | 2021-10-19 | 2021-10-25 | 4 | 2021-11-01
NST-238451 | SCE | NEM | VNEM-SOMAH | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 58.702 | No | 2021-10-19 | 2021-10-19 | 0 | 2021-10-19 | [9 empty] | 2021-10-28 | 7
NST-238452 | SCE | NEM | VNEM-SOMAH | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 39.655 | No | 2021-10-19 | 2021-10-19 | 0 | 2021-10-19 | 2021-10-28 | 7 | 2021-11-04 | [6 empty] | 2021-11-08 | 2
NST-238453 | SCE | NEM | VNEM-SOMAH | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 84.931 | No | 2021-10-19 | 2021-10-19 | 0 | 2021-10-19 | [9 empty] | 2021-10-28 | 7
NST-238578 | SCE | NEM | NEMA | Withdrawn | Solar PV + Battery Storage | 1584.307 | No | 2021-10-20 | 2021-10-20 | 0 | 2021-10-20 | [6 empty] | 2021-11-10 | 15
NST-238954 | SCE | NEM | NEMA | Withdrawn | Solar PV | 42.509 | No | 2021-10-21 | 2021-10-21 | 0 | 2021-10-21 | 2021-10-29 | 6 | 2021-11-07 | 2021-11-08 | 0 |  | 2021-11-17 | 6
NST-238961 | SCE | NEM | NEM-ST | Application Review In Progress |  | 1055.194 | No |  |  |  | 2022-02-01
NST-238961 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 1055.194 | No | 2021-10-21 | 2021-10-21 | 0 | 2021-10-21 |  |  |  | 2021-11-08 |  |  | 2021-12-16 | 25
NST-238971 | SCE | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 104.128 | No | 2021-11-17 | 2021-11-17 | 0 | 2021-11-17 | 2021-11-23 | 4 | 2021-11-23
NST-239276 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 49.887 | No | 2021-10-22 | 2021-10-22 | 0 | 2021-10-22 | [9 empty] | 2021-10-25 | 1
NST-239366 | SCE | NEM | NEM Aggregation | Application Review In Progress |  | 1217.025 | No |  |  |  | 2021-11-08
NST-239366 | SCE | NEM | NEMA | SCE Engineer Assigned. Pending Technical Review | Solar PV | 1217.025 | No | 2021-10-22 | 2021-10-22 | 0 | 2021-10-22
NST-239682 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 142.111 | No | 2021-10-25 | 2021-10-25 | 0 | 2021-10-25 | [9 empty] | 2021-10-29 | 4
NST-23972 | SCE | NEM | NEMA | Withdrawn | Solar PV | 142.502 | No | 2021-06-27 | 2021-06-27 | 0 | 2021-06-27 | 2021-06-30 | 2 |  |  |  |  | 2021-08-05 | 25
NST-23977 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 153.308 | No | 2021-08-02 | 2021-08-02 | 0 | 2021-08-02 | 2021-08-10 | 6 | 2021-08-17 | [6 empty] | 2021-09-02 | 12
NST-239800 | SCE | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 31.329 | No | 2021-10-25 | 2021-10-25 | 0 | 2021-10-25
NST-239870 | SCE | NEM | NEMA | Withdrawn | Solar PV | 110.039 | No | 2021-10-25 | 2021-10-25 | 0 | 2021-10-25 |  |  |  | 2021-11-02 |  |  | 2021-12-03 | 20
NST-239917 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 31.615 | No | 2021-10-25 | 2021-10-25 | 0 | 2021-10-25 | [9 empty] | 2021-10-25 | 0 | [49 empty] | 2021-11-04 |  | 10
NST-240125 | SCE | NEM | NEMA | NEMI - Sent to Engineering | Solar PV | 290.145 | No | 2021-10-26 | 2021-10-26 | 0 | 2021-10-26 | [9 empty] | 2021-10-29 | 3
NST-240125 | SCE | NEM | NEM-ST | Application Review In Progress |  | 290.145 | No |  |  |  | 2021-10-29
NST-240332 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 38.206 | No | 2021-10-27 | 2021-10-27 | 0 | 2021-10-27 | 2021-10-28 | 1 | 2021-11-01 | [6 empty] | 2021-11-09 | 6 | [49 empty] | 2022-03-16 |  | 140
NST-240381 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 33.579 | No | 2021-10-27 | 2021-10-27 | 0 | 2021-10-27 | 2021-11-03 | 5 | 2021-11-12 | [6 empty] | 2021-11-12 | 0 | [49 empty] | 2021-12-10 |  | 44
NST-240504 | SCE | NEM | NEMA | NEMI - 1.0 Expansion Ineligible | Solar PV | 760.466 | No | 2021-10-27 | 2021-10-27 | 0 | 2021-10-27
NST-240650 | SCE | NEM | VNEM-SOMAH | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 99.785 | No | 2021-10-28 | 2021-10-28 | 0 | 2021-10-28 | 2021-11-15 | 11
NST-240738 | SCE | NEM | NEMA | Withdrawn | Solar PV | 250.83 | No | 2021-10-28 | 2021-10-28 | 0 | 2021-10-28
NST-240808 | SCE | NEM | VNEM-SOMAH | NGOM Installation. Pending Local Planner Process | Solar PV | 60.576 | No | 2021-10-28 | 2021-10-28 | 0 | 2021-10-28 | 2021-11-10 | 9 | 2021-11-28 | 2021-11-29 | 0 |  |  |  |  | 2021-12-20 | 15
NST-240813 | SCE | NEM | VNEM-SOMAH | SCE System Upgrades. Pending Local Planner Process | Solar PV | 82.745 | No | 2021-10-28 | 2021-10-28 | 0 | 2021-10-28 | 2021-11-10 | 9 | 2021-11-28 | 2021-11-29 | 0 |  |  |  |  | 2021-12-20 | 15
NST-240816 | SCE | NEM | VNEM-SOMAH | NGOM Installation. Pending Local Planner Process | Solar PV | 88.053 | No | 2021-10-28 | 2021-10-28 | 0 | 2021-10-28 | 2021-11-10 | 9 | 2021-11-28 | 2021-11-29 | 0 |  |  |  |  | 2021-12-20 | 15
NST-240821 | SCE | NEM | Other-NEM-V | NGOM Installation. Pending New Service Request and AHJ Panel Permit | Solar PV | 39.039 | No | 2021-10-28 | 2021-10-28 | 0 | 2021-10-28 | 2021-11-05 | 6 | 2021-11-17 | 2021-11-18 | 1 |  |  |  |  | 2022-01-12 | 35
NST-240822 | SCE | NEM | Other-NEM-V | NGOM Installation. Pending New Service Request and AHJ Panel Permit | Solar PV | 60.638 | No | 2021-10-28 | 2021-10-28 | 0 | 2021-10-28 | 2021-11-04 | 5 | 2021-11-15 | 2021-11-16 | 1 |  |  |  |  | 2022-01-12 | 37
NST-240828 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 36.867 | No | 2021-10-28 | 2021-10-28 | 0 | 2021-10-28 | [9 empty] | 2021-11-01 | 2 | [49 empty] | 2021-11-04 |  | 7
NST-240907 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 290.796 | No | 2021-10-28 | 2021-10-28 | 0 | 2021-10-28 | [9 empty] | 2021-10-28 | 0 | [49 empty] | 2021-11-03 |  | 6
NST-241058 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 174.473 | No | 2021-10-29 | 2021-10-29 | 0 | 2021-10-29 | 2021-11-03 | 3 | 2021-11-05
NST-241064 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 98.009 | No | 2021-10-29 | 2021-10-29 | 0 | 2021-10-29 | 2021-11-04 | 4 | 2021-11-05
NST-241068 | SCE | NEM | NEMA | Withdrawn | Solar PV | 71.796 | No | 2021-10-29 | 2021-10-29 | 0 | 2021-10-29 | 2021-11-03 | 3 | 2021-11-22 | 2021-11-23 | 1 |  | 2021-11-19 | 11
NST-241097 | SCE | NEM | NEM-ST | Supplemental Review In Progress |  | 2206.415 | No | 2021-11-29 | 2021-11-29 | 0 | 2021-11-29 | 2021-12-13 | 10 | 2021-12-20 | 2021-12-27 | 4 | 2022-02-14 |  |  |  | 2022-02-22 | 5 | 2022-02-22 | 2022-03-16 | 16 |  |  | 2022-03-31
NST-241097 | SCE | NEM | NEMA | SCE Engineer. Initial Review Complete | Solar PV + Battery Storage | 2206.415 | No | 2021-10-29 | 2021-10-29 | 0 | 2021-10-29 | [9 empty] | 2022-02-22 | 5
NST-241122 | SCE | NEM | NEMA | NEMI - Application Re-Submitted | Solar PV | 127 | No | 2021-10-29 | 2021-10-29 | 0 | 2021-10-29 | 2021-11-05 | 5 | [7 empty] | 2021-11-16 | 6
NST-241130 | SCE | NEM | NEMA | Withdrawn | Solar PV | 522.149 | No | 2021-10-29 | 2021-10-29 | 0 | 2021-10-29 | 2021-11-02 | 2 | 2021-11-04 | 2021-11-05 | 1 |  | 2021-11-10 | 3
NST-24116 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 98.394 | No | 2021-05-26 | 2021-05-26 | 0 | 2021-05-26 | [9 empty] | 2021-05-28 | 2
NST-24117 | SCE | NEM | NEMA | Withdrawn | Solar PV | 838.315 | No | 2021-03-19 | 2021-03-19 | 0 | 2021-03-19 | 2021-03-24 | 3 | 2021-03-30 | 2021-04-02 | 2 |  | 2021-04-19 | 11
NST-24118 | SCE | NEM | NEMA | Withdrawn | Solar PV | 208.086 | No | 2021-05-27 | 2021-05-27 | 0 | 2021-05-27 | 2021-06-01 | 2 | 2021-06-13 | 2021-06-14 | 0 |  | 2021-07-13 | 20
NST-24119 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 107.218 | No | 2021-05-27 | 2021-05-27 | 0 | 2021-05-27 | 2021-06-01 | 2 | 2021-06-07 | [6 empty] | 2021-06-11 | 4
NST-24120 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 99.06 | No | 2021-08-03 | 2021-08-03 | 0 | 2021-08-03 | 2021-08-11 | 6 | 2021-08-24 | [6 empty] | 2021-09-02 | 7
NST-24121 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 54.273 | No | 2021-08-03 | 2021-08-03 | 0 | 2021-08-03 | 2021-08-12 | 7 | 2021-08-24 | [6 empty] | 2021-09-02 | 7
NST-24122 | SCE | NEM | NEMA | Withdrawn | Solar PV | 135.121 | No | 2021-05-27 | 2021-05-27 | 0 | 2021-05-27 | 2021-06-02 | 3 | 2021-06-13 | 2021-06-14 | 0 |  | 2021-07-13 | 20
NST-24123 | SCE | NEM | NEMA | Withdrawn | Solar PV | 119.479 | No | 2021-05-27 | 2021-05-27 | 0 | 2021-05-27 | 2021-06-01 | 2 | 2021-06-13 | 2021-06-14 | 0 |  | 2021-07-13 | 20
NST-24124 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 783.877 | No | 2021-03-19 | 2021-03-19 | 0 | 2021-03-19 | 2021-03-24 | 3 | 2021-03-30 | [6 empty] | 2021-04-07 | 5
NST-24125 | SCE | NEM | NEMA | Withdrawn | Solar PV | 491.582 | No | 2021-05-27 | 2021-05-27 | 0 | 2021-05-27 | 2021-06-02 | 3 | 2021-06-13 | 2021-06-14 | 0 |  | 2021-07-13 | 20
NST-24126 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 63.254 | No | 2021-05-27 | 2021-05-27 | 0 | 2021-05-27 | 2021-06-02 | 3 | 2021-06-07 | [6 empty] | 2021-06-14 | 5
NST-24127 | SCE | NEM | NEMA | Withdrawn | Solar PV | 201.902 | No | 2021-05-27 | 2021-05-27 | 0 | 2021-05-27 | 2021-06-02 | 3 | 2021-06-13 | 2021-06-14 | 0 |  | 2021-07-13 | 20
NST-24129 | SCE | NEM | NEMA | Withdrawn | Solar PV | 152.099 | No | 2021-05-27 | 2021-05-27 | 0 | 2021-05-27 | 2021-06-02 | 3 | 2021-06-07 | 2021-06-21 | 10 |  | 2021-07-20 | 20
NST-24130 | SCE | NEM | NEMA | Withdrawn | Solar PV | 549.369 | No | 2021-05-26 | 2021-05-26 | 0 | 2021-05-26 | 2021-05-28 | 2 | 2021-06-13 | 2021-06-14 | 0 |  | 2021-07-13 | 20
NST-24131 | SCE | NEM | NEMA | Withdrawn | Solar PV | 196.789 | No | 2021-05-27 | 2021-05-27 | 0 | 2021-05-27 | 2021-06-02 | 3 | 2021-06-13 | 2021-06-14 | 0 |  | 2021-07-13 | 20
NST-24132 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 126.507 | No | 2021-08-02 | 2021-08-02 | 0 | 2021-08-02 | 2021-08-10 | 6 | 2021-08-11 | 2021-08-17 | 4 | 2021-08-24 |  |  |  | 2021-09-02 | 7
NST-24133 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 107.218 | No | 2021-08-02 | 2021-08-02 | 0 | 2021-08-02 | 2021-08-10 | 6 | 2021-08-11 | 2021-08-17 | 4 | 2021-08-24 |  |  |  | 2021-09-02 | 7
NST-24135 | SCE | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 91.188 | No | 2021-05-26 | 2021-05-26 | 0 | 2021-05-26 | [9 empty] | 2021-05-28 | 2
NST-24136 | SCE | NEM | NEMA | Withdrawn | Solar PV | 126.507 | No | 2021-06-27 | 2021-06-27 | 0 | 2021-06-27 | 2021-06-30 | 2 |  |  |  |  | 2021-08-05 | 25
NST-241362 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 103.011 | No | 2021-11-01 | 2021-11-01 | 0 | 2021-11-01
NST-24137 | SCE | NEM | NEMA | Withdrawn | Solar PV | 107.765 | No | 2021-05-27 | 2021-05-27 | 0 | 2021-05-27 | 2021-06-02 | 3 | 2021-06-13 | 2021-06-14 | 0 |  | 2021-07-13 | 20
NST-24138 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 163.812 | No | 2021-05-26 | 2021-05-26 | 0 | 2021-05-26 | [9 empty] | 2021-05-28 | 2
NST-24139 | SCE | NEM | NEMA | Withdrawn | Solar PV | 236.615 | No | 2021-06-27 | 2021-06-27 | 0 | 2021-06-27 | 2021-06-30 | 2 |  |  |  |  | 2021-08-05 | 25
NST-24140 | SCE | NEM | NEMA | Withdrawn | Solar PV | 98.394 | No | 2021-06-27 | 2021-06-27 | 0 | 2021-06-27 | 2021-06-30 | 2 |  |  |  |  | 2021-08-05 | 25
NST-24141 | SCE | NEM | NEMA | Withdrawn | Solar PV | 145.071 | No | 2021-06-27 | 2021-06-27 | 0 | 2021-06-27 | 2021-06-30 | 2 |  |  |  |  | 2021-08-05 | 25
NST-24142 | SCE | NEM | NEMA | Withdrawn | Solar PV | 145.071 | No | 2021-06-27 | 2021-06-27 | 0 | 2021-06-27 | 2021-06-30 | 2 |  |  |  |  | 2021-08-05 | 25
NST-24143 | SCE | NEM | NEMA | Withdrawn | Solar PV | 196.789 | No | 2021-06-14 | 2021-06-14 | 0 | 2021-06-14 | 2021-06-21 | 5 |  |  |  |  | 2021-07-06 | 10
NST-24144 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 565.802 | No | 2021-03-19 | 2021-03-19 | 0 | 2021-03-19 | 2021-03-24 | 3 | 2021-03-30 | [6 empty] | 2021-04-08 | 6
NST-24145 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 100.737 | No | 2021-06-27 | 2021-06-27 | 0 | 2021-06-27 | 2021-06-30 | 2 | 2021-08-02 | 2021-08-10 | 6 | 2021-08-11 |  |  |  | 2021-08-17 | 4
NST-24146 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 208.122 | No | 2021-03-19 | 2021-03-19 | 0 | 2021-03-19 | 2021-03-24 | 3 | 2021-03-30 | [6 empty] | 2021-04-02 | 2
NST-241670 | SCE | NEM | NEMA | SCE Engineer Assigned. Pending Technical Review | Solar PV | 657.826 | No | 2021-11-02 | 2021-11-02 | 0 | 2021-11-02
NST-241670 | SCE | NEM | NEM Aggregation | Application Review In Progress |  | 657.826 | No | 2021-12-16 | 2021-12-16 | 0 | 2021-12-16 | 2021-12-30 | 9 | 2022-01-14
NST-241773 | SCE | NEM | NEMA | Withdrawn | Solar PV | 1348.361 | No | 2021-11-02 | 2021-11-02 | 0 | 2021-11-02 | [9 empty] | 2021-11-05 | 3
NST-241773 | SCE | NEM | NEM-ST | Withdrawn |  | 1348.361 | No |  |  |  | 2021-11-05
NST-241941 | SCE | NEM | NEMA | NEMI - Application Re-Submitted | Solar PV | 48.95 | No | 2021-11-09 | 2021-11-09 | 0 | 2021-11-09 | 2021-11-16 | 4 | 2021-11-28 | 2021-11-29 | 0 |  |  |  |  | 2021-12-15 | 12
NST-242130 | SCE | NEM | NEMA | Withdrawn | Solar PV | 552.589 | No | 2021-11-03 | 2021-11-03 | 0 | 2021-11-03 | 2021-11-16 | 8 |  |  |  |  | 2021-12-03 | 11
NST-242477 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 70.278 | No | 2021-11-04 | 2021-11-04 | 0 | 2021-11-04 | 2021-11-08 | 2 | 2021-11-18
NST-242488 | SCE | NEM | NEMA | NEMI - Returned from Engineering | Solar PV | 61.4 | No | 2021-11-04 | 2021-11-04 | 0 | 2021-11-04 | 2021-11-08 | 2 | 2021-12-14 | 2021-12-15 | 1 |  |  |  |  | 2022-01-03 | 11
NST-242500 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 74.963 | No | 2021-11-04 | 2021-11-04 | 0 | 2021-11-04 | 2021-11-08 | 2 | 2021-11-18
NST-242543 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 117.378 | No | 2021-11-04 | 2021-11-04 | 0 | 2021-11-04 | 2021-11-08 | 2 | 2021-11-18
NST-242656 | SCE | NEM | NEMA | Withdrawn | Solar PV | 395.416 | No | 2021-11-04 | 2021-11-04 | 0 | 2021-11-04 | 2021-11-10 | 4 |  |  |  |  | 2021-12-22 | 27
NST-242762 | SCE | NEM | Other-NEM-V | SCE Engineer Assigned. Pending Technical Review | Solar PV | 42.995 | No | 2021-11-05 | 2021-11-05 | 0 | 2021-11-05 | 2021-11-18 | 8 | 2021-12-19 | 2021-12-20 | 0 |  |  |  |  | 2022-01-11 | 14
NST-242821 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 31.911 | No | 2021-11-05 | 2021-11-05 | 0 | 2021-11-05 | 2021-11-16 | 6 | 2021-11-17 | [6 empty] | 2021-11-29 | 6 | [49 empty] | 2022-01-10 |  | 66
NST-242822 | SCE | NEM | NEM-ST | System Impact Study Complete |  | 2134.879 | No | 2021-11-15 | 2021-11-15 | 0 | 2021-11-15 | [11 empty] | 2021-12-20 | 2022-01-21 | 21 |  |  | 2022-02-11 | 2022-03-17 | 23
NST-242822 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV + Battery Storage | 2134.879 | No | 2021-11-05 | 2021-11-05 | 0 | 2021-11-05
NST-242966 | SCE | NEM | NEMA | NGOM Installation. Pending Invoice Payment and AHJ Panel Permit | Solar PV + Battery Storage | 59.986 | No | 2021-11-08 | 2021-11-08 | 0 | 2021-11-08 | 2021-11-15 | 4 | 2021-11-16 | [6 empty] | 2021-11-22 | 4
NST-242968 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 112.5 | No | 2021-11-05 | 2021-11-05 | 0 | 2021-11-05 | 2021-11-10 | 3 | 2021-11-29 | 2021-11-30 | 1 |  |  |  |  | 2022-02-14 | 51
NST-242974 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 259.874 | No | 2021-11-05 | 2021-11-05 | 0 | 2021-11-05
NST-243141 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 368.355 | No | 2021-11-10 | 2021-11-10 | 0 | 2021-11-10
NST-243152 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 241.939 | No | 2021-11-08 | 2021-11-08 | 0 | 2021-11-08 | 2021-11-17 | 6 | 2021-12-22 | [6 empty] | 2021-12-22 | 0
NST-243421 | SCE | NEM | NEMA | Withdrawn | Solar PV + Battery Storage | 45.441 | No | 2021-11-08 | 2021-11-08 | 0 | 2021-11-08 | 2021-11-15 | 4 | 2021-12-13 | 2021-12-14 | 1 |  | 2021-12-30 | 11
NST-243443 | SCE | NEM | NEM-ST | Application Review In Progress |  | 0 | No |  |  |  | 2021-12-20
NST-243564 | SCE | NEM | VNEM-SOMAH | NGOM Installation. Pending New Service Request and AHJ Panel Permit | Solar PV | 50.584 | No | 2021-11-09 | 2021-11-09 | 0 | 2021-11-09 | [9 empty] | 2021-11-15 | 3
NST-243566 | SCE | NEM | VNEM-SOMAH | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 66.508 | No | 2021-11-09 | 2021-11-09 | 0 | 2021-11-09 | [9 empty] | 2021-11-15 | 3
NST-243636 | SCE | NEM | VNEM-SOMAH | SCE Engineer Review. Pending Applicant Response | Solar PV | 48.499 | No | 2021-11-09 | 2021-11-09 | 0 | 2021-11-09 | 2021-11-19 | 7 | 2021-12-05 | 2021-12-06 | 0 |  |  |  |  | 2022-01-20 | 30
NST-243976 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 155.051 | No | 2021-11-10 | 2021-11-10 | 0 | 2021-11-10 | 2021-11-15 | 2 | 2021-12-14 | [6 empty] | 2021-12-29 | 10
NST-244089 | SCE | NEM | NEMA | Withdrawn | Solar PV | 32.398 | No | 2021-11-10 | 2021-11-10 | 0 | 2021-11-10 | 2021-11-16 | 3 | 2021-11-23 | 2021-11-24 | 1 |  | 2021-12-28 | 21
NST-244376 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 83.417 | No | 2021-11-11 | 2021-11-11 | 0 | 2021-11-11
NST-244608 | SCE | NEM | NEMA | Withdrawn | Solar PV | 147.494 | No | 2021-11-12 | 2021-11-12 | 0 | 2021-11-12 | 2021-11-18 | 4 |  |  |  |  | 2021-12-27 | 24
NST-244631 | SCE | NEM | NEMA | SCE Engineer Assigned. Pending Technical Review | Solar PV | 114.717 | No | 2021-11-12 | 2021-11-12 | 0 | 2021-11-12 | [9 empty] | 2021-11-22 | 6
NST-245073 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 52.177 | No | 2021-11-15 | 2021-11-15 | 0 | 2021-11-15
NST-245164 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 196.61 | No | 2021-11-15 | 2021-11-15 | 0 | 2021-11-15 | 2021-11-19 | 4 | 2021-12-02
NST-245180 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 236.27 | No | 2021-11-15 | 2021-11-15 | 0 | 2021-11-15 | 2021-11-19 | 4 | 2021-12-02 | [6 empty] | 2021-12-07 | 3
NST-245183 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 247.574 | No | 2021-11-15 | 2021-11-15 | 0 | 2021-11-15 | 2021-11-19 | 4 | 2021-12-02
NST-245188 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 114.793 | No | 2021-11-15 | 2021-11-15 | 0 | 2021-11-15 | 2021-11-19 | 4 | 2021-12-06 | 2021-12-07 | 1 |  |  |  |  | 2021-12-30 | 16
NST-245190 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 147.592 | No | 2021-11-15 | 2021-11-15 | 0 | 2021-11-15 | 2021-11-19 | 4 | 2021-12-02
NST-245195 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 226.091 | No | 2021-11-15 | 2021-11-15 | 0 | 2021-11-15
NST-245201 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 206.16 | No | 2021-11-15 | 2021-11-15 | 0 | 2021-11-15 | 2021-11-18 | 3 | 2021-12-02
NST-245205 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 463.859 | No | 2021-11-15 | 2021-11-15 | 0 | 2021-11-15 | 2021-11-23 | 6 | 2021-12-02
NST-245223 | SCE | NEM | VNEM-SOMAH | SCE Engineer Review. Pending Applicant Response | Solar PV | 48.843 | No | 2021-11-15 | 2021-11-15 | 0 | 2021-11-15 | 2021-11-24 | 7 | 2021-11-24 | [6 empty] | 2021-12-08 | 8
NST-245315 | SCE | NEM | NEMA | Withdrawn | Solar PV | 306.535 | No | 2021-11-16 | 2021-11-16 | 0 | 2021-11-16 | 2021-11-22 | 4 | 2021-12-28 |  |  |  | 2021-12-09 | 11
NST-245380 | SCE | NEM | NEMA | Withdrawn | Solar PV | 325.146 | No | 2021-11-16 | 2021-11-16 | 0 | 2021-11-16 | 2021-11-22 | 4 | 2021-11-29 | 2021-11-30 | 1 |  | 2021-12-08 | 6
NST-245384 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 361.213 | No | 2021-11-24 | 2021-11-24 | 0 | 2021-11-24 | 2021-12-01 | 3 | 2021-12-20 | [6 empty] | 2021-12-29 | 6
NST-245563 | SCE | NEM | NEMA | Withdrawn | Solar PV | 634.205 | No | 2021-11-16 | 2021-11-16 | 0 | 2021-11-16 | 2021-11-22 | 4 |  |  |  |  | 2022-01-14 | 35
NST-245576 | SCE | NEM | VNEM-SOMAH | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 71.504 | No | 2021-11-16 | 2021-11-16 | 0 | 2021-11-16 | 2021-11-29 | 7 | 2021-11-29 | [6 empty] | 2021-12-10 | 9
NST-245578 | SCE | NEM | VNEM-SOMAH | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 31.512 | No | 2021-11-16 | 2021-11-16 | 0 | 2021-11-16 | 2021-11-29 | 7 | 2021-11-29 | [6 empty] | 2021-12-10 | 9
NST-245586 | SCE | NEM | VNEM-SOMAH | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 39.655 | No | 2021-11-16 | 2021-11-16 | 0 | 2021-11-16 | 2021-11-29 | 7 | 2021-11-29 | [6 empty] | 2021-12-10 | 9
NST-245590 | SCE | NEM | VNEM-SOMAH | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 76.188 | No | 2021-11-16 | 2021-11-16 | 0 | 2021-11-16 | 2021-11-29 | 7 | 2021-11-29 | [6 empty] | 2021-12-10 | 9
NST-245592 | SCE | NEM | VNEM-SOMAH | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 48.086 | No | 2021-11-16 | 2021-11-16 | 0 | 2021-11-16 | 2021-11-29 | 7 | 2021-11-29 | [6 empty] | 2021-12-10 | 9
NST-245593 | SCE | NEM | VNEM-SOMAH | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 31.849 | No | 2021-11-16 | 2021-11-16 | 0 | 2021-11-16 | 2021-11-29 | 7 | 2021-11-29 | [6 empty] | 2021-12-10 | 9
NST-245661 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 872.587 | No | 2021-11-16 | 2021-11-16 | 0 | 2021-11-16 | 2021-11-24 | 6 | 2022-01-06 | 2022-01-07 | 1 |  |  |  |  | 2022-01-25 | 11
NST-245662 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 959.183 | No | 2021-11-16 | 2021-11-16 | 0 | 2021-11-16 | 2021-11-23 | 5 | 2022-01-09 | 2022-01-10 | 0 |  |  |  |  | 2022-01-25 | 10
NST-245749 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 110.719 | No | 2021-11-17 | 2021-11-17 | 0 | 2021-11-17 | 2021-11-24 | 5 | 2021-12-21 | [6 empty] | 2021-12-30 | 6
NST-245752 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 110.758 | No | 2021-11-17 | 2021-11-17 | 0 | 2021-11-17 | 2021-11-24 | 5 | 2021-12-21 | [6 empty] | 2021-12-30 | 6
NST-245927 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 110.917 | No | 2021-11-17 | 2021-11-17 | 0 | 2021-11-17 | 2021-11-24 | 5 | 2021-12-21 | [6 empty] | 2021-12-30 | 6
NST-246045 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 129.672 | No | 2021-11-17 | 2021-11-17 | 0 | 2021-11-17 | 2021-11-23 | 4 | 2021-12-31 | [6 empty] | 2022-01-10 | 5
NST-246066 | SCE | NEM | NEMA | Applicant Response Received. Pending SCE Engineer Review | Solar PV + Battery Storage | 3527.933 | No | 2021-11-17 | 2021-11-17 | 0 | 2021-11-17 | [9 empty] | 2022-04-08 | 95
NST-246066 | SCE | NEM | NEM-ST | Application Review In Progress |  | 3527.933 | No |  |  |  | 2021-12-27
NST-246469 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 118.943 | No | 2021-11-18 | 2021-11-18 | 0 | 2021-11-18 | 2021-11-24 | 4 | 2021-12-06 | [6 empty] | 2021-12-21 | 11
NST-246590 | SCE | NEM | NEMA | Withdrawn | Solar PV | 32.59 | No | 2021-11-19 | 2021-11-19 | 0 | 2021-11-19 | 2021-11-22 | 1 |  |  |  |  | 2021-12-09 | 11
NST-246891 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 372.488 | No | 2021-11-23 | 2021-11-23 | 0 | 2021-11-23 | [9 empty] | 2021-11-30 | 3
NST-24690 | SCE | NEM | NEM-ST | Application Review In Progress |  | 0 | No | 2021-08-14 | 2021-08-14 | 0 | 2021-08-14 | 2021-08-25 | 7 | 2021-08-26 | 2021-09-02 | 5 | 2021-09-02
NST-246972 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 345.274 | No | 2021-11-23 | 2021-11-23 | 0 | 2021-11-23 | 2021-11-30 | 3 | 2021-12-19 | 2021-12-20 | 0 |  |  |  |  | 2021-12-23 | 3
NST-247220 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 32.761 | No | 2021-11-22 | 2021-11-22 | 0 | 2021-11-22 | 2021-11-30 | 4 | 2021-11-30 | [6 empty] | 2021-12-06 | 4 | [49 empty] | 2022-01-06 |  | 45
NST-247251 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 36.133 | No | 2021-11-22 | 2021-11-22 | 0 | 2021-11-22 | [9 empty] | 2021-12-05 | 7 | [49 empty] | 2021-12-20 |  | 28
NST-247374 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 59.568 | No | 2021-11-23 | 2021-11-23 | 0 | 2021-11-23 | [9 empty] | 2021-12-01 | 4 | [49 empty] | 2022-03-22 |  | 119
NST-247510 | SCE | NEM | NEMA | Withdrawn | Solar PV | 33.773 | No | 2021-11-23 | 2021-11-23 | 0 | 2021-11-23 | 2021-12-06 | 7 | 2021-12-08 | 2021-12-09 | 1 |  | 2021-12-24 | 10
NST-247523 | SCE | NEM | VNEM-SOMAH | SCE Engineer Review. Pending Applicant Response | Solar PV | 34.972 | No | 2021-11-23 | 2021-11-23 | 0 | 2021-11-23 | [9 empty] | 2021-11-30 | 3
NST-247620 | SCE | NEM | VNEM-SOMAH | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 32.318 | No | 2021-11-29 | 2021-11-29 | 0 | 2021-11-29 | 2021-12-09 | 8 | 2021-12-22 | [6 empty] | 2022-02-07 | 30
NST-247731 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 180 | No | 2021-11-29 | 2021-11-29 | 0 | 2021-11-29 | 2021-12-02 | 3 | 2022-01-02 | 2022-01-03 | 0 |  |  |  |  | 2022-01-10 | 5
NST-247776 | SCE | NEM | NEMA | Withdrawn | Solar PV | 144.401 | No | 2021-11-24 | 2021-11-24 | 0 | 2021-11-24 | 2021-12-02 | 4 | 2022-01-04 | 2022-01-05 | 1 |  | 2022-02-25 | 35
NST-24778 | SCE | NEM | NEM-ST | Application Review In Progress |  | 0.54726 | No |  |  |  | 2021-10-05
NST-247811 | SCE | NEM | NEM Aggregation | IA Negotiation |  | 250.83 | No | 2021-12-02 | 2021-12-02 | 0 | 2021-12-02 | 2021-12-15 | 9 | 2021-12-20 | [6 empty] | 2022-01-06 | 11 | 2022-01-06 | 2022-01-24 | 11 | 2022-02-09 | 12 | [17 empty] | 2022-02-25
NST-247811 | SCE | NEM | NEMA | SCE Engineer. Initial Review Complete | Solar PV | 250.83 | No | 2021-11-24 | 2021-11-24 | 0 | 2021-11-24 | [9 empty] | 2022-01-06 | 11
NST-247920 | SCE | NEM | NEMA | Withdrawn | Solar PV | 76.848 | No | 2021-11-24 | 2021-11-24 | 0 | 2021-11-24 | 2021-12-03 | 5 |  |  |  |  | 2021-12-20 | 11
NST-247976 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 32.153 | No | 2021-11-24 | 2021-11-24 | 0 | 2021-11-24 | 2021-12-01 | 3 | 2021-12-01 | [6 empty] | 2021-12-01 | 0 | [49 empty] | 2021-12-06 |  | 12
NST-247999 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 679.237 | No | 2021-11-24 | 2021-11-24 | 0 | 2021-11-24 | 2021-12-02 | 4 | 2021-12-14 | 2021-12-15 | 1 |  |  |  |  | 2022-01-03 | 11
NST-248292 | SCE | NEM | VNEM-SOMAH | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 44.887 | No | 2021-11-29 | 2021-11-29 | 0 | 2021-11-29 | 2021-12-10 | 9 | 2021-12-22 | [6 empty] | 2022-02-07 | 30
NST-248303 | SCE | NEM | VNEM-SOMAH | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 32.318 | No | 2021-11-29 | 2021-11-29 | 0 | 2021-11-29 | 2021-12-09 | 8 | 2021-12-22 | [6 empty] | 2022-02-07 | 30
NST-248322 | SCE | NEM | VNEM-SOMAH | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 39.5 | No | 2021-11-29 | 2021-11-29 | 0 | 2021-11-29 | 2021-12-09 | 8 | 2021-12-22 | [6 empty] | 2022-02-07 | 30
NST-248344 | SCE | NEM | VNEM-SOMAH | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 39.5 | No | 2021-11-29 | 2021-11-29 | 0 | 2021-11-29 | 2021-12-09 | 8 | 2021-12-22 | [6 empty] | 2022-02-07 | 30
NST-248351 | SCE | NEM | VNEM-SOMAH | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 46.323 | No | 2021-11-29 | 2021-11-29 | 0 | 2021-11-29 | 2021-12-09 | 8 | 2021-12-22 | [6 empty] | 2022-02-07 | 30
NST-248360 | SCE | NEM | VNEM-SOMAH | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 40.937 | No | 2021-11-29 | 2021-11-29 | 0 | 2021-11-29 | 2021-12-09 | 8 | 2021-12-22 | [6 empty] | 2022-02-07 | 30
NST-248376 | SCE | NEM | VNEM-SOMAH | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 47.4 | No | 2021-11-29 | 2021-11-29 | 0 | 2021-11-29 | 2021-12-09 | 8 | 2021-12-22 | [6 empty] | 2022-02-07 | 30
NST-248378 | SCE | NEM | VNEM-SOMAH | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 40.219 | No | 2021-11-29 | 2021-11-29 | 0 | 2021-11-29 | 2021-12-09 | 8 | 2021-12-22 | [6 empty] | 2022-02-07 | 30
NST-248694 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 42.29 | No | 2021-11-30 | 2021-11-30 | 0 | 2021-11-30 | 2021-12-13 | 9 | 2021-12-15 | 2022-01-04 | 12 | 2022-01-04 |  |  |  | 2022-01-14 | 8 | [49 empty] | 2022-01-28 |  | 59
NST-248702 | SCE | NEM | NEMA | NEMI - Equipment Change Submitted | Solar PV | 200 | No | 2021-12-03 | 2021-12-03 | 0 | 2021-12-03 | 2021-12-09 | 4 | 2021-12-20 | 2021-12-21 | 1 |  |  |  |  | 2021-12-30 | 6
NST-248756 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 605.75 | No | 2021-11-30 | 2021-11-30 | 0 | 2021-11-30 | 2021-12-07 | 5 | 2021-12-20 | [6 empty] | 2021-12-28 | 5
NST-248761 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 381.67 | No | 2021-11-30 | 2021-11-30 | 0 | 2021-11-30 | 2021-12-03 | 3 | 2021-12-20 | [6 empty] | 2021-12-28 | 5
NST-248982 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 46.791 | No | 2021-12-01 | 2021-12-01 | 0 | 2021-12-01 | 2021-12-08 | 5 | 2021-12-14 | [6 empty] | 2021-12-20 | 4 | [49 empty] | 2022-03-09 |  | 98
NST-249052 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 358.366 | No | 2021-12-01 | 2021-12-01 | 0 | 2021-12-01 | 2021-12-06 | 3 | 2021-12-08
NST-249066 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 129.671 | No | 2021-12-01 | 2021-12-01 | 0 | 2021-12-01
NST-249069 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 43.136 | No | 2021-12-01 | 2021-12-01 | 0 | 2021-12-01 | 2021-12-02 | 1 | 2021-12-05 | 2021-12-09 | 3 | 2021-12-09 |  |  |  | 2021-12-15 | 4 | [49 empty] | 2022-03-28 |  | 117
NST-249104 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 479.565 | No | 2021-12-03 | 2021-12-03 | 0 | 2021-12-03 | 2021-12-09 | 4 | 2021-12-13
NST-249442 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 42.726 | No | 2021-12-02 | 2021-12-02 | 0 | 2021-12-02 | 2021-12-07 | 3 | 2021-12-07 | [6 empty] | 2021-12-13 | 4 | [49 empty] | 2022-01-06 |  | 35
NST-249654 | SCE | NEM | NEM Aggregation | Supplemental Review Complete |  | 1497.511 | No | 2021-12-20 | 2021-12-20 | 0 | 2021-12-20 | 2022-01-04 | 9 | 2022-01-06 | 2022-01-06 | 0 | 2022-01-10 |  |  |  | 2022-01-11 | 1 | 2022-01-11 | 2022-02-02 | 15 |  |  | 2022-02-07 | 2022-03-08 | 20 | 2022-03-29 | 15
NST-249654 | SCE | NEM | NEMA | SCE Engineer. Supplemental Review Complete | Solar PV | 1497.511 | No | 2021-12-02 | 2021-12-02 | 0 | 2021-12-02 | 2021-12-08 | 4 | 2021-12-10 | 2022-01-07 | 18 | 2022-01-10 |  |  |  | 2022-01-11 | 1
NST-249655 | SCE | NEM | NEMA | Applicant Response Received. Pending SCE Engineer Review | Solar PV | 65.598 | No | 2021-12-02 | 2021-12-02 | 0 | 2021-12-02 | [9 empty] | 2021-12-11 | 6
NST-249656 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 111.144 | No | 2021-12-02 | 2021-12-02 | 0 | 2021-12-02 | 2021-12-11 | 6 | 2021-12-15 | [6 empty] | 2021-12-29 | 9
NST-249750 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 334.994 | No | 2021-12-03 | 2021-12-03 | 0 | 2021-12-03 | 2021-12-08 | 3 | 2021-12-15 | 2021-12-16 | 1 |  |  |  |  | 2021-12-20 | 2
NST-249844 | SCE | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 565.268 | No | 2021-12-10 | 2021-12-10 | 0 | 2021-12-10 | [9 empty] | 2021-12-16 | 4
NST-249894 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 121.494 | No | 2021-12-03 | 2021-12-03 | 0 | 2021-12-03 | 2021-12-13 | 6 | 2021-12-14 | [6 empty] | 2021-12-29 | 10
NST-250098 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 65.38 | No | 2021-12-06 | 2021-12-06 | 0 | 2021-12-06 | 2021-12-13 | 5 | 2021-12-17 | [6 empty] | 2021-12-29 | 7 | [49 empty] | 2022-02-03 |  | 59
NST-250102 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 127.067 | No | 2021-12-06 | 2021-12-06 | 0 | 2021-12-06
NST-250114 | SCE | NEM | NEMA | NEMI - Sent to Engineering | Solar PV + Battery Storage | 784.207 | No | 2021-12-06 | 2021-12-06 | 0 | 2021-12-06 | [9 empty] | 2022-02-24 | 54
NST-250268 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 71.796 | No | 2021-12-06 | 2021-12-06 | 0 | 2021-12-06 | 2021-12-09 | 3 | 2021-12-10
NST-250284 | SCE | NEM | NEMA | NEMI - Sent to Engineering | Solar PV + Battery Storage | 688.819 | No | 2021-12-06 | 2021-12-06 | 0 | 2021-12-06 | 2022-02-24 | 54 | 2022-02-24 | [6 empty] | 2022-03-02 | 4
NST-250431 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 206.05 | No | 2021-12-06 | 2021-12-06 | 0 | 2021-12-06
NST-250433 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 332.66 | No | 2021-12-06 | 2021-12-06 | 0 | 2021-12-06
NST-250437 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 126.609 | No | 2021-12-06 | 2021-12-06 | 0 | 2021-12-06
NST-250438 | SCE | NEM | NEMA | Withdrawn | Solar PV | 126.609 | No | 2021-12-06 | 2021-12-06 | 0 | 2021-12-06 | 2021-12-09 | 3 |  |  |  |  | 2021-12-24 | 10
NST-250442 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 218.463 | No | 2021-12-06 | 2021-12-06 | 0 | 2021-12-06
NST-250447 | SCE | NEM | NEMA | Withdrawn | Solar PV | 130.56 | No | 2021-12-06 | 2021-12-06 | 0 | 2021-12-06 | 2021-12-09 | 3 |  |  |  |  | 2021-12-24 | 10
NST-250448 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 677.732 | No | 2021-12-06 | 2021-12-06 | 0 | 2021-12-06 | 2021-12-10 | 4 | 2021-12-14
NST-250451 | SCE | NEM | NEM-ST | Application Review In Progress |  | 1052.595 | No |  |  |  | 2021-12-06
NST-250451 | SCE | NEM | NEMA | SCE Engineer Assigned. Pending Technical Review | Solar PV | 1052.595 | No | 2021-12-06 | 2021-12-06 | 0 | 2021-12-06
NST-250455 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 119.162 | No | 2021-12-06 | 2021-12-06 | 0 | 2021-12-06
NST-250460 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 158.882 | No | 2021-12-06 | 2021-12-06 | 0 | 2021-12-06
NST-250465 | SCE | NEM | NEMA | Withdrawn | Solar PV | 1108.866 | No | 2021-12-06 | 2021-12-06 | 0 | 2021-12-06 | [6 empty] | 2021-12-24 | 13
NST-250467 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 129.092 | No | 2021-12-06 | 2021-12-06 | 0 | 2021-12-06
NST-250722 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 99.427 | No | 2021-12-07 | 2021-12-07 | 0 | 2021-12-07
NST-250730 | SCE | NEM | Other-NEM-V | Withdrawn | Solar PV | 362.024 | No | 2021-12-07 | 2021-12-07 | 0 | 2021-12-07 | 2021-12-16 | 7 | 2021-12-27 |  |  |  | 2022-02-18 | 37
NST-250915 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 122.423 | No | 2021-12-08 | 2021-12-08 | 0 | 2021-12-08 | 2021-12-13 | 3 | 2021-12-14 | [6 empty] | 2021-12-21 | 5 | [49 empty] | 2022-02-16 |  | 70
NST-251046 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 123.891 | No | 2021-12-08 | 2021-12-08 | 0 | 2021-12-08 | 2021-12-21 | 9 | 2021-12-27 | 2022-01-20 | 16 | 2022-01-20 |  |  |  | 2022-01-26 | 4 | [49 empty] | 2022-03-16 |  | 98
NST-251093 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 371.208 | No | 2021-12-08 | 2021-12-08 | 0 | 2021-12-08
NST-251099 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 37.669 | No | 2021-12-08 | 2021-12-08 | 0 | 2021-12-08 | [9 empty] | 2021-12-13 | 3 | [49 empty] | 2022-03-30 |  | 112
NST-251193 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 148.858 | No | 2021-12-15 | 2021-12-15 | 0 | 2021-12-15 | [9 empty] | 2021-12-21 | 4
NST-251197 | SCE | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 72.318 | No | 2021-12-08 | 2021-12-08 | 0 | 2021-12-08
NST-251212 | SCE | NEM | NEMA | Withdrawn | Solar PV | 52.487 | No | 2021-12-08 | 2021-12-08 | 0 | 2021-12-08 | 2021-12-21 | 9 |  |  |  |  | 2022-01-05 | 9
NST-251304 | SCE | NEM | NEM-ST | System Impact Study In Progress |  | 4922.188 | No | 2022-01-24 | 2022-01-24 | 0 | 2022-01-24 | [21 empty] | 2022-03-09 | 2022-03-17 | 6 | 2022-03-21 |  | 2022-03-29 | [35 empty] | 0
NST-251304 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 4922.188 | No | 2022-01-12 | 2022-01-12 | 0 | 2022-01-12 | 2022-01-19 | 4 | 2022-01-23 | [59 empty] | 0
NST-251393 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 117.412 | No | 2021-12-10 | 2021-12-10 | 0 | 2021-12-10 | [9 empty] | 2021-12-22 | 8
NST-251430 | SCE | NEM | NEMA | Withdrawn | Solar PV | 492.08 | No | 2021-12-09 | 2021-12-09 | 0 | 2021-12-09 | 2021-12-15 | 4 | 2021-12-16 |  |  |  | 2022-01-05 | 12
NST-251502 | SCE | NEM | NEMA | Withdrawn | Solar PV | 397 | No | 2021-12-09 | 2021-12-09 | 0 | 2021-12-09 | 2021-12-15 | 4 | 2021-12-21 |  |  |  | 2022-01-12 | 14
NST-251585 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 110.436 | No | 2021-12-09 | 2021-12-09 | 0 | 2021-12-09 | 2021-12-15 | 4 | 2021-12-17 | [6 empty] | 2021-12-28 | 6
NST-251718 | SCE | NEM | Other-NEM-V | Withdrawn | Solar PV | 105.284 | No | 2021-12-09 | 2021-12-09 | 0 | 2021-12-09 | 2021-12-20 | 7 |  |  |  |  | 2022-01-04 | 9
NST-251787 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 991.559 | No | 2021-12-10 | 2021-12-10 | 0 | 2021-12-10
NST-251803 | SCE | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 38.241 | No | 2022-01-12 | 2022-01-12 | 0 | 2022-01-12 | 2022-01-19 | 4 | 2022-01-19 | [6 empty] | 2022-03-24 | 45
NST-251838 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 49.433 | No | 2021-12-10 | 2021-12-10 | 0 | 2021-12-10 | 2021-12-13 | 1 | [7 empty] | 2021-12-20 | 5
NST-251846 | SCE | NEM | NEMA | Withdrawn | Solar PV | 994.866 | No | 2021-12-10 | 2021-12-10 | 0 | 2021-12-10 | 2021-12-22 | 8 |  |  |  |  | 2022-01-06 | 9
NST-251914 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 35.957 | No | 2021-12-13 | 2021-12-13 | 0 | 2021-12-13
NST-251924 | SCE | NEM | NEMA | Withdrawn | Solar PV | 77.303 | No | 2021-12-13 | 2021-12-13 | 0 | 2021-12-13 | 2021-12-17 | 4 | 2022-01-17 |  |  |  | 2022-02-07 | 14
NST-251942 | SCE | NEM | NEMA | Withdrawn | Solar PV | 79.721 | No | 2021-12-10 | 2021-12-10 | 0 | 2021-12-10 | 2021-12-16 | 4 | 2022-01-31 | 2022-02-23 | 16 | 2022-03-02 | 2022-03-10 | 6
NST-251948 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 32.604 | No | 2021-12-14 | 2021-12-14 | 0 | 2021-12-14 | 2021-12-15 | 1 | 2021-12-28 | [6 empty] | 2022-01-11 | 9
NST-251959 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 69.708 | No | 2021-12-10 | 2021-12-10 | 0 | 2021-12-10
NST-251984 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 997.192 | No | 2021-12-20 | 2021-12-20 | 0 | 2021-12-20 | 2022-02-04 | 31 | 2022-02-07 | [6 empty] | 2022-02-11 | 4
NST-252007 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 781.228 | No | 2021-12-11 | 2021-12-11 | 0 | 2021-12-11 | 2021-12-22 | 7 | 2021-12-23 | 2022-01-19 | 16 | 2022-01-19 |  |  |  | 2022-01-26 | 5
NST-252032 | SCE | NEM | NEMA | Withdrawn | Solar PV | 53.18 | No | 2021-12-12 | 2021-12-12 | 0 | 2021-12-12 | 2021-12-16 | 3 |  |  |  |  | 2021-12-31 | 9
NST-252034 | SCE | NEM | NEMA | Withdrawn | Solar PV | 59.396 | No | 2021-12-12 | 2021-12-12 | 0 | 2021-12-12 | 2021-12-16 | 3 |  |  |  |  | 2021-12-31 | 9
NST-252037 | SCE | NEM | NEMA | Withdrawn | Solar PV | 70.669 | No | 2021-12-12 | 2021-12-12 | 0 | 2021-12-12 | 2021-12-16 | 3 |  |  |  |  | 2021-12-31 | 9
NST-252039 | SCE | NEM | NEMA | Withdrawn | Solar PV | 82.091 | No | 2021-12-12 | 2021-12-12 | 0 | 2021-12-12 | 2021-12-16 | 3 |  |  |  |  | 2021-12-31 | 9
NST-252041 | SCE | NEM | NEMA | Withdrawn | Solar PV | 97.438 | No | 2021-12-12 | 2021-12-12 | 0 | 2021-12-12 | 2021-12-16 | 3 |  |  |  |  | 2021-12-31 | 9
NST-252046 | SCE | NEM | NEMA | Withdrawn | Solar PV | 60.011 | No | 2021-12-12 | 2021-12-12 | 0 | 2021-12-12 | 2021-12-16 | 3 |  |  |  |  | 2021-12-31 | 9
NST-252049 | SCE | NEM | NEMA | Withdrawn | Solar PV | 82.448 | No | 2021-12-12 | 2021-12-12 | 0 | 2021-12-12 | 2021-12-16 | 3 |  |  |  |  | 2021-12-31 | 9
NST-252050 | SCE | NEM | NEMA | Withdrawn | Solar PV | 110.644 | No | 2021-12-12 | 2021-12-12 | 0 | 2021-12-12 | 2021-12-16 | 3 |  |  |  |  | 2021-12-31 | 9
NST-252051 | SCE | NEM | NEMA | Withdrawn | Solar PV | 102.792 | No | 2021-12-12 | 2021-12-12 | 0 | 2021-12-12 | 2021-12-16 | 3 |  |  |  |  | 2021-12-31 | 9
NST-252098 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 42.415 | No | 2021-12-13 | 2021-12-13 | 0 | 2021-12-13
NST-252150 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 42.415 | No | 2021-12-13 | 2021-12-13 | 0 | 2021-12-13
NST-252151 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 42.415 | No | 2021-12-14 | 2021-12-14 | 0 | 2021-12-14
NST-252152 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 42.415 | No | 2021-12-13 | 2021-12-13 | 0 | 2021-12-13
NST-252153 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 42.415 | No | 2021-12-13 | 2021-12-13 | 0 | 2021-12-13
NST-252154 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 42.8 | No | 2021-12-13 | 2021-12-13 | 0 | 2021-12-13
NST-252191 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 42.415 | No | 2021-12-13 | 2021-12-13 | 0 | 2021-12-13
NST-252195 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 42.415 | No | 2021-12-13 | 2021-12-13 | 0 | 2021-12-13
NST-252235 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 42.415 | No | 2021-12-13 | 2021-12-13 | 0 | 2021-12-13
NST-252244 | SCE | NEM | NEMA | Applicant Response Received. Pending SCE Engineer Review | Solar PV | 376.508 | No | 2021-12-13 | 2021-12-13 | 0 | 2021-12-13 | 2021-12-20 | 5 | [7 empty] | 2022-02-18 | 41
NST-252245 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 42.415 | No | 2021-12-13 | 2021-12-13 | 0 | 2021-12-13
NST-252291 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 42.415 | No | 2021-12-13 | 2021-12-13 | 0 | 2021-12-13
NST-252297 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 42.415 | No | 2021-12-13 | 2021-12-13 | 0 | 2021-12-13
NST-252301 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 42.415 | No | 2021-12-13 | 2021-12-13 | 0 | 2021-12-13
NST-252305 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 42.415 | No | 2021-12-13 | 2021-12-13 | 0 | 2021-12-13
NST-252306 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 42.415 | No | 2021-12-13 | 2021-12-13 | 0 | 2021-12-13
NST-252311 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 42.415 | No | 2021-12-13 | 2021-12-13 | 0 | 2021-12-13
NST-252314 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 42.415 | No | 2021-12-13 | 2021-12-13 | 0 | 2021-12-13
NST-252316 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 42.415 | No | 2021-12-13 | 2021-12-13 | 0 | 2021-12-13
NST-252334 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 42.415 | No | 2021-12-14 | 2021-12-14 | 0 | 2021-12-14
NST-252400 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 42.415 | No | 2021-12-14 | 2021-12-14 | 0 | 2021-12-14
NST-252401 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 42.415 | No | 2021-12-14 | 2021-12-14 | 0 | 2021-12-14
NST-252402 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 41.855 | No | 2021-12-14 | 2021-12-14 | 0 | 2021-12-14
NST-252407 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 42.415 | No | 2021-12-14 | 2021-12-14 | 0 | 2021-12-14
NST-252408 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 42.415 | No | 2021-12-14 | 2021-12-14 | 0 | 2021-12-14
NST-252411 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 42.415 | No | 2021-12-14 | 2021-12-14 | 0 | 2021-12-14
NST-252414 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 42.415 | No | 2021-12-14 | 2021-12-14 | 0 | 2021-12-14
NST-252420 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 42.415 | No | 2021-12-14 | 2021-12-14 | 0 | 2021-12-14
NST-252425 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 42.415 | No | 2021-12-14 | 2021-12-14 | 0 | 2021-12-14
NST-252427 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 42.415 | No | 2021-12-14 | 2021-12-14 | 0 | 2021-12-14
NST-252450 | SCE | NEM | NEM-ST | Fast Track Initial Review In Progress |  | 2051.039 | No | 2022-01-07 | 2022-01-07 | 0 | 2022-01-07 | 2022-01-20 | 8 | 2022-01-20 | 2022-02-04 | 11 | 2022-02-12 |  |  |  | 2022-03-29 | 30 | 2022-03-29
NST-252450 | SCE | NEM | NEMA | SCE Engineer. Initial Review In Progress | Solar PV + Battery Storage | 2051.039 | No | 2021-12-14 | 2021-12-14 | 0 | 2021-12-14 | [9 empty] | 2022-03-29 | 30
NST-252457 | SCE | NEM | NEMA | Withdrawn | Solar PV | 87.041 | No | 2021-12-14 | 2021-12-14 | 0 | 2021-12-14 | 2021-12-17 | 3 | 2021-12-28 | 2021-12-29 | 1 |  | 2022-03-03 | 43
NST-252462 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 606.981 | No | 2021-12-14 | 2021-12-14 | 0 | 2021-12-14 | 2021-12-20 | 4 | 2021-12-21 | [6 empty] | 2021-12-30 | 6
NST-252468 | SCE | NEM | NEMA | Withdrawn | Solar PV | 187.057 | No | 2021-12-14 | 2021-12-14 | 0 | 2021-12-14 | 2021-12-23 | 7 | 2022-01-04 | 2022-01-19 | 10 | 2022-01-19 | 2022-02-25 | 26
NST-252501 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 781.228 | No | 2021-12-14 | 2021-12-14 | 0 | 2021-12-14 | 2021-12-28 | 9 | 2021-12-28 | 2022-01-19 | 14 | 2022-01-19 |  |  |  | 2022-01-26 | 5
NST-252517 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 42.415 | No | 2021-12-14 | 2021-12-14 | 0 | 2021-12-14
NST-252526 | SCE | NEM | NEMA | Withdrawn | Solar PV | 42.415 | No | 2021-12-14 | 2021-12-14 | 0 | 2021-12-14 | 2021-12-15 | 1 |  |  |  |  | 2021-12-30 | 10
NST-252535 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 32.388 | No | 2021-12-14 | 2021-12-14 | 0 | 2021-12-14 | 2021-12-17 | 3 | 2021-12-17 | [6 empty] | 2021-12-27 | 5 | [49 empty] | 2022-02-18 |  | 66
NST-252543 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 42.415 | No | 2021-12-14 | 2021-12-14 | 0 | 2021-12-14
NST-252547 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 42.415 | No | 2021-12-16 | 2021-12-16 | 0 | 2021-12-16
NST-252559 | SCE | NEM | NEMA | Withdrawn | Solar PV | 991.559 | No | 2021-12-14 | 2021-12-14 | 0 | 2021-12-14 | 2021-12-28 | 9 |  |  |  |  | 2022-02-10 | 30
NST-252560 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 42.415 | No | 2021-12-16 | 2021-12-16 | 0 | 2021-12-16
NST-252575 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 248.953 | No | 2021-12-15 | 2021-12-15 | 0 | 2021-12-15 | 2021-12-30 | 10 | 2021-12-31 | [6 empty] | 2022-01-19 | 11
NST-252618 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 428.831 | No | 2021-12-14 | 2021-12-14 | 0 | 2021-12-14 | [9 empty] | 2021-12-22 | 6
NST-252730 | SCE | NEM | VNEM-SOMAH | NGOM Installation. Pending Local Planner Process | Solar PV | 42.153 | No | 2021-12-14 | 2021-12-14 | 0 | 2021-12-14 | [9 empty] | 2021-12-27 | 8
NST-252877 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 111.575 | No | 2021-12-15 | 2021-12-15 | 0 | 2021-12-15 | 2021-12-30 | 10 | 2022-01-11 | 2022-01-24 | 8 | 2022-01-27 |  |  |  | 2022-01-27 | 0 | [49 empty] | 2022-02-15 |  | 62
NST-252883 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 238.307 | No | 2021-12-15 | 2021-12-15 | 0 | 2021-12-15 | [9 empty] | 2021-12-21 | 4
NST-252884 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 302.274 | No | 2021-12-15 | 2021-12-15 | 0 | 2021-12-15 | 2021-12-20 | 3 | 2022-01-05 | 2022-01-06 | 1 |  |  |  |  | 2022-02-07 | 21
NST-252884 | SCE | NEM | NEM-ST | Application Review In Progress |  | 302.274 | No |  |  |  | 2022-02-07
NST-253322 | SCE | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 92.471 | No | 2021-12-16 | 2021-12-16 | 0 | 2021-12-16 | 2021-12-21 | 3 | 2021-12-27 | 2021-12-28 | 1 |  |  |  |  | 2022-01-04 | 4
NST-253425 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Construction | Solar PV | 997.456 | No | 2021-12-16 | 2021-12-16 | 0 | 2021-12-16 | 2021-12-28 | 7 | 2022-01-03 | 2022-01-04 | 1 |  |  |  |  | 2022-01-12 | 6
NST-253488 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 143.869 | No | 2021-12-17 | 2021-12-17 | 0 | 2021-12-17 | 2021-12-22 | 3 | 2021-12-29 | [6 empty] | 2022-01-07 | 6
NST-253627 | SCE | NEM | NEMA | Withdrawn | Solar PV | 30.191 | No | 2021-12-17 | 2021-12-17 | 0 | 2021-12-17 | 2021-12-22 | 3 | 2022-01-06 | 2022-01-07 | 1 |  | 2022-01-18 | 6
NST-253693 | SCE | NEM | NEMA | SCE Engineer Assigned. Pending Technical Review | Solar PV + Battery Storage | 1706.443 | No | 2021-12-22 | 2021-12-22 | 0 | 2021-12-22
NST-253693 | SCE | NEM | NEM-ST | Application Review In Progress |  | 1706.443 | No | 2022-02-23 | 2022-02-23 | 0 | 2022-02-23 | 2022-03-09 | 10
NST-253723 | SCE | NEM | NEM Aggregation | Application Review In Progress |  | 1075.526 | No |  |  |  | 2022-01-26 | [62 empty] | 0
NST-253723 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 1075.526 | No | 2021-12-17 | 2021-12-17 | 0 | 2021-12-17 | [62 empty] | 0
NST-253725 | SCE | NEM | VNEM-SOMAH | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 94.611 | No | 2021-12-17 | 2021-12-17 | 0 | 2021-12-17 | 2021-12-29 | 7 | 2021-12-30 | [6 empty] | 2022-01-12 | 8
NST-253790 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 232.795 | No | 2021-12-21 | 2021-12-21 | 0 | 2021-12-21 | [9 empty] | 2021-12-28 | 4
NST-254114 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 44.06 | No | 2021-12-20 | 2021-12-20 | 0 | 2021-12-20 | 2021-12-21 | 1 | 2021-12-21 | 2021-12-29 | 5 | 2022-02-04 |  |  |  | 2022-02-22 | 11 | [49 empty] | 2022-02-22 |  | 64
NST-254163 | SCE | NEM | NEM-ST | Application Review In Progress |  | 16500 | No | 2022-01-08 | 2022-01-08 | 0 | 2022-01-08 | 2022-01-20 | 7 | 2022-02-10 | 2022-03-04 | 15
NST-254163 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 16500 | No | 2021-12-22 | 2021-12-22 | 0 | 2021-12-22
NST-254256 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 33.646 | No | 2021-12-20 | 2021-12-20 | 0 | 2021-12-20 | [9 empty] | 2021-12-20 | 0 | [49 empty] | 2021-12-21 |  | 1
NST-254377 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 884.458 | No | 2021-12-21 | 2021-12-21 | 0 | 2021-12-21 | 2022-01-03 | 7 | 2022-01-05 | [6 empty] | 2022-01-19 | 9
NST-254405 | SCE | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 37.198 | No | 2021-12-21 | 2021-12-21 | 0 | 2021-12-21 | 2021-12-22 | 1 | 2021-12-22 | [6 empty] | 2022-01-05 | 8
NST-254415 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 234.917 | No | 2021-12-21 | 2021-12-21 | 0 | 2021-12-21 | 2021-12-28 | 4 | 2022-01-05 | [6 empty] | 2022-01-13 | 6 | [49 empty] | 2022-02-02 |  | 43
NST-254435 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 413.639 | No | 2021-12-21 | 2021-12-21 | 0 | 2021-12-21 | [9 empty] | 2021-12-28 | 4
NST-254490 | SCE | NEM | NEMA | Withdrawn | Solar PV | 101.853 | No | 2021-12-21 | 2021-12-21 | 0 | 2021-12-21 | 2021-12-28 | 4 | 2022-01-03 | 2022-01-04 | 1 |  | 2022-01-12 | 6
NST-254511 | SCE | NEM | NEMA | Withdrawn | Solar PV | 208.306 | No | 2021-12-21 | 2021-12-21 | 0 | 2021-12-21 | 2022-01-05 | 9 | 2022-01-12 | 2022-01-21 | 6 |  | 2022-01-31 | 6
NST-254546 | SCE | NEM | NEMA | Withdrawn | Solar PV | 456.123 | No | 2021-12-21 | 2021-12-21 | 0 | 2021-12-21 | 2021-12-28 | 4 |  |  |  |  | 2022-02-09 | 29
NST-254613 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 177.793 | No | 2021-12-21 | 2021-12-21 | 0 | 2021-12-21 | [9 empty] | 2021-12-28 | 4
NST-254677 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 94.577 | No | 2021-12-22 | 2021-12-22 | 0 | 2021-12-22 | 2022-01-10 | 11 | 2022-01-24 | [6 empty] | 2022-01-28 | 4 | [49 empty] | 2022-02-25 |  | 65
NST-254817 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 243.043 | No | 2021-12-22 | 2021-12-22 | 0 | 2021-12-22 | 2021-12-29 | 4 | 2022-01-05 | [6 empty] | 2022-01-11 | 4
NST-254843 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 895.332 | No | 2021-12-22 | 2021-12-22 | 0 | 2021-12-22 | 2021-12-29 | 4 | 2022-01-12 | 2022-01-13 | 1 |  |  |  |  | 2022-01-27 | 9
NST-254882 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 184.41 | No | 2021-12-27 | 2021-12-27 | 0 | 2021-12-27 | [9 empty] | 2022-01-03 | 4
NST-254968 | SCE | NEM | NEM-ST | Application Review In Progress |  | 869.26 | No | 2021-12-22 | 2021-12-22 | 0 | 2021-12-22 | 2022-01-07 | 10 | 2022-02-10 | 2022-02-17 | 5 | 2022-02-24 |  |  |  | 2022-03-10 | 10 | 2022-03-10
NST-254968 | SCE | NEM | Other-MT | Pending Agreement Approval/Execution | Solar PV + Battery Storage | 869.26 | No | 2021-12-22 | 2021-12-22 | 0 | 2021-12-22 | [9 empty] | 2022-03-10 | 10
NST-255071 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 34.136 | No | 2021-12-23 | 2021-12-23 | 0 | 2021-12-23 | [9 empty] | 2021-12-27 | 1
NST-255104 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 61.389 | No | 2021-12-23 | 2021-12-23 | 0 | 2021-12-23 | [9 empty] | 2021-12-30 | 4 | [49 empty] | 2022-01-14 |  | 22
NST-255153 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 176.347 | No | 2021-12-23 | 2021-12-23 | 0 | 2021-12-23 | 2021-12-30 | 4 | 2022-01-12 | [6 empty] | 2022-02-08 | 18
NST-255191 | SCE | NEM | Other-NEM-V | NEMI - Load Justification Reviewed | Solar PV | 502.288 | No | 2021-12-23 | 2021-12-23 | 0 | 2021-12-23 | 2021-12-30 | 4 | 2022-01-18 | 2022-03-08 | 34 | 2022-03-09 |  |  |  | 2022-04-13 | 24
NST-255282 | SCE | NEM | NEMA | Withdrawn | Solar PV | 76.848 | No | 2021-12-23 | 2021-12-23 | 0 | 2021-12-23 | 2021-12-30 | 4 |  |  |  |  | 2022-01-14 | 10
NST-255297 | SCE | NEM | VNEM | SCE Engineer Review. Pending Applicant Response | Solar PV | 120.815 | No | 2021-12-23 | 2021-12-23 | 0 | 2021-12-23 | 2022-01-10 | 10 | 2022-01-14 | [6 empty] | 2022-01-25 | 6
NST-255301 | SCE | NEM | VNEM | SCE Engineer Review. Pending Applicant Response | Solar PV | 64.586 | No | 2021-12-23 | 2021-12-23 | 0 | 2021-12-23 | 2022-01-10 | 10 | 2022-01-14 | [6 empty] | 2022-01-25 | 6
NST-255315 | SCE | NEM | NEMA | Withdrawn | Solar PV | 683.774 | No | 2021-12-23 | 2021-12-23 | 0 | 2021-12-23 | 2021-12-30 | 4 |  |  |  |  | 2022-02-09 | 27
NST-255319 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 634.629 | No | 2021-12-23 | 2021-12-23 | 0 | 2021-12-23 | [9 empty] | 2021-12-30 | 4
NST-255359 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 931.18 | No | 2021-12-24 | 2021-12-24 | 0 | 2021-12-24 | 2022-01-03 | 4 | [7 empty] | 2022-01-19 | 11
NST-255404 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 84.194 | No | 2022-01-28 | 2022-01-28 | 0 | 2022-01-28 | [9 empty] | 2022-02-02 | 3
NST-255429 | SCE | NEM | NEMA | Withdrawn | Solar PV | 92.774 | No | 2022-01-28 | 2022-01-28 | 0 | 2022-01-28 | 2022-02-02 | 3 |  |  |  |  | 2022-02-17 | 11
NST-255516 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 172.666 | No | 2021-12-27 | 2021-12-27 | 0 | 2021-12-27 | 2022-01-10 | 9 | 2022-02-10 | 2022-02-17 | 5 | 2022-02-24 |  |  |  | 2022-03-11 | 11
NST-255533 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 30.628 | No | 2021-12-27 | 2021-12-27 | 0 | 2021-12-27 | 2022-01-03 | 4 | 2022-01-03 | 2022-01-07 | 4 | 2022-01-11 |  |  |  | 2022-01-18 | 4 | [49 empty] | 2022-02-02 |  | 37
NST-255603 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 143.83 | No | 2021-12-27 | 2021-12-27 | 0 | 2021-12-27 | [9 empty] | 2021-12-30 | 3
NST-255692 | SCE | NEM | NEMA | Withdrawn | Solar PV | 36.2563 | No | 2021-12-28 | 2021-12-28 | 0 | 2021-12-28 | 2022-01-03 | 3 | 2022-01-13 | 2022-01-14 | 1 |  | 2022-01-25 | 6
NST-255734 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 136.916 | No | 2021-12-28 | 2021-12-28 | 0 | 2021-12-28 | 2022-01-05 | 5 | 2022-01-18 | 2022-01-24 | 4 | 2022-02-09 |  |  |  | 2022-02-18 | 7
NST-255739 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 372.128 | No | 2021-12-28 | 2021-12-28 | 0 | 2021-12-28 | 2022-01-04 | 4 | [7 empty] | 2022-02-25 | 36
NST-255739 | SCE | NEM | NEM-ST | Application Review In Progress |  | 372.128 | No |  |  |  | 2022-02-25
NST-255743 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 322.584 | No | 2021-12-28 | 2021-12-28 | 0 | 2021-12-28 | 2022-01-06 | 6 | [7 empty] | 2022-01-31 | 16
NST-255747 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 176.319 | No | 2021-12-28 | 2021-12-28 | 0 | 2021-12-28 | 2022-01-06 | 6 | [7 empty] | 2022-02-11 | 25
NST-255749 | SCE | NEM | NEM-ST | Application Review In Progress |  | 317.079 | No |  |  |  | 2022-02-17
NST-255749 | SCE | NEM | NEMA | Applicant Response Received. Pending SCE Engineer Review | Solar PV | 317.079 | No | 2021-12-28 | 2021-12-28 | 0 | 2021-12-28 | 2022-01-04 | 4 | 2022-02-09 | 2022-02-15 | 4 | 2022-02-17
NST-255795 | SCE | NEM | NEM-ST | Application Review In Progress |  | 1871.21 | No |  |  |  | 2022-03-09
NST-255795 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 1871.21 | No | 2021-12-28 | 2021-12-28 | 0 | 2021-12-28 | 2021-12-29 | 1 | 2022-01-12 | 2022-02-03 | 15 | 2022-03-09
NST-255801 | SCE | NEM | NEM-ST | Application Review In Progress |  | 1876.208 | No |  |  |  | 2022-03-09
NST-255801 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 1876.208 | No | 2021-12-28 | 2021-12-28 | 0 | 2021-12-28 | 2021-12-30 | 2 | 2022-01-12 | 2022-02-09 | 19 | 2022-03-09
NST-255852 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 178.414 | No | 2021-12-28 | 2021-12-28 | 0 | 2021-12-28 | 2022-01-04 | 4 | 2022-01-04 | [6 empty] | 2022-01-20 | 11
NST-255875 | SCE | NEM | VNEM-SOMAH | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 143.535 | No | 2021-12-28 | 2021-12-28 | 0 | 2021-12-28 | 2022-01-05 | 5 | 2022-01-06 | [6 empty] | 2022-01-28 | 15
NST-255876 | SCE | NEM | VNEM-SOMAH | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 78.32 | No | 2021-12-28 | 2021-12-28 | 0 | 2021-12-28 | 2022-01-05 | 5 | 2022-01-06 | [6 empty] | 2022-01-28 | 15
NST-255877 | SCE | NEM | VNEM-SOMAH | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 34.877 | No | 2021-12-28 | 2021-12-28 | 0 | 2021-12-28 | 2022-01-05 | 5 | 2022-01-06 | [6 empty] | 2022-01-28 | 15
NST-255881 | SCE | NEM | VNEM-SOMAH | NGOM Installation. Pending Local Planner Process | Solar PV | 70.618 | No | 2021-12-28 | 2021-12-28 | 0 | 2021-12-28 | [9 empty] | 2022-01-07 | 7
NST-255883 | SCE | NEM | VNEM-SOMAH | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 112.891 | No | 2021-12-28 | 2021-12-28 | 0 | 2021-12-28 | [9 empty] | 2022-01-07 | 7
NST-255972 | SCE | NEM | NEM-ST | Application Review In Progress |  | 2065.994 | No |  |  |  | 2022-02-04
NST-255972 | SCE | NEM | NEMA | SCE Engineer Assigned. Pending Technical Review | Solar PV + Battery Storage | 2065.994 | No | 2021-12-29 | 2021-12-29 | 0 | 2021-12-29
NST-255973 | SCE | NEM | NEMA | Applicant Response Received. Pending SCE Engineer Review | Solar PV | 907.796 | No | 2021-12-29 | 2021-12-29 | 0 | 2021-12-29 | [9 empty] | 2022-01-25 | 17
NST-255989 | SCE | NEM | Other-NEM-V | SCE Engineer Review. Pending Applicant Response | Solar PV | 344.776 | No | 2021-12-29 | 2021-12-29 | 0 | 2021-12-29 | 2022-01-05 | 4 | 2022-01-06 | [6 empty] | 2022-02-10 | 24
NST-256038 | SCE | NEM | Other-NEM-V | NEMI - Application Returned. Pending Applicant Corrections | Solar PV | 113.427 | No | 2021-12-29 | 2021-12-29 | 0 | 2021-12-29 | 2022-01-11 | 8 | 2022-01-26 | 2022-03-25 | 41
NST-256047 | SCE | NEM | NEMA | Applicant Response Received. Pending SCE Engineer Review | Solar PV | 758.201 | No | 2021-12-30 | 2021-12-30 | 0 | 2021-12-30 | [9 empty] | 2022-04-11 | 68 | [51 empty] | 0
NST-256047 | SCE | NEM | NEM-ST | Application Review In Progress |  | 758.201 | No |  |  |  | 2022-01-17 | [62 empty] | 0
NST-256051 | SCE | NEM | NEM-ST | Application Review In Progress |  | 739.852 | No |  |  |  | 2022-01-17 | [62 empty] | 0
NST-256051 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 739.852 | No | 2021-12-30 | 2021-12-30 | 0 | 2021-12-30 | [62 empty] | 0
NST-256052 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 171.966 | No | 2021-12-29 | 2021-12-29 | 0 | 2021-12-29 | 2022-01-05 | 4 | [7 empty] | 2022-01-24 | 12
NST-256053 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 173.061 | No | 2021-12-29 | 2021-12-29 | 0 | 2021-12-29 | [9 empty] | 2022-01-04 | 3 | [51 empty] | 0
NST-256053 | SCE | NEM | NEM-ST | Application Review In Progress |  | 173.061 | No |  |  |  | 2022-01-04 | [62 empty] | 0
NST-256054 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 101.865 | No | 2021-12-29 | 2021-12-29 | 0 | 2021-12-29 | 2022-01-06 | 5 | [7 empty] | 2022-03-01 | 36
NST-256056 | SCE | NEM | Other-NEM-V | NEMI - Application Returned. Pending Applicant Corrections | Solar PV | 95.708 | No | 2021-12-29 | 2021-12-29 | 0 | 2021-12-29 | 2022-01-11 | 8 | 2022-01-26 | 2022-03-25 | 41
NST-256057 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 173.061 | No | 2021-12-29 | 2021-12-29 | 0 | 2021-12-29 | [9 empty] | 2022-01-04 | 3
NST-256057 | SCE | NEM | NEM-ST | Application Review In Progress |  | 173.061 | No |  |  |  | 2022-01-04
NST-256059 | SCE | NEM | Other-NEM-V | Withdrawn | Solar PV | 91.471 | No | 2021-12-29 | 2021-12-29 | 0 | 2021-12-29 | 2022-01-05 | 4 | 2022-01-11 | 2022-01-12 | 1 |  | 2022-03-01 | 32
NST-256065 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 171.966 | No | 2021-12-30 | 2021-12-30 | 0 | 2021-12-30 | 2022-01-06 | 4 | [7 empty] | 2022-01-28 | 15
NST-256070 | SCE | NEM | Other-NEM-V | Withdrawn | Solar PV | 147.761 | No | 2021-12-29 | 2021-12-29 | 0 | 2021-12-29 | 2022-01-05 | 4 | 2022-01-11 | 2022-01-12 | 1 |  | 2022-02-25 | 30
NST-256102 | SCE | NEM | VNEM-SOMAH | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 50.573 | No | 2021-12-29 | 2021-12-29 | 0 | 2021-12-29 | [9 empty] | 2022-01-12 | 9
NST-256182 | SCE | NEM | NEMA | Withdrawn | Solar PV | 531.222 | No | 2021-12-29 | 2021-12-29 | 0 | 2021-12-29 | 2022-01-14 | 11 |  |  |  |  | 2022-02-01 | 11
NST-256216 | SCE | NEM | Other-NEM-V | NEMI - Application Re-Submitted | Solar PV | 1367.053 | No | 2021-12-29 | 2021-12-29 | 0 | 2021-12-29 | 2022-01-04 | 3 | 2022-01-10 | 2022-03-25 | 52 | 2022-03-30
NST-256229 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 33.152 | No | 2021-12-30 | 2021-12-30 | 0 | 2021-12-30 | [9 empty] | 2022-01-03 | 1 | [49 empty] | 2022-02-02 |  | 34
NST-256285 | SCE | NEM | NEMA | Withdrawn | Solar PV | 334.056 | No | 2021-12-30 | 2021-12-30 | 0 | 2021-12-30 | 2022-01-18 | 11 |  |  |  |  | 2022-03-03 | 31
NST-256295 | SCE | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 46.086 | No | 2021-12-30 | 2021-12-30 | 0 | 2021-12-30 | 2022-01-10 | 6 | 2022-02-03 | 2022-03-04 | 20 | 2022-03-09 |  |  |  | 2022-03-17 | 6
NST-256306 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 131.439 | No | 2021-12-30 | 2021-12-30 | 0 | 2021-12-30 | 2022-01-07 | 5 | [7 empty] | 2022-01-28 | 14
NST-256312 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 171.966 | No | 2021-12-30 | 2021-12-30 | 0 | 2021-12-30 | 2022-01-06 | 4 | [7 empty] | 2022-02-15 | 27
NST-256318 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 376.532 | No | 2021-12-30 | 2021-12-30 | 0 | 2021-12-30 | 2022-01-06 | 4 | [7 empty] | 2022-01-27 | 14
NST-256325 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 262.031 | No | 2021-12-30 | 2021-12-30 | 0 | 2021-12-30 | 2022-01-06 | 4 | [7 empty] | 2022-01-28 | 15
NST-256327 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 123.621 | No | 2021-12-30 | 2021-12-30 | 0 | 2021-12-30 | 2022-01-06 | 4 | [7 empty] | 2022-02-08 | 22
NST-256331 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 86.977 | No | 2021-12-30 | 2021-12-30 | 0 | 2021-12-30 | 2022-01-06 | 4 | 2022-02-11 | 2022-02-17 | 4 | 2022-02-23 |  |  |  | 2022-03-04 | 7
NST-256333 | SCE | NEM | NEMA | Withdrawn | Solar PV | 90.335 | No | 2021-12-30 | 2021-12-30 | 0 | 2021-12-30 | 2022-01-06 | 4 |  |  |  |  | 2022-02-17 | 29
NST-256335 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 177.442 | No | 2021-12-30 | 2021-12-30 | 0 | 2021-12-30 | 2022-01-06 | 4 | [7 empty] | 2022-01-28 | 15
NST-256337 | SCE | NEM | NEMA | Withdrawn | Solar PV | 170.904 | No | 2021-12-30 | 2021-12-30 | 0 | 2021-12-30 | 2022-01-06 | 4 |  |  |  |  | 2022-02-17 | 29
NST-256339 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 132.534 | No | 2021-12-30 | 2021-12-30 | 0 | 2021-12-30 | 2022-01-06 | 4 | [7 empty] | 2022-02-17 | 29
NST-256342 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 65.493 | No | 2021-12-30 | 2021-12-30 | 0 | 2021-12-30 | 2022-01-06 | 4 | 2022-01-07 | [6 empty] | 2022-01-13 | 4
NST-256344 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 770.679 | No | 2021-12-30 | 2021-12-30 | 0 | 2021-12-30 | [62 empty] | 0
NST-256344 | SCE | NEM | NEM-ST | Application Review In Progress |  | 770.679 | No | 2022-01-18 | 2022-01-18 | 0 | 2022-01-18 | 2022-03-29 | 49 | [60 empty] | 0
NST-256347 | SCE | NEM | NEM-ST | Fast Track Initial Review In Progress |  | 713.429 | No | 2022-02-09 | 2022-02-09 | 0 | 2022-02-09 | 2022-02-23 | 9 | 2022-03-07 | [6 empty] | 2022-03-21 | 10 | 2022-03-21
NST-256347 | SCE | NEM | NEMA | SCE Engineer. Initial Review In Progress | Solar PV | 713.429 | No | 2021-12-30 | 2021-12-30 | 0 | 2021-12-30 | 2022-01-06 | 4 | 2022-01-18 | 2022-01-24 | 4 | 2022-02-09 |  |  |  | 2022-03-21 | 10
NST-256350 | SCE | NEM | NEMA | Withdrawn | Solar PV | 66.751 | No | 2021-12-30 | 2021-12-30 | 0 | 2021-12-30 | 2022-01-06 | 4 | 2022-01-06 |  |  |  | 2022-01-31 | 16
NST-256351 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 176.347 | No | 2021-12-30 | 2021-12-30 | 0 | 2021-12-30 | 2022-01-07 | 5 | [7 empty] | 2022-01-28 | 14
NST-256360 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 136.727 | No | 2021-12-30 | 2021-12-30 | 0 | 2021-12-30 | 2022-01-05 | 3 | 2022-01-07 | [6 empty] | 2022-01-13 | 4
NST-256362 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 373.596 | No | 2021-12-30 | 2021-12-30 | 0 | 2021-12-30 | [9 empty] | 2022-01-05 | 3
NST-256366 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 264.233 | No | 2021-12-30 | 2021-12-30 | 0 | 2021-12-30 | 2022-01-06 | 4 | 2022-01-18 | 2022-01-28 | 8 | 2022-02-09 |  |  |  | 2022-02-17 | 6
NST-256371 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 135.82 | No | 2021-12-30 | 2021-12-30 | 0 | 2021-12-30 | 2022-01-06 | 4 | [7 empty] | 2022-01-28 | 15
NST-256384 | SCE | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 45.527 | No | 2021-12-30 | 2021-12-30 | 0 | 2021-12-30 | 2022-01-03 | 1 | 2022-01-13 | 2022-01-20 | 4 | 2022-01-26 |  |  |  | 2022-02-01 | 4
NST-256407 | SCE | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 35.578 | No | 2021-12-30 | 2021-12-30 | 0 | 2021-12-30 | 2022-01-05 | 3 | 2022-01-06 | [6 empty] | 2022-01-12 | 4
NST-256408 | SCE | NEM | NEMA | Withdrawn | Solar PV | 235.093 | No | 2021-12-30 | 2021-12-30 | 0 | 2021-12-30 | 2022-01-06 | 4 | 2022-01-14 | 2022-03-07 | 34 |  | 2022-03-15 | 6
NST-256428 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 221.011 | No | 2021-12-30 | 2021-12-30 | 0 | 2021-12-30 | 2022-01-06 | 4 | 2022-01-14 | [6 empty] | 2022-01-24 | 5
NST-256437 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 188.153 | No | 2021-12-30 | 2021-12-30 | 0 | 2021-12-30 | 2022-01-06 | 4 | 2022-01-14 | 2022-03-01 | 30 | 2022-03-01 |  |  |  | 2022-03-07 | 4
NST-256462 | SCE | NEM | NEMA | Withdrawn | Solar PV | 76.239 | No | 2021-12-30 | 2021-12-30 | 0 | 2021-12-30 | 2022-01-06 | 4 |  |  |  |  | 2022-01-24 | 11
NST-256476 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 943.859 | No | 2021-12-30 | 2021-12-30 | 0 | 2021-12-30 | [9 empty] | 2022-01-07 | 5
NST-256510 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 174.756 | No | 2021-12-30 | 2021-12-30 | 0 | 2021-12-30 | 2022-01-07 | 5 | [7 empty] | 2022-03-03 | 37
NST-256514 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 260.135 | No | 2021-12-30 | 2021-12-30 | 0 | 2021-12-30 | 2022-01-06 | 4 | [7 empty] | 2022-01-31 | 16
NST-256516 | SCE | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 186.892 | No | 2021-12-30 | 2021-12-30 | 0 | 2021-12-30 | [9 empty] | 2022-01-06 | 4
NST-256529 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 41.37 | No | 2021-12-30 | 2021-12-30 | 0 | 2021-12-30 | 2022-01-07 | 5 | 2022-01-17 | 2022-01-18 | 0 |  |  |  |  | 2022-01-28 | 8
NST-256560 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 146.298 | No | 2021-12-31 | 2021-12-31 | 0 | 2021-12-31 | 2022-01-06 | 3 | 2022-01-11 | 2022-01-22 | 7 | 2022-01-31 |  |  |  | 2022-02-04 | 4
NST-256565 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 232.783 | No | 2021-12-31 | 2021-12-31 | 0 | 2021-12-31 | 2022-01-07 | 4 | 2022-01-14 | [6 empty] | 2022-02-22 | 25
NST-256569 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 211.918 | No | 2021-12-31 | 2021-12-31 | 0 | 2021-12-31 | 2022-01-06 | 3 | 2022-01-14 | [6 empty] | 2022-02-22 | 25
NST-256606 | SCE | NEM | NEMA | Withdrawn | Solar PV | 33.734 | No | 2022-01-03 | 2022-01-03 | 0 | 2022-01-03 | 2022-01-07 | 4 |  |  |  |  | 2022-02-11 | 24
NST-256677 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 987.579 | No | 2022-01-03 | 2022-01-03 | 0 | 2022-01-03 | 2022-01-12 | 7 | 2022-01-12 | [6 empty] | 2022-01-20 | 5
NST-256727 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 238.157 | No | 2022-01-03 | 2022-01-03 | 0 | 2022-01-03 | [9 empty] | 2022-01-10 | 5
NST-256754 | SCE | NEM | NEM-ST | Application Review In Progress |  | 0.024726 | No |  |  |  | 2022-03-08
NST-256785 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 30.561 | No | 2022-01-05 | 2022-01-05 | 0 | 2022-01-05 | 2022-01-11 | 4 | 2022-01-11 | [6 empty] | 2022-01-26 | 10
NST-256817 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 35.88 | No | 2022-01-03 | 2022-01-03 | 0 | 2022-01-03 | 2022-01-07 | 4 | 2022-01-07 | [6 empty] | 2022-02-03 | 18
NST-256866 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 506.61 | No | 2022-01-04 | 2022-01-04 | 0 | 2022-01-04 | 2022-01-19 | 10 | 2022-01-19 | [6 empty] | 2022-02-11 | 17
NST-256869 | SCE | NEM | NEMA | Withdrawn | Solar PV | 149.906 | No | 2022-01-26 | 2022-01-26 | 0 | 2022-01-26 | 2022-01-31 | 3 | 2022-02-14 | 2022-03-04 | 13 |  | 2022-03-21 | 11
NST-256872 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 372.493 | No | 2022-01-04 | 2022-01-04 | 0 | 2022-01-04 | 2022-01-19 | 10 | 2022-01-19 | [6 empty] | 2022-02-11 | 17
NST-256967 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 517.99 | No | 2022-01-04 | 2022-01-04 | 0 | 2022-01-04 | 2022-01-10 | 4 | 2022-01-10 | [6 empty] | 2022-01-15 | 4
NST-256971 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 579.95 | No | 2022-01-04 | 2022-01-04 | 0 | 2022-01-04 | [9 empty] | 2022-01-10 | 4
NST-256984 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 38.302 | No | 2022-01-04 | 2022-01-04 | 0 | 2022-01-04 | [9 empty] | 2022-01-05 | 1
NST-257005 | SCE | NEM | NEMA | NEMI - Application Returned 2nd Time. Pending Applicant Corrections | Solar PV | 491.583 | No | 2022-01-04 | 2022-01-04 | 0 | 2022-01-04 | 2022-01-07 | 3 | 2022-01-10 | 2022-03-29 | 54
NST-257010 | SCE | NEM | NEMA | SCE Engineer. Supplemental Review Complete | Solar PV | 84.745 | No | 2022-01-04 | 2022-01-04 | 0 | 2022-01-04 | [9 empty] | 2022-01-10 | 4 | [51 empty] | 0
NST-257010 | SCE | NEM | NEM-ST | Application Review In Progress |  | 84.745 | No |  |  |  | 2022-01-10 | [62 empty] | 0
NST-257365 | SCE | NEM | NEMA | Applicant Response Received. Pending SCE Engineer Review | Solar PV | 66.295 | No | 2022-01-05 | 2022-01-05 | 0 | 2022-01-05 | 2022-01-11 | 4 | 2022-01-13 | 2022-02-22 | 26 | 2022-02-28 |  |  |  | 2022-03-04 | 4
NST-257394 | SCE | NEM | NEMA | Withdrawn | Solar PV | 35.723 | No | 2022-01-05 | 2022-01-05 | 0 | 2022-01-05 | 2022-01-11 | 4 | 2022-01-17 | 2022-01-21 | 3 |  | 2022-01-31 | 6
NST-257474 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 105.284 | No | 2022-01-05 | 2022-01-05 | 0 | 2022-01-05 | 2022-01-19 | 9 | 2022-01-19 | [6 empty] | 2022-01-31 | 8
NST-257513 | SCE | NEM | NEMA | NEMI - 1.0 Expansion Ineligible | Solar PV | 447.454 | No | 2022-01-06 | 2022-01-06 | 0 | 2022-01-06
NST-257572 | SCE | NEM | NEMA | Withdrawn | Solar PV | 263.235 | No | 2022-01-06 | 2022-01-06 | 0 | 2022-01-06 | 2022-01-13 | 5 | 2022-01-20 | 2022-01-25 | 3 |  |  |  | 2022-02-02
NST-257662 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 86.188 | No | 2022-01-06 | 2022-01-06 | 0 | 2022-01-06 | [9 empty] | 2022-01-12 | 4
NST-257779 | SCE | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 48.655 | No | 2022-01-06 | 2022-01-06 | 0 | 2022-01-06 | 2022-01-07 | 1 | 2022-01-21 | 2022-02-08 | 12 | 2022-03-04 |  |  |  | 2022-03-15 | 7
NST-257786 | SCE | NEM | NEMA | Withdrawn | Solar PV | 1894.456 | No | 2022-01-06 | 2022-01-06 | 0 | 2022-01-06 | 2022-01-19 | 8 |  |  |  |  | 2022-03-03 | 30
NST-257922 | SCE | NEM | NEMA | Withdrawn | Solar PV | 997.192 | No | 2022-01-07 | 2022-01-07 | 0 | 2022-01-07 | [9 empty] | 2022-01-14 | 5
NST-257972 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 896.1482 | No | 2022-01-07 | 2022-01-07 | 0 | 2022-01-07 | 2022-01-10 | 1 | 2022-01-10 | 2022-01-14 | 4 | 2022-01-18 |  |  |  | 2022-01-21 | 3 | [49 empty] | 2022-02-09 |  | 33
NST-258041 | SCE | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 34.588 | No | 2022-01-07 | 2022-01-07 | 0 | 2022-01-07 | [9 empty] | 2022-01-13 | 4
NST-258042 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 101.589 | No | 2022-01-07 | 2022-01-07 | 0 | 2022-01-07 | [9 empty] | 2022-01-13 | 4 | [49 empty] | 2022-01-13 |  | 6
NST-258155 | SCE | NEM | NEMA | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 32.161 | No | 2022-01-07 | 2022-01-07 | 0 | 2022-01-07 | 2022-01-12 | 3 | 2022-01-17 | 2022-01-21 | 3 | 2022-01-25 |  |  |  | 2022-01-28 | 3
NST-258182 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 82.216 | No | 2022-01-07 | 2022-01-07 | 0 | 2022-01-07 | [9 empty] | 2022-01-14 | 5
NST-258360 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 388.4 | No | 2022-01-10 | 2022-01-10 | 0 | 2022-01-10 | 2022-01-18 | 5 | 2022-01-18 | [6 empty] | 2022-01-25 | 5
NST-258409 | SCE | NEM | NEM-ST | Transferred to NEM |  | 0 | No |  |  |  | 2022-01-24 | [62 empty] | 0
NST-258442 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 113.595 | No | 2022-01-10 | 2022-01-10 | 0 | 2022-01-10 | 2022-01-14 | 4 | 2022-01-25 | 2022-02-03 | 7 | 2022-02-08 |  |  |  | 2022-02-11 | 3
NST-258449 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 372.109 | No | 2022-01-10 | 2022-01-10 | 0 | 2022-01-10 | 2022-01-14 | 4 | 2022-01-14 | [6 empty] | 2022-01-27 | 8
NST-258455 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 423.819 | No | 2022-01-10 | 2022-01-10 | 0 | 2022-01-10 | 2022-01-14 | 4 | 2022-01-14 | [6 empty] | 2022-01-27 | 8
NST-258464 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 196.361 | No | 2022-01-10 | 2022-01-10 | 0 | 2022-01-10 | 2022-01-18 | 5 | 2022-01-18 | [6 empty] | 2022-01-21 | 3
NST-258471 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 200.5 | No | 2022-01-10 | 2022-01-10 | 0 | 2022-01-10 | [9 empty] | 2022-01-14 | 4
NST-258474 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 215.328 | No | 2022-01-10 | 2022-01-10 | 0 | 2022-01-10 | [9 empty] | 2022-01-14 | 4
NST-258479 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 266.642 | No | 2022-01-10 | 2022-01-10 | 0 | 2022-01-10 | 2022-01-14 | 4 | 2022-01-14 | [6 empty] | 2022-01-25 | 6
NST-258481 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 388.4 | No | 2022-01-10 | 2022-01-10 | 0 | 2022-01-10 | [9 empty] | 2022-01-14 | 4
NST-258486 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 432.3 | No | 2022-01-10 | 2022-01-10 | 0 | 2022-01-10 | [9 empty] | 2022-01-14 | 4
NST-258487 | SCE | NEM | NEMA | Withdrawn | Solar PV | 205.755 | No | 2022-01-10 | 2022-01-10 | 0 | 2022-01-10 | 2022-01-14 | 4 | 2022-01-18 | 2022-01-25 | 5 | 2022-01-27 | 2022-02-08 | 8
NST-258493 | SCE | NEM | NEMA | NEMI - Pending Permanent Service | Solar PV | 39.752 | No | 2022-01-10 | 2022-01-10 | 0 | 2022-01-10 | 2022-01-11 | 1 | 2022-01-11 | [6 empty] | 2022-02-03 | 16
NST-258583 | SCE | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 30.824 | No | 2022-01-10 | 2022-01-10 | 0 | 2022-01-10 | 2022-01-11 | 1 | 2022-01-11 | [6 empty] | 2022-01-24 | 8
NST-258587 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 284.657 | No | 2022-01-12 | 2022-01-12 | 0 | 2022-01-12 | [9 empty] | 2022-01-19 | 4
NST-258592 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 234.09 | No | 2022-01-12 | 2022-01-12 | 0 | 2022-01-12 | 2022-01-19 | 4 | 2022-01-19 | [6 empty] | 2022-01-24 | 3
NST-258674 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 46.533 | No | 2022-01-10 | 2022-01-10 | 0 | 2022-01-10 | 2022-01-11 | 1 | 2022-01-11 | [6 empty] | 2022-01-25 | 9
NST-258679 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 85.284 | No | 2022-01-10 | 2022-01-10 | 0 | 2022-01-10 | 2022-01-14 | 4 | 2022-01-14 | [6 empty] | 2022-01-25 | 6
NST-258682 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 348.444 | No | 2022-01-10 | 2022-01-10 | 0 | 2022-01-10 | [9 empty] | 2022-01-14 | 4
NST-259231 | SCE | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 41.753 | No | 2022-01-12 | 2022-01-12 | 0 | 2022-01-12 | [9 empty] | 2022-01-20 | 5
NST-259299 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 95.027 | No | 2022-01-12 | 2022-01-12 | 0 | 2022-01-12 | [9 empty] | 2022-01-19 | 4
NST-259319 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 804.698 | No | 2022-01-12 | 2022-01-12 | 0 | 2022-01-12 | [9 empty] | 2022-01-19 | 4
NST-259325 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 56.898 | No | 2022-01-12 | 2022-01-12 | 0 | 2022-01-12 | [9 empty] | 2022-01-18 | 3
NST-259329 | SCE | NEM | NEMA | Withdrawn | Solar PV | 450.324 | No | 2022-01-12 | 2022-01-12 | 0 | 2022-01-12 | 2022-01-18 | 3 | 2022-01-28 | 2022-02-02 | 3 |  | 2022-02-10 | 6
NST-259334 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 136.961 | No | 2022-01-12 | 2022-01-12 | 0 | 2022-01-12 | 2022-01-19 | 4 | 2022-01-19 | [6 empty] | 2022-02-17 | 21
NST-259346 | SCE | NEM | NEMA | SCE Engineer. Supplemental Review In Progress | Solar PV | 994.866 | No | 2022-01-12 | 2022-01-12 | 0 | 2022-01-12 | 2022-01-24 | 7 | 2022-01-24 | [6 empty] | 2022-01-26 | 2
NST-259346 | SCE | NEM | NEM-ST | Application Review In Progress |  | 994.866 | No |  |  |  | 2022-01-26
NST-259348 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 366.779 | No | 2022-01-12 | 2022-01-12 | 0 | 2022-01-12 | 2022-01-20 | 5 | 2022-01-20 | 2022-03-18 | 40 | 2022-03-18 |  |  |  | 2022-03-28 | 6
NST-259356 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 130.56 | No | 2022-01-12 | 2022-01-12 | 0 | 2022-01-12 | 2022-01-19 | 4 | 2022-01-19 | [6 empty] | 2022-02-03 | 11
NST-259362 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 126.609 | No | 2022-01-12 | 2022-01-12 | 0 | 2022-01-12 | 2022-01-19 | 4 | 2022-01-19 | [6 empty] | 2022-02-04 | 12
NST-259409 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 33.793 | No | 2022-01-12 | 2022-01-12 | 0 | 2022-01-12 | [9 empty] | 2022-01-19 | 4 | [49 empty] | 2022-02-28 |  | 47
NST-259526 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 713.342 | No | 2022-01-13 | 2022-01-13 | 0 | 2022-01-13 | 2022-01-21 | 5 | 2022-01-21 | 2022-01-27 | 4 | 2022-01-27 |  |  |  | 2022-02-01 | 3
NST-259571 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 46.76 | No | 2022-01-13 | 2022-01-13 | 0 | 2022-01-13 | 2022-01-21 | 5 | 2022-01-21 | [6 empty] | 2022-01-28 | 5 | [49 empty] | 2022-01-28 |  | 15
NST-259754 | SCE | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 85.422 | No | 2022-01-13 | 2022-01-13 | 0 | 2022-01-13 | [9 empty] | 2022-01-20 | 4
NST-260062 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 65.426 | No | 2022-01-14 | 2022-01-14 | 0 | 2022-01-14 | 2022-01-20 | 3 | 2022-01-20 | [6 empty] | 2022-02-08 | 13
NST-260385 | SCE | NEM | NEMA | NEMI - Equipment Change Submitted | Solar PV | 316.373 | No | 2022-01-17 | 2022-01-17 | 0 | 2022-01-17 | [9 empty] | 2022-01-24 | 4
NST-260575 | SCE | NEM | NEMA | Withdrawn | Solar PV | 415.276 | No | 2022-01-18 | 2022-01-18 | 0 | 2022-01-18 | 2022-01-22 | 3 |  |  |  |  | 2022-02-08 | 11
NST-260607 | SCE | NEM | NEMA | Withdrawn | Solar PV | 130.234 | No | 2022-01-18 | 2022-01-18 | 0 | 2022-01-18 | 2022-01-22 | 3 |  |  |  |  | 2022-02-08 | 11
NST-260676 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 897.851 | No | 2022-01-18 | 2022-01-18 | 0 | 2022-01-18 | 2022-01-24 | 4 | 2022-01-24 | 2022-02-09 | 12 | 2022-02-18 |  |  |  | 2022-02-18 | 0
NST-260781 | SCE | NEM | NEM Aggregation | Withdrawn |  | 781.056 | No | 2022-01-21 | 2022-01-21 | 0 | 2022-01-21 | [9 empty] | 2022-02-04 | 10 | 2022-02-04 | 2022-02-28 | 15 | [48 empty] | 0
NST-260781 | SCE | NEM | NEMA | SCE Engineer. Initial Review Complete | Solar PV | 781.056 | No | 2022-01-18 | 2022-01-18 | 0 | 2022-01-18 | 2022-01-21 | 3 | 2022-01-21 | [6 empty] | 2022-02-04 | 10 | [51 empty] | 0
NST-260817 | SCE | NEM | NEMA | Withdrawn | Solar PV | 166.035 | No | 2022-01-25 | 2022-01-25 | 0 | 2022-01-25 | 2022-01-28 | 3 |  |  |  |  | 2022-02-14 | 11
NST-260835 | SCE | NEM | NEM-ST | Application Review In Progress |  | 1313.517 | No | 2022-02-16 | 2022-02-16 | 0 | 2022-02-16 | 2022-03-02 | 9
NST-260835 | SCE | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 1313.517 | No | 2022-01-18 | 2022-01-18 | 0 | 2022-01-18 | 2022-01-21 | 3 | 2022-01-28 | 2022-03-02 | 22
NST-260849 | SCE | NEM | NEMA | SCE Engineer Assigned. Pending Technical Review | Solar PV | 132.097 | No | 2022-01-19 | 2022-01-19 | 0 | 2022-01-19 | 2022-01-27 | 6 | 2022-02-03 | [6 empty] | 2022-02-08 | 3
NST-260849 | SCE | NEM | NEM Aggregation | Application Review In Progress |  | 132.097 | No |  |  |  | 2022-02-08
NST-261089 | SCE | NEM | NEMA | NEMI - Sent to Engineering | Solar PV | 70.255 | No | 2022-01-28 | 2022-01-28 | 0 | 2022-01-28 | 2022-02-02 | 3 | 2022-02-02 | [6 empty] | 2022-02-22 | 13
NST-261114 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 36.611 | No | 2022-01-19 | 2022-01-19 | 0 | 2022-01-19 | 2022-02-07 | 13 | 2022-02-07 | [6 empty] | 2022-03-08 | 20
NST-261177 | SCE | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 36.296 | No | 2022-01-19 | 2022-01-19 | 0 | 2022-01-19 | 2022-01-25 | 4 | 2022-01-25 | [6 empty] | 2022-02-07 | 9
NST-261229 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 178.804 | No | 2022-01-20 | 2022-01-20 | 0 | 2022-01-20 | 2022-01-28 | 6 | 2022-01-28 | [6 empty] | 2022-03-25 | 39
NST-261230 | SCE | NEM | NEMA | SCE Engineer Assigned. Pending Technical Review | Solar PV | 648.163 | No | 2022-01-21 | 2022-01-21 | 0 | 2022-01-21 | 2022-01-25 | 2 | 2022-02-04 | 2022-03-01 | 16 | 2022-03-16
NST-261231 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 175.656 | No | 2022-01-20 | 2022-01-20 | 0 | 2022-01-20 | 2022-01-28 | 6 | 2022-01-28 | [6 empty] | 2022-03-25 | 39
NST-261244 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 626.012 | No | 2022-01-20 | 2022-01-20 | 0 | 2022-01-20 | 2022-01-31 | 7 | 2022-01-31 | [6 empty] | 2022-03-08 | 25
NST-261246 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 351.598 | No | 2022-01-20 | 2022-01-20 | 0 | 2022-01-20 | 2022-01-31 | 7 | 2022-01-31 | [6 empty] | 2022-03-08 | 25
NST-261247 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 289.627 | No | 2022-01-20 | 2022-01-20 | 0 | 2022-01-20 | 2022-01-31 | 7 | 2022-01-31 | [6 empty] | 2022-02-17 | 13
NST-261389 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 51.233 | No | 2022-01-20 | 2022-01-20 | 0 | 2022-01-20 | 2022-01-25 | 3 | 2022-01-25 | 2022-02-11 | 13 | 2022-02-11 |  |  |  | 2022-02-16 | 3 | [49 empty] | 2022-03-03 |  | 42
NST-261400 | SCE | NEM | NEMA | Withdrawn | Solar PV | 600 | No | 2022-01-20 | 2022-01-20 | 0 | 2022-01-20 | 2022-01-26 | 4 |  | 2022-02-24 |  |  | 2022-03-11 | 11
NST-261411 | SCE | NEM | NEMA | Withdrawn | Solar PV | 232.819 | No | 2022-01-20 | 2022-01-20 | 0 | 2022-01-20 | 2022-02-01 | 8 |  |  |  |  | 2022-03-14 | 28
NST-261449 | SCE | NEM | NEMA | Withdrawn | Solar PV | 261.921 | No | 2022-01-20 | 2022-01-20 | 0 | 2022-01-20 | 2022-02-01 | 8 |  |  |  |  | 2022-03-14 | 28
NST-261478 | SCE | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 248.149 | No | 2022-01-20 | 2022-01-20 | 0 | 2022-01-20 | 2022-01-25 | 3 | 2022-01-25 | [6 empty] | 2022-02-22 | 19
NST-261502 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 278.313 | No | 2022-01-20 | 2022-01-20 | 0 | 2022-01-20 | 2022-01-26 | 4 | 2022-01-26 | [6 empty] | 2022-02-03 | 6
NST-261605 | SCE | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 442.891 | No | 2022-01-21 | 2022-01-21 | 0 | 2022-01-21 | 2022-01-27 | 4 | 2022-02-04 | 2022-03-25 | 34
NST-261606 | SCE | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 224.767 | No | 2022-01-21 | 2022-01-21 | 0 | 2022-01-21 | 2022-01-27 | 4 | 2022-02-04 | 2022-03-25 | 34
NST-261784 | SCE | NEM | NEM Aggregation | Supplemental Review In Progress |  | 998.341 | No | 2022-02-10 | 2022-02-10 | 0 | 2022-02-10 | [11 empty] | 2022-02-25 | 2022-03-18 | 15 |  |  | 2022-03-18
NST-261784 | SCE | NEM | NEMA | SCE Engineer. Supplemental Review In Progress | Solar PV | 998.341 | No | 2022-01-21 | 2022-01-21 | 0 | 2022-01-21 | 2022-01-27 | 4 | 2022-02-04 | 2022-02-10 | 4 | 2022-02-10
NST-261814 | SCE | NEM | NEM-ST | Fast Track Initial Review Complete |  | 1023.216 | No | 2022-02-08 | 2022-02-08 | 0 | 2022-02-08 | 2022-02-15 | 5 | 2022-03-02 | [6 empty] | 2022-03-08 | 4 | 2022-03-08 | 2022-03-22 | 10
NST-261814 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 1023.216 | No | 2022-01-21 | 2022-01-21 | 0 | 2022-01-21 | 2022-01-27 | 4 | 2022-02-02 | 2022-02-07 | 3 | 2022-02-08 |  |  |  | 2022-03-08 | 4
NST-261845 | SCE | NEM | NEMA | Withdrawn | Solar PV | 1821.542 | No | 2022-01-21 | 2022-01-21 | 0 | 2022-01-21 | 2022-01-26 | 3 | 2022-02-03 | 2022-02-08 | 3 |  | 2022-02-24 | 11
NST-261889 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 515.802 | No | 2022-01-25 | 2022-01-25 | 0 | 2022-01-25 | 2022-01-31 | 4 | 2022-01-31 | 2022-03-21 | 34 | 2022-03-24 |  |  |  | 2022-03-28 | 2
NST-261903 | SCE | NEM | NEM-ST | Application Review In Progress |  | 3491.473 | No | 2022-01-21 | 2022-01-21 | 0 | 2022-01-21 | 2022-02-15 | 17 | 2022-03-01 | 2022-03-23 | 16 | [57 empty] | 0
NST-261903 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 3491.473 | No | 2022-01-21 | 2022-01-21 | 0 | 2022-01-21 | [62 empty] | 0
NST-261906 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 277.894 | No | 2022-01-21 | 2022-01-21 | 0 | 2022-01-21 | 2022-01-27 | 4 | 2022-01-27 | [6 empty] | 2022-02-07 | 7
NST-262143 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 36.804 | No | 2022-01-24 | 2022-01-24 | 0 | 2022-01-24 | 2022-02-01 | 6 | 2022-02-01 | [6 empty] | 2022-02-09 | 6
NST-262144 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 34.396 | No | 2022-01-24 | 2022-01-24 | 0 | 2022-01-24 | 2022-02-04 | 9 | 2022-02-04 | [6 empty] | 2022-02-09 | 3
NST-262452 | SCE | NEM | NEMA | NEMI - Application Returned 2nd Time. Pending Applicant Corrections | Solar PV | 909.388 | No | 2022-01-25 | 2022-01-25 | 0 | 2022-01-25 | 2022-01-28 | 3 | 2022-01-28 | 2022-03-29 | 41
NST-262485 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 448.956 | No | 2022-01-25 | 2022-01-25 | 0 | 2022-01-25 | [9 empty] | 2022-01-27 | 2
NST-262500 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 151.423 | No | 2022-01-25 | 2022-01-25 | 0 | 2022-01-25 | [9 empty] | 2022-01-28 | 3
NST-262618 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 129.935 | No | 2022-01-25 | 2022-01-25 | 0 | 2022-01-25 | 2022-01-27 | 2 | 2022-01-27 | [6 empty] | 2022-02-11 | 11
NST-262643 | SCE | NEM | NEMA | Withdrawn | Solar PV | 39.25 | No | 2022-01-25 | 2022-01-25 | 0 | 2022-01-25 | 2022-01-28 | 3 |  |  |  |  | 2022-03-10 | 28
NST-262644 | SCE | NEM | NEMA | Withdrawn | Solar PV | 30.061 | No | 2022-01-25 | 2022-01-25 | 0 | 2022-01-25 | 2022-01-28 | 3 |  |  |  |  | 2022-03-10 | 28
NST-262678 | SCE | NEM | NEMA | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 69.319 | No | 2022-01-25 | 2022-01-25 | 0 | 2022-01-25 | 2022-02-04 | 8 | 2022-02-04 | 2022-02-17 | 9 | 2022-02-22 |  |  |  | 2022-03-01 | 5
NST-262679 | SCE | NEM | NEMA | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 73.378 | No | 2022-01-25 | 2022-01-25 | 0 | 2022-01-25 | 2022-02-04 | 8 | 2022-02-04 | 2022-02-17 | 9 | 2022-02-22 |  |  |  | 2022-03-01 | 5
NST-262712 | SCE | NEM | NEM-ST | Application Review In Progress |  | 668.958 | No | 2022-01-31 | 2022-01-31 | 0 | 2022-01-31 | 2022-02-14 | 10 | 2022-03-01 | [59 empty] | 0
NST-262712 | SCE | NEM | NEMA | Withdrawn | Solar PV | 668.958 | No | 2022-01-26 | 2022-01-26 | 0 | 2022-01-26 | 2022-01-31 | 3 | 2022-01-31 |  |  |  | 2022-03-29 | 40 | [54 empty] | 0
NST-262724 | SCE | NEM | NEMA | NEMI - Application Re-Submitted | Solar PV | 80.471 | No | 2022-01-27 | 2022-01-27 | 0 | 2022-01-27 | 2022-02-02 | 4 | 2022-02-02 | 2022-03-04 | 21 | 2022-03-23
NST-262733 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 779.012 | No | 2022-01-26 | 2022-01-26 | 0 | 2022-01-26 | [9 empty] | 2022-02-01 | 4
NST-262737 | SCE | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 810.172 | No | 2022-01-26 | 2022-01-26 | 0 | 2022-01-26 | 2022-01-31 | 3 | 2022-01-31 | 2022-02-14 | 10
NST-262749 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 470.067 | No | 2022-01-26 | 2022-01-26 | 0 | 2022-01-26 | 2022-01-31 | 3 | 2022-01-31 | [6 empty] | 2022-02-03 | 3
NST-262824 | SCE | NEM | NEMA | Withdrawn | Solar PV | 241.839 | No | 2022-01-26 | 2022-01-26 | 0 | 2022-01-26 | 2022-01-28 | 2 |  |  |  |  | 2022-02-14 | 11
NST-262856 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 33.29 | No | 2022-01-26 | 2022-01-26 | 0 | 2022-01-26 | 2022-01-27 | 1 | 2022-01-27 | [6 empty] | 2022-02-10 | 10
NST-262882 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 79.721 | No | 2022-01-26 | 2022-01-26 | 0 | 2022-01-26 | [9 empty] | 2022-01-31 | 3
NST-262906 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 155.668 | No | 2022-01-26 | 2022-01-26 | 0 | 2022-01-26 | [9 empty] | 2022-02-01 | 4
NST-262926 | SCE | NEM | NEMA | Withdrawn | Solar PV | 76.807 | No | 2022-01-26 | 2022-01-26 | 0 | 2022-01-26 | 2022-01-31 | 3 |  |  |  |  | 2022-02-15 | 11
NST-262985 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 77.725 | No | 2022-01-26 | 2022-01-26 | 0 | 2022-01-26 | 2022-01-31 | 3 | 2022-01-31 | [6 empty] | 2022-02-07 | 5
NST-262994 | SCE | NEM | NEMA | Withdrawn | Solar PV | 183.972 | No | 2022-01-26 | 2022-01-26 | 0 | 2022-01-26 | 2022-01-31 | 3 |  |  |  |  | 2022-02-15 | 11
NST-263013 | SCE | NEM | NEMA | NEMI - Application Returned. Pending Applicant Corrections | Solar PV | 797.214 | No | 2022-01-27 | 2022-01-27 | 0 | 2022-01-27 | 2022-02-01 | 3 | 2022-02-23 | 2022-03-22 | 19
NST-263018 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 70.523 | No | 2022-01-26 | 2022-01-26 | 0 | 2022-01-26 | [9 empty] | 2022-01-31 | 3
NST-263142 | SCE | NEM | NEMA | NGOM Installation. Pending New Service Request, Invoice Payment and AHJ Panel Permit | Solar PV | 61.2 | No | 2022-01-26 | 2022-01-26 | 0 | 2022-01-26 | 2022-02-08 | 9 | 2022-02-08 | [6 empty] | 2022-02-23 | 10
NST-263323 | SCE | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 417.847 | No | 2022-01-27 | 2022-01-27 | 0 | 2022-01-27 | 2022-02-03 | 5 | 2022-02-22 | 2022-03-14 | 14
NST-263334 | SCE | NEM | NEMA | Withdrawn | Solar PV | 250.778 | No | 2022-02-16 | 2022-02-16 | 0 | 2022-02-16 | 2022-02-23 | 4 | 2022-02-23 | 2022-03-01 | 4 |  | 2022-03-16 | 11
NST-263532 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 189.979 | No | 2022-01-27 | 2022-01-27 | 0 | 2022-01-27 | 2022-02-04 | 6 | 2022-02-04 | 2022-03-11 | 24 | 2022-03-16 |  |  |  | 2022-03-16 | 0
NST-263533 | SCE | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 626.048 | No | 2022-01-27 | 2022-01-27 | 0 | 2022-01-27 | 2022-02-08 | 8 | 2022-03-09 | 2022-03-22 | 9
NST-263618 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 79.075 | No | 2022-01-27 | 2022-01-27 | 0 | 2022-01-27 | [9 empty] | 2022-02-01 | 3
NST-263625 | SCE | NEM | NEMA | NEMI - Application Returned 2nd Time. Pending Applicant Corrections | Solar PV | 177.016 | No | 2022-01-27 | 2022-01-27 | 0 | 2022-01-27 | 2022-02-08 | 8 | 2022-02-08 | 2022-03-31 | 35
NST-263626 | SCE | NEM | NEMA | NEMI - Application Returned 2nd Time. Pending Applicant Corrections | Solar PV | 177.016 | No | 2022-01-27 | 2022-01-27 | 0 | 2022-01-27 | 2022-02-08 | 8 | 2022-02-08 | 2022-03-31 | 35
NST-263627 | SCE | NEM | NEMA | NEMI - Application Returned 2nd Time. Pending Applicant Corrections | Solar PV | 177.016 | No | 2022-01-27 | 2022-01-27 | 0 | 2022-01-27 | 2022-02-08 | 8 | 2022-02-08 | 2022-03-31 | 35
NST-263628 | SCE | NEM | NEMA | NEMI - Application Returned 2nd Time. Pending Applicant Corrections | Solar PV | 486.795 | No | 2022-01-27 | 2022-01-27 | 0 | 2022-01-27 | 2022-02-14 | 12 | 2022-02-14
NST-263629 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 177.016 | No | 2022-01-27 | 2022-01-27 | 0 | 2022-01-27 | 2022-02-08 | 8 | 2022-02-08 | [6 empty] | 2022-03-21 | 28
NST-263630 | SCE | NEM | NEMA | NEMI - Application Returned. Pending Applicant Corrections | Solar PV | 265.524 | No | 2022-01-27 | 2022-01-27 | 0 | 2022-01-27 | 2022-02-09 | 9 | 2022-02-09
NST-263631 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 132.538 | No | 2022-01-27 | 2022-01-27 | 0 | 2022-01-27 | 2022-02-09 | 9 | 2022-02-09 | [6 empty] | 2022-03-25 | 31
NST-263632 | SCE | NEM | NEMA | NEMI - Application Returned. Pending Applicant Corrections | Solar PV | 407.138 | No | 2022-01-27 | 2022-01-27 | 0 | 2022-01-27 | 2022-02-09 | 9 | 2022-02-09
NST-263638 | SCE | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 520.682 | No | 2022-01-27 | 2022-01-27 | 0 | 2022-01-27 | 2022-02-08 | 8 | 2022-03-16 | 2022-03-23 | 5
NST-263642 | SCE | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 336.331 | No | 2022-01-27 | 2022-01-27 | 0 | 2022-01-27 | 2022-02-08 | 8 | 2022-03-16 | 2022-03-23 | 5
NST-263643 | SCE | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 336.331 | No | 2022-01-27 | 2022-01-27 | 0 | 2022-01-27 | 2022-02-08 | 8 | 2022-03-16 | 2022-03-23 | 5
NST-263653 | SCE | NEM | NEMA | Withdrawn | Solar PV | 238.972 | No | 2022-01-28 | 2022-01-28 | 0 | 2022-01-28 | 2022-02-03 | 4 | 2022-02-03 | 2022-02-04 | 1 |  | 2022-03-21 | 30
NST-263654 | SCE | NEM | NEMA | Withdrawn | Solar PV | 238.972 | No | 2022-01-28 | 2022-01-28 | 0 | 2022-01-28 | 2022-02-03 | 4 | 2022-02-03 | 2022-02-04 | 1 |  | 2022-03-21 | 30
NST-263655 | SCE | NEM | NEMA | Withdrawn | Solar PV | 159.315 | No | 2022-01-28 | 2022-01-28 | 0 | 2022-01-28 | 2022-02-03 | 4 | 2022-02-03 | 2022-02-04 | 1 |  | 2022-03-21 | 30
NST-263656 | SCE | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 88.508 | No | 2022-01-28 | 2022-01-28 | 0 | 2022-01-28 | 2022-02-08 | 7 | 2022-03-17 | 2022-03-25 | 6
NST-263657 | SCE | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 88.508 | No | 2022-01-28 | 2022-01-28 | 0 | 2022-01-28 | 2022-02-08 | 7 | 2022-03-17 | 2022-03-25 | 6
NST-263658 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 354.033 | No | 2022-01-28 | 2022-01-28 | 0 | 2022-01-28 | 2022-02-07 | 6 | 2022-02-07 | [6 empty] | 2022-03-15 | 25
NST-263659 | SCE | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 141.613 | No | 2022-01-28 | 2022-01-28 | 0 | 2022-01-28 | 2022-02-08 | 7 | 2022-03-16 | 2022-03-22 | 4
NST-263660 | SCE | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 141.613 | No | 2022-01-28 | 2022-01-28 | 0 | 2022-01-28 | 2022-02-08 | 7 | 2022-03-16 | 2022-03-22 | 4
NST-263701 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 66.933 | No | 2022-02-09 | 2022-02-09 | 0 | 2022-02-09 | [9 empty] | 2022-02-15 | 4
NST-263775 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 101.116 | No | 2022-01-28 | 2022-01-28 | 0 | 2022-01-28 | [9 empty] | 2022-02-02 | 3
NST-263786 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 35.2 | No | 2022-01-28 | 2022-01-28 | 0 | 2022-01-28 | 2022-02-02 | 3 | 2022-02-02 | 2022-02-08 | 4 | 2022-02-08 |  |  |  | 2022-02-14 | 4 | [49 empty] | 2022-02-14 |  | 17
NST-263802 | SCE | NEM | NEM-ST | Application Review In Progress |  | 1742.694 | No |  |  |  | 2022-01-28 | [62 empty] | 0
NST-263802 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 1742.694 | No | 2022-01-28 | 2022-01-28 | 0 | 2022-01-28 | [62 empty] | 0
NST-263840 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 537.126 | No | 2022-01-28 | 2022-01-28 | 0 | 2022-01-28 | 2022-02-02 | 3 | 2022-02-02 | [6 empty] | 2022-02-18 | 12
NST-263871 | SCE | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 76.41 | No | 2022-01-28 | 2022-01-28 | 0 | 2022-01-28 | 2022-02-02 | 3 | 2022-02-02 | [6 empty] | 2022-02-18 | 12
NST-263872 | SCE | NEM | NEM-ST | Application Review In Progress |  | 3509.296 | No |  |  |  | 2022-01-28 | [62 empty] | 0
NST-263872 | SCE | NEM | NEMA | NEMI - Equipment Change Submitted | Solar PV | 3509.296 | No | 2022-01-28 | 2022-01-28 | 0 | 2022-01-28 | [62 empty] | 0
NST-263891 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 331.528 | No | 2022-01-28 | 2022-01-28 | 0 | 2022-01-28 | 2022-02-02 | 3 | 2022-02-02 | [6 empty] | 2022-02-22 | 13
NST-264116 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 623.26 | No | 2022-02-03 | 2022-02-03 | 0 | 2022-02-03 | [9 empty] | 2022-02-08 | 3
NST-264129 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 234.234 | No | 2022-01-31 | 2022-01-31 | 0 | 2022-01-31 | [9 empty] | 2022-02-04 | 4
NST-264168 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 474.284 | No | 2022-01-31 | 2022-01-31 | 0 | 2022-01-31 | [9 empty] | 2022-02-07 | 5
NST-264178 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 50.584 | No | 2022-01-31 | 2022-01-31 | 0 | 2022-01-31 | [9 empty] | 2022-02-08 | 6
NST-264182 | SCE | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 481.258 | No | 2022-01-31 | 2022-01-31 | 0 | 2022-01-31 | [9 empty] | 2022-02-04 | 4
NST-264188 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 86.492 | No | 2022-01-31 | 2022-01-31 | 0 | 2022-01-31 | [9 empty] | 2022-02-08 | 6
NST-264195 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 131.106 | No | 2022-01-31 | 2022-01-31 | 0 | 2022-01-31 | [9 empty] | 2022-02-03 | 3
NST-264199 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 432.435 | No | 2022-01-31 | 2022-01-31 | 0 | 2022-01-31 | [9 empty] | 2022-02-03 | 3
NST-264208 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 481.258 | No | 2022-01-31 | 2022-01-31 | 0 | 2022-01-31 | [9 empty] | 2022-02-04 | 4
NST-264210 | SCE | NEM | NEMA | Withdrawn | Solar PV | 4688.326 | No | 2022-01-31 | 2022-01-31 | 0 | 2022-01-31 | 2022-02-02 | 2 | 2022-02-11 | 2022-02-16 | 3 |  | 2022-02-25 | 6
NST-264219 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 411.511 | No | 2022-01-31 | 2022-01-31 | 0 | 2022-01-31 | [9 empty] | 2022-02-03 | 3
NST-264225 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 327.814 | No | 2022-01-31 | 2022-01-31 | 0 | 2022-01-31 | [9 empty] | 2022-02-03 | 3
NST-264235 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 376.637 | No | 2022-01-31 | 2022-01-31 | 0 | 2022-01-31 | [9 empty] | 2022-02-03 | 3
NST-264241 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 411.511 | No | 2022-01-31 | 2022-01-31 | 0 | 2022-01-31 | [9 empty] | 2022-02-03 | 3
NST-264249 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 411.212 | No | 2022-01-31 | 2022-01-31 | 0 | 2022-01-31 | 2022-02-04 | 4 | 2022-02-04 | 2022-02-09 | 3 | 2022-02-15 |  |  |  | 2022-02-22 | 4
NST-264256 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 526.158 | No | 2022-01-31 | 2022-01-31 | 0 | 2022-01-31 | [9 empty] | 2022-02-04 | 4
NST-264267 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 334.788 | No | 2022-01-31 | 2022-01-31 | 0 | 2022-01-31 | [9 empty] | 2022-02-04 | 4
NST-264286 | SCE | NEM | NEMA | Withdrawn | Solar PV | 45.081 | No | 2022-01-31 | 2022-01-31 | 0 | 2022-01-31 | 2022-02-01 | 1 |  |  |  |  | 2022-03-11 | 27
NST-264288 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 81.669 | No | 2022-02-08 | 2022-02-08 | 0 | 2022-02-08 | 2022-02-11 | 3 | 2022-02-11 | [6 empty] | 2022-02-22 | 6
NST-264312 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 168.676 | No | 2022-01-31 | 2022-01-31 | 0 | 2022-01-31 | [9 empty] | 2022-02-03 | 3
NST-264313 | SCE | NEM | NEMA | Withdrawn | Solar PV | 840.033 | No | 2022-01-31 | 2022-01-31 | 0 | 2022-01-31 | 2022-03-02 | 21 |  |  |  |  | 2022-03-17 | 11
NST-264462 | SCE | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 209.243 | No | 2022-02-01 | 2022-02-01 | 0 | 2022-02-01 | [9 empty] | 2022-02-04 | 3
NST-264529 | SCE | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 308.28 | No | 2022-02-07 | 2022-02-07 | 0 | 2022-02-07 | 2022-02-14 | 5 | 2022-02-14 | [6 empty] | 2022-03-10 | 17
NST-264530 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 98.65 | No | 2022-02-07 | 2022-02-07 | 0 | 2022-02-07 | 2022-02-10 | 3 | 2022-02-10 | [6 empty] | 2022-03-10 | 19
NST-264532 | SCE | NEM | NEMA | Applicant Response Received. Pending SCE Engineer Review | Solar PV | 147.975 | No | 2022-02-07 | 2022-02-07 | 0 | 2022-02-07 | [9 empty] | 2022-02-10 | 3
NST-264534 | SCE | NEM | NEMA | Applicant Response Received. Pending SCE Engineer Review | Solar PV | 110.981 | No | 2022-02-07 | 2022-02-07 | 0 | 2022-02-07 | [9 empty] | 2022-02-10 | 3
NST-264536 | SCE | NEM | NEMA | Withdrawn | Solar PV | 110.981 | No | 2022-02-07 | 2022-02-07 | 0 | 2022-02-07 | 2022-02-11 | 4 |  |  |  |  | 2022-03-25 | 29
NST-264537 | SCE | NEM | NEMA | Withdrawn | Solar PV | 135.643 | No | 2022-02-07 | 2022-02-07 | 0 | 2022-02-07 | 2022-02-10 | 3 |  |  |  |  | 2022-03-25 | 30
NST-264538 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 86.319 | No | 2022-02-07 | 2022-02-07 | 0 | 2022-02-07 | 2022-02-11 | 4 | 2022-02-11 | [6 empty] | 2022-03-10 | 18
NST-264539 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 73.987 | No | 2022-02-07 | 2022-02-07 | 0 | 2022-02-07 | 2022-02-10 | 3 | 2022-02-10 | [6 empty] | 2022-03-10 | 19
NST-264540 | SCE | NEM | NEMA | Withdrawn | Solar PV | 86.319 | No | 2022-02-07 | 2022-02-07 | 0 | 2022-02-07 | 2022-02-10 | 3 |  |  |  |  | 2022-03-25 | 30
NST-264542 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 147.975 | No | 2022-02-07 | 2022-02-07 | 0 | 2022-02-07 | 2022-02-10 | 3 | 2022-02-10 | [6 empty] | 2022-03-10 | 19
NST-264620 | SCE | NEM | NEMA | NEMI - Application Returned. Pending Applicant Corrections | Solar PV | 457.356 | No | 2022-02-01 | 2022-02-01 | 0 | 2022-02-01 | 2022-02-08 | 5 | 2022-03-17 | 2022-03-21 | 2
NST-264623 | SCE | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 189.979 | No | 2022-02-01 | 2022-02-01 | 0 | 2022-02-01 | 2022-02-08 | 5 | 2022-03-17 | 2022-03-25 | 6
NST-264625 | SCE | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 210.909 | No | 2022-02-01 | 2022-02-01 | 0 | 2022-02-01 | 2022-02-08 | 5 | 2022-03-17 | 2022-03-25 | 6
NST-264627 | SCE | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 513.646 | No | 2022-02-01 | 2022-02-01 | 0 | 2022-02-01 | 2022-02-10 | 7
NST-264630 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 265.524 | No | 2022-02-01 | 2022-02-01 | 0 | 2022-02-01 | 2022-02-11 | 8 | 2022-02-11 | [6 empty] | 2022-03-17 | 23
NST-264634 | SCE | NEM | NEMA | NEMI - Application Returned 2nd Time. Pending Applicant Corrections | Solar PV | 371.51 | No | 2022-02-01 | 2022-02-01 | 0 | 2022-02-01 | 2022-02-11 | 8 | 2022-02-11 | 2022-03-30 | 32
NST-264636 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 203.569 | No | 2022-02-01 | 2022-02-01 | 0 | 2022-02-01 | 2022-02-11 | 8 | 2022-02-11 | [6 empty] | 2022-03-17 | 23
NST-264642 | SCE | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 531.049 | No | 2022-02-01 | 2022-02-01 | 0 | 2022-02-01 | 2022-02-11 | 8
NST-264903 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 31.536 | No | 2022-02-02 | 2022-02-02 | 0 | 2022-02-02 | [9 empty] | 2022-02-07 | 3 | [49 empty] | 2022-02-23 |  | 21
NST-264919 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 57.247 | No | 2022-02-02 | 2022-02-02 | 0 | 2022-02-02 | [9 empty] | 2022-02-08 | 4
NST-264968 | SCE | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 253.305 | No | 2022-02-02 | 2022-02-02 | 0 | 2022-02-02 | 2022-02-16 | 10 | 2022-02-28 | 2022-03-16 | 12
NST-264972 | SCE | NEM | NEMA | NEMI - Application Returned. Pending Applicant Corrections | Solar PV | 309.779 | No | 2022-02-02 | 2022-02-02 | 0 | 2022-02-02 | 2022-02-15 | 9 | 2022-03-23 | 2022-03-29 | 4
NST-264973 | SCE | NEM | NEMA | NEMI - Application Returned. Pending Applicant Corrections | Solar PV | 318.629 | No | 2022-02-02 | 2022-02-02 | 0 | 2022-02-02 | 2022-02-15 | 9 | 2022-03-23 | 2022-03-29 | 4
NST-264976 | SCE | NEM | NEMA | NEMI - Application Returned. Pending Applicant Corrections | Solar PV | 327.48 | No | 2022-02-02 | 2022-02-02 | 0 | 2022-02-02 | 2022-02-15 | 9 | 2022-03-23 | 2022-03-29 | 4
NST-264980 | SCE | NEM | NEMA | NEMI - Application Returned. Pending Applicant Corrections | Solar PV | 327.48 | No | 2022-02-02 | 2022-02-02 | 0 | 2022-02-02 | 2022-02-15 | 9 | 2022-03-23 | 2022-03-29 | 4
NST-264983 | SCE | NEM | NEMA | NEMI - Application Returned. Pending Applicant Corrections | Solar PV | 327.48 | No | 2022-02-02 | 2022-02-02 | 0 | 2022-02-02 | 2022-02-15 | 9 | 2022-03-23 | 2022-03-29 | 4
NST-264987 | SCE | NEM | NEMA | NEMI - Application Re-Submitted | Solar PV | 212.24 | No | 2022-02-02 | 2022-02-02 | 0 | 2022-02-02 | 2022-02-15 | 9 | 2022-03-24
NST-264992 | SCE | NEM | NEMA | NEMI - Application Re-Submitted | Solar PV | 212.24 | No | 2022-02-02 | 2022-02-02 | 0 | 2022-02-02 | 2022-02-15 | 9 | 2022-03-24
NST-264994 | SCE | NEM | NEMA | NEMI - Application Re-Submitted | Solar PV | 123.732 | No | 2022-02-02 | 2022-02-02 | 0 | 2022-02-02 | 2022-02-16 | 10 | 2022-03-24
NST-264997 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 256.674 | No | 2022-02-02 | 2022-02-02 | 0 | 2022-02-02 | 2022-02-15 | 9 | 2022-02-15 | [6 empty] | 2022-03-07 | 13
NST-265002 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 309.554 | No | 2022-02-02 | 2022-02-02 | 0 | 2022-02-02 | 2022-02-15 | 9 | 2022-02-15 | [6 empty] | 2022-03-07 | 13
NST-265006 | SCE | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 265.524 | No | 2022-02-02 | 2022-02-02 | 0 | 2022-02-02 | 2022-02-11 | 7 | 2022-03-17 | 2022-03-17 | 0
NST-265012 | SCE | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 354.033 | No | 2022-02-02 | 2022-02-02 | 0 | 2022-02-02 | 2022-02-11 | 7 | 2022-03-17 | 2022-03-17 | 0
NST-265016 | SCE | NEM | NEMA | NEMI - Application Returned 2nd Time. Pending Applicant Corrections | Solar PV | 189.979 | No | 2022-02-02 | 2022-02-02 | 0 | 2022-02-02 | 2022-02-15 | 9 | 2022-02-15 | 2022-03-31 | 30
NST-265021 | SCE | NEM | NEMA | NEMI - Application Returned 2nd Time. Pending Applicant Corrections | Solar PV | 147.761 | No | 2022-02-02 | 2022-02-02 | 0 | 2022-02-02 | 2022-02-15 | 9 | 2022-02-15 | 2022-03-31 | 30
NST-265024 | SCE | NEM | NEMA | NEMI - Application Returned 2nd Time. Pending Applicant Corrections | Solar PV | 386.994 | No | 2022-02-02 | 2022-02-02 | 0 | 2022-02-02 | 2022-02-15 | 9 | 2022-02-15 | 2022-03-31 | 30
NST-265027 | SCE | NEM | NEMA | NEMI - Application Returned 2nd Time. Pending Applicant Corrections | Solar PV | 84.435 | No | 2022-02-02 | 2022-02-02 | 0 | 2022-02-02 | 2022-02-15 | 9 | 2022-02-15 | 2022-03-31 | 30
NST-265028 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 87.566 | No | 2022-02-02 | 2022-02-02 | 0 | 2022-02-02 | [9 empty] | 2022-02-07 | 3
NST-265029 | SCE | NEM | NEMA | NEMI - Application Returned 2nd Time. Pending Applicant Corrections | Solar PV | 358.849 | No | 2022-02-02 | 2022-02-02 | 0 | 2022-02-02 | 2022-02-15 | 9 | 2022-02-15 | 2022-03-31 | 30
NST-265031 | SCE | NEM | NEMA | NEMI - Application Returned 2nd Time. Pending Applicant Corrections | Solar PV | 147.761 | No | 2022-02-02 | 2022-02-02 | 0 | 2022-02-02 | 2022-02-15 | 9 | 2022-02-15 | 2022-03-31 | 30
NST-265035 | SCE | NEM | NEMA | NEMI - Application Returned 2nd Time. Pending Applicant Corrections | Solar PV | 70.362 | No | 2022-02-02 | 2022-02-02 | 0 | 2022-02-02 | 2022-02-15 | 9 | 2022-02-15 | 2022-03-31 | 30
NST-265036 | SCE | NEM | NEMA | NEMI - Application Returned 2nd Time. Pending Applicant Corrections | Solar PV | 140.725 | No | 2022-02-02 | 2022-02-02 | 0 | 2022-02-02 | 2022-02-15 | 9 | 2022-02-15 | 2022-03-31 | 30
NST-265041 | SCE | NEM | NEMA | NEMI - Application Returned 2nd Time. Pending Applicant Corrections | Solar PV | 415.139 | No | 2022-02-02 | 2022-02-02 | 0 | 2022-02-02 | 2022-02-15 | 9 | 2022-02-15 | 2022-03-31 | 30
NST-265127 | SCE | NEM | NEM-ST | Application Review Complete |  | 987.579 | No | 2022-02-14 | 2022-02-14 | 0 | 2022-02-14 | [9 empty] | 2022-03-29 | 30 | 2022-03-29
NST-265127 | SCE | NEM | NEMA | SCE Engineer. Initial Review In Progress | Solar PV | 987.579 | No | 2022-02-02 | 2022-02-02 | 0 | 2022-02-02 | 2022-02-07 | 3 | 2022-02-14 | [6 empty] | 2022-03-29 | 30
NST-265217 | SCE | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 226.476 | No | 2022-03-09 | 2022-03-09 | 0 | 2022-03-09 | 2022-03-14 | 3 | 2022-03-18 | 2022-03-23 | 3
NST-265271 | SCE | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 593.005 | No | 2022-02-03 | 2022-02-03 | 0 | 2022-02-03 | 2022-02-15 | 8 | 2022-02-28 | 2022-03-08 | 6
NST-265279 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 177.016 | No | 2022-02-03 | 2022-02-03 | 0 | 2022-02-03 | 2022-02-16 | 9 | 2022-02-16 | [6 empty] | 2022-03-08 | 13
NST-265297 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 55.967 | No | 2022-02-03 | 2022-02-03 | 0 | 2022-02-03 | 2022-02-09 | 4 | 2022-02-09 | [6 empty] | 2022-02-17 | 6
NST-265299 | SCE | NEM | NEMA | NEMI - Application Re-Submitted | Solar PV | 194.718 | No | 2022-02-03 | 2022-02-03 | 0 | 2022-02-03 | 2022-02-16 | 9 | 2022-03-24
NST-265304 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 247.823 | No | 2022-02-03 | 2022-02-03 | 0 | 2022-02-03 | 2022-02-17 | 10 | 2022-02-17 | [6 empty] | 2022-03-09 | 13
NST-265311 | SCE | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 247.823 | No | 2022-02-03 | 2022-02-03 | 0 | 2022-02-03 | 2022-02-17 | 10 | 2022-03-01 | 2022-03-16 | 11
NST-265314 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 247.823 | No | 2022-02-03 | 2022-02-03 | 0 | 2022-02-03 | 2022-02-17 | 10 | 2022-02-17 | [6 empty] | 2022-03-10 | 14
NST-265323 | SCE | NEM | NEMA | NEMI - Application Returned 2nd Time. Pending Applicant Corrections | Solar PV | 327.48 | No | 2022-02-03 | 2022-02-03 | 0 | 2022-02-03 | 2022-02-08 | 3 | 2022-02-08 | 2022-03-31 | 35
NST-265326 | SCE | NEM | NEMA | NEMI - Application Returned 2nd Time. Pending Applicant Corrections | Solar PV | 256.674 | No | 2022-02-03 | 2022-02-03 | 0 | 2022-02-03 | 2022-02-08 | 3 | 2022-02-08 | 2022-03-31 | 35
NST-265330 | SCE | NEM | NEMA | NEMI - Application Returned 2nd Time. Pending Applicant Corrections | Solar PV | 256.674 | No | 2022-02-03 | 2022-02-03 | 0 | 2022-02-03 | 2022-02-08 | 3 | 2022-02-08 | 2022-03-31 | 35
NST-265484 | SCE | NEM | NEM-ST | Application Review In Progress |  | 1638.172 | No |  |  |  | 2022-02-07
NST-265484 | SCE | NEM | NEMA | Applicant Response Received. Pending SCE Engineer Review | Solar PV | 1638.172 | No | 2022-02-07 | 2022-02-07 | 0 | 2022-02-07
NST-265622 | SCE | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 312.5 | No | 2022-02-18 | 2022-02-18 | 0 | 2022-02-18 | 2022-02-28 | 5 | 2022-03-01 | 2022-03-11 | 8
NST-265644 | SCE | NEM | NEMA | NEMI - Load Justification Reviewed | Solar PV | 32.109 | No | 2022-02-04 | 2022-02-04 | 0 | 2022-02-04 | 2022-02-07 | 1 | 2022-02-15 | 2022-03-25 | 27 | 2022-03-25
NST-265677 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 192.663 | No | 2022-02-04 | 2022-02-04 | 0 | 2022-02-04 | 2022-02-14 | 6 | 2022-02-14 | [6 empty] | 2022-02-22 | 5
NST-265752 | SCE | NEM | NEM-ST | Supplemental Review In Progress |  | 1103.674 | No | 2022-02-10 | 2022-02-10 | 0 | 2022-02-10 | [9 empty] | 2022-03-02 | 13 | 2022-03-02 | 2022-03-10 | 6 |  |  | 2022-03-18
NST-265752 | SCE | NEM | NEMA | SCE Engineer. Initial Review Complete | Solar PV | 1103.674 | No | 2022-02-04 | 2022-02-04 | 0 | 2022-02-04 | 2022-02-09 | 3 | 2022-02-10 | [6 empty] | 2022-03-02 | 13
NST-266056 | SCE | NEM | NEMA | Withdrawn | Solar PV | 30.865 | No | 2022-02-07 | 2022-02-07 | 0 | 2022-02-07 | 2022-02-08 | 1 |  |  |  |  | 2022-02-24 | 11
NST-266110 | SCE | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 94.707 | No | 2022-02-07 | 2022-02-07 | 0 | 2022-02-07 | 2022-02-08 | 1 | 2022-02-08 | 2022-02-14 | 4 | 2022-02-14 |  |  |  | 2022-02-18 | 4
NST-266135 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 86.998 | No | 2022-02-07 | 2022-02-07 | 0 | 2022-02-07 | 2022-02-11 | 4 | 2022-02-11 | [6 empty] | 2022-02-18 | 5
NST-266160 | SCE | NEM | NEMA | Applicant Response Received. Pending SCE Engineer Review | Solar PV | 46.527 | No | 2022-02-07 | 2022-02-07 | 0 | 2022-02-07 | 2022-02-11 | 4 | 2022-02-11 | 2022-02-28 | 10 | 2022-03-06 |  |  |  | 2022-03-21 | 10
NST-266189 | SCE | NEM | NEMA | Applicant Response Received. Pending SCE Engineer Review | Solar PV | 198.604 | No | 2022-02-07 | 2022-02-07 | 0 | 2022-02-07 | [9 empty] | 2022-03-05 | 18
NST-266199 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 183.302 | No | 2022-02-07 | 2022-02-07 | 0 | 2022-02-07 | [9 empty] | 2022-02-11 | 4
NST-266201 | SCE | NEM | NEMA | NEMI - Sent to Engineering | Solar PV | 163.642 | No | 2022-02-07 | 2022-02-07 | 0 | 2022-02-07 | [9 empty] | 2022-03-05 | 18
NST-266201 | SCE | NEM | NEM-ST | Application Review In Progress |  | 163.642 | No |  |  |  | 2022-02-07
NST-266254 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 92.799 | No | 2022-02-07 | 2022-02-07 | 0 | 2022-02-07 | [9 empty] | 2022-02-11 | 4
NST-266290 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 159.393 | No | 2022-02-07 | 2022-02-07 | 0 | 2022-02-07 | 2022-02-09 | 2 | 2022-02-09 | [6 empty] | 2022-03-03 | 15
NST-266300 | SCE | NEM | NEMA | Withdrawn | Solar PV | 60.366 | No | 2022-02-07 | 2022-02-07 | 0 | 2022-02-07 | 2022-02-11 | 4 |  |  |  |  | 2022-03-01 | 11
NST-266323 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 37.759 | No | 2022-02-07 | 2022-02-07 | 0 | 2022-02-07 | 2022-02-08 | 1 | 2022-02-08 | [6 empty] | 2022-02-15 | 5
NST-266330 | SCE | NEM | NEMA | Withdrawn | Solar PV | 30.576 | No | 2022-02-07 | 2022-02-07 | 0 | 2022-02-07 | 2022-02-08 | 1 |  |  |  |  | 2022-02-24 | 11
NST-266339 | SCE | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 46.279 | No | 2022-02-07 | 2022-02-07 | 0 | 2022-02-07 | [9 empty] | 2022-02-08 | 1
NST-266340 | SCE | NEM | NEMA | Withdrawn | Solar PV | 60.011 | No | 2022-02-07 | 2022-02-07 | 0 | 2022-02-07 | 2022-02-11 | 4 |  |  |  |  | 2022-03-01 | 11
NST-266355 | SCE | NEM | NEMA | Withdrawn | Solar PV | 276.281 | No | 2022-02-07 | 2022-02-07 | 0 | 2022-02-07 | 2022-02-09 | 2 |  |  |  |  | 2022-02-25 | 11
NST-266510 | SCE | NEM | NEMA | Withdrawn | Solar PV | 85.303 | No | 2022-02-08 | 2022-02-08 | 0 | 2022-02-08 | 2022-02-11 | 3 | 2022-02-14 | 2022-02-18 | 4 |  | 2022-03-01 | 6
NST-266632 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 75.299 | No | 2022-02-08 | 2022-02-08 | 0 | 2022-02-08 | [9 empty] | 2022-02-14 | 4
NST-266745 | SCE | NEM | NEM-ST | Application Review In Progress |  | 6629.28 | No | 2022-03-11 | 2022-03-11 | 0 | 2022-03-11 | 2022-03-31 | 13
NST-266745 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 6629.28 | No | 2022-02-08 | 2022-02-08 | 0 | 2022-02-08 | 2022-02-11 | 3 | 2022-03-02 | 2022-03-02 | 0 | 2022-03-11
NST-266747 | SCE | NEM | NEM Aggregation | Application Review In Progress |  | 4547.958 | No |  |  |  | 2022-02-14
NST-266747 | SCE | NEM | NEMA | SCE Engineer. Detail Study In Progress | Solar PV | 4547.958 | No | 2022-02-08 | 2022-02-08 | 0 | 2022-02-08 | 2022-02-12 | 3 | 2022-02-14
NST-266754 | SCE | NEM | NEMA | Withdrawn | Solar PV | 247.755 | No | 2022-02-11 | 2022-02-11 | 0 | 2022-02-11 | 2022-02-17 | 4 |  |  |  |  | 2022-03-07 | 11
NST-266811 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 53.279 | No | 2022-02-09 | 2022-02-09 | 0 | 2022-02-09 | [9 empty] | 2022-02-15 | 4
NST-266813 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 188.248 | No | 2022-02-09 | 2022-02-09 | 0 | 2022-02-09 | [9 empty] | 2022-02-15 | 4
NST-266814 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 71.953 | No | 2022-02-09 | 2022-02-09 | 0 | 2022-02-09 | [9 empty] | 2022-02-15 | 4
NST-266815 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 45.902 | No | 2022-02-09 | 2022-02-09 | 0 | 2022-02-09 | [9 empty] | 2022-02-10 | 1
NST-266818 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 54.918 | No | 2022-02-09 | 2022-02-09 | 0 | 2022-02-09 | [9 empty] | 2022-02-14 | 3
NST-266971 | SCE | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 85.511 | No | 2022-02-14 | 2022-02-14 | 0 | 2022-02-14 | 2022-02-18 | 4 | 2022-02-18 | [6 empty] | 2022-03-03 | 8
NST-267007 | SCE | NEM | NEMA | NEMI - Sent to Engineering | Solar PV | 34.954 | No | 2022-02-09 | 2022-02-09 | 0 | 2022-02-09 | [9 empty] | 2022-02-10 | 1
NST-267038 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 31.583 | No | 2022-02-09 | 2022-02-09 | 0 | 2022-02-09 | [9 empty] | 2022-02-15 | 4 | [49 empty] | 2022-03-09 |  | 28
NST-267276 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 78.919 | No | 2022-02-10 | 2022-02-10 | 0 | 2022-02-10 | 2022-02-14 | 2 | 2022-02-14 | 2022-03-01 | 10 | 2022-03-07 |  |  |  | 2022-03-14 | 5
NST-267513 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 67.644 | No | 2022-02-11 | 2022-02-11 | 0 | 2022-02-11 | [9 empty] | 2022-02-17 | 4
NST-267593 | SCE | NEM | NEMA | NEMI - Sent to Engineering | Solar PV | 43.443 | No | 2022-02-11 | 2022-02-11 | 0 | 2022-02-11 | 2022-02-14 | 1 | 2022-02-14 | [6 empty] | 2022-03-31 | 31
NST-267666 | SCE | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 49.072 | No | 2022-02-11 | 2022-02-11 | 0 | 2022-02-11 | 2022-02-18 | 5 | 2022-02-22 | 2022-03-08 | 10 | 2022-03-11
NST-267668 | SCE | NEM | NEMA | NEMI - Load Justification Reviewed | Solar PV | 49.072 | No | 2022-02-11 | 2022-02-11 | 0 | 2022-02-11 | 2022-02-18 | 5 | 2022-02-22 | 2022-03-08 | 10 | 2022-03-11
NST-267676 | SCE | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 49.072 | No | 2022-02-11 | 2022-02-11 | 0 | 2022-02-11 | 2022-02-18 | 5 | 2022-02-22 | 2022-03-17 | 17
NST-267677 | SCE | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 274.196 | No | 2022-02-11 | 2022-02-11 | 0 | 2022-02-11 | 2022-02-24 | 8 | 2022-02-24
NST-267680 | SCE | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 194.538 | No | 2022-02-11 | 2022-02-11 | 0 | 2022-02-11 | 2022-02-25 | 9
NST-267681 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 61.475 | No | 2022-02-11 | 2022-02-11 | 0 | 2022-02-11 | [9 empty] | 2022-02-17 | 4
NST-267683 | SCE | NEM | NEMA | NEMI - Application Re-Submitted | Solar PV | 256.674 | No | 2022-02-11 | 2022-02-11 | 0 | 2022-02-11 | 2022-02-23 | 7 | 2022-03-30
NST-267686 | SCE | NEM | NEMA | NEMI - Application Returned 2nd Time. Pending Applicant Corrections | Solar PV | 6446.997 | No | 2022-02-11 | 2022-02-11 | 0 | 2022-02-11
NST-267686 | SCE | NEM | NEM-ST | Application Review In Progress |  | 6446.997 | No | 2022-02-11 | 2022-02-11 | 0 | 2022-02-11 | 2022-03-07 | 15 | 2022-03-22
NST-267822 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 78.895 | No | 2022-02-11 | 2022-02-11 | 0 | 2022-02-11 | 2022-02-17 | 4 | 2022-02-17 | [6 empty] | 2022-03-16 | 18
NST-268062 | SCE | NEM | NEMA | Withdrawn | Solar PV | 54.782 | No | 2022-02-14 | 2022-02-14 | 0 | 2022-02-14 | 2022-02-18 | 4 |  |  |  |  | 2022-03-08 | 11
NST-268092 | SCE | NEM | NEMA | Withdrawn | Solar PV | 5000 | No | 2022-02-14 | 2022-02-14 | 0 | 2022-02-14 | 2022-02-24 | 7 |  |  |  |  | 2022-03-11 | 11
NST-268292 | SCE | NEM | NEMA | NEMI - 1.0 Expansion Ineligible | Solar PV | 186.096 | No | 2022-02-15 | 2022-02-15 | 0 | 2022-02-15
NST-268293 | SCE | NEM | NEMA | NEMI - 1.0 Expansion Ineligible | Solar PV | 219.11 | No | 2022-02-15 | 2022-02-15 | 0 | 2022-02-15
NST-268294 | SCE | NEM | NEMA | NEMI - 1.0 Expansion Ineligible | Solar PV | 163.825 | No | 2022-02-15 | 2022-02-15 | 0 | 2022-02-15
NST-268298 | SCE | NEM | NEMA | NEMI - 1.0 Expansion Ineligible | Solar PV | 391.957 | No | 2022-02-15 | 2022-02-15 | 0 | 2022-02-15
NST-268299 | SCE | NEM | NEMA | NEMI - 1.0 Expansion Ineligible | Solar PV | 606.768 | No | 2022-02-15 | 2022-02-15 | 0 | 2022-02-15
NST-268300 | SCE | NEM | NEMA | NEMI - 1.0 Expansion Ineligible | Solar PV | 410.201 | No | 2022-02-15 | 2022-02-15 | 0 | 2022-02-15
NST-268304 | SCE | NEM | NEMA | NEMI - 1.0 Expansion Ineligible | Solar PV | 547.234 | No | 2022-02-15 | 2022-02-15 | 0 | 2022-02-15
NST-268308 | SCE | NEM | NEMA | NEMI - 1.0 Expansion Ineligible | Solar PV | 126.273 | No | 2022-02-15 | 2022-02-15 | 0 | 2022-02-15
NST-268309 | SCE | NEM | NEMA | NEMI - 1.0 Expansion Ineligible | Solar PV | 203.724 | No | 2022-02-15 | 2022-02-15 | 0 | 2022-02-15
NST-268310 | SCE | NEM | NEMA | NEMI - Sent to Engineering | Solar PV | 378.284 | No | 2022-02-15 | 2022-02-15 | 0 | 2022-02-15 | [9 empty] | 2022-02-23 | 5
NST-268319 | SCE | NEM | NEMA | Applicant Response Received. Pending SCE Engineer Review | Solar PV | 39.064 | No | 2022-02-15 | 2022-02-15 | 0 | 2022-02-15 | 2022-02-16 | 1 | 2022-02-16 | 2022-03-11 | 16 | 2022-03-14 |  |  |  | 2022-03-17 | 3
NST-268369 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 36.544 | No | 2022-02-15 | 2022-02-15 | 0 | 2022-02-15 | [9 empty] | 2022-02-16 | 1 | [49 empty] | 2022-03-23 |  | 36
NST-268514 | SCE | NEM | NEMA | NEMI - 1.0 Expansion Ineligible | Solar PV | 268.966 | No | 2022-02-16 | 2022-02-16 | 0 | 2022-02-16
NST-268515 | SCE | NEM | NEMA | NEMI - 1.0 Expansion Ineligible | Solar PV | 569.366 | No | 2022-02-16 | 2022-02-16 | 0 | 2022-02-16
NST-268516 | SCE | NEM | NEMA | NEMI - 1.0 Expansion Ineligible | Solar PV | 253.254 | No | 2022-02-16 | 2022-02-16 | 0 | 2022-02-16
NST-268517 | SCE | NEM | NEMA | NEMI - 1.0 Expansion Ineligible | Solar PV | 226.908 | No | 2022-02-16 | 2022-02-16 | 0 | 2022-02-16
NST-268556 | SCE | NEM | NEMA | NEMI - Pending Final NEM Review | Solar PV | 255.821 | No | 2022-02-16 | 2022-02-16 | 0 | 2022-02-16 | [9 empty] | 2022-02-23 | 4
NST-268657 | SCE | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 153.692 | No | 2022-02-16 | 2022-02-16 | 0 | 2022-02-16 | 2022-02-25 | 6
NST-268662 | SCE | NEM | NEMA | Applicant Response Received. Pending SCE Engineer Review | Solar PV | 502.597 | No | 2022-02-16 | 2022-02-16 | 0 | 2022-02-16 | [9 empty] | 2022-02-25 | 6
NST-268664 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 681.986 | No | 2022-02-16 | 2022-02-16 | 0 | 2022-02-16 | 2022-03-01 | 8 | 2022-03-01 | [6 empty] | 2022-03-07 | 4
NST-268789 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 456.123 | No | 2022-02-16 | 2022-02-16 | 0 | 2022-02-16 | 2022-02-23 | 4 | 2022-02-23 | [6 empty] | 2022-03-07 | 8
NST-268930 | SCE | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 397.561 | No | 2022-02-17 | 2022-02-17 | 0 | 2022-02-17 | 2022-02-24 | 4 | [6 empty] | 2022-03-11
NST-268948 | SCE | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 446.385 | No | 2022-02-17 | 2022-02-17 | 0 | 2022-02-17 | 2022-02-24 | 4 | 2022-02-24
NST-268958 | SCE | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 648.653 | No | 2022-02-17 | 2022-02-17 | 0 | 2022-02-17 | 2022-02-24 | 4
NST-268972 | SCE | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 495.208 | No | 2022-02-17 | 2022-02-17 | 0 | 2022-02-17 | 2022-02-24 | 4 | 2022-02-24
NST-268975 | SCE | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 404.536 | No | 2022-02-17 | 2022-02-17 | 0 | 2022-02-17 | 2022-02-24 | 4 | 2022-02-24
NST-269014 | SCE | NEM | NEMA | NEMI - Application Returned 2nd Time. Pending Applicant Corrections | Solar PV | 202.562 | No | 2022-03-09 | 2022-03-09 | 0 | 2022-03-09 | 2022-03-14 | 3 | 2022-03-14 | 2022-03-24 | 8
NST-269105 | SCE | NEM | NEMA | NEMI - Application Re-Submitted | Solar PV | 56.213 | No | 2022-02-17 | 2022-02-17 | 0 | 2022-02-17 | 2022-02-24 | 4 | 2022-02-24
NST-269116 | SCE | NEM | NEMA | Withdrawn | Solar PV | 244.772 | No | 2022-02-18 | 2022-02-18 | 0 | 2022-02-18 | 2022-02-24 | 3 |  |  |  |  | 2022-03-11 | 11
NST-269156 | SCE | NEM | NEMA | NEMI - Application Re-Submitted | Solar PV | 265.266 | No | 2022-02-17 | 2022-02-17 | 0 | 2022-02-17 | 2022-02-24 | 4 | 2022-02-24
NST-269172 | SCE | NEM | NEMA | Withdrawn | Solar PV | 31.83 | No | 2022-02-17 | 2022-02-17 | 0 | 2022-02-17 | 2022-02-25 | 5 |  |  |  |  | 2022-03-14 | 11
NST-269193 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 1451.615 | No | 2022-02-17 | 2022-02-17 | 0 | 2022-02-17 | 2022-02-28 | 6 | 2022-03-10
NST-269674 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 306.535 | No | 2022-02-21 | 2022-02-21 | 0 | 2022-02-21 | 2022-02-28 | 4 | 2022-02-28 | [6 empty] | 2022-03-17 | 13
NST-269713 | SCE | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 220.24 | No | 2022-02-21 | 2022-02-21 | 0 | 2022-02-21 | [9 empty] | 2022-03-01 | 5
NST-269714 | SCE | NEM | NEMA | NEMI - Application Returned. Pending Applicant Corrections | Solar PV | 627.728 | No | 2022-02-21 | 2022-02-21 | 0 | 2022-02-21 | [9 empty] | 2022-02-28 | 4
NST-269929 | SCE | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 82.359 | No | 2022-02-21 | 2022-02-21 | 0 | 2022-02-21 | 2022-02-26 | 3
NST-269977 | SCE | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 47.891 | No | 2022-02-22 | 2022-02-22 | 0 | 2022-02-22 | 2022-03-01 | 5
NST-270218 | SCE | NEM | NEMA | NEMI - Application Re-Submitted | Solar PV | 2024.764 | No | 2022-02-22 | 2022-02-22 | 0 | 2022-02-22 | 2022-03-14 | 14 | 2022-03-22 | 2022-03-28 | 4 | 2022-03-29
NST-270403 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 35.284 | No | 2022-02-23 | 2022-02-23 | 0 | 2022-02-23 | 2022-03-01 | 4 | 2022-03-01 | [6 empty] | 2022-03-01 | 0
NST-270431 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 291.162 | No | 2022-02-23 | 2022-02-23 | 0 | 2022-02-23 | 2022-03-01 | 4 | 2022-03-01 | [6 empty] | 2022-03-07 | 4
NST-270478 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 67.562 | No | 2022-02-23 | 2022-02-23 | 0 | 2022-02-23 | 2022-03-03 | 6 | 2022-03-03 | [6 empty] | 2022-03-28 | 17
NST-270682 | SCE | NEM | NEMA | NEMI - Application Re-Submitted | Solar PV | 186.096 | No | 2022-02-24 | 2022-02-24 | 0 | 2022-02-24 | 2022-03-09 | 9 | 2022-03-09
NST-270683 | SCE | NEM | NEMA | NEMI - Application Re-Submitted | Solar PV | 219.11 | No | 2022-02-24 | 2022-02-24 | 0 | 2022-02-24 | 2022-03-09 | 9 | 2022-03-09
NST-270684 | SCE | NEM | NEMA | NEMI - Application Re-Submitted | Solar PV | 163.825 | No | 2022-02-24 | 2022-02-24 | 0 | 2022-02-24 | 2022-03-09 | 9 | 2022-03-09
NST-270686 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 391.957 | No | 2022-02-24 | 2022-02-24 | 0 | 2022-02-24 | [9 empty] | 2022-03-11 | 11
NST-270687 | SCE | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 606.768 | No | 2022-02-24 | 2022-02-24 | 0 | 2022-02-24 | 2022-03-11 | 11
NST-270688 | SCE | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 410.201 | No | 2022-02-24 | 2022-02-24 | 0 | 2022-02-24 | 2022-03-11 | 11
NST-270690 | SCE | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 268.966 | No | 2022-02-24 | 2022-02-24 | 0 | 2022-02-24 | 2022-03-09 | 9
NST-270691 | SCE | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 569.366 | No | 2022-02-24 | 2022-02-24 | 0 | 2022-02-24 | 2022-03-09 | 9
NST-270692 | SCE | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 253.254 | No | 2022-02-24 | 2022-02-24 | 0 | 2022-02-24 | 2022-03-09 | 9
NST-270693 | SCE | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 226.908 | No | 2022-02-24 | 2022-02-24 | 0 | 2022-02-24 | 2022-03-09 | 9
NST-270694 | SCE | NEM | NEMA | NEMI - Application Re-Submitted | Solar PV | 547.234 | No | 2022-02-24 | 2022-02-24 | 0 | 2022-02-24 | 2022-03-09 | 9 | 2022-03-22
NST-270695 | SCE | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 126.97 | No | 2022-02-24 | 2022-02-24 | 0 | 2022-02-24 | 2022-03-09 | 9 | 2022-03-09 | [6 empty] | 2022-03-25 | 12
NST-270696 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 203.724 | No | 2022-02-24 | 2022-02-24 | 0 | 2022-02-24 | [9 empty] | 2022-03-11 | 11
NST-270699 | SCE | NEM | NEMA | Applicant Response Received. Pending SCE Engineer Review | Solar PV | 79.882 | No | 2022-02-24 | 2022-02-24 | 0 | 2022-02-24 | [9 empty] | 2022-03-04 | 6
NST-270702 | SCE | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 98 | No | 2022-02-24 | 2022-02-24 | 0 | 2022-02-24 | 2022-03-02 | 4
NST-270796 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 149.615 | No | 2022-02-24 | 2022-02-24 | 0 | 2022-02-24 | [9 empty] | 2022-03-02 | 4
NST-270809 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 156.739 | No | 2022-02-24 | 2022-02-24 | 0 | 2022-02-24 | [9 empty] | 2022-03-01 | 3
NST-270841 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 206.611 | No | 2022-02-24 | 2022-02-24 | 0 | 2022-02-24 | 2022-03-02 | 4 | 2022-03-02 | [6 empty] | 2022-03-21 | 13
NST-270853 | SCE | NEM | NEMA | NEMI - Application Re-Submitted | Solar PV | 427.471 | No | 2022-02-25 | 2022-02-25 | 0 | 2022-02-25 | 2022-03-02 | 3 | 2022-03-15 | 2022-03-21 | 4 | 2022-03-28
NST-270936 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 597.604 | No | 2022-02-24 | 2022-02-24 | 0 | 2022-02-24 | 2022-03-02 | 4 | 2022-03-02 | [6 empty] | 2022-03-22 | 14
NST-270951 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 78.772 | No | 2022-02-24 | 2022-02-24 | 0 | 2022-02-24 | 2022-03-02 | 4 | 2022-03-02 | [6 empty] | 2022-03-15 | 9
NST-270958 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 95.804 | No | 2022-02-24 | 2022-02-24 | 0 | 2022-02-24 | [9 empty] | 2022-03-02 | 4
NST-270959 | SCE | NEM | NEMA | Withdrawn | Solar PV | 77.303 | No | 2022-02-24 | 2022-02-24 | 0 | 2022-02-24 | 2022-03-02 | 4 | 2022-03-02 | 2022-03-09 | 5 |  | 2022-03-17 | 6
NST-270961 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 168.642 | No | 2022-02-24 | 2022-02-24 | 0 | 2022-02-24 | 2022-03-02 | 4 | 2022-03-02 | [6 empty] | 2022-03-15 | 9
NST-270966 | SCE | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 144.879 | No | 2022-02-24 | 2022-02-24 | 0 | 2022-02-24 | 2022-03-02 | 4 | 2022-03-02 | 2022-03-08 | 4 | 2022-03-15 |  |  |  | 2022-03-24 | 7
NST-271062 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 488.233 | No | 2022-02-25 | 2022-02-25 | 0 | 2022-02-25 | 2022-03-03 | 4 | 2022-03-03 | [6 empty] | 2022-03-21 | 12
NST-271069 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 488.233 | No | 2022-02-25 | 2022-02-25 | 0 | 2022-02-25 | [9 empty] | 2022-03-03 | 4
NST-271081 | SCE | NEM | NEMA | Withdrawn | Solar PV | 3412.645 | No | 2022-02-25 | 2022-02-25 | 0 | 2022-02-25 | 2022-03-02 | 3 |  |  |  |  | 2022-03-17 | 11
NST-271090 | SCE | NEM | NEM-ST | Application Review In Progress |  | 2443.71 | No | 2022-03-15 | 2022-03-15 | 0 | 2022-03-15 | 2022-03-29 | 10
NST-271090 | SCE | NEM | NEMA | NEMI - Application Returned. Pending Applicant Corrections | Solar PV | 2443.71 | No | 2022-02-25 | 2022-02-25 | 0 | 2022-02-25 | 2022-03-02 | 3 | 2022-03-15 | 2022-03-29 | 10
NST-271208 | SCE | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 253.652 | No | 2022-02-25 | 2022-02-25 | 0 | 2022-02-25 | 2022-03-02 | 3
NST-271293 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 31.235 | No | 2022-02-25 | 2022-02-25 | 0 | 2022-02-25 | [9 empty] | 2022-02-28 | 1 | [49 empty] | 2022-02-28 |  | 3
NST-271349 | SCE | NEM | NEMA | Withdrawn | Solar PV | 134.936 | No | 2022-02-27 | 2022-02-27 | 0 | 2022-02-27 | 2022-03-04 | 4 |  |  |  |  | 2022-03-21 | 11
NST-271351 | SCE | NEM | NEMA | Withdrawn | Solar PV | 53.421 | No | 2022-02-27 | 2022-02-27 | 0 | 2022-02-27 | 2022-03-04 | 4 | 2021-03-15 | 2022-03-21 | 253 |  | 2022-03-29 | 6
NST-271388 | SCE | NEM | NEMA | NEMI - Equipment Change Submitted | Solar PV | 358.491 | No | 2022-02-28 | 2022-02-28 | 0 | 2022-02-28 | [9 empty] | 2022-03-04 | 4
NST-271576 | SCE | NEM | NEMA | NEMI - Returned from Engineering | Solar PV | 57.914 | No | 2022-02-28 | 2022-02-28 | 0 | 2022-02-28 | 2022-03-03 | 3 | 2022-03-03 | [6 empty] | 2022-03-10 | 5
NST-271583 | SCE | NEM | NEM-ST | Application Review In Progress |  | 1092.931 | No |  |  |  | 2022-03-04
NST-271583 | SCE | NEM | NEMA | SCE Engineer Assigned. Pending Technical Review | Solar PV | 1092.931 | No | 2022-03-04 | 2022-03-04 | 0 | 2022-03-04
NST-271588 | SCE | NEM | NEMA | NEMI - Application Re-Submitted | Solar PV | 50.062 | No | 2022-02-28 | 2022-02-28 | 0 | 2022-02-28 | 2022-03-05 | 4 | 2022-03-30
NST-271719 | SCE | NEM | NEMA | SCE Engineer Assigned. Pending Technical Review | Solar PV | 251.102 | No | 2022-03-01 | 2022-03-01 | 0 | 2022-03-01 | [9 empty] | 2022-03-07 | 4
NST-271723 | SCE | NEM | NEMA | NEMI - Application Returned. Pending Applicant Corrections | Solar PV | 589.638 | No | 2022-03-01 | 2022-03-01 | 0 | 2022-03-01 | 2022-03-03 | 2 | 2022-03-17 | 2022-03-22 | 3
NST-271725 | SCE | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 888.432 | No | 2022-03-01 | 2022-03-01 | 0 | 2022-03-01 | 2022-03-06 | 3
NST-271729 | SCE | NEM | NEMA | SCE Engineer Assigned. Pending Technical Review | Solar PV | 444.758 | No | 2022-03-01 | 2022-03-01 | 0 | 2022-03-01 | [9 empty] | 2022-03-07 | 4
NST-271734 | SCE | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 742.106 | No | 2022-03-01 | 2022-03-01 | 0 | 2022-03-01 | 2022-03-07 | 4
NST-271987 | SCE | NEM | NEMA | NEMI - Returned from Engineering | Solar PV | 167.557 | No | 2022-03-01 | 2022-03-01 | 0 | 2022-03-01 | [9 empty] | 2022-03-07 | 4
NST-271994 | SCE | NEM | NEMA | NEMI - Application Re-Submitted | Solar PV | 52.487 | No | 2022-03-01 | 2022-03-01 | 0 | 2022-03-01 | 2022-03-10 | 7 | 2022-03-10 | 2022-03-28 | 12 | 2022-03-31
NST-272010 | SCE | NEM | NEMA | Withdrawn | Solar PV | 53.421 | No | 2022-03-01 | 2022-03-01 | 0 | 2022-03-01 | 2022-03-04 | 3 | 2021-03-15 | 2021-03-15 | 0 |  | 2022-03-21 | 11
NST-272020 | SCE | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 147.761 | No | 2022-03-02 | 2022-03-02 | 0 | 2022-03-02 | 2022-03-15 | 9 | 2022-03-15
NST-272021 | SCE | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 91.471 | No | 2022-03-02 | 2022-03-02 | 0 | 2022-03-02 | 2022-03-15 | 9 | 2022-03-15
NST-272051 | SCE | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 74.595 | No | 2022-03-02 | 2022-03-02 | 0 | 2022-03-02 | 2022-03-09 | 5
NST-272056 | SCE | NEM | NEMA | Withdrawn | Solar PV | 1367.262 | No | 2022-03-02 | 2022-03-02 | 0 | 2022-03-02 | 2022-03-08 | 4 |  |  |  |  | 2022-03-23 | 11
NST-272098 | SCE | NEM | NEM-ST | Application Review In Progress |  | 2409.557 | No |  |  |  | 2022-03-16
NST-272098 | SCE | NEM | NEMA | SCE Engineer Assigned. Pending Technical Review | Solar PV | 2409.557 | No | 2022-03-03 | 2022-03-03 | 0 | 2022-03-03 | 2022-03-08 | 3 | 2022-03-16
NST-272174 | SCE | NEM | NEMA | Withdrawn | Solar PV | 33.27 | No | 2022-03-02 | 2022-03-02 | 0 | 2022-03-02 | 2022-03-08 | 4 | 2022-03-11 | 2022-03-21 | 6 |  | 2022-03-29 | 6
NST-272209 | SCE | NEM | NEMA | NEMI - Application Returned. Pending Applicant Corrections | Solar PV | 245.695 | No | 2022-03-22 | 2022-03-22 | 0 | 2022-03-22 | 2022-03-25 | 3
NST-272257 | SCE | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 31.175 | No | 2022-03-03 | 2022-03-03 | 0 | 2022-03-03 | 2022-03-11 | 6
NST-272356 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 400 | No | 2022-03-03 | 2022-03-03 | 0 | 2022-03-03 | [9 empty] | 2022-03-09 | 4 | [49 empty] | 2022-03-09 |  | 6
NST-272397 | SCE | NEM | NEMA | NEMI - Sent to Engineering | Solar PV | 46.76 | No | 2022-03-03 | 2022-03-03 | 0 | 2022-03-03 | 2022-03-10 | 5 | 2022-03-21 | [6 empty] | 2022-03-23 | 2
NST-272441 | SCE | NEM | NEMA | NEMI - Sent to Engineering | Solar PV | 42.29 | No | 2022-03-03 | 2022-03-03 | 0 | 2022-03-03 | 2022-03-10 | 5 | 2022-03-10 | [6 empty] | 2022-03-23 | 9
NST-272571 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 37.094 | No | 2022-03-03 | 2022-03-03 | 0 | 2022-03-03 | 2022-03-04 | 1 | 2022-03-04 | [6 empty] | 2022-03-24 | 14
NST-272602 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 58.236 | No | 2022-03-03 | 2022-03-03 | 0 | 2022-03-03 | 2022-03-09 | 4 | 2022-03-09 | [6 empty] | 2022-03-23 | 10
NST-272612 | SCE | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 110.039 | No | 2022-03-03 | 2022-03-03 | 0 | 2022-03-03 | 2022-03-10 | 5
NST-272689 | SCE | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 42.726 | No | 2022-03-04 | 2022-03-04 | 0 | 2022-03-04 | [9 empty] | 2022-03-04 | 0
NST-272718 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 187.118 | No | 2022-03-07 | 2022-03-07 | 0 | 2022-03-07 | [9 empty] | 2022-03-11 | 4
NST-272866 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 121.013 | No | 2022-03-07 | 2022-03-07 | 0 | 2022-03-07 | [9 empty] | 2022-03-11 | 4
NST-272900 | SCE | NEM | NEMA | NEMI - Application Returned. Pending Applicant Corrections | Solar PV | 723.631 | No | 2022-03-16 | 2022-03-16 | 0 | 2022-03-16 | 2022-03-23 | 5
NST-272937 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 300.54 | No | 2022-03-04 | 2022-03-04 | 0 | 2022-03-04 | [9 empty] | 2022-03-17 | 9
NST-273001 | SCE | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 73.071 | No | 2022-03-06 | 2022-03-06 | 0 | 2022-03-06 | [9 empty] | 2022-03-16 | 7
NST-273076 | SCE | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 91.66 | No | 2022-03-07 | 2022-03-07 | 0 | 2022-03-07 | 2022-03-15 | 6
NST-273265 | SCE | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 94.359 | No | 2022-03-07 | 2022-03-07 | 0 | 2022-03-07 | [9 empty] | 2022-03-11 | 4
NST-273629 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 536.515 | No | 2022-03-08 | 2022-03-08 | 0 | 2022-03-08 | 2022-03-14 | 4 | 2022-03-14 | [6 empty] | 2022-03-23 | 7
NST-273659 | SCE | NEM | NEMA | NEMI - Application Re-Submitted | Solar PV | 323.863 | No | 2022-03-08 | 2022-03-08 | 0 | 2022-03-08 | 2022-03-14 | 4 | 2022-03-28
NST-273733 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 60.366 | No | 2022-03-08 | 2022-03-08 | 0 | 2022-03-08 | 2022-03-15 | 5 | 2022-03-15 | [6 empty] | 2022-03-24 | 7
NST-274219 | SCE | NEM | NEMA | NEMI - Application Returned 2nd Time. Pending Applicant Corrections | Solar PV | 96.144 | No | 2022-03-10 | 2022-03-10 | 0 | 2022-03-10 | 2022-03-15 | 3 | 2022-03-15 | 2022-03-30 | 11
NST-274222 | SCE | NEM | NEMA | Withdrawn | Solar PV | 238.43 | No | 2022-03-10 | 2022-03-10 | 0 | 2022-03-10 | 2022-03-15 | 3 |  |  |  |  | 2022-03-30 | 11
NST-274240 | SCE | NEM | NEMA | Withdrawn | Solar PV | 61.781 | No | 2022-03-10 | 2022-03-10 | 0 | 2022-03-10 | [6 empty] | 2022-03-31 | 14 |  | 2022-03-15 | 3
NST-274265 | SCE | NEM | NEMA | NEMI - Sent to Engineering | Solar PV | 92.787 | No | 2022-03-18 | 2022-03-18 | 0 | 2022-03-18 | 2022-03-23 | 3 | 2022-03-23 | [6 empty] | 2022-03-29 | 4
NST-274267 | SCE | NEM | NEMA | SCE Engineer Assigned. Pending Technical Review | Solar PV | 130.7 | No | 2022-03-11 | 2022-03-11 | 0 | 2022-03-11 | 2022-03-16 | 3 | 2022-03-16 | [6 empty] | 2022-03-24 | 6
NST-274529 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 40.927 | No | 2022-03-11 | 2022-03-11 | 0 | 2022-03-11 | [9 empty] | 2022-03-14 | 1 | [49 empty] | 2022-03-24 |  | 13
NST-274533 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 428.641 | No | 2022-03-11 | 2022-03-11 | 0 | 2022-03-11 | [9 empty] | 2022-03-16 | 3
NST-274726 | SCE | NEM | NEMA | Applicant Response Received. Pending SCE Engineer Review | Solar PV | 781.056 | No | 2022-03-11 | 2022-03-11 | 0 | 2022-03-11 | [9 empty] | 2022-03-22 | 7
NST-274836 | SCE | NEM | NEMA | NEMI - Application Returned. Pending Applicant Corrections | Solar PV | 76.272 | No | 2022-03-21 | 2022-03-21 | 0 | 2022-03-21 | 2022-03-25 | 4 | 2022-03-25
NST-274837 | SCE | NEM | NEMA | NEMI - Pending Final Documents | Solar PV | 65.278 | No | 2022-03-21 | 2022-03-21 | 0 | 2022-03-21 | [9 empty] | 2022-03-24 | 3
NST-275116 | SCE | NEM | NEMA | NEMI - Equipment Change Submitted | Solar PV | 71.062 | No | 2022-03-14 | 2022-03-14 | 0 | 2022-03-14 | 2022-03-17 | 3 | 2022-03-17 | [6 empty] | 2022-03-24 | 5
NST-275337 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 849.142 | No | 2022-03-15 | 2022-03-15 | 0 | 2022-03-15 | [9 empty] | 2022-03-21 | 4
NST-275375 | SCE | NEM | NEMA | NEMI - Application Re-Submitted | Solar PV | 52.603 | No | 2022-03-15 | 2022-03-15 | 0 | 2022-03-15 | 2022-03-22 | 5 | 2022-03-30
NST-275378 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 45.365 | No | 2022-03-15 | 2022-03-15 | 0 | 2022-03-15 | 2022-03-16 | 1 | 2022-03-16 | [6 empty] | 2022-03-25 | 7 | [49 empty] | 2022-03-25 |  | 10
NST-275427 | SCE | NEM | NEMA | NEMI - PTO Issued | Solar PV | 171.638 | No | 2022-03-22 | 2022-03-22 | 0 | 2022-03-22 | [9 empty] | 2022-03-25 | 3 | [49 empty] | 2022-03-25 |  | 3
NST-275434 | SCE | NEM | NEMA | NEMI - Application Re-Submitted | Solar PV | 86.776 | No | 2022-03-15 | 2022-03-15 | 0 | 2022-03-15 | 2022-03-23 | 6 | 2022-03-24
NST-275439 | SCE | NEM | NEMA | NEMI - Sent to Engineering | Solar PV | 163.21 | No | 2022-03-15 | 2022-03-15 | 0 | 2022-03-15 | 2022-03-25 | 8 | 2022-03-25 | [6 empty] | 2022-03-31 | 3
NST-275472 | SCE | NEM | NEMA | NEMI - Application Returned 2nd Time. Pending Applicant Corrections | Solar PV | 75.299 | No | 2022-03-15 | 2022-03-15 | 0 | 2022-03-15 | 2022-03-21 | 4 | 2022-03-21 | 2022-03-24 | 3
NST-275526 | SCE | NEM | NEMA | NEMI - Application Returned. Pending Applicant Corrections | Solar PV | 72.439 | No | 2022-03-15 | 2022-03-15 | 0 | 2022-03-15 | 2022-03-22 | 5
NST-275530 | SCE | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 56.754 | No | 2022-03-15 | 2022-03-15 | 0 | 2022-03-15 | 2022-03-22 | 5
NST-275576 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 276.281 | No | 2022-03-15 | 2022-03-15 | 0 | 2022-03-15 | [9 empty] | 2022-03-23 | 6
NST-275577 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 79.721 | No | 2022-03-15 | 2022-03-15 | 0 | 2022-03-15 | [9 empty] | 2022-03-22 | 5
NST-275706 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 377.541 | No | 2022-03-16 | 2022-03-16 | 0 | 2022-03-16 | 2022-03-22 | 4 | 2022-03-22 | [6 empty] | 2022-03-28 | 4
NST-275727 | SCE | NEM | NEMA | Applicant Response Received. Pending SCE Engineer Review | Solar PV | 103.48 | No | 2022-03-16 | 2022-03-16 | 0 | 2022-03-16 | [9 empty] | 2022-03-22 | 4
NST-275844 | SCE | NEM | NEMA | NEMI - Application Returned. Pending Applicant Corrections | Solar PV | 36.034 | No | 2022-03-16 | 2022-03-16 | 0 | 2022-03-16 | 2022-03-23 | 5
NST-275867 | SCE | NEM | NEM-ST | Fast Track Initial Review In Progress |  | 0.016037 | No |  |  |  | 2022-03-22
NST-275939 | SCE | NEM | NEMA | NEMI - Load Justification Reviewed | Solar PV | 88.774 | No | 2022-03-16 | 2022-03-16 | 0 | 2022-03-16
NST-275951 | SCE | NEM | NEMA | NEMI - Sent to Engineering | Solar PV | 136.905 | No | 2022-03-16 | 2022-03-16 | 0 | 2022-03-16 | 2022-03-25 | 7 | 2022-03-25 | [6 empty] | 2022-03-31 | 3
NST-275967 | SCE | NEM | NEMA | NEMI - Application Re-Submitted | Solar PV | 93.229 | No | 2022-03-16 | 2022-03-16 | 0 | 2022-03-16 | 2022-03-22 | 4 | 2022-03-22
NST-275974 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 40.481 | No | 2022-03-16 | 2022-03-16 | 0 | 2022-03-16 | [9 empty] | 2022-03-17 | 1
NST-276088 | SCE | NEM | NEMA | NEMI - Application Re-Submitted | Solar PV | 242.473 | No | 2022-03-17 | 2022-03-17 | 0 | 2022-03-17 | 2022-03-23 | 4 | 2022-03-23
NST-276133 | SCE | NEM | NEMA | NEMI - Application Re-Submitted | Solar PV | 77.562 | No | 2022-03-21 | 2022-03-21 | 0 | 2022-03-21 | 2022-03-25 | 4 | 2022-03-25
NST-276220 | SCE | NEM | NEMA | NEMI - Returned from Engineering | Solar PV | 54.782 | No | 2022-03-17 | 2022-03-17 | 0 | 2022-03-17 | [9 empty] | 2022-03-22 | 3
NST-276300 | SCE | NEM | NEM-ST | Application Review In Progress |  | 850.804 | No |  |  |  | 2022-03-17
NST-276300 | SCE | NEM | NEMA | SCE Engineer Assigned. Pending Technical Review | Solar PV | 850.804 | No | 2022-03-17 | 2022-03-17 | 0 | 2022-03-17 | 2022-03-22 | 3 | 2022-03-22
NST-276577 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 115.903 | No | 2022-03-18 | 2022-03-18 | 0 | 2022-03-18 | [9 empty] | 2022-03-23 | 3
NST-276595 | SCE | NEM | NEMA | SCE Engineer Review. Pending Applicant Response | Solar PV | 76.807 | No | 2022-03-18 | 2022-03-18 | 0 | 2022-03-18 | [9 empty] | 2022-03-24 | 4
NST-276747 | SCE | NEM | NEMA | NEMI - Application Returned. Pending Applicant Corrections | Solar PV | 36.567 | No | 2022-03-20 | 2022-03-20 | 0 | 2022-03-20 | 2022-03-25 | 4
NST-276954 | SCE | NEM | NEM-ST | Application Review In Progress |  | 712.125 | No |  |  |  | 2022-03-21
NST-276954 | SCE | NEM | NEMA | SCE Engineer Assigned. Pending Technical Review | Solar PV | 712.125 | No | 2022-03-21 | 2022-03-21 | 0 | 2022-03-21
NST-277053 | SCE | NEM | NEMA | SCE Engineer Assigned. Pending Technical Review | Solar PV | 291.37 | No | 2022-03-21 | 2022-03-21 | 0 | 2022-03-21 | [9 empty] | 2022-03-25 | 4
NST-277116 | SCE | NEM | NEMA | NEMI - Application Re-Submitted | Solar PV | 46.468 | No | 2022-03-22 | 2022-03-22 | 0 | 2022-03-22 | 2022-03-29 | 5 | 2022-03-30
NST-277193 | SCE | NEM | NEMA | NEMI - Application Re-Submitted | Solar PV | 54.098 | No | 2022-03-22 | 2022-03-22 | 0 | 2022-03-22 | 2022-03-28 | 4 | 2022-03-28
NST-277519 | SCE | NEM | NEMA | NEMI - Application Re-Submitted | Solar PV | 58.045 | No | 2022-03-22 | 2022-03-22 | 0 | 2022-03-22 | 2022-03-28 | 4 | 2022-03-28
NST-277609 | SCE | NEM | NEMA | NEMI - Application Submitted | Solar PV | 429.032 | No | 2022-03-23 | 2022-03-23 | 0 | 2022-03-23
NST-277764 | SCE | NEM | NEMA | NEMI - Application Returned. Pending Applicant Corrections | Solar PV | 537.983 | No | 2022-03-23 | 2022-03-23 | 0 | 2022-03-23 | 2022-03-29 | 4 | 2022-03-29
NST-277936 | SCE | NEM | NEMA | NEMI - Application Submitted | Solar PV | 66.757 | No | 2022-03-24 | 2022-03-24 | 0 | 2022-03-24
NST-277939 | SCE | NEM | NEMA | NEMI - Application Submitted | Solar PV | 86.941 | No | 2022-03-24 | 2022-03-24 | 0 | 2022-03-24
NST-277978 | SCE | NEM | NEMA | NEMI - Equipment Change Submitted | Solar PV | 398.614 | No | 2022-03-24 | 2022-03-24 | 0 | 2022-03-24
NST-277987 | SCE | NEM | NEMA | NEMI - Extension Requested. Pending Applicant Corrections | Solar PV | 322.047 | No | 2022-03-24 | 2022-03-24 | 0 | 2022-03-24 | 2022-03-30 | 4
NST-278163 | SCE | NEM | NEMA | NEMI - Application Returned. Pending Applicant Corrections | Solar PV | 247.755 | No | 2022-03-24 | 2022-03-24 | 0 | 2022-03-24 | 2022-03-31 | 4 | 2022-03-31
NST-278598 | SCE | NEM | NEMA | NEMI - Application Submitted | Solar PV | 260.54 | No | 2022-03-29 | 2022-03-29 | 0 | 2022-03-29
NST-278862 | SCE | NEM | NEMA | NEMI - Application Submitted | Solar PV | 198.727 | No | 2022-03-28 | 2022-03-28 | 0 | 2022-03-28
NST-278913 | SCE | NEM | NEMA | NEMI - Application Submitted | Solar PV | 232.819 | No | 2022-03-28 | 2022-03-28 | 0 | 2022-03-28
NST-278915 | SCE | NEM | NEMA | NEMI - Equipment Change Submitted | Solar PV | 997.192 | No | 2022-03-28 | 2022-03-28 | 0 | 2022-03-28
NST-278918 | SCE | NEM | NEMA | NEMI - Application Submitted | Solar PV | 261.921 | No | 2022-03-28 | 2022-03-28 | 0 | 2022-03-28
NST-278952 | SCE | NEM | NEMA | NEMI - Application Submitted | Solar PV | 312.5 | No | 2022-03-28 | 2022-03-28 | 0 | 2022-03-28
NST-279091 | SCE | NEM | NEMA | NEMI - Application Submitted | Solar PV | 643.754 | No | 2022-03-28 | 2022-03-28 | 0 | 2022-03-28
NST-279200 | SCE | NEM | NEMA | NEMI - Application Submitted | Solar PV | 51.297 | No | 2022-03-29 | 2022-03-29 | 0 | 2022-03-29
NST-279215 | SCE | NEM | NEMA | NEMI - Application Submitted | Solar PV | 69.652 | No | 2022-03-29 | 2022-03-29 | 0 | 2022-03-29
NST-279228 | SCE | NEM | NEMA | NEMI - Equipment Change Submitted | Solar PV | 247.761 | No | 2022-03-29 | 2022-03-29 | 0 | 2022-03-29
NST-279229 | SCE | NEM | NEMA | NEMI - Application Submitted | Solar PV | 218.956 | No | 2022-03-29 | 2022-03-29 | 0 | 2022-03-29
NST-279248 | SCE | NEM | NEMA | NEMI - Application Submitted | Solar PV | 249.848 | No | 2022-03-29 | 2022-03-29 | 0 | 2022-03-29
NST-279327 | SCE | NEM | NEMA | NEMI - Application Submitted | Solar PV | 30.099 | No | 2022-03-29 | 2022-03-29 | 0 | 2022-03-29
NST-279372 | SCE | NEM | NEMA | NEMI - Equipment Change Submitted | Solar PV | 215.914 | No | 2022-03-29 | 2022-03-29 | 0 | 2022-03-29
NST-279376 | SCE | NEM | NEMA | NEMI - Application Submitted | Solar PV | 38.307 | No | 2022-03-29 | 2022-03-29 | 0 | 2022-03-29
NST-279383 | SCE | NEM | NEMA | NEMI - Application Submitted | Solar PV | 741.2799 | No | 2022-03-29 | 2022-03-29 | 0 | 2022-03-29
NST-279441 | SCE | NEM | NEMA | NEMI - Application Submitted | Solar PV | 1365.731 | No | 2022-03-29 | 2022-03-29 | 0 | 2022-03-29
NST-279454 | SCE | NEM | NEMA | NEMI - Application Submitted | Solar PV | 114.539 | No | 2022-03-29 | 2022-03-29 | 0 | 2022-03-29
NST-279457 | SCE | NEM | NEMA | NEMI - Application Submitted | Solar PV | 432.51 | No | 2022-03-29 | 2022-03-29 | 0 | 2022-03-29
NST-279458 | SCE | NEM | NEMA | NEMI - Application Submitted | Solar PV | 464.521 | No | 2022-03-29 | 2022-03-29 | 0 | 2022-03-29
NST-279461 | SCE | NEM | NEMA | NEMI - Application Submitted | Solar PV | 199.383 | No | 2022-03-29 | 2022-03-29 | 0 | 2022-03-29
NST-279664 | SCE | NEM | NEMA | NEMI - Application Submitted | Solar PV | 850.641 | No | 2022-03-30 | 2022-03-30 | 0 | 2022-03-30
NST-279726 | SCE | NEM | NEMA | NEMI - Application Submitted | Solar PV | 150.96 | No | 2022-03-30 | 2022-03-30 | 0 | 2022-03-30
NST-279808 | SCE | NEM | NEMA | NEMI - Application Submitted | Solar PV | 122.353 | No | 2022-03-30 | 2022-03-30 | 0 | 2022-03-30
NST-280019 | SCE | NEM | NEMA | NEMI - Application Submitted | Solar PV | 46.541 | No | 2022-03-31 | 2022-03-31 | 0 | 2022-03-31
NST-280130 | SCE | NEM | NEMA | NEMI - Application Submitted | Solar PV | 992.607 | No | 2022-03-31 | 2022-03-31 | 0 | 2022-03-31
NST-280153 | SCE | NEM | NEMA | NEMI - Application Submitted | Solar PV | 77.635 | No | 2022-03-31 | 2022-03-31 | 0 | 2022-03-31
NST-98090 | SCE | NEM | NEM-ST | Transferred to NEM | Solar PV | 0.0388 | No |  |  |  | 2021-01-25

## Notes
Note # | Date | Note
1 | 2021-01-28 | NGOM Design does not commence until SCE is in receipt of the following: 1) NGOM Payment from Customer 2) Meter Socket Cut Sheets from Customer 3) Customer Project Information Sheet (CPIS) from Customer 4) Authority Having Jurisdiction (AHJ) Release of Meter Socket Pre-Inspection from AHJ 5) Electrical Service Requirements (ESR) Compliance
2 | 2021-01-28 | This is how SCE views the distinction between “minor” and “major” distribution upgrades and other facilities. Discussion of this distinction is also found in various Sections of the D20-09-035; such as Section 4.4.7 (Issue 10 Proposal 6), Section 4.4.10 (Resolving Issue 10) and Section 5.7.2 (Proposal 24a).
Minor Distribution Upgrades include (not an exhaustive list) 1) Single wood pole relocation of same type/size (not replacement) to nearby location 2) Single wood pole replacement of same or next larger size at the same location 3) Transformer relocation (not replacement) within the same premises 4) Distribution line extension of no more than 500 feet with no transformer change 5) Transformer upgrade (to next highest size) servicing the same customer service point
Major distribution upgrades include (not an exhaustive list) 1) Multiple wood pole replacement 2) Distribution line extension of more than 500 feet in distance 3) Reconductoring of greater than 500 feet in distance 4) Relocation, replacement or installation of any non-wood type pole (such steel poles) 5) Any work performed to distribution voltage system greater than 50kV 6) Any work related to work inside an SCE substation (relay replacement, installation of metering equipment, etc.) 7) Replacement, upgrades, and/or relocation of any voltage regulation or protection equipment (voltage regulators, capacitor banks, automatic reclosers) 8) Any work type where SCE is responsible for contracting the civil engineering work (ducts and structures, typically this is work performed by the customer and inspected/signed off by SCE)
As far as interconnection facilities, most of these would be considered “minor” and subject to the 60/60 requirement, unless they are located inside of a substation (see #6 above) Examples of typical “minor” interconnection facilities to serve a single service point/Point of Interconnection/Point of Common Coupling include the following (not an exhaustive list and not all required for each facility) 1) Switching device 2) Primary Wiring required for switching device 3) UAD (underground automated device) cabinet with Netcomm radio 4) Metering equipment 5) Transformation installation (for services requesting secondary service) 6) Installation of secondary service wires (for secondary services) 7) Primary service wire connections (for primary services) 8) Ground bank/ground detector 9) RTU/telemetry (Centralized RTU if between 1-10MW, RTU if over 10 MW)* * In addition to the capital cost, SCE typically charges a one-time cost for programming required to connect the generating facility telemetry to its SCADA system/Grid Control Center
3 | 2021-01-28 | Common Acronymns:
NEM-ST: NEM Successor Tariff
NEM-MT: NEM Multi-Tariff
NGOM: Net Generation Output Meter
RTU: Remote Terminal Unit
PTO: Permission to Operate
SOMAH-VNM: Solar on Multifamily Affordable Housing - Virtual Net Metering
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
|  |  | 0 | #N/A | #N/A | #N/A
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Holidays (hidden)
2020-01-01
2020-01-20
2020-02-17
2020-03-31
2020-05-25
2020-07-03
2020-09-07
2020-10-12
2020-11-11
2020-11-26
2020-11-27
2020-12-25
2021-01-01
2021-01-18
2021-02-15
2021-03-31
2021-05-31
2021-07-05
2021-09-06
2021-10-12
2021-11-11
2021-11-25
2021-11-26
2021-12-24
2021-12-31